## ITP Cover Page
Retaining Wall 04 - Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210-SP2 - ITP 010-002-001 - Rev 1.0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | ITP 010-002-001
Project Number: |  |  | DN1210-SP2 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Retaining Wall 4 Base-Slab/Toe/Kicker-Chamfer |  |  |  |  | Revision: | 1000 |  | 1.0
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets:
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification:
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval |  |  | Cordelia Girdler-Brown & Nick Adams |  | Item 3.5 removed, as DPM is no longer required |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) |  | HSE | HSE Manager / Rep
1 | [9 empty] | H | Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) |  | PE/SE | QA Manager / Rep
[10 empty] | I | Inspection (Formal inspection activity to be undertaken and recorded) |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point (Review of text reports/records or other evidence of compliance) |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | NICK ADAMS |  |  | #VALUE! |  | 19/06/2025 | Downer PM |  | NICK ADAMS
Downer QM |  | CORDELIA GIRDLER-BROWN |  |  |  |  | 19/06/2025 | Downer QM |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Retaining Wall 4 Base Slab
Tauriko Enabling Works
DN1210 - SP2- ITP010-002-001 - REV 0
Item No. | Inspection and Test Point | Detail / Activity | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | ConQA Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION - MATERIAL , PERSONNEL & THIRD PARTY APPROVALS (P&G / ESTABLISHMENT)
3.1 | Methodology | Method statement | As Per Specification and IFC Drawings | PS- 22.3 Appendix V | RW-04 Permanentworks Construction Work Pack Sign off | Prior to Construction | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.2 | Reinforcement Modelling | 3D modelling completed, bar bending schedule checked against latest construction drawings and submitted to the Engineeer for review | Downer | Reinforcment shop drawings | Each batch of reinforcement |  | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.3 | Steel Supply, Delivery and Storage | Mill & test certificates for each batch of reinforcement used to be provided to the Engineer. . | Design Drawings | AS/NZS 4671 PS 19.13 | Delivery Dockets / Mill Certs | Each Delivery to site | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
3.4 | Concrete Mix Design | Concrete mix design to be completed and reviewed by the contractor prior to use on site. The following criteria are to be satisfied: • Strength: 50MPa • Normal maximum aggregate size: 19mm • Concrete materials and manufacturing are to comply with NZS3109 • Aggregate Used And Overall Mix Design (Including Additives) Shall Meet The Provisions Of 'Tr3 Alkali Silica Reaction 2003 (Ccatnz)'. | NZS 3104 Design Drawings | PS 19.3.3 | Concrete Mix Design | All Mix Designs | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.5 | Subsoil Drainage | Shall be 110mm diameter NZTA F/2 compliant smooth bore perforated pipe with filter sock | Engineers Approval | PS 21.5.17 | Material certificate/NTC | Prior to construction | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.6 | Granular Material (Imported Pumice Sand, GAP65/AP65) | Confirm Specification and material in good condition. NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load NZS4407:2015, Test 3.8.1 - Particle Size Distribution NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | Confirm Specification and material in good condition. | PS 22.4.1 | Delivery Dockets / Inspection Checksheet(DG-QA-TP019) | Each Delivery to site | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
SECTION 4 | CONSTRUCTION ACTIVITY - CONCRETE BASE- Excavation and Subgrade Preparation
4.1 | Cut Subgrade - Inspection | Engineer to inspect all foundation surface inspections | Engineers Approval | Appendix V | Visual Observation | Across stripped area | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
4.2 | Cut Subgrade Testing - Cohesive Soil Shear Vane | NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level | Average Minimum SU: > 60kPa Single Test Min SU: >50kPa 2-3m deep | Appendix XVIII | Shear Vane Report | 0.5m interval 4 test per 400M2 | M | SE
4.3 | Cut Subgrade Testing - Non-Cohesive Soil Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material | Minimum 3 blows per 100mm penetration | Appendix XVIII | Scala Report | 4 test per 400M2 | M | SE
4.4 | Cut Subgrade - Import Structural fill Release of Hold Point | To release the subgrade hold point in-order to start placing the Blinding Contractor shall provide written certification that all inspected and tested subgrade complies with the requirements in PS 16.6 | Engineers Approval | PS 16.9.3 | CONQA Approval | Engineers Approval | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
SECTION 5 – CONSTRUCTION ACTIVITY - CONCRETE BASE + TOE + KICKER-CHAMFER - Steelworks
5.1 | STEEL - Reinforcing Ties | Tie bar diameter, grade, and length match shop drawings and bending schedule Spaced correctly as per design (e.g., 200mm c/c), full enclosure of longitudinal bars | As per Drawing | NZS 3109 PS 19.13 | Delivery Dockets Checksheet | During constuction | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
5.2 | STEEL - Onsite Cutting & bending | Complies with bending schedule & radius limits | As per Drawing | NZS 3109 PS 19.14 | Visual Inspection | During constuction | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
5.3 | STEEL - Reinforcing Bars (lapping/starter bars/dowels) | Correct bar size, spacing, cover, lapping as per shop drawings Min. lap length, staggered laps as per design Location, projection & alignment must match prior pour | As per Drawing | NZS 3109 NZS 3604 PS 19.13 | Delivery Dockets Checksheet | During construction | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
SECTION 6 – CONSTRUCTION ACTIVITY - CONCRETE BASE + TOE + KICKER-CHAMFER - Concreteworks
6.1 | CONCRETE - Unfavourable Conditions - Cold Weather | Concrete shall not be placed in conditions where temperature is below 5°C with temperature decreasing or below 2°C with temperature increasing. | Prepour Checklist | NZS3901:1997 Cl 7.2 | Pre Pour | During construction | M | SE
6.22 | CONCRETE - Unfavourable Conditions - Hot Weather | Concrete shall not be placed in excessively hot dry conditions. Concrete temperature should not be higher than 30°C | Prepour Checklist | NZS3901:1997 Cl. 7.2.1 & Cl. 7.2.2 | Pre Pour | During construction | M | SE
6.34 | CONCRETE - Unfavourable Conditions - Rain | Concrete shall not be commenced when heavy rains is falling or threathening and if rain commences during a pour, the work shall be protected as directed to prevent damage to the concrete or to any newly finished surfaces until the concrete has set to such a stage as to withstand leaching of the cement. | Prepour Checklist | NZS3901:1997 Cl. 7.1 | Pre / During Pour | During construction | M | SE
6.4 | CONCRETE - Spacer Blocks | Correct type, spacing, and fixity Shall be concrete spacer blocks made from concrete containing 8% Microsilica 10MPa | Prepour Checklist | NZS 3109 | Delivery Dockets Checksheet | During construction | M | SE
6.52 | CONCRETE - Construction Joints | Where a concrete surface is to act as a construction joint to receive infill over or adjacent, the contact surface interface shall be prepared to the Engineer’s satisfaction to be clean, free of laitance, and with a peak to trough roughness of not less than 5mm to ensure compliance with Type B construction joints as defined by NZS3109 Section 5.6. | Prepour Checklist As per Drawing | NZS3109:1997 Cl 5.6 PS 19.5 | Photos/Checksheet | During construction | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
6.622 | CONCRETE - Delivery Dockets | Each batch delivered shall be accompanied by a delivery docket certifying the cement type, maximum aggregate size, specified strength, slump or spread, date, time mixing completed, and time water added at the plant. Delivery dockets and other certified records of concrete quality and quantity shall be kept on site for inspection by the Engineer. | Engineer Inspection | PS 19.4.1 | Dockets Checksheet | During construction | M | SE
6.724 | CONCRETE - Slump Tests | Slump tests or spread tests shall be taken for each delivery of concrete and the results recorded by the Contractor | Prepour Checklist | NZS3109 Table 9.1 | Photos/Visual Inspection or slumps and on-site records | Each Delivery | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
6.826 | CONCRETE - Time Limits | Any addition of water or admixtures to the concrete mix subsequent to leaving the ready mix plant shall be only be undertaken by, or with the approval of, the ready mix plant supplier. Any such addition of water shall be strictly in accordance with clause 9.4.2.1 of NZS3109. All ready-mix concrete supplied shall be poured within 90 minutes of batching. For concrete mixes containing set accelerating admixtures the above times shall be halved. | Prepour Checklist | NZS 3104 NZS3109 Cl 9.4.2.1 PS 19.4.3 | Dockets Checksheet | During construction | M | SE
6.928 | CONCRETE - Compression Testing | The Contractor shall have the off-site testing carried out by an approved IANZ-accredited laboratory at his own expense and shall supply copies of IANZ-endorsed test results to the Engineer. For pours under 150m³: three standard cylinders shall be made for each 50m³ of concrete placed, or part thereof, for testing of 28-day compressive strength in an approved laboratory | 28 days concrete strength test of 50 Mpa | NZS3109 PS 19.4.2 | Compression Test Result | During construction | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
6.1 | CONCRETE - Curing | After concrete has set sufficiently its exposed surfaces shall be kept continuously wet for a period of at least 7 days. Special attention shall be paid to curing in the early stages. | Acceptance / Repair Details | NZS 3109:1997 Cl 7.1.3 PS 19.8 | Post Concreting/Compression Test Result | During construction | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
6.11 | CONCRETE - Finishes | Concrete finishes are to be as specified by NZS3114 & AS/NZS 3661, scheduled as follows: Top surface of Base: U5 Brushed Finish Type B construction joints to NZS3109 | Drawings | NZS3114 NZS3109 | Photos/Approva/Repair Details | Post Concreting | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
6.12 | CONCRETE POSTPOUR - Falsework and Formwork Installation/Removal | Formwork shall not be removed until the minimum periods set down in Table 5.3 of NZS3109 have elapsed. Design details, construction drawings, and a formwork certificate (PF-T-442) shall be supplied to the Engineer prior to the formwork assembly and at least 14 days prior to concreting of the component, for review | As per Temporary works Drawings Engineer Approval | NZS3109 Table 5.3 PS 19.11.3 Appendix XIX Downer | Approval | Before installation and removal of Falsework and Formwork | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
6.13 | CONCRETE POSTPOUR - Post Pour Inspection | Post pour inspection undertaken by the site engineer and captured in the ConQA web app. Engineer notified of any defects. | Downer | Site Photos | Each pour |  | H Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) | PE/SE
6.14 | CONCRETE POSTPOUR - Repair | Repair of any minor surface defect or structural defect of concrete shall only be carried out with the Engineer’s acceptance. All repaired concrete shall have the same strength, durability and surface finish as the parent concrete unless otherwise accepted by the Engineer. |  |  | Acceptance / Repair Details | Prior to Each Repair | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7.1 | Survey As-Builts | Quality Check on Nee pipeline and structure based on the tolerances in RITS | Meets spec as per drawings and capture any NCR or change to design. | Project Specifications | Red pen markup only | Post works completion of a lot | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
7.2 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Drawings | Downer | Redlines