## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-036
[11 empty] | Revision : 1 | Date : 25/06/2025
Client: |  | MRPA |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Watergardens Station Carpark |  | Beaching Installation |  | Name: Jake Cardillo |  | Name: Patrick Fagan |  |  | Name: Shaun Kent
Job No: |  | 7432000 |  | Specifications: VicRoads Standard Specification Section 713 and Drawings
|  |  |  | Structure / Component: Drainage |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Watergardens Station |  | Date : 25/06/2025 |  | Date : 25/06/2025 |  |  | Date : 25/06/2025
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | Visual Inspection | This ITP signed off | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Material Approval |  | Prior to Placement | Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications. Materials used for rock beaching shall be resistant to weathering action of air, wind and water and shall be free from staining, laminations, cracks and other structural defects which may reduce its mechanical strength. | Material specification sheets | Verfiy | Teambinder Acceptance | HP | Site Engineer/ Superintendent | N/A |  | N/A
2 | Construction Works
2.1 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | This ITP Signed Off | HP* | Site Engineer | N/A |  | N/A
2.2 | Set out beaching extents |  | Prior to backfilling | The position of all beaching locations are to be confirmed with the superintendent | IFC Drawings | Visual Inspection | ITP Signed | HP* | Site Engineer | N/A |  | N/A
2.3 | Preparation of surface |  | Each Lot | Areas on which beaching is to be placed shall be compacted and trimmed as required to provide a finished surface level of beaching in accordance with the drawings. Any scours or hollows in the surface shall be filled with compacted Class 4 crushed rock. | 713.04 | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.4 | Placement of bedding / geotextile |  | Each Lot | Type 1 beaching shall not routinely require a granular bedding, however a very robust needle-punched non woven geotextile (mass >250 g/m2) shall be laid over the trimmed surface where rock beaching is to be placed. The geotextile shall be laid evenly with no kinks or folds, and joints shall be formed by overlapping the geotextile by not less than 300 mm and not more than 500 mm. | 713.03(b) | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.5 | Excavation of anchor trench |  | Each Lot | Geotextiles used shall comply with and be placed in accordance with Section 210. The geotextile shall be buried to a depth of 300 mm at the edges of beaching and placed under and around the excavation for the toe wall and for any other perimeter walls provided. | 713.03(b) | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.6 | Placement of beaching |  | Each Lot | Rock for Type 1 beaching shall consist of field or quarry rock. All rocks shall have a mass of between 20 and 70 kg and at least 60% by number shall be over 40 kg. Rocks shall be of such size that the layer of beaching is not less than 225 mm thick | 713.03(a) | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.7 | Interlocking of beaching |  | Each Lot | Beaching materials shall be firmly bedded on the prepared embankment and/or bedding if required and laid in courses commencing from the bottom of any slope. Un-grouted beaching and armour stone when placed shall form a tight ‘interlocking grid’, which shall prevent the removal of individual rocks. | 713.05 (a) | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
3 | Finishing Works
3.1 | Finishing of beaching |  | Each lot | Finished surface levels of rock beaching placed in open drains shall be flush with adjacent soil levels to allow mowing and maintenance. Rock beaching shall not protrude more than 50 mm above the surrounding ground levels. | 713.05(a) | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
3.2 | Conformity with drawings |  | Each Lot | The finished surface of the beaching shall conform to the levels, lines and grades as shown on the drawings or as specified. | 713.02 | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.