## Table 1
Inspection and Test Plan: Cast-in Conduit Installation Heyday5 Pty Ltd Lic: 2012817
Project Name: |  | WSA Canine Facility and Command Centre |  |  |  | ITP Issue Date: |  | 2025-06-25 |  | Trade: |  | Electrical
Document Number: |  | WSA81-CPB-05250-EL-ITP-000014-A |  |  |  | Prepared By: |  | Adnan Qaisar |  | Sign off: |  | Supervisor/Project Manager
Client: |  | CPB |  |  |  | Approved By: |  | Chris Baker |  | Revision: |  | A
Project No: |  | NEC00153 |  |  |  | Location: |  | Canine Facility
Site Location |  | 3B Pitt St Badgerys Creek NSW 2555 |  |  |  | Lot:
Item | Inspection/test Point |  | Responsibility | Method |  |  | Conformance Criteria & Standard Reference |  |  |  | Frequency Required |  | Records
Preliminaries
1 | Approved IFC Drawings |  | Heyday Supervisor/Management Team | Document Review |  |  | Review drawings and specifications & revision status with Heyday drawing register, ensuring to only work to AFC drawings, and approved documents: WSA81-CPB-05250-EL-DRG-400001 - Heyday Drawing Register |  |  |  | Prior to works and as amended
2 | Material |  | Heyday Management Team | Document Review |  |  | Only use material approved by CPB through the required sample process listed on Heyday samples register as approved: WSA81-CPB- 05250-EL-SAM-000014 Conduits and Bends WSA81-CPB-05250-EL-SAM-000110 Trench Backfill 10mm Agg WSA81-CPB-05250-EL-SAM-000111 Enviro Sand WSA81- CPB-05250-EL-SAM-000112 Stab Sand 10.1 |  |  |  | Prior to use and on delivery |  | Material Approval
3 | Applicable ITC (Attached below) |  | Heyday Management Team | Document Review |  |  | WSA81-CPB-05250-EL-ITC-000014-A - Cast-in Conduit Installation |  |  |  | Prior to works and as amended
Project specific installation requirements
1 | Receipt of conduit delivery to site & storage. |  | Heyday Supervisor | Visual Inspection |  |  | Review all delivered against approved product submission and confirm conformance. Components parts list, as stated on the purchase order/invoice, to be validated against received items. |  |  |  | Per Lot |  | Inspection Test Checklist
2 | Set out. |  | Heyday Supervisor | Visual Inspection |  |  | Set out to be confirmed with latest AFC drawings. WSA81-CPB-05250-EL-DRG-400201 - SITE PLAN CONDUIT SET-OUT PLAN |  |  |  | Per Lot |  | Inspection Test Checklist
3 | Conduit Installation. |  | Heyday Supervisor | Visual Inspection & Record (Photo required) |  |  | Conduits to be installed as per set out drawings, with reference to th e below. • WSA81-CPB-05250-EL-DRG-400001 • WSA81-CPB-05250-EL-DRG-400201 • WSA81-CPB-05250-EL-DRG-401200 • WSA81-CPB-05250-EL-DRG-402200 • WSA81-CPB-05250-EL-DRG-403200 • WSA81-CPB-05250-EL-DRG-405200 • WSA81-CPB-05250-EL-DRG-406030 • WSA81-CPB-05250-EL-DRG-406200 • WSA81-CPB-05250-EL-DRG-407200 |  |  |  | Per Lot |  | Inspection Test Checklist
4 | Change of direction/bend Installation (Correct bending radius used as per drawing). |  | Heyday Supervisor | Visual Inspection |  |  | Conduits to be installed as per set out drawings, with reference to th e below. • WSA81-CPB-05250-EL-DRG-400001 • WSA81-CPB-05250-EL-DRG-400201 • WSA81-CPB-05250-EL-DRG-401200 • WSA81-CPB-05250-EL-DRG-402200 • WSA81-CPB-05250-EL-DRG-403200 • WSA81-CPB-05250-EL-DRG-405200 • WSA81-CPB-05250-EL-DRG-406030 • WSA81-CPB-05250-EL-DRG-406200 • WSA81-CPB-05250-EL-DRG-407200 |  |  |  | Per Lot |  | Inspection Test Checklist
5 | Bellmouths installed within the slab. |  | Heyday Supervisor | Visual Inspection |  |  | Bellmouths to be installed as per set out drawings, with reference to the below. • WSA81-CPB-05250-EL-DRG-400001 • WSA81-CPB-05250-EL-DRG-400201 • WSA81-CPB-05250-EL-DRG-401200 • WSA81-CPB-05250-EL-DRG-402200 • WSA81-CPB-05250-EL-DRG-403200 • WSA81-CPB-05250-EL-DRG-405200 • WSA81-CPB-05250-EL-DRG-406030 • WSA81-CPB-05250-EL-DRG-406200 • WSA81-CPB-05250-EL-DRG-407200 |  |  |  | Per Lot |  | Inspection Test Checklist
6 | Glue Conduits together. |  | Heyday Supervisor | Visual Inspection |  |  | Glue to be applied to both a joining pieces of conduit, covering the complete surface area were contact is made. |  |  |  | Per Lot |  | Inspection Test Checklist
7 | Rope & pathway test. |  | Heyday Supervisor | Hold Point |  |  | To confirm clear pathway within conduit route, provide draw rope for future contractor. |  |  |  | Per Lot |  | Inspection Test Checklist
8 | Sealing of Conduits. |  | Heyday Supervisor | Record |  |  | Confirm all conduits are sealed using plugs. |  |  |  | Per Lot |  | Inspection Test Checklist
9 | Record photo evidence. |  | Heyday Supervisor | Record |  |  | Photo evidence to be captured, stored and provided for formal submission where applicable/outlined within ITP. |  |  |  | Per Lot |  | Inspection Test Checklist
Post construction works
4 | Completion of installation |  | Heyday Supervisor | Record |  |  | Heyday supervisor to ensure that all work has been completed to relevant standards(AS3000) & approved drawings |  |  |  | Post Installation
5 | Photo Evidence |  | Heyday Supervisor | Record |  |  | Heyday supervisor to capture & submit photo evidence as part of completed works specified within ITC. |  |  |  | During all steps of Installation
6 | As-built survey & report |  | Heyday Supervisor | Record |  |  | Heyday supervisor to submit As-built drawings as part of completed works where applicable. |  |  |  | Post Installation
FINAL ACCEPTANCE |  |  | NAME |  | SIGNATURE | POSITION |  |  | DATE
HEYDAY GROUP (REPRESENTATIVE) |  |  | Geoff Summers |  |  | Project Manager |  |  | 2025-06-25
CPB (REPRESENTATIVE)
OTHERS (IF APPLICABLE)
ABN 85 158 865 091