## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 24.10 ITP - Carpet | itp |  |  |  |  | 24.10 ITP - Carpet
section | Carpet ITP
checkpoint | RISK ASSESMENT/SWMS/INDUCTION
label | ACCEPTANCE CRITERIA - Safe Work Method Statement complies with WorkCover regulations and NSW Govt OHS&R guidelines.
label | ○ Work Health & Safety Act 2011 & Safety Regulation 2017
label | ○ Submitted at least 14 days prior to affected work commencing.
date | Date:
checkpoint | WORKSHOP DRAWING
label | ACCEPTANCE CRITERIA - Provide a floor covering plan / Shop drawing plan layout is approved by Client/Builder prior to install.
date | Date:
checkpoint | INSPECTION NOTIFICATION
label | ACCEPTANCE CRITERIA - Give three days notice for background prior to laying carpet
label | ○ Give three days notice for smooth edge and underlay ready for carpet
label | ○ Give three days notice for each batch of carpet upon delivery to site
label | ○ Give three days notice for completion of carpet prior to placing protection
date | Date:
checkpoint | FLOOR PREPARATION
label | ACCEPTANCE CRITERIA - Dry and clean.
label | ○ Ardit areas which are low. Ensure areas are correctly fanned out to minimise noticeable ramp in levels adjusted.
date | Date:
checkpoint | UNDERLAY
label | ACCEPTANCE CRITERIA - Ensure that underlay is even, level, joints are flush and fixed according to manufacturer’s details
label | ○ UNDERLAY is Conventional Government Red.
date | Date:
checkpoint | WORKMANSHIP
label | ACCEPTANCE CRITERIA - Set out carpet to minimise joints
label | ○ Ensure that carpet in a single area comes from one manufacturing batch and dye lot
label | ○ Aluminium reducing strips to exposed edges
date | Date:
checkpoint | GENERAL
label | ACCEPTANCE CRITERIA - High traffic areas free of joins
label | ○ Anchor weld or equivalent adhesive
label | ○ Drill plug and screw edge strips
label | ○ Clearance under doorways 25 mm
date | Date:
checkpoint | PROTECTION OF SURFACES
label | ACCEPTANCE CRITERIA - Floor Protection installed prior to opening access to other trades
date | Date:
checkpoint | FINAL INSPECTION
label | ACCEPTANCE CRITERIA - Non-conformances all closed out
date | Date:
checkpoint | WARRANTIES
label | ACCEPTANCE CRITERIA - Warranties provided
label | ○ Submit 3 copies of maintenance manuals, including care and maintenance.
label | ○ Submit 1% of carpet used as spare material, wrapped in protective plastic, stored off the ground.
date | Date:
checklist | 24.10 ITP - Vinyl | itp |  |  |  |  | 24.10 ITP - Vinyl
section | Vinyl ITP
checkpoint | RISK ASSESMENT/SWMS/INDUCTION
label | ACCEPTANCE CRITERIA - Safe Work Method Statement complies with WorkCover regulations and NSW Govt OHS&R guidelines.
label | ○ Work Health & Safety Act 2011 & Safety Regulation 2017
label | ○ Submitted at least 14 days prior to affected work commencing.
date | Date:
checkpoint | WORKSHOP DRAWING
label | ACCEPTANCE CRITERIA - Provide a floor covering plan / Shop drawing plan layout is approved by Client/Builder prior to install.
date | Date:
checkpoint | INSPECTION NOTIFICATION
label | ACCEPTANCE CRITERIA - Give three days notice for background prior to laying Vinyl ; Give three days notice for each batch of Vinyl upon delivery to site; Give three days notice for completion of Vinyl prior to placing protection
date | Date:
checkpoint | FLOOR PREPARATION
label | ACCEPTANCE CRITERIA - Dry and clean.
label | ○ Ardit areas which are low. Ensure areas are correctly fanned out to minimise noticeable ramp in levels adjusted.
date | Date:
checkpoint | UNDERLAY
label | ACCEPTANCE CRITERIA - N/A
date | Date:
checkpoint | WORKMANSHIP
label | ACCEPTANCE CRITERIA - Set out Vinyl to minimise joints
label | ○ Ensure that Vinyl in a single area comes from one manufacturing batch and dye lot
label | ○ Aluminium reducing strips to exposed edges
date | Date:
checkpoint | GENERAL
label | ACCEPTANCE CRITERIA - High traffic areas free of joins
label | ○ Anchor weld or equivalent adhesive
label | ○ Drill plug and screw edge strips
label | ○ Clearance under doorways 25 mm
date | Date:
checkpoint | PROTECTION OF SURFACES
label | ACCEPTANCE CRITERIA - Floor Protection installed prior to opening access to other trades
date | Date:
checkpoint | FINAL INSPECTION
label | ACCEPTANCE CRITERIA - Non-conformances all closed out
date | Date:
checkpoint | WARRANTIES
label | ACCEPTANCE CRITERIA - Warranties provided
label | ○ Submit 3 copies of maintenance manuals, including care and maintenance.
label | ○ Submit 1% of Vinyl used as spare material, wrapped in protective plastic, stored off the ground.
date | Date: