## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Contract Quality Management Plan | itp |  |  |  |  | ITP - Contract Quality Management Plan
section | Details
checkpoint | Stabilising Repairs Downer Activity #39
label | VERIFICATION ACTIVITY: Visual - Levelling pavements
label | METHODS OR REFERENCE: As per work procedure: HDC WMS STABILISED REPAIR
label | FREQ.: As Programmed
label | ACCEPTANCE CRITERIA: C2 MINOR SURFACE LEVELLING
label | INSPECTORATE* V/W/H - DNZ: V
label | INSPECTORATE* V/W/H - CLIENT: W
label | RECORDS / REMARKS incl NCR ref: Record on: HDC Pavement Repairs QA Spreadsheet/ConQA and hand in to supervisor
checkpoint | Rip & Remake Downer Activity #40
label | VERIFICATION ACTIVITY: Visual - Levelling pavements
label | METHODS OR REFERENCE: As per work procedure: HDC WMS Rip and Remake REPAIR
label | FREQ.: As Programmed
label | ACCEPTANCE CRITERIA: C2 MINOR SURFACE LEVELLING
label | INSPECTORATE* V/W/H - DNZ: V
label | INSPECTORATE* V/W/H - CLIENT: W
label | RECORDS / REMARKS incl NCR ref: Record on: HDC Pavement Repairs QA Spreadsheet/ConQA and hand in to supervisor
checkpoint | Dig outs Downer Activity #036
label | VERIFICATION ACTIVITY: Identify and method
label | METHODS OR REFERENCE: As per work procedure: HDC WMS DIGOUT REPAIR
label | FREQ.: As Programmed
label | ACCEPTANCE CRITERIA: C5 DIG-OUT REPAIRS IN SEALED PAVEMENTS
label | INSPECTORATE* V/W/H - DNZ: V
label | INSPECTORATE* V/W/H - CLIENT: W
label | RECORDS / REMARKS incl NCR ref: Record on: HDC Pavement Repairs QA Spreadsheet/ConQA and hand in to supervisor
checkpoint | Concrete footpaths, Vehicle crossings Downer Activity #249
label | VERIFICATION ACTIVITY: Replacement
label | METHODS OR REFERENCE: As per work procedure: HDC WMS CONCRETE FOOTPATH REPAIR
label | FREQ.: As programmed or reactive
label | ACCEPTANCE CRITERIA: F1 FOOTPATH REPAIR AND KERB & CHANNEL MAINTENANCE
label | INSPECTORATE* V/W/H - S/C: V
label | INSPECTORATE* V/W/H - DNZ: V
label | INSPECTORATE* V/W/H - CLIENT: W
label | RECORDS / REMARKS incl NCR ref: Record on: HDC Concrete footpath Repairs QA Spreadsheet/ConQA and hand in to supervisor
checkpoint | Kerb and Channel / Stormwater outlets Downer Activity #143
label | VERIFICATION ACTIVITY: Replacement
label | METHODS OR REFERENCE: As per work procedure: DN-GD-GP092 Repair Broken Kerb and Channel In Situ
label | FREQ.: As programmed
label | ACCEPTANCE CRITERIA: F1 FOOTPATH REPAIR AND KERB & CHANNEL MAINTENANCE
label | INSPECTORATE* V/W/H - DNZ: V
label | INSPECTORATE* V/W/H - CLIENT: W
label | RECORDS / REMARKS incl NCR ref: Record on: HDC Concrete kerb/ Channel Repairs QA Spreadsheet/ConQA and hand in to supervisor