## Table 1
|  |  |  | Inspection and Test Plan – Precast Drainage Structures | [9 empty] | Doc ID: FH-ZU2-QU-ITP007 Rev: 0
Client: Melbourne Airport (APAM) |  |  |  |  | Contract No: CP14038-01 | [7 empty] | Prepared By: John Kakoliris
Project: Taxiway Zulu Project 2.0 | [9 empty] | Reviewed By: Cristin Swar | [5 empty] | Date: 22/04/2024
Construction Process: | [9 empty] | Approved By: Jordan Nicolaou | [5 empty] | Date: 29/04/2024
Specifications: Taxiway Zulu 2.0 Program – Works Specification ZULU-BECA-SPC-00002[C03]
Structure / Component: Precast Drainage Structures
Lot No: |  | Lot Details: |  |  |  | Lot size/Quantity: | [5 empty] | Date:
Item No. | Task/Activity Description |  | Inspection/Test | [7 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility Project Engineer Superintendent Surveyor Foreman |  | Checked by:
|  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection/ Test Method |  |  | Record of conformity |  |  |  |  | Beca | Fulton Hogan |  | Other | Date
1 | Preliminaries
1.1 | Check for correct documentation |  | Prior to commencing activity | Ensure that all employees and subcontractors are:  using the correct and complete set of drawings.  all drawings are the latest revision. | IFC Drawings | Document Review |  |  | This ITP Signed |  | HP* | Project / Site Engineer
1.2 | Implementation of all measures and controls |  | Prior to commencing activity | All necessary measures and controls are being implemented, that is: CEMP, TMP, SWMS & WP. | CEMP, TMP, SWMS & WP | Visual Inspection |  |  | Site and Office Inspection |  | HP* | Project/ Site Engineer/ Supervisor
1.3 | Excavation Permit |  | Prior to commencing activity | Excavation Permit issued by APAM obtained prior to any excavation on site. | Approved Permits | Verify |  |  | Proof of permit & ITP signed |  | HP* | Project/ Site Engineer
2 | Material Approvals
2.1 | Precast Structures |  | Prior to commencing activity | Details of the proposed precast drainage pits, headwalls, and culverts to be as specified on the IFC Drawings. Approval of the shop drawings constitutes a Hold Point.  Outline of sampling and test program | Cl16.6.1 & Manufactu rer’s document s | Document Review |  |  | Aconex Correspond ence |  | HP | Project/ Site Engineer
2.2 | Access Cover and Grates |  | Prior to commencing activity | All Pit covers to conform to AS 3996 and the applicable load class to be as noted on the Drawings. For all drainage pits, pit lids are to be Class D. | Cl16.5.7.1 & IFC Drawings | Verify |  |  | This ITP Signed |  | HP* | Project/ Site Engineer
2.3 | Box Culverts Bedding, Side, Overlay and Backfill Zone Materials. |  | Prior to commencing activity | Materials are to be compliant with the requirements detailed in Cl.16.5.6. Material submission approval. | Cl16.5.6 & 16.6.2.2 | Document Review |  |  | Aconex Correspond ence |  | HP | Project/ Site Engineer Beca
2.4 | Blinding for Drainage Pits and Headwalls |  | Prior to commencing activity | Approved bedding material as per IFC Drawings. | IFC Drawings | Document Review |  |  | Aconex Correspond ence |  | HP* | Project/ Site Engineer
2.5 | Geotextile Fabric |  | Prior to commencing work | Non-woven type complying with the requirements of VicRoads for first stage filter. | Cl.16.5.8 & VicRoads Section 702 | Verify |  |  | Visual Inspection & Delivery Docket |  | IP | Project/ Site Engineer
3 | Material Receival
3.1 | Precast Structure Delivery |  | Each Lot | Ensure each precast component is inspected upon arrival ensuring:  Dimensions are as shown on manufacturer drawings.  All blockouts in correct positions and to dimensions.  No damage to any precast structure component to the satisfaction of FH Engineer  No modifications to the pits are to be made without written approval from manufacturer.  Manufacturer’s conformance report | Cl16.6.1 & IFC Drawings | Visual Inspection |  |  | Order Acceptance Form |  | HP* | Project/ Site Engineer
4 | Drainage Pit, Headwall and Culvert Installation
4.1 | Survey Setout |  | Prior to construction and each lot | Set out the drainage structures as shown on the Drawings to identify the locations, lengths and levels:  All pits, and inlet and outlet structures.  Ends of wing walls and headwalls.  At outlets and inlets of box culvert structures. Setout of each drainage system to constitute a Hold Point. | Cl16.7.1 | Survey |  |  | This ITP Signed |  | HP | Project/ Site Engineer Beca
4.2 | Excavation |  | Each Lot | Excavation to be performed to the minimum depths, widths and batter slopes as shown on the Drawings, regardless of the type of material. Inspection of completed excavation works to constitute a Hold Point. Pits: The shape of the excavation to be as required and the size sufficient to enable construction of the structure. Box Culverts: The width of trench to be not less than the exterior width of the culvert plus 400mm, and not greater than that required for satisfactory backfilling. | Cl16.8 & Cl 16.6.2.2 | Verify |  |  | This ITP Signed |  | HP | Project/ Site Engineer Beca
4.3 | Confirm Ground Conditions |  | Each Structure | Min. 1 x DCP test to be undertaken per drainage line / structure to confirm ground conditions. If the first DCP is inconclusive or fails, additional DCP to be taken as needed based on on-site assessment of the ground. Contractor to notify the Contract Administrator of any area of the foundation with inadequate material to support the proposed drainage structure. Inadequate material is deemed to have a bearing pressure less than 130kPa, equivalent to 4 DCP blows per 100mm, as per note 4 on drawing ZULU-BECA-012- DWG-07102. Inadequate foundation material is to be replaced with a layer of coarse crushed aggregate compacted to 95% relative standard compaction to AS1289 Section 5.5.1 over a geotextile Bidim A29 or approved equivalent. | Cl16.8.2 & Tender Clarification #38 | Site Inspection |  |  | DCP, Test Results |  | TP | Project/ Site Engineer
4.4 | Blinding for Drainage Pits and Headwalls |  | Each Lot | Blinding to be installed as per the depths and widths shown on the Drawings. Pits: 50mm Crushed Rock bedding Headwalls: 100mm 15MPa Concrete blinding and 600x150mm apron cut off wall | IFC Drawings & VicRoads SD | Verify and Visual Inspection |  |  | Delivery Docket & This ITP Signed |  | HP* | Project/ Site Engineer
4.5 | Bedding for Box Culverts |  | Each Lot | Bedding material to comprise of approved select fill and to be placed for the full width of the trench. Upon completion, the bedding is to provide a uniform firm foundation with the top surface of the bedding shaped to the details shown on the drawings. This to constitute a Witness Point. | CL16.5.6. 1 | Verify and Visual Inspection |  |  | Delivery Docket & This ITP Signed |  | WP | Project/ Site Engineer Beca
4.6 | Positioning of Precast Structures |  | Each Lot | Precast structures installed as per survey set out points marked on blinding / bedding layer | Cl.16.8.1 & IFC Drawings | Verify |  |  | This ITP Signed |  | IP | Project/ Site Engineer
4.7 | Backfill Materials for Box Culverts |  | Each Lot | Side Zone, Overlay Zone and Backfill Zone Subject to Vehicle Loads  Approved Select fill material.  Completed in layers with maximum thickness of Cl200mm loose material. Overlay and Backfill Zone – Not Subject to Vehicle Loads  Ordinary fill material compliant with Cl.16.5.6.3 of Beca’s specification | Cl.16.5.6 & IFC Drawings | Verify and Site Inspection |  |  | This ITP Signed |  | IP | Project/ Site Engineer
4.8 | Compaction Requirements (Box Culvert) |  | 1 test per lot. “1 test per layer of bedding for bedding materials and every 2nd layer for side, overlay and backfill zone materials.” | Bed Zone – Minimum 90% SMDD Side Zone Not Subject to Vehicle Loads – Minimum RD of 95% SMDD Side Zone Subject to Vehicle Loads – Minimum of 95% SMDD Overlay Not Subject to Vehicle Loads – Minimum RD of 90% SMDD Backfill Zone Not Subject to Vehicle Loads – Minimum RD of 90% SMDD Overlay and Backfill Zone Subject to Vehicle Loads – Minimum 95% SMDD. Top 300mm under pavement to a minimum of 98% SMDD. | Cl.16.5.6. 1 (b) (iv) | Site Inspection |  |  | Test Records |  | TP | Project/ Site Engineer
Final Inspection The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend:
HP | Hold Point | Work to not proceed past the HP until released by the Superintendent |  |  |  |  | IP | Inspection point |  |  |  | Formal Inspection to be done and recorded
HP* | Fulton Hogan Hold Point | Work to not proceed past the HP* until released by Fulton Hogan |  |  |  |  | TP | Test Point |  |  |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  |  |  | SCP | Survey conformance point |  |  |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
|  |  |  | Inspection and Test Plan – Precast Drainage Structures | [9 empty] | Doc ID: FH-ZU2-QU-ITP007 Rev: 0
Client: Melbourne Airport (APAM) |  |  |  |  | Contract No: CP14038-01 | [7 empty] | Prepared By: John Kakoliris
Project: Taxiway Zulu Project 2.0 | [9 empty] | Reviewed By: Cristin Swar | [5 empty] | Date: 22/04/2024
Construction Process: | [9 empty] | Approved By: Jordan Nicolaou | [5 empty] | Date: 29/04/2024
Specifications: Taxiway Zulu 2.0 Program – Works Specification ZULU-BECA-SPC-00002[C03]
Structure / Component: Precast Drainage Structures
Notes