## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP005 - Stormwater Drainage | itp |  |  |  |  | FH-ZU2-QU-ITP005 - Stormwater Drainage - Rev 0 | 83f202df-0ed7-499d-abd2-6f7b84d31412
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | ○ using the correct and complete set of drawings
label | ○ all drawings are the latest revision.
label | Reference Documents - Drawings and Aconex Register
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Up to date drawing sets & ITP
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: CEMP, TMP, SWMS & WP.
label | Reference Documents - CEMP, TMP, SWMS & WP
label | Inspection/Test Method - Verify
label | Record of conformity - Site and Office Inspection
label | HP*
label | Responsibility - Project/Site Engineer/Supervisor
date | Date Completed:
checkpoint | 1.3 - Excavation Permit
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Excavation Permit issued by APAM obtained prior to any excavation on site.
label | Reference Documents - Excavation Permit
label | Inspection/Test Method - Verify
label | Record of conformity - Proof of signed permit
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 2.0 - Stormwater Products and Materials
checkpoint | 2.1 - Drainage Pipes (RCPs)
label | Frequency - Prior to commencem ent of works
label | Acceptance Criteria - Drainage pipes supplied in accordance with AS4058.
label | ○ Material submission approval.
label | Reference Documents - CL16.6.1
label | Aconex ref: DCWC Mgt-GCOR-009281
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Pipe Support Cradles
label | Frequency - Prior to commencem ent of works
label | Acceptance Criteria - Pipe to sit on firm foundation with pipe support cradles.
label | ○ Material submission/ Shop drawing submission.
label | Reference Documents - Cl16.5.6.1
label | Aconex ref: DCWC Mgt-GCOR-009496
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.3 - Encasement Material
label | Frequency - Prior to commencem ent of works
label | Acceptance Criteria - Encasement Material to be 5Mpa lean mix concrete for all RCP’s.
label | ○ Material submission approval.
label | Reference Documents - Cl16.5.6.1 & 16.6.2.2 & Tender Clarifications #36
label | Aconex ref: BecaCPL-RTRFI-000089
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Backfill Material
label | Frequency - Prior to commencem ent of works
label | Acceptance Criteria - Backfill material to be 6% cement stabilised sand to pavement formation level.
label | ○ Material submission approval.
label | Reference Documents - Cl16.5.6, 16.5.6.3 (a)(i) & 16.6.2.2.
label | Aconex ref: BecaCPL-GCOR-000802
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex Ref
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Stormwater Delivery
checkpoint | 3.1 - RCP Delivery
label | Frequency - Each Delivery
label | Acceptance Criteria - Drainage pipes supplied and delivered as per approved Material submission.
label | ○ Manufacturer’s conformance report.
label | Reference Documents - CL16.6.1 & AS4058
label | Inspection/Test Method - Verify
label | Record of conformity - Order Acceptance Form
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 4.0 - Construction Activities
checkpoint | 4.1 - Survey Setout
label | Frequency - Prior to construction and each lot
label | Acceptance Criteria - Set out the stormwater drainage as shown on the Drawings to identify the locations, lengths and levels at outlets and inlets of pipes.
label | ○ This constitutes a Hold Point.
label | Reference Documents - Cl16.7.1
label | Inspection/Test Method - Survey
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Excavation
label | Frequency - Each Lot
label | Acceptance Criteria - All excavation to be performed to the minimum depths, widths and batter slopes as shown on the Drawings, regardless of the type of material.
label | ○ Trench excavation is to commence at the downstream end, where practical.
label | ○ The width of trench to be such that the horizontal clearance from the outside of the pipe to wall of the trench to be minimum 300mm when under the runway and taxiway graded strip. Trench width outside of the runway and taxiway graded strip to be the greater of 150mm and D/6.
label | ○ Subgrade Inspection to constitute a Hold Point.
label | Reference Documents - Cl16.8.1 & Cl16.6.2.2
label | Inspection/Test Method - Verify
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Site Dewatering
label | Frequency - Each Lot
label | Acceptance Criteria - Excavations are to be kept free from water during construction and backfilling and provide pumps, well-points or other equipment as necessary.
label | ○ Any temporary works to be designed such that flooding upstream of the diversion does not occur. This constitutes a Hold Point.
label | Reference Documents - Cl16.8.4
label | Inspection/Test Method - Site Inspection
label | Record of conformity - Aconex Ref
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Confirm Ground Conditions
label | Frequency - Each Drainage Line
label | Acceptance Criteria - Min. 1 x DCP test to be undertaken per drainage line / structure to confirm ground conditions. If the first DCP is inconclusive or fails, additional DCP to be taken as needed based on on-site assessment of the ground.
label | ○ Contractor to notify the Contract Administrator of any area of the foundation which contains material that is inadequate to support the proposed drainage structure.
label | ○ Inadequate material is deemed to have a bearing pressure less than 130kPa, equivalent to 4 DCP blows per 100mm, per note 4 on drawing ZULU-BECA-012-DWG-07102.
label | ○ Inadequate foundation material is to be replaced with a layer of coarse crushed aggregate compacted to 95% relative standard compaction to AS1289 Section 5.5.1 over a geotextile Bidim A29 or approved equivalent.
label | Reference Documents - Cl16.8.2 & Tender Clarification 179
label | Inspection/Test Method - Site Inspection
label | Record of conformity - DCP, Test Results
label | TP
label | Responsibility - Project/Site Engineer/ Beca
date | Date Completed:
checkpoint | 4.5 - Bedding
label | Frequency - Each Lot
label | Acceptance Criteria - Bedding material/subgrade to be prepared for laying the pipes. Pipe support cradles to be placed on firm bedding. This constitutes a Witness Point.
label | Reference Documents - Cl.16.6.2.1
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
checkpoint | 4.6 - Laying of Pipes (Sample)
label | Frequency - First Lot
label | Acceptance Criteria - Initial sample 20m length of concrete pipeline to be laid and approved by the Contract Administrator for line and level before continuing construction of pipe network, Hold Point.
label | Reference Documents - Cl.16.9.1.6
label | Inspection/Test Method - Verify & Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Laying and Jointing of Pipes
label | Frequency - Each Lot
label | Acceptance Criteria - Concrete Pipes to be rigidly supported by approved steel pipe cradle during laying.
label | ○ Pipes to be placed with spigot end facing downstream.
label | ○ Pipes to be laid with the word ‘TOP’ and or lifting holes uppermost. Lifting holes to be plugged after installation.
label | ○ All Concrete Pipes to be checked and subject to the approval of the Contract Administrator prior to commencement of backfilling, Hold Point.
label | Reference Documents - Cl.16.9.1.6
label | Inspection/Test Method - Verify & Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.8 - Survey
label | Frequency - Each Lot
label | Acceptance Criteria - The alignment, level and grade to be checked on the obvert of every third concrete pipe unit.
label | ○ Pipes shall be laid to the lines, grades and invert levels shown on the Drawings. No deviation shall be made without the prior approval of the Contract Administrator.
label | Deviation from Invert Level
label | ○ Maximum deviation from design invert level to not exceed 20mm and not result in zero grade or reversal of grade in any length of concrete pipe.
label | ○ Where the design pipe grade is less than 1%, maximum deviation from pipe socket to pipe socket does not exceed 20 mm.
label | ○ Maximum deviation from design invert level between upstream and downstream structures to not exceed 20mm and not result in zero grade or reversal of grade in any length of concrete pipe.
label | Deviation from Alignment
label | ○ Maximum deviation of the concrete pipe from the alignment shown on the Drawings to not exceed 25mm.
label | Reference Documents - Cl.16.7 & 16.9.1.6
label | Inspection/Test Method - Survey
label | Record of conformity - Survey Report
label | SCP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.9 - Backfill Materials
label | Frequency - Each Lot
label | Acceptance Criteria - RCP’s under Runway and Taxiway Graded Strip
label | ○ 5MPa wet lean mix to 200mm above pipe obvert
label | ○ 6% Cement Stabilised Sand to pavement formation level
label | RCP’s outside Runway and Taxiway Graded Strip
label | ○ 5MPa wet lean mix 150mm above pipe overt completed in stages
label | ○ Site won material completed in 200mm loose layer thickness (maximum) to pavement formation level or 6% stabilised sand
label | Reference Documents - Cl.16.5.6 & IFC Drawings & Tender Clarification #164
label | Inspection/Test Method - Verify and Site Inspection
label | Record of conformity - Delivery Docket and ITP Signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 5.0 - Testing and Inspection
checkpoint | 5.1 - Compaction Requirements (RCPs)
label | Frequency - 1 test per lot.
label | Acceptance Criteria - Concrete Backfill Under Runway and Taxiway Graded Strip
label | ○ 1 compressive strength test for each 50m3 of backfill
label | Concrete Backfill Outside Runway and Taxiway Graded Strip
label | ○ 1 compressive strength test for each 100m3 of backfill
label | Backfill Zone - Outside the Runway and Taxiway Graded Strip
label | ○ Minimum RD of 95% SMDD (1 lot consists of every 50m3 for concrete backfill and every 2nd layer of backfill zone material every 40m.)
label | Reference Documents - Cl.16.5.6.3 (c), Cl.16.9.6 & AS3798.1 Table 8.1
label | Inspection/Test Method - Site Inspection
label | Record of conformity - Test Records
label | TP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 5.2 - Inspection of drainage lines
label | Frequency - Prior to constructing pavement
label | Acceptance Criteria - CCTV inspection of RCPs required at the completion of the works.
label | ○ Submission of CCTV footage to the Contract Administrator for review is a Hold Point.
label | Reference Documents - Cl.16.10.1
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Ref
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date:
checklist | ITP007 - Precast Drainage Structures | itp |  |  |  |  | FH-ZU2-QU-ITP007 - Precast Drainage Structures - Rev 0 | 402839a9-e811-488c-99cd-5670e095de16
section | 1.0 - Preliminaries
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | ○ using the correct and complete set of drawings.
label | ○ all drawings are the latest revision.
label | Reference Documents - IFC Drawings
label | Inspection/Test Method - Document Review
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: CEMP, TMP, SWMS & WP.
label | Reference Documents - CEMP, TMP, SWMS & WP
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Site and Office Inspection
label | HP*
label | Responsibility - Project/Site Engineer/Supervisor
date | Date Completed:
checkpoint | 1.3 - Excavation Permit
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Excavation Permit issued by APAM obtained prior to any excavation on site.
label | Reference Documents - Approved Permits
label | Inspection/Test Method - Verify
label | Record of conformity - Proof of permit & ITP signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 2.0 - Material Approvals
checkpoint | 2.1 - Precast Structures
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Details of the proposed precast drainage pits, headwalls, and culverts to be as specified on the IFC Drawings.
label | ○ Approval of the shop drawings constitutes a Hold Point.
label | – Outline of sampling and test program
label | Reference Documents - Cl16.6.1 & Manufacturer's documents
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex Correspond ence
label | HP
label | Responsibility - Project/Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Access Cover and Grates
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - All Pit covers to conform to AS 3996 and the applicable load class to be as noted on the Drawings.
label | ○ For all drainage pits, pit lids are to be Class D.
label | Reference Documents - Cl16.5.7.1 & IFC Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.3 - Box Culverts Bedding, Side, Overlay and Backfill Zone Materials.
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Materials are to be compliant with the requirements detailed in Cl.16.5.6.
label | ○ Material submission approval.
label | Reference Documents - Cl16.5.6 & 16.6.2.2
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex Correspond ence
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Blinding for Drainage Pits and Headwalls
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Approved bedding material as per IFC Drawings.
label | Reference Documents - IFC Drawings
label | Inspection/Test Method - Document Review
label | Record of conformity - Aconex Correspond ence
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.5 - Geotextile Fabric
label | Frequency - Prior to commencing work
label | Acceptance Criteria - Non-woven type complying with the requirements of VicRoads for first stage filter.
label | Reference Documents - Cl.16.5.8 & VicRoads Section 702
label | Inspection/Test Method - Verify
label | Record of conformity - Visual Inspection & Delivery Docket
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 3.0 - Material Receival
checkpoint | 3.1 - Precast Structure Delivery
label | Frequency - Each Lot
label | Acceptance Criteria - Ensure each precast component is inspected upon arrival ensuring:
label | ○ Dimensions are as shown on manufacturer drawings.
label | ○ All blockouts in correct positions and to dimensions.
label | ○ No damage to any precast structure component to the satisfaction of FH Engineer
label | ○ No modifications to the pits are to be made without written approval from manufacturer.
label | ○ Manufacturer’s conformance report
label | Reference Documents - Cl16.6.1 & IFC Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Order Acceptance Form
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 4.0 - Drainage Pit, Headwall and Culvert Installation
checkpoint | 4.1 - Survey Setout
label | Frequency - Prior to construction and each lot
label | Acceptance Criteria - Set out the drainage structures as shown on the Drawings to identify the locations, lengths and levels:
label | – All pits, and inlet and outlet structures.
label | – Ends of wing walls and headwalls.
label | – At outlets and inlets of box culvert structures.
label | ○ Setout of each drainage system to constitute a Hold Point.
label | Reference Documents - Cl16.7.1
label | Inspection/Test Method - Survey
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Excavation
label | Frequency - Each Lot
label | Acceptance Criteria - Excavation to be performed to the minimum depths, widths and batter slopes as shown on the Drawings, regardless of the type of material.
label | ○ Inspection of completed excavation works to constitute a Hold Point.
label | ○ Pits: The shape of the excavation to be as required and the size sufficient to enable construction of the structure.
label | ○ Box Culverts: The width of trench to be not less than the exterior width of the culvert plus 400mm, and not greater than that required for satisfactory backfilling.
label | Reference Documents - Cl16.8 & Cl 16.6.2.2
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project/Site Engineer, Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Confirm Ground Conditions
label | Frequency - Each Structure
label | Acceptance Criteria - Min. 1 x DCP test to be undertaken per drainage line / structure to confirm ground conditions. If the first DCP is inconclusive or fails, additional DCP to be taken as needed based on on-site assessment of the ground.
label | ○ Contractor to notify the Contract Administrator of any area of the foundation with inadequate material to support the proposed drainage structure. Inadequate material is deemed to have a bearing pressure less than 130kPa, equivalent to 4 DCP blows per 100mm, as per note 4 on drawing ZULU-BECA-012- DWG-07102.
label | ○ Inadequate foundation material is to be replaced with a layer of coarse crushed aggregate compacted to 95% relative standard compaction to AS1289 Section 5.5.1 over a geotextile Bidim A29 or approved equivalent.
label | Reference Documents - Cl16.8.2 & Tender Clarification #38
label | Inspection/Test Method - Site Inspection
label | Record of conformity - DCP, Test Results
label | TP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.4 - Blinding for Drainage Pits and Headwalls
label | Frequency - Each Lot
label | Acceptance Criteria - Blinding to be installed as per the depths and widths shown on the Drawings.
label | ○ Pits: 50mm Crushed Rock bedding
label | ○ Headwalls: 100mm 15MPa Concrete blinding and 600x150mm apron cut off wall
label | Reference Documents - IFC Drawings & VicRoads SD
label | Inspection/Test Method - Verify and Visual Inspection
label | Record of conformity - Delivery Docket & This ITP Signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.5 - Bedding for Box Culverts
label | Frequency - Each Lot
label | Acceptance Criteria - Bedding material to comprise of approved select fill and to be placed for the full width of the trench.
label | ○ Upon completion, the bedding is to provide a uniform firm foundation with the top surface of the bedding shaped to the details shown on the drawings. This to constitute a Witness Point.
label | Reference Documents - CL16.5.6. 1
label | Inspection/Test Method - Verify and Visual Inspection
label | Record of conformity - Delivery Docket & This ITP Signed
label | WP
label | Responsibility - Project/Site Engineer Beca
date | Date Completed:
checkpoint | 4.6 - Positioning of Precast Structures
label | Frequency - Each Lot
label | Acceptance Criteria - Precast structures installed as per survey set out points marked on blinding / bedding layer
label | Reference Documents - Cl.16.8.1 & IFC Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.7 - Backfill Materials for Box Culverts
label | Frequency - Each Lot
label | Acceptance Criteria - Side Zone, Overlay Zone and Backfill Zone Subject to Vehicle Loads
label | ○ Approved Select fill material.
label | ○ Completed in layers with maximum thickness of Cl200mm loose material.
label | Overlay and Backfill Zone – Not Subject to Vehicle Loads
label | ○ Ordinary fill material compliant with Cl.16.5.6.3 of Beca’s specification
label | Reference Documents - Cl.16.5.6 & IFC Drawings
label | Inspection/Test Method - Verify and Site Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.8 - Compaction Requirements (Box Culvert)
label | Frequency - 1 test per lot.
label | ○ "1 test per layer of bedding for bedding materials and every 2nd layer for side, overlay and backfill zone materials."
label | Acceptance Criteria - Bed Zone – Minimum 90% SMDD
label | ○ Side Zone Not Subject to Vehicle Loads – Minimum RD of 95% SMDD
label | ○ Side Zone Subject to Vehicle Loads – Minimum of 95% SMDD
label | ○ Overlay Not Subject to Vehicle Loads – Minimum RD of 90% SMDD
label | ○ Backfill Zone Not Subject to Vehicle Loads – Minimum RD of 90% SMDD
label | ○ Overlay and Backfill Zone Subject to Vehicle Loads – Minimum 95% SMDD. Top 300mm under pavement to a minimum of 98% SMDD.
label | Reference Documents - Cl.16.5.6. 1 (b) (iv)
label | Inspection/Test Method - Site Inspection
label | Record of conformity - Test Records
label | TP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: