## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-177-CIV-SSB-Type A Fill-Structures | itp |  |  |  |  | ITP-177-CIV-SSB-Type A Fill-Structures Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-177-CIV-SSB-Type A Fill - Structures
label | ITP Description: SSB-Type A Fill - Structures
label | Discipline (e.g. CIV/STR/RAIL): 177-CIV
label | Revision Number: 0
label | Revision Date: 3/06/2024
label | ITP created by: Jay Bradley Power
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: IFC Drawings VR 204, RC500.20, RC500.5
section | Preliminaries-Materials
checkpoint | 2.1 Material Conformance
label | REFERENCE: VR 204.04 b) Table 204.041
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | ○ Assigned CBR≥ 6%
label | ○ Swell ≤ 1.5%
label | ○ Permeability N/A
label | Grading:
label | ○ 75.0mm 100%
label | ○ 4.75mm 40-80%
label | ○ 0.075mm 10-40%
textbox | Reference: Material approval in Teambinder:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Document Review
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Supplier Material Conformance Certificate
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries-Documentations
checkpoint | 3.1 Pre-Commencement of Fill Works
label | REFERENCE: VR 204.10 (b), VR 204.11 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
textbox | Reference: Previous layer Lot Number:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencement of fill works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set Out
label | REFERENCE: Design Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
label | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot prior to commencement
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Signed ITP, Lot Map
date | Date Completed:
section | Type A Fill/Verge Activities
checkpoint | 5.1 Placing of Fill
label | REFERENCE: VR 204.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
checkpoint | 5.2 Test Roll
label | REFERENCE: VR 173.03, VR 204.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test Roll as per 173.03
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot/Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 Compaction Testing
label | REFERENCE: Table 204.131, VR 204.14 c) Table 204.142
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Testing as per 204. Ensure testing is tracked and reports available.
label | Standard Compactive Effort
label | ○ For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | Compaction and Moisture content
label | ○ Scale A: Characteristic Density Ratio 99%.
label | ○ Scale B: Characteristic Density Ratio 98%.
label | ○ Scale C: Mean Value of Density Ratio: 100%
label | Lot size - the leser of one day's production or 5,000sqm
label | ATTACH: COMPACTION TEST RESULTS
label | – – – – – – – – – – – – – – – – –
label | METHOD: Review Document
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Sign ITP, Attach Compaction Test Report
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.2 Survey Conformance andPreparation of final surface
label | REFERENCE: VR 204.15, VR 204.03f,g and h
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | ○ The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Level tolerances Scale C: Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Top of Type A/Verge
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Survey Conformance Report
date | Date Completed:
checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP