## Resources
Type | Id | Name | Values | Prompting Name | Postfix | Resource Id
checklist |  | ITC - Type C Earthworks | itp | Type C Earthworks |  | 2ccd3d0f-3e2b-4f0f-a09b-82bc9892a00c
section |  | PRELIMINARIES
checkpoint |  | Design Issued for Construction
checkpoint |  | Drawings Issue for Construction
checkpoint |  | Material Hold Points Released
checkpoint |  | Survey Request
checkpoint |  | Traffic Management Plan Approved
checkpoint |  | Subcontractor/Provider approved?
checkpoint |  | Kick-off meeting (Subcontractor)
section |  | CONSTRUCTION
checkpoint |  | Safety; SWMS
note | d2ab4352-cf52-5b42-b9ac-56085d230f5d | Applicable Standard / Reference - HSMP
note | e72e17dc-4756-53a3-8b33-4222bf7af579 | Acceptance Criteria - SMWS to be written for each activity on Project and shall be reviewed by a competent person.
number | 973c18da-8a92-5f03-a556-1d023c4955f0 | Submitted to the client |  |  | days prior to commencement of Activity.
note | a360f659-cf22-5b1e-8492-1dba4964dc88 | Frequency - Each Activity
note | d26120aa-276e-51a2-8f0f-7e22bad8249e | Verification Records - Records
note | 9fb0dd41-3a76-540c-8246-608338509c97 | Action Respon. - PE/SE
date | 9fd532c9-f47f-5454-bec4-8ec6f6dafc42 | Date:
checkpoint |  | Environmental Controls
note | 2b720312-56bb-55de-bc4c-37a6c2c22eda | Applicable Standard / Reference - EMP
note | 365eb977-0170-56b3-9b7a-21e76a8f13f5 | Acceptance Criteria - No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP.
note | 9501355a-1e05-567f-9344-e1d3838fe2c9 | Frequency - Each Activity
note | bf45d789-d9b5-502d-af07-91993176f478 | Verification Records - ECP
note | 2f0c8452-e957-553f-bb34-6d55bb5157a4 | Action Respon. - PE/SE
date | d1df9d83-f267-535b-8042-0813383f7c7e | Date:
checkpoint |  | Excavation Permit
note | 8b91083f-e339-524c-a9d5-bb1059c8f289 | Applicable Standard / Reference - OHS
note | 061245b4-4f15-58dd-96e9-1c5076668343 | Acceptance Criteria - DBYD information available on site, Excavation permit issued and spotter at location before commencement of excavation works
note | 5e228316-ea87-5b6f-b2a0-0a391adac718 | Frequency - Each Lot
note | e68d26eb-3164-558e-a735-5a3c103ead0a | Verification Records - Records
note | d877424e-2f75-5c95-882b-afa1c82f2793 | Action Respon. - PE/SE
date | bed0491b-47a6-529a-97c7-00d27329623e | Date:
checkpoint |  | Survey Control
note | e67de314-0d8c-585c-a4e3-04385b225c50 | Applicable Standard / Reference - VR204.03 (a), (b, c)
note | d992258b-c13c-5d63-b156-13ce01e5c6db | Acceptance Criteria - All Earthworks shall be finished to conform to the levels, lines, grades and cross sections showed in the plans.
note | 44e8bf29-c5a9-5214-81fb-d45f863c7a49 | Frequency - Each Lot
note | e6cae79e-af49-522f-86a2-7da16add872f | Verification Records - Setout
note | 305bd8df-b92f-5cf9-9e62-6d1bca701be9 | Action Respon. - Surveyor
date | a768d030-bb19-5ceb-aa11-25b5aac5ba6b | Date:
checkpoint |  | Material - Type C
note | 02d9ac33-f47a-5bc6-b972-867c59991a7e | HP
note | 15a16939-151b-5dae-91ae-7cb0b612d53a | Applicable Standard / Reference - VR204.04 (b)
note | d4dda14d-267f-522d-b624-43fbf4a24ce5 | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type C material unless otherwise approved by the Superintendent.
note | 497dea33-4d7e-5a50-88fb-eee745932e25 | Frequency - Each Lot
note | 5effff8f-43af-55f2-b94a-761ebc709c75 | Verification Records - Visual
note | 2b06b595-64b5-51df-a605-927f469bf812 | Action Respon. - FM
date | 0ea96a09-61d3-5fad-a6dd-1cee7bbb97db | Date:
signoff |  | HOLD POINT
checkpoint |  | Site excavation - material category
note | 3038d5e9-12d7-5db3-8884-48a67ffeb7ef | HP
note | 1a23d328-6b4a-54cd-922e-f7cd5cd67678 | Applicable Standard / Reference - VR204.06 (b)
note | f8a34ffd-9d74-5a1d-ac55-41f4fd9f3f19 | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
note | 13e36bc4-bd8a-596b-9cbd-eb2f0fc56bd1 | Frequency - Each Lot
note | 6d5b5d29-1625-5fc3-a94a-b3657461273c | Verification Records - Visual
note | 5541317d-d724-51cd-b3e7-bcbfc35c0957 | Action Respon. - FM
date | b8ccec88-a397-500b-8731-d6c5ebf67a50 | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - Groundwater Seepage
note | 5caaf58f-6878-59d0-84f4-4ce9e2c0b864 | HP
note | 566e4154-c451-58c8-8d18-d020fdf71d76 | Applicable Standard / Reference - VR204.06 (h)
note | 642ef667-b4df-5132-926c-dc1f7b6335b2 | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
note | 682106e1-fe7f-5f3c-a529-72a6e81d6604 | Frequency - Each Lot
note | 0ea3cc8b-8364-5c60-9864-180a866defac | Verification Records - Visual
note | 3412ba23-89f1-5cf3-ae1b-7bbb538c9d78 | Action Respon. - PE/SE
date | ea3b05c6-b1b9-5d2e-9b51-70b2e8863664 | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - treatment of Unsuitable Material
note | 246112fa-7b21-5f01-b9dc-d0af926922ff | HP
note | 6ae56856-d595-53ff-91e9-15221ce75c82 | Applicable Standard / Reference - VR204.07 (d)
note | fcf89922-365f-575b-80f5-428d512de424 | Acceptance Criteria - Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review.
note | b316aa2d-57d8-5662-ae50-37b372054a9e | Frequency - Each Lot
note | ad402816-0b1b-5dc3-b057-675212cc4689 | Verification Records - Visual
note | cb1bc34d-d436-5e9f-996d-45ae1a43557c | Action Respon. - FM
date | 3852298b-46e1-5efe-a801-5dd93d5e170c | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - Fill construction
note | 4259831b-a4c0-5872-b984-9b6ca5b7812c | HP
note | 0fac03b7-d96c-5d74-ac85-f22f7e9cf0e6 | Applicable Standard / Reference - VR204.10 (b)
note | b330cf3d-1dec-5075-8165-eee09679cc0e | Acceptance Criteria - The Contractor shall not commence placing of any fill on the prepared surface until the area has been reviewed by the Superintendent.
note | 85decdfe-f2f1-5207-8ed3-f931cbd7564d | Frequency - Each Lot
note | def0fe93-9888-5829-b7b5-4aa244e67192 | Verification Records - Visual
note | 69b440f4-5166-5ca1-9a20-baefa74e92f6 | Action Respon. - FM
date | d9041c30-3e59-5e51-bd04-2fc0ec220335 | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - Fill at Structures (wing walls, culverts >1200mm)
note | 225636cc-0b5c-529a-877f-4b1f2b65bd4c | HP
note | 4ba546b4-b94b-5c47-a358-35bde0466807 | Applicable Standard / Reference - VR204.11 (b)
note | 77d9ed98-6684-5442-a79b-026912ef1e93 | Acceptance Criteria - No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent.
note | c8c69d23-d619-5649-abfa-7c5ea73fad3f | Frequency - Each Lot
note | 2150abba-d67d-5c43-beb1-34537dcb6526 | Verification Records - Visual
note | f3cc1f09-9cb0-501d-a774-3214b22163ae | Action Respon. - FM
date | a83c4dc3-2363-5d8c-9d6a-4083cfa6e664 | Date:
signoff |  | HOLD POINT
checkpoint |  | Test Rolling
note | c8c6b663-a916-5986-a08a-1e08e6446cbe | Applicable Standard / Reference - VR173.03, VR204.12
note | a00dad14-b8ac-5fa1-af21-10aa705ddbe9 | Acceptance Criteria - Undertake test roll prior to placement of fill/or proceeding layer.
note | ac6ec417-83ad-5893-85c9-b7cdd9b20fa0 | Frequency - Each Lot
note | 0babd9ce-7f55-5a39-86af-2f70b34de880 | Verification Records - Visual
note | 25363048-20c5-5238-92fc-08057df2a17b | Action Respon. - FM
date | bb0033d2-55dc-50a1-b3ab-2652468a1890 | Date:
checkpoint |  | Compaction - Lot size
note | 13deffdb-b71f-5af6-aa96-10306c70e45e | Applicable Standard / Reference - VR204.13
note | 558533b1-2476-5e9d-87db-9616d94fc9b6 | Acceptance Criteria - Type C: 10,000m2 or one day's production, whichever is the lesser
note | 2f5cbc15-0a3a-5a4f-afd5-0ea52bcb86b9 | Frequency - Each Lot
note | 7fa7b6d5-a4ec-5aa4-bf5d-f97a4a99fb6f | Verification Records - Records
note | 3758410a-c562-52b9-9746-ef3d2156b85e | Action Respon. - PE/SE
date | c0030969-f54c-565b-a257-cfcf3d4625bc | Date:
checkpoint |  | Compaction
note | 5607f70a-6efc-537e-bcf9-85f9cd709236 | Applicable Standard / Reference - VR204.13 (b), VR204.14
note | 1dda1615-fcef-5751-9643-d156c3f2d15e | Acceptance Criteria - Compaction
note | 76aa9873-9378-5207-aa75-dd07f770681d | ○ All Type C material should conform to 95% of a standard density
note | 440991ff-9f3f-57f8-a3ab-f88b029c6d74 | ○ Max. particle size <100mm (visual inspection)
note | ba390d5b-ba0e-582f-aaae-2d60dbc6c061 | Frequency - 1 test per each 6 lots
note | 30f38b23-6263-5a7e-b02c-a667193e68cd | Verification Records - Records/Visual
note | 38516a2d-3e09-5e9d-b0ce-266823d02898 | Action Respon. - FM
date | 529966e8-7b84-5ba2-9df0-81003a71c726 | Date:
checkpoint |  | Other Contract Specific Requirements
textbox | 817bc309-2c03-5b43-9b3b-bddcae5ba5db | Requirement(s):
date | 74efc221-af12-5383-a44b-d2ea2f5e0f81 | Date:
checklist |  | ITC - Drainage Pit | itp | Drainage Pit |  | 4f94952e-2787-426f-a0fb-e44ba97fe38c
section |  | PRELIMINARIES
checkpoint |  | Design Issued for Construction
checkpoint |  | Drawings Issue for Construction
checkpoint |  | Material Hold Points Released
checkpoint |  | Survey Request
checkpoint |  | Traffic Management Plan Approved
checkpoint |  | Subcontractor/Provider approved?
checkpoint |  | Kick-off meeting (Subcontractor)
section |  | CONSTRUCTION
checkpoint |  | Safety; SWMS
note | 2c069adf-4821-5a45-943c-91bd3f3da84c | W
note | e0152f14-13b9-5112-a471-0cac2614eedd | Applicable Standard / Reference - HSMP
note | 5ce42bba-c891-52b7-889b-4bb0a50dd758 | Acceptance Criteria - SMWS to be written for each activity on Project and shall be reviewed by a competent person.
number | 27d4ed61-748a-504a-aa6f-d9b072f43468 | Submitted to the client |  |  | days prior to commencement of Activity.
note | 61580692-5546-539e-9d23-81328021af21 | Frequency - Each Activity
note | 8642d739-1db3-5f8f-b9a9-9caba849ecf3 | Verification Records - Records
note | 11ea7f75-7cde-5983-982c-45d38574fde9 | Action Respon. - PE/SE
date | 51cd4805-d0f1-553e-8827-cf07aeaff7a1 | Date:
checkpoint |  | Environmental Controls
note | 80551931-0635-541a-922f-4b51490b28c8 | W
note | 29202470-c8e1-579d-902a-55ba8ef651dc | Applicable Standard / Reference - EMP
note | 2e1ae175-4480-5694-876f-88555b7dd770 | Acceptance Criteria - No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP.
note | 7550f321-aed3-5ddb-aeee-25a7b7e4ec49 | Frequency - Each Activity
note | 17168461-2183-5fb1-b418-588f523ec57b | Verification Records - ECP
note | 902e4ae2-ba5c-5e72-bc29-8149076bbc6a | Action Respon. - PE/SE
date | bd762d6a-fb97-5b0a-85c8-291d16ff6381 | Date:
checkpoint |  | Excavation Permit
note | 307a07ee-5883-5b62-ba3a-70b1f70993bc | H
note | b5dfd2d3-aad4-5e4f-9339-09a0a67ba802 | Applicable Standard / Reference - OHS
note | fbcb6396-9607-5a63-a05e-ad7923cd9fde | Acceptance Criteria - DBYD information available on site, Excavation permit issued and spotter at location before commencement of excavation works
note | e74b651e-7685-52e7-a2ee-a9ca13725078 | Frequency - Each Lot
note | acc9f7c8-4e27-5ac5-8904-0550424a717a | Verification Records - Records
note | 4173bb78-72a2-5e85-ba3c-24d152c74f48 | Action Respon. - PE/SE
date | f0a4b56e-dc66-5486-acf9-db65953fd434 | Date:
signoff |  | HOLD POINT
checkpoint |  | Manufacture Precast Documentation (QMP, ITPs,ITCs, Shop Drawings, Reports)
note | d127e527-1d31-50af-a192-83a6d58880d7 | W
note | e4eee257-3704-5f5e-a337-be4b0f2349e0 | Applicable Standard / Reference - ITP
note | aead8a78-6fc1-5124-974a-5e3c0f030d71 | Acceptance Criteria -
note | 36d8b662-5774-57dc-9b8d-2d825c655a3c | Frequency - For Each Manufacture
note | 7ba32e22-64df-525b-86fe-f6216f6c6b61 | Verification Records - Records
note | 87095faa-ad8b-5fdb-8aa9-56e9a0f2f3f4 | Action Respon. - PE/SE
date | c4316d42-694c-5d57-8925-58d2503b32dd | Date:
checkpoint |  | Delivery Dockets
note | 2ab792f9-a90a-5c7d-bc19-31dca2a22245 | R
note | b2d3e8a2-edc9-5bfd-ad41-859c26b3ab94 | Applicable Standard / Reference - ITP
note | d6f13cd5-e466-58c1-bf61-74ae3778495c | Acceptance Criteria - Delivery Docket for each Pit must be clearly identified and uploaded to the lot
note | 5aff589b-0bba-5a0e-8d66-c4b3514424a2 | Frequency - Each Pit
note | 5a98f8fc-e48b-55dc-a3cd-fea25ab101ff | Verification Records - Delivery Docket
note | d4415b4f-58ca-5207-aa71-97584e3710fe | Action Respon. - PE/SE
date | 60a7f091-073e-509b-a6d3-319913121f34 | Date:
checkpoint |  | Unit Identification (Pit number, other)
note | 7dab31a0-58bd-5563-bf2e-969013d3797f | S
note | 3d718021-2b1a-51c3-9096-3092ef6151bf | Applicable Standard / Reference - ITP
note | bd81b91b-0d9a-5eee-b305-227f379b6b73 | Acceptance Criteria - Pit Unit Identification must be visible after installation for further identification
note | 66d611e9-1a5c-535b-9ae2-071508226db4 | Frequency - Each Pit
note | fef79108-3e9b-55a2-9552-b1a334842d31 | Verification Records - Picture
note | a0951f6e-e868-55f6-9d64-d60f848f3b8d | Action Respon. - PE/SE
date | ce3e3bcc-c3b5-536c-8f06-1c00e75c0e31 | Date:
checkpoint |  | Materials
note | da962fd8-e879-50fc-b0f0-664c061e3c47 | W
note | 9ce49f24-cf2a-5a82-9b81-d89dd16cc432 | Applicable Standard / Reference - VR705.04 (c) & (d)
note | 24dfc8b2-8ab9-5aff-9248-16e84d34a552 | Acceptance Criteria - Concrete - Shall be N32 standard strength grade?
note | 52dc7ff4-71a0-53b1-8873-a19fe3a96da8 | ○ Covers, Lids, Grates, Lintels as shown on drawings
note | 56a9ffe2-d274-58ae-995d-cc07d7123853 | ○ Step Irons - Those manufactured from 13mm steel bar covered with polypropylene plastic must be approved by superintendent
note | f1aae10d-9079-5023-8aef-784b4084c34e | Frequency - Once
note | c3274c1e-a0b3-5386-83c9-a89aa3da0b40 | Verification Records - Records
note | 13d4a3ea-ce5d-5b2c-bfaa-5389f1adf6d7 | Action Respon. - PE/SE
date | 4a1c36dd-07eb-5167-a8e5-7c563d1c4eac | Date:
checkpoint |  | Excavation - Precast Pits
note | c17fcd2a-b755-52f8-809d-28d30fe57a7f | I
note | 123bd835-70ac-5fa0-811e-a7940011611e | Applicable Standard / Reference - VR705.05 (b)
note | 3c4c7a69-63f7-5f61-b312-e3ad1774efd3 | Acceptance Criteria - Clearance from all external faces of the pit to each face of the excavation shall be not less than 400mm.
note | 014dce96-92f5-5fe5-bf62-f9f926b24429 | ○ Bedding shall be supplied, placed and compacted to a thickness not less than 80mm on a clay foundation or 150mm on a rock foundation.
note | d3fc06b1-e29d-56d7-be20-7d6a96f9ddb3 | Frequency - Each Lot
note | d4c8f312-9a21-5134-870b-0e87d31fe43e | Verification Records - Visual / Pictures
note | 7d82ca6f-a303-5d35-9bae-92baa3490494 | Action Respon. - SE/FM
date | ebaa179e-e15b-5546-b5f5-fd816a0f9708 | Date:
checkpoint |  | Precast Pits
note | d9641a04-4e01-5bc3-918f-7ab7e3e56a41 | I
note | 960fc058-f56e-59cd-897c-cf800f40cba3 | Applicable Standard / Reference - VR705.09
note | bdb71d8b-78cc-55b2-8e79-a01c84a162b2 | Acceptance Criteria - Holes for subsurface drains should be 150mm unless specified otherwise.
note | ce817e3f-59e6-5762-90f1-141afaf82c0d | ○ Weepholes of 50mm shall be provided in all precast pits (see spec for location)
note | 94ecf57a-277e-5331-8552-ebcc41360472 | ○ Segmented pits require a minimum 15mm rebate.
note | 943a07ff-7cb5-5028-b6b4-9c2e4ccd61bd | Frequency - Each Lot
note | 0d0b1935-7237-5dfa-b7cc-f9ac6f93a447 | Verification Records - Visual / Pictures
note | 209bb861-d467-51b6-bb0a-a62b1b867c82 | Action Respon. - SE/FM
date | 08b97539-f4a6-527f-a629-6a483c0db007 | Date:
checkpoint |  | Stormwater drainage connections
note | b56a471f-b01f-5e80-843c-155cb762d2b4 | I
note | 97adef71-02a2-58ff-ab2a-14763ed1db7e | Applicable Standard / Reference - VR705.1
note | 672dd232-0204-5e6b-a302-74db46a09d9d | Acceptance Criteria - All stormwater drainage connections to pits shall be neatly made, and where necessary the ends of all drains shall be trimmed off and finished with cement mortar.
note | d9cb8af3-e6b2-581a-be72-d03c673a2bca | Frequency - Each Lot
note | 16545276-d7cc-5ed8-b814-d2c797d0a18d | Verification Records - Visual / Pictures
note | 78bab2cb-9565-539c-b6f9-68aa7b809c2e | Action Respon. - SE/FM
date | d1b7e5c1-2383-57d0-9c3e-18fcd1e90b61 | Date:
checkpoint |  | Step Irons
note | a9c8323b-9999-56db-a8cd-1aeb5b744d06 | S
note | 2f905ae1-ab2f-5579-82ca-ce3b465407e6 | Applicable Standard / Reference - VR705.11
note | c0c07bd6-7465-5445-b784-5ba519a5d70d | Acceptance Criteria - Pits greater than 1.0m deep shall be fitted with step irons. Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
note | 5c06b7c4-6346-5616-9ee8-7f52e7a4672e | Frequency - Each Lot
note | 3afef1fe-8453-5222-a173-90f12afbf1a7 | Verification Records - Visual / Pictures
note | 5067be92-5a16-56f8-90c9-4fe255220a92 | Action Respon. - SE/FM
date | 40a4ae72-dda1-563a-85f3-138414c25b80 | Date:
checkpoint |  | Shape of floor
note | ba6dac60-267a-5043-8496-7e4b2511624b | S
note | ec8e364a-9acb-52f1-9165-0d19deb778d0 | Applicable Standard / Reference - VR705.12
note | 54ac72cd-b7b3-5f4e-bd0a-de78f09111be | Acceptance Criteria - Pit floors shall be smoothly shaped from the inlet to the outlet for a height of 1/3 of the diameter of the outlet pipe.
note | a41a6b4a-2f64-55ec-a559-65c0a8d365c0 | Frequency - Each Lot
note | 7fc3780e-94e9-5cd3-9a2c-6791b56e2177 | Verification Records - Visual / Pictures
note | 8e03bee5-ee11-56f0-8c51-b701bc7206a0 | Action Respon. - SE/FM
date | 8f6c4360-bebb-537b-891e-8266b10f968e | Date:
checkpoint |  | Fitting of Covers
note | 98191ba8-4110-5056-9857-a3a91c5d2174 | W
note | 8fedd045-5a26-5c09-be4a-94efd7015b48 | Applicable Standard / Reference - VR705.16
note | 31d8660f-fae1-5568-aee1-1678a3f997d0 | Acceptance Criteria - Frames for pit covers shall be cast into the top of the pit or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand : 1 part cement and sufficient water.
note | a2aefe78-ca18-5c43-bd1c-595dabcb5b17 | ○ Level at every point of the perimeter shall be within 10mm of the design level for that point, and the line of the cover shall be within 10mm of the design kerb line.
note | b149d308-f6d1-5950-90e2-c112ba29fed9 | Frequency - Each Lot
note | 9b78c086-28f3-5cff-b891-85657a78ec59 | Verification Records - Visual / Pictures
note | da898b63-004a-5b05-a224-c6a5e692844c | Action Respon. - SE/FM
date | 7b25ce15-2272-56e7-aebe-2a35703bde25 | Date:
checkpoint |  | Backfilling
note | b61f7017-6266-5550-8d6b-a9440f979ac6 | W
note | 6b54ad02-c68b-537b-b571-dcdc5aa7254b | Applicable Standard / Reference - VR705.17
note | 55be80bf-2fce-53f9-8595-4d8be631db14 | Acceptance Criteria - Backfilling around pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal using hand held mechanical equipment.
note | 28709efc-0325-5aab-a0c5-319a5b65ac34 | Frequency - Each Lot
note | 2187e4ed-cdd7-5095-9504-e3b7f5765b37 | Verification Records - Visual / Pictures, Report
note | 0cd24154-ca2d-59bb-b6a4-878da10573fe | Action Respon. - SE/FM
date | 8bce5a67-6f71-5c4a-9a4f-f7f4f3bc38ab | Date:
checkpoint |  | Other Contract Specific Requirements
textbox | fa20320f-8e26-5628-951e-44f6255c376e | Requirement(s):
note | cbff3bf2-7fdb-522f-955b-e735bf3cf1c8 | S
note | 818d4b31-fdf6-5270-af41-caab567066c1 | Applicable Standard / Reference - ITP
date | 7ff5d18d-fc55-583b-83e3-b3544ca74a6b | Date:
checklist |  | ITC - Capping Layer | itp | Capping Layer |  | 7ad43959-9c63-4b3a-bdb5-018fc6a16cb5
section |  | PRELIMINARIES
checkpoint |  | Design Issued for Construction
checkpoint |  | Drawings Issue for Construction
checkpoint |  | Material Hold Points Released
checkpoint |  | Survey Request
checkpoint |  | Traffic Management Plan Approved
checkpoint |  | Subcontractor/Provider approved?
checkpoint |  | Kick-off meeting (Subcontractor)
section |  | CONSTRUCTION
checkpoint |  | Safety; SWMS
note | c62862b3-1f36-5ef1-add1-cf2544cec851 | Applicable Standard / Reference - HSMP
note | 4e0bc24b-1300-5f57-af40-b745e0e6ee13 | Acceptance Criteria - SMWS to be written for each activity on Project and shall be reviewed by a competent person.
number | c27e5cde-5fc6-564f-94b8-daefeff53899 | Submitted to the client |  |  | days prior to commencement of Activity.
note | e6e01b90-ce99-51b1-b0bd-2cbb9f378c0f | Frequency - Each Activity
note | b73bbe78-1bbe-57f3-a214-832293e238e5 | Verification Records - Records
note | 1c6bba55-8e2e-5f4b-8c92-25c6ac69d6f8 | Action Respon. - PE/SE
date | fe49a528-2403-55c0-94c9-4e12760905a1 | Date:
checkpoint |  | Environmental Controls
note | a56faac8-3feb-5f2c-aa25-d483555479e5 | Applicable Standard / Reference - EMP
note | d3727f5b-f621-5d8d-82ff-cd5f03bba0cf | Acceptance Criteria - No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP.
note | b43042e1-ba6f-5708-852b-948ccb096e44 | Frequency - Each Activity
note | c3c25744-b64a-56be-a54a-18c34e579d70 | Verification Records - ECP
note | 4b44a1d8-d134-50e7-8280-5175f3a8c6c0 | Action Respon. - PE/SE
date | c2686678-b780-5b75-81d1-2719347f3261 | Date:
checkpoint |  | Excavation Permit
note | bf66d4d1-9909-5b39-9b9b-642d528a8e85 | Applicable Standard / Reference - OHS
note | 90992dc8-e534-5d61-b249-fa373eb69873 | Acceptance Criteria - DBYD information available on site, Excavation permit issued and spotter at location befotre commencement of excavation works
note | 2d647c50-8ee8-587f-9e12-bb6be6f5754b | Frequency - Each Lot
note | e09324e0-0fb2-5973-bd3e-122f8f6b8554 | Verification Records - Records
note | d2c7dc1a-a673-537b-acdd-76500bdc6a4d | Action Respon. - PE/SE
date | 5c6861d8-554f-5bd9-8405-a104199f934c | Date:
checkpoint |  | Survey Control
note | 73a9bb70-3623-57b7-a2af-a27271dc290c | Applicable Standard / Reference - VR204.03 (a), (b, c)
note | fc7449c5-b9b8-551e-acd0-2c0b7787bec9 | Acceptance Criteria - All Earthworks shall be finished to conform to the levels, lines, grades and cross sections showed in the plans.
date | 24ff4f98-f6ef-5c48-80ca-bbb6441e47b4 | Machine GPS File Date
note | af35b6f8-cfe3-5a09-9a35-ce80e5f621ef | Frequency - Each Lot
note | 402f9480-32bf-5d65-8ce3-da798134cbd2 | Verification Records - Setout
note | cd29d0b4-79b4-5d7f-a0ac-aa57fbf3e13c | Action Respon. - Surveyor
date | cc3c3a1b-f748-5162-85b1-6ca0b48dce9c | Date:
checkpoint |  | Material - Type A
note | a79b90f2-c071-5bb2-a959-abe8caee0925 | HP
note | 690e890e-e3e5-518c-8744-b2054f743ad6 | Applicable Standard / Reference - VR204.04 (b)
note | 6a55ce6e-61b3-5032-a953-d4de8255ad3a | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material unless otherwise approved by the Superintendent.
note | 6a8be750-cfba-50f1-86f8-fb0f7f9fe789 | Frequency - Each Lot
note | d76624a2-969e-5757-a2ce-cd344928894f | Verification Records - Visual
note | d1571b81-ff8d-53c4-bd90-05cf9bd735d3 | Action Respon. - SE
date | 090e281a-ceb4-5408-9684-3b3c6ba9a9a3 | Date:
signoff |  | HOLD POINT
checkpoint |  | Site excavation - Cut Floor Level
note | 0b73d8d7-4348-551d-b93c-18801e9ff64f | Applicable Standard / Reference - VR204.03 (f)
note | b33b9f4f-9144-52b4-b529-57aed06cdd6e | Acceptance Criteria - The level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level.
note | 24fdefc6-c964-57aa-bd26-ccc6e96209a7 | Frequency - Each Lot
note | ec98e6c6-663b-56e5-80f7-5e43cc0bf33c | Verification Records - Visual
note | b8bfe0bc-db3e-598c-9a19-90e043f1be2b | Action Respon. - SE
date | eb77d84d-4d39-589d-9027-082f6868fd60 | Date:
checkpoint |  | Site excavation - material category
note | 89416277-5964-5307-ae05-9e0975f6bd00 | HP
note | df06c80a-ef30-564f-9249-b09272d02c13 | Applicable Standard / Reference - VR204.06 (c)
note | fc6c6a1b-fa7b-55c3-b6b2-540aa3011eac | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
note | 2d8882fb-37be-5178-9d2b-fef0c3a9f439 | Frequency - Each Lot
note | faf69779-f9f4-549a-843f-8664c6016e78 | Verification Records - Visual
note | 41be4cb6-08c3-558f-b218-6079dd5c1205 | Action Respon. - SE
date | 0b1aeeb2-d901-5d67-ac39-955573e58287 | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - treatment of cutting at cut floor level
note | 80e22a02-bf23-54ad-aa7f-db16f17867c1 | Applicable Standard / Reference - VR204.06 (e) (i)
note | 21a903de-065a-501e-b501-d82645b3abcb | Acceptance Criteria - In situ material below cut floor level having an assigned CBR less than 6, or a swell of 2.5% or greater, shall be removed to a depth of 400mm below cut floor level and replaced with conforming type B material to the underside of the capping or selected material layer
note | afc44092-4ebf-563b-b3aa-8a7a663ffceb | Frequency - Each Lot
note | 1f1794aa-c802-5636-8e20-4411dc89e117 | Verification Records - Visual
note | 0c9905f5-9aea-5ccd-a6ac-416ee8667dc0 | Action Respon. - SE
date | b8f718b8-a808-5739-9916-608572a37a6c | Date:
checkpoint |  | Earthworks - Groundwater Seepage
note | 503e2938-138c-5f30-ad1e-e36593f6b781 | HP
note | df8f26c5-4297-5e74-9ca6-31d6767c8fac | Applicable Standard / Reference - VR204.06 (h)
note | 19bf5a6e-5d43-502b-ad28-9c4cf53bdf50 | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
note | 1fb5f519-a347-58d2-b360-c10a10429d5a | Frequency - Each Lot
note | ca6a0b43-aac1-5c90-971a-3ddd2f3a4864 | Verification Records - Visual
note | 8c5f5084-f7c0-571a-972c-322f42f9cd36 | Action Respon. - SE
date | 48ffdc9d-114e-5720-b285-cd8fa57dad79 | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - treatment of Unsuitable Material
note | a1135e07-42f5-5457-b7b1-50328f33a758 | HP
note | bd2eb139-f061-545c-b72c-59870077100d | Applicable Standard / Reference - VR204.07 (d)
note | 37e3556b-d731-5f2d-825c-4458e9a4ab0b | Acceptance Criteria - Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review.
note | 41d79e07-5e41-5651-a989-d56776f436a6 | Frequency - Each Lot
note | 691d485f-c54c-5851-bc55-530b6383036c | Verification Records - Visual
note | 5b54d6c9-bb18-53a9-8385-38c13e7a6227 | Action Respon. - SE
date | bbd7574d-c3b4-5d56-9b8b-289f43dc44cd | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - Fill construction
note | 843a27a6-7b2e-5a38-918a-b14e345395ce | HP
note | 459ff318-b49d-51b2-a95e-ba3d1646aa40 | Applicable Standard / Reference - VR204.10 (b)
note | a7e3f6f5-e53b-52d8-9e51-a82b4fa86494 | Acceptance Criteria - The Contractor shall not commence placing of any fill on the prepared surface until the area has been reviewed by the Superintendent.
note | b2d4c5c7-b744-5107-9214-c25d3595dd04 | Frequency - Each Lot
note | 5efba59e-fc68-50b9-9e9a-0c9e8b571ab5 | Verification Records - Visual
note | f6beff01-107d-5760-b145-992c3652a535 | Action Respon. - SE
date | 5ee124a5-b621-548f-8601-151765b538f3 | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - Fill at Structures (wing walls, culverts >1200mm)
note | db268d0b-1fe9-5e46-9011-544ad0c261be | HP
note | 0d75ac07-4bb0-554f-8c11-cd92b6f607a4 | Applicable Standard / Reference - VR204.11 (b)
note | cbe1d535-7eae-50d4-ac01-7ec0a9eb6207 | Acceptance Criteria - No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent.
note | 36b88cb5-815e-50a7-a0e3-53a30654df52 | Frequency - Each Lot
note | ae3c2897-4734-5bc4-ba73-481258f4c3fb | Verification Records - Visual
note | ba300ffc-6be5-5ae6-83e7-860715fa5b66 | Action Respon. - SE
date | 64b9df79-c237-59c4-a25b-13a5b286af92 | Date:
signoff |  | HOLD POINT
checkpoint |  | Test Rolling
note | 5923c61f-c400-584f-ac95-32b867b76925 | HP
note | 0fb2eb30-afdf-5d09-9fd0-85d4d2f08f5b | Applicable Standard / Reference - VR173.03, VR204.12
note | b8318e1a-1551-5d2e-8b8c-127d20c0c544 | Acceptance Criteria - Undertake test roll prior to placement of fill/or proceeding layer. Contractor shall provide for the Superintendant to be present during all test rolling.
note | c03b07ed-2884-5324-b203-9858c8a4e30a | Frequency - Each Lot
note | a2191d35-c746-56bc-bffa-3e5dcb49911a | Verification Records - Visual
note | cf22ea82-0b28-51a5-9190-146b75a2e56e | Action Respon. - SE
date | 31fdb4c6-ca49-566d-a445-8bdee3e52a57 | Date:
signoff |  | HOLD POINT
checkpoint |  | Lot size
note | 121ae783-388c-5c18-9b9e-9b5973b2813b | Applicable Standard / Reference - VR204.13, Table 204.142
note | 17f64d5a-862a-577a-9abe-92245e1b8efd | Acceptance Criteria - Type A: max 5000m2 or one day's production, whichever is the lesser
textbox | c0b94dff-fa88-539c-b96e-b7550f4ac05e | Actual |  |  | m2
note | 0058f006-40b1-5417-94fa-b11c2859188f | Frequency - Each Lot
note | 0e42e98e-f6a3-5b2c-a859-d6643de635dd | Verification Records - Records
note | 9aededff-51b3-53e9-be3e-130d9107a3e4 | Action Respon. - PE/SE
date | bc1bb014-ab7b-5da2-9491-bc08bf367a45 | Date:
checkpoint |  | Compaction & Grading
note | 202bde6f-076b-5b1f-b142-0cd9f5d06dfd | Applicable Standard / Reference - VR204.13 (b), Tables 204.042, 204.14 1
note | 064fc007-8302-57f4-84f0-67c5cb44f350 | Acceptance Criteria - Compaction:
note | aa3755f1-cf1f-5a85-b6ea-a4343bc27f73 | ○ All Type A Material, and Type B material placed within 400mm of top of cut floor level: min. 100%
textbox | 845b5b3b-4741-5801-be17-d9da6da0a9a9 | Actual % / Minimum Frequency Testing
note | bbdcdc92-cbc6-59f1-9b20-3ba3a0a4e734 | Grading:
note | 74eb6cf4-1b09-58fc-a79e-0c1d4483dbc4 | ○ as per Table 204.041
note | a4885157-f8cb-58c6-8b11-2f88f1e6f591 | ○ Pass/ Fail/ Minimum Frequency testing
note | 5e6319d9-8b84-5056-b965-567b614a71f7 | Frequency - 1 test for each lot then reduced to 1 test for every second lot
note | 588f3356-7e09-550f-a072-dcf2d91cde3b | Verification Records - Records/Visual
note | e273a689-1e42-51d6-9774-d26afbea8327 | Action Respon. - SE
date | e38453c5-7c6b-5f27-a29b-d1b95da671d6 | Date:
checkpoint |  | Compaction - CBR & Swell
note | 05e5dd28-4aec-54b3-a49a-2bf4fbe2c52d | Applicable Standard / Reference - Table 204.141 & Table 204.041
note | cc44a9f2-45f3-5eb6-9d1c-1c3d7826e3d8 | Acceptance Criteria - Type A: initial 1 lot test to determine assigned CBR >6% and swell <1.5%
textbox | b72af234-20c7-580b-84d6-da481273e0e8 | Assigned CBR |  |  | %
textbox | 592f1b33-57cd-521c-a949-e9688e954313 | Actual |  |  | %
textbox | a07f6dfd-310c-5dfc-8bea-5e00f84ce599 | Assigned Swell |  |  | %
textbox | 59ee9e2e-3227-55c1-bade-b687e631d0d0 | Actual |  |  | %
note | 857a3f93-6fc9-5b0d-9811-8d411673ba26 | Frequency - Single CBR test to confrim assigned CBR and swell - first lot only
note | ee9a8a05-52a0-517b-8852-dee19952d190 | Verification Records - Records
note | e543e1e6-4b82-55ca-b4bd-8d38b06f7bc6 | Action Respon. - PE/SE
date | cbdfec1c-fac2-5cd1-a51a-f0ba4ef178f6 | Date:
checkpoint |  | Compaction - PI
note | f81555ec-1703-5db1-8e55-0ffc611eae7c | Applicable Standard / Reference - Table 204.141 & Table 204.041
note | b59e490e-5623-5e71-9f17-43c10be96a01 | Acceptance Criteria - Type A: plasticity index (PI) calculation x % Passing 0.425mm, Max. 1000
note | 227cde37-1e38-5c45-8fef-9de3985710b2 | Frequency - 1 test per 2 lots then 1 test per 4 lots
note | 08556a68-d326-5656-8f73-f2db6916e5a2 | Verification Records - Records
note | 56492a2f-0357-5384-94b3-63e2b8db9723 | Action Respon. - PE/SE
date | 5f03ae86-7e4a-5bb1-88ee-f07f997a9a0b | Date:
checkpoint |  | Compaction - LL & Permeability
note | 90532e82-6e2d-5435-b786-0606642ee3dc | Applicable Standard / Reference - Table 204.141 & Table 204.041
note | 5db801fe-4a09-5538-9f32-c5ffb6d7d82c | Acceptance Criteria - Type A: liquid limit and comparison of PI against LL, Permeability <5 x 10-9m/sec
note | 5c6774c6-916e-5716-96a3-c0e80c1e44e5 | Frequency - 1 test per 2 lots then 1 test per 4 lots
note | a7c2cf99-9a87-5733-a657-558916913015 | Verification Records - Records
note | b4e95d06-913a-5d64-bbe3-02118953072f | Action Respon. - PE/SE
date | 7faaecb0-2e54-58d4-a73e-44bca32dac69 | Date:
checkpoint |  | Other Contract Specific Requirements
textbox | d558909b-2eaa-5bbd-9d5f-1d20c168433c | Requirement(s):
note | 61d9149c-7cb8-5752-b459-76dca57d5439 | S
date | 6e413039-c199-5f1f-ba07-94e43122b139 | Date:
checklist |  | ITC - Type B Earthworks | itp | Type B Earthworks |  | d5e8f31b-6634-4a75-9b04-bdeee0c5826b
section |  | PRELIMINARIES
checkpoint |  | Design Issued for Construction
checkpoint |  | Drawings Issue for Construction
checkpoint |  | Material Hold Points Released
checkpoint |  | Survey Request
checkpoint |  | Traffic Management Plan Approved
checkpoint |  | Subcontractor/Provider approved?
checkpoint |  | Kick-off meeting (Subcontractor)
section |  | CONSTRUCTION
checkpoint |  | Safety; SWMS
note | 634f97a6-8a98-5466-b33d-f92310ff9dd8 | Applicable Standard / Reference - HSMP
note | e62e57c7-1b16-5cba-8a79-16744ab4ae65 | Acceptance Criteria - SMWS to be written for each activity on Project and shall be reviewed by a competent person.
number | 768d8001-7254-515a-a697-b069858d4ea7 | Submitted to the client |  |  | days prior to commencement of Activity.
note | f5cce882-0c38-5c83-98c9-0f93bf93bc53 | Frequency - Each Activity
note | 0eace351-135e-5fc4-b513-b51427bbe50e | Verification Records - Records
note | 5cbc5f1a-86ee-5707-8749-89c714b2631f | Action Respon. - PE/SE
date | 494a3bff-bef0-5c5b-9ec8-4af93ec8dd75 | Date:
checkpoint |  | Environmental Controls
note | d57088c0-c797-5cd5-b722-bb338cc0dee5 | Applicable Standard / Reference - EMP
note | a0730a12-304e-5dc5-827e-5a9a89fdb8fa | Acceptance Criteria - No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP.
note | 75245ae8-df3d-597b-9a11-71f999c1a8c5 | Frequency - Each Activity
note | 1fdd5100-e344-5868-9861-6ccc2ef455a2 | Verification Records - ECP
note | 45b7e945-59b2-5170-a548-87ad785f643f | Action Respon. - PE/SE
date | ef4e82c1-f990-50fe-83a3-eec2aed27424 | Date:
checkpoint |  | Excavation Permit
note | 6cb12d70-0a07-5913-acd4-cd9773adbba1 | Applicable Standard / Reference - OHS
note | d15469b4-529b-5c3c-8283-c3c9ac983d32 | Acceptance Criteria - DBYD information available on site, Excavation permit issued and spotter at location before commencement of excavation works
note | db334dfe-e86a-530f-9942-23faf45b3143 | Frequency - Each Lot
note | 803534fe-01fa-5432-808b-5eb20c1be60a | Verification Records - Records
note | dc198de8-7965-5c02-9a6b-39d749a46c57 | Action Respon. - PE/SE
date | b2905b70-4361-5a02-a2bd-a6979a3ae9d8 | Date:
checkpoint |  | Survey Control
note | ea24f8c9-1215-5c38-9e98-4a8e91c4695b | Applicable Standard / Reference - VR204.03 (a), (b, c)
note | 03e229f4-4935-513b-964d-2ae29984913f | Acceptance Criteria - All Earthworks shall be finished to conform to the levels, lines, grades and cross sections showed in the plans.
note | 71c8a952-0225-51a3-8742-59e94f45cdb2 | Frequency - Each Lot
note | b780e067-4d17-5003-8769-8b19464ea541 | Verification Records - Setout
note | fe2efef7-2f7f-5023-97d9-519b6343e5f0 | Action Respon. - Surveyor
date | 60f6be1c-c66b-507c-8d84-827091a4c4e6 | Date:
checkpoint |  | Material - Type B
note | c31d91c3-e205-576c-a2bb-dda1218a9c8a | HP
note | d5a29ce1-f0e8-595e-98d5-f8c67e970297 | Applicable Standard / Reference - VR204.04 (b)
note | 8f5ea1ec-6225-53a5-916d-97f911da4e0d | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type B material unless otherwise approved by the Superintendent.
note | 948743d6-789f-5ad6-b3eb-c49de8c303c8 | Frequency - Each Lot
note | bac5112d-b940-542c-ade9-208249fceef6 | Verification Records - Visual
note | 34bc7594-8c6e-5a79-be53-5f230cba9f32 | Action Respon. - FM
date | 4317e84b-85c1-547a-a78f-5fffe8df4fdf | Date:
signoff |  | HOLD POINT
checkpoint |  | Site excavation - cutting floor
note | e224d1ef-6e8e-535f-b4c7-33a2633c7820 | Applicable Standard / Reference - VR204.03 (f)
note | 82a2631f-1fe6-5546-929b-897160277083 | Acceptance Criteria - The level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level.
note | d6df1fba-4049-5105-bdeb-a68444f60a4c | Frequency - Each Lot
note | 0d699d13-9a5a-5257-a6bd-77aebcee2b8a | Verification Records - Visual
note | c1aabeb9-bfd1-5dd8-9e37-110a0e46edac | Action Respon. - FM
date | 0dc2f313-5aaf-56ed-82d9-0cfbb87620ed | Date:
checkpoint |  | Site excavation - material category
note | f4715be8-2066-578e-9e67-b75511b38d36 | HP
note | 160696de-6393-5580-a105-796f7917cef3 | Applicable Standard / Reference - VR204.06 (b)
note | 2ff41680-c0a8-5574-98c3-004154f17a6a | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
note | 46156407-1e26-5ac1-86f5-7eb650b78d37 | Frequency - Each Lot
note | 7b25c364-dc97-51a5-a86a-da6450a62650 | Verification Records - Visual
note | cd79cbcf-0704-587f-b048-49a17157a0af | Action Respon. - FM
date | e98b7bc3-1a65-5974-80e6-a0d1d7ece242 | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - Groundwater Seepage
note | d3a54c3b-1f8c-5a03-a0df-565ce875811c | HP
note | d8e58685-657a-5339-8ebc-09dd3b4710a5 | Applicable Standard / Reference - VR204.06 (h)
note | 6c503c8a-d57c-5113-95a9-5e228574c6bd | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
note | f824845f-86d8-5faf-8e55-3b6173646774 | Frequency - Each Lot
note | c5a0cf6d-ef99-52b8-8bb2-3e1161b48f7a | Verification Records - Visual
note | e0038c01-42b5-5ee0-9419-bacb9c099f36 | Action Respon. - PE/SE
date | d12f8f00-3235-5253-9b54-988221c6fa5c | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - treatment of Unsuitable Material
note | 7cba7fd9-b3b5-5cd7-b8ce-c39be3824370 | HP
note | 52165e9c-f064-5a28-a978-29ff1783cbc9 | Applicable Standard / Reference - VR204.07 (d)
note | 9c2014ba-cc1e-5749-b342-6f1045e8ce39 | Acceptance Criteria - Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review.
note | 74dd0af0-0008-50fd-8e21-bb4570af5b17 | Frequency - Each Lot
note | 81d2ec61-3bc0-54a9-b862-051e0137ffcb | Verification Records - Visual
note | 0911cd09-dbef-500e-8c49-1458ac4553db | Action Respon. - FM
date | 478eebbc-4516-56e8-8f48-08dfcb886a85 | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - Fill construction
note | d941b4e7-6959-5f80-a3c3-0e1681c58238 | HP
note | f3030c96-4dff-5d98-b6d8-01b620f4cdc5 | Applicable Standard / Reference - VR204.10 (b)
note | 1dbf799e-35a0-5f11-95c9-4eec3e0742e8 | Acceptance Criteria - The Contractor shall not commence placing of any fill on the prepared surface until the area has been reviewed by the Superintendent.
note | af8fab00-166c-5570-98cc-89fe48f5e4e3 | Frequency - Each Lot
note | 49a3dca2-8526-532f-9151-43911797c99d | Verification Records - Visual
note | 8ed54b33-efa8-599c-85ef-b081055d060d | Action Respon. - FM
date | 3cdeedf7-4c42-59ed-8f7e-b9c5f95f4a4e | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - Fill at Structures (wing walls, culverts >1200mm)
note | 5ec80b94-3514-5d1a-b17d-4c5b575b3ec3 | HP
note | 22d2e302-824a-5498-9aa8-b04baa083ac7 | Applicable Standard / Reference - VR204.11 (b)
note | 7230f434-e35d-520a-b24f-7c44867826de | Acceptance Criteria - No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent.
note | 985565e1-45d1-5d76-a754-25202053f188 | Frequency - Each Lot
note | 63c66ba2-fcda-5b0e-9e57-961d0a38a39f | Verification Records - Visual
note | cbd51a88-5c36-5b01-a1d1-ea8b14e1c23c | Action Respon. - FM
date | d192698f-722a-56a6-8259-ad817c4a3129 | Date:
signoff |  | HOLD POINT
checkpoint |  | Test Rolling
note | b03028ca-1e17-53e8-9466-4ad133072a12 | Applicable Standard / Reference - VR173.03, VR204.12
note | 712a9959-8fcf-55b1-ba5e-2d8806bdf3ff | Acceptance Criteria - Undertake test roll prior to placement of fill/or proceeding layer.
note | e5dbc790-eaed-500a-a751-535c68535d7e | Frequency - Each Lot
note | 69f637f1-032f-586f-8e95-701ef3c7ec52 | Verification Records - Visual
note | dda6ebb5-0b0a-5db7-b3a0-b81691ab7cd9 | Action Respon. - FM
date | f66aa388-4d6d-5d4b-b96c-01044b346667 | Date:
checkpoint |  | Compaction - Lot size
note | 524dd9e1-ebdc-566b-b77c-abc5c1f2e2ae | Applicable Standard / Reference - VR204.13
note | 24dc9575-1db0-5c68-95ff-7787bb3ac7d7 | Acceptance Criteria - Type B: max 10,000m2 or one day's production, whichever is the lesser
note | 90b85e9d-63d6-54e7-b23d-78c0b8eb9d5f | Frequency - Each Lot
note | 44f04c86-2ba2-5d54-9e85-642f149234d6 | Verification Records - Records
note | 1e82ee5e-0172-5c1c-a17e-677f4abd48d0 | Action Respon. - PE/SE
date | f0bcde23-b4fa-59fc-8c94-1bfb84dc5a05 | Date:
checkpoint |  | Compaction
note | 2b841e1f-41e0-5181-89ea-e8bc594756b2 | Applicable Standard / Reference - VR204.13 (b), VR204.14
note | afbe80c9-2cf8-5135-aa3f-f4821198a2fe | Acceptance Criteria - Compaction:
note | b80c4651-4a19-57a6-b187-f2ebf983dfdd | ○ Type B material placed within 400mm of top of Type B level: min. 99%
note | fbc56b33-569c-5e7f-8250-c2e207f98033 | ○ Type B material placed more than 400mm of top of Type B level: min. 97%
note | 41609d7c-b160-5676-b6a0-14dae5d6279d | Grading:
note | e323e7e4-324f-570b-a455-c15ce2b5e84e | ○ Max. particle size <100mm (visual inspection)
note | 4470d9c8-505c-550a-a0de-0a382926585d | Frequency - 1 test for each lot then reduced to 1 test for every second lot
note | e2a6c93a-9698-5ca4-8d14-f4a7841133d3 | Verification Records - Records/Visual
note | 344032b0-b2ca-5b91-8f03-d32a9efb6733 | Action Respon. - FM
date | b845da89-ac50-5e1f-a9c1-9582c692faef | Date:
checkpoint |  | Compaction - CBR & Swell
note | 2de5ae18-1a70-5e28-883f-bef093f801ea | Applicable Standard / Reference - Table 204.141
note | 2d456e64-fa8a-5bdd-857c-85f00478843a | Acceptance Criteria - Type B: initial 1 lot test to determine assigned CBR and swell
note | 74121102-e846-5637-acc8-202ca0406803 | Frequency - Single CBR test to confirm assigned CBR and swell per every 8 lots
note | e071b01c-e6ae-5184-8ddc-36aa79969a91 | Verification Records - Records
note | 3cc0790a-b4dd-5cf9-8d76-bb099fcc017d | Action Respon. - PE/SE
date | 42654b9f-41fa-531c-ba51-0fc541f7ead1 | Date:
checkpoint |  | Compaction - LL
note | 7d312be5-9cba-59b3-93ef-d5e8d2c7ee0b | Applicable Standard / Reference - Table 204.141
note | 5e6785fb-8973-5429-ba33-ffd4d801ecbf | Acceptance Criteria - Type B: liquid limit and comparison of PI against LL
note | ea232734-e546-55c9-afa8-601318cf706d | Frequency - 1 test per 2 lots then reduced to 1 test per 4 lots
note | 2b7e3560-2b57-5978-9636-3f4b8945fd98 | Verification Records - Records
note | 49a4f5b4-a672-58d1-8bf0-17926dfe7f9a | Action Respon. - PE/SE
date | 8b56607b-0c85-5049-b398-0385e6f1eeef | Date:
checkpoint |  | Other Contract Specific Requirements
textbox | 9ffe41b7-07b7-5bc0-8e44-988c88212fd7 | Requirement(s):
date | a50e855a-b0f4-5ecd-96b9-4623b7903dac | Date:
checklist |  | ITC - Stormwater | itp | Stormwater |  | e391f158-d34a-4f46-a49a-61bd4e44d5bf
section |  | PRELIMINARIES
checkpoint |  | Design Issued for Construction
checkpoint |  | Drawings Issue for Construction
checkpoint |  | Material Hold Points Released
checkpoint |  | Survey Request
checkpoint |  | Traffic Management Plan Approved
checkpoint |  | Subcontractor/Provider approved?
checkpoint |  | Kick-off meeting (Subcontractor)
section |  | CONSTRUCTION
checkpoint |  | Safety; SWMS
note | 78a9b5e6-63bc-59d5-b832-7883d2567945 | W
note | 422fc738-68c2-5998-b9ef-78031387c615 | Applicable Standard / Reference - HSMP
note | 72705fe4-9038-5d29-a861-9626004173db | Acceptance Criteria - SMWS to be written for each activity on Project and shall be reviewed by a competent person.
number | 168f2033-652f-5f13-85a7-b16daccb8c3f | Submitted to the client |  |  | days prior to commencement of Activity.
note | 2871f53d-9a07-57e8-b2e5-30e198d6274e | Frequency - Each Activity
note | fd28c72d-2a94-5aab-be49-ee17fdccc319 | Verification Records - Records
note | 08c72f95-8694-55b3-bc59-ff9d667b687c | Action Respon. - PE/SE
date | 32835a4d-358b-5793-8603-7c74e5eea4b3 | Date:
checkpoint |  | Excavation Permit
note | 33d157a5-b65a-576a-a3cc-4736bf3be132 | W
note | 8146097f-8c23-54ba-afa8-821ffc7bfb09 | Applicable Standard / Reference - OHS
note | d3f530ed-b80c-5cf8-9b5e-23184b4ac02d | Acceptance Criteria - DBYD information available on site, Permit to work- Services issued with assest protection Plan. All services identified located proved and protected. Spotter at location before commencement of excavation works (If required)
note | 525d0c92-3b73-5946-a075-472db6279d9b | Frequency - Each Lot
note | 77b818d5-acf7-5cec-ba53-d138228ff788 | Verification Records - Records
note | 47927645-65d4-5fa5-97a0-9506a39da422 | Action Respon. - PE/SE
date | 79e32103-c76d-532c-ba66-3909bad67b29 | Date:
checkpoint |  | Environmental Controls
note | 75eda769-b0c0-54d9-8435-c19d3dc607a6 | H
note | 7a6eb439-fb57-5ba3-9868-ea96ffe1a4f6 | Applicable Standard / Reference - EMP
note | 31ef4e80-7f29-5f1d-ad8d-ea7c34b2b9ad | Acceptance Criteria - No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP.
note | cceab05f-0931-5813-9eea-1d45e8129055 | Frequency - Each Activity
note | b8d5e4c3-629f-5180-9409-0fe9a3b048b3 | Verification Records - ECP
note | 1e1b0a23-ce71-51ad-98a1-385842568358 | Action Respon. - SE/FM
date | 2a42719f-e1cc-59c0-9e9c-e470f293628a | Date:
signoff |  | HOLD POINT
checkpoint |  | Set out
note | 6ea064a2-ad0f-52a2-bb74-4c333c1bd825 | W
note | 716a24b4-17e5-5eca-9552-4e44de7d9d22 | Applicable Standard / Reference - 701.05
note | 00257bb2-a2d4-5e5b-aaeb-99db92d4db37 | Acceptance Criteria - Prior to commencement of excavation for the pipes the Contractor shall confirm the position of all pipes with the Superintendent after survey pegs have been installed
note | 8633ab63-2d97-5386-acb2-31fc93d25fd7 | Frequency - Each Lot
note | 040f35e7-5f57-5bad-a29e-74e21b30912f | Verification Records - Visual / Pictures
note | 4e7893ed-94a9-5223-8752-cb694ab4f84f | Action Respon. - FM & SR
date | d6f26f34-b60e-531a-87c5-52f471e978e6 | Date:
checkpoint |  | Excavation
note | 2504d5ed-1b77-54c1-91c0-f57377c7fcbe | R
note | be93cf52-8c18-5498-944f-c3bc2fa5795d | Applicable Standard / Reference - VR701.10
note | 75528324-a40b-5dae-9e93-3fbead017781 | Acceptance Criteria - Pipe culverts – the width of the trench at and below the level of the top of the pipe shall have a horizontal clearance of 300 – 600mm
note | 6e2431fc-0ab2-557b-a329-2117c40367e7 | ○ The base of the trench shall be compacted
note | dd0bb5fe-c692-5f98-8722-b845737c55b5 | ○ Soft, wet or unusable material at the base of the pipes should be treated or replaced
note | dfaf06bf-b723-52cd-b4ee-fd8ef28e3990 | Frequency - Each Lot
note | 607c93f7-d8a5-50ec-a6e9-a5b16fb9d9c7 | Verification Records - Visual / Pictures
note | f9348d77-e372-5fb4-9f91-21004a722a1d | Action Respon. - SE/FM
date | bb966822-616a-5856-a3c4-6c607a96233a | Date:
checkpoint |  | Culvert Bedding
note | 656dc617-d38e-510d-b1fd-14e101084fc7 | S
note | 0a6cccb5-dfb5-5ff9-8e47-45e128322c64 | Applicable Standard / Reference - VR701.11
note | 2a95be13-9aea-5576-ac37-337e64ba7968 | Acceptance Criteria - Depth of the layer of Compacted bedding material shall be:
note | f726877c-d691-5280-bb7e-8cf824ab67e6 | ○ 100mm where pipe diameter is less than 1500mm
note | 2772fca0-9ddb-541e-8211-3f44d7751991 | ○ 200mm where pipe diameter is greater than 1500mm
textbox | 7138ca48-50a5-54d1-be95-488ad4deefd5 | ○ Class of Bedding material
note | 675ff2c8-13b9-5187-840c-3da3131206a4 | Frequency - Each Lot
note | b6fb5af2-7ba2-577e-a884-612378da4e54 | Verification Records - Visual / Pictures
note | 9dc22adb-8932-55e6-84a2-a14a9dde51f8 | Action Respon. - SE/FM
date | 0bdc5fba-f3c1-5ba1-a95b-f41df34849f3 | Date:
checkpoint |  | Laying pipes.
note | cc8067ce-c969-5209-9de2-6395ba6b9d80 | W
note | b38582bb-11e9-5eaf-b0af-d335f7e820c4 | Applicable Standard / Reference - VR701.12
note | a664ceea-4b04-5e9e-bfac-a9811fa05ebc | Acceptance Criteria -
textbox | e42e39f6-d7e0-5fbb-a9ba-1d25e8c8bdf4 | ○ Class of Pipe
note | 1d08a40f-9d01-52a0-b340-d79118830d1e | ○ Pipes – Rebate and socket ends of pipe shall be placed facing upstream. The lower portion of the pipe shall be in contact with the bedding for the full length of the section. (Pipes are free of cracks/ damage )
note | f179473c-7033-53f4-bf2a-8a686a7b1124 | Frequency - Each Lot
note | 7ad8db78-0a4e-5f70-9849-0e56e42d60b8 | Verification Records - Visual / Pictures
note | 66695aba-743d-53d6-a3c3-cd3b8e1ea63a | Action Respon. - SE/FM
date | a51dacad-6a9f-5312-92d3-36fb2420475f | Date:
checkpoint |  | Jointing
note | 28d7c87f-3e15-5387-aeb6-ef81065ec725 | I
note | 1e3c3521-1f91-59c1-a276-ce31bee5e5fe | Applicable Standard / Reference - VR701.13
note | 6a547411-852b-5521-9a1d-c39822045bad | Acceptance Criteria - Interlocking (Flash) Joint Pipes:
note | 755299c4-6771-5234-9eba-77bcaf3f973e | ○ Joint shall be mortar jointed, or wrapped with a 200mm wide external joint rubber band.Rubber band thickness shall not be less than 2mm. In case of internally jointed pipes 600 mm diameter and larger, the mortar shall be struck off flush with the bore of the pipe.
note | 107459fb-ef62-5747-a1e0-5aea78ea465e | Rubber ring Joint Points:
note | d5502773-9662-58de-bed4-5b11d26cd970 | ○ Rubber ring joint pipes shall be jointed with rubber rings. Rubber rings shall be undisturbed clean and free from dirt.
note | b3efe0e5-17ba-5002-949f-959092318e0b | Frequency - Each Lot
note | b89b6734-ed78-5287-b44c-31550f2e700e | Verification Records - Visual / Pictures
note | 1e0022f8-7ae8-5426-9525-66e971985cce | Action Respon. - SE/FM
date | cd7d9f7e-cbbe-51a9-b99f-a88e04428a30 | Date:
checkpoint |  | Backfilling
note | bd9de219-be7a-560d-b5fa-7ddd3d66aecf | I
note | 2e4c77f2-6aa5-5d24-bad6-f537125ff72c | Applicable Standard / Reference - VR701.12, & VR701.14
note | 411621d1-eb99-5b5d-97a1-6c8bc2ae7dc9 | Acceptance Criteria -
textbox | 2ec305dd-0c7e-5d6f-af38-26ef4a731439 | ○ Class of backfill material
textbox | 6be0dbe1-a1ca-5752-840a-9091eb0073a1 | ○ Compaction Requirements
textbox | e06ff60d-d297-5d0b-90d7-6d3ba05d5660 | ○ Depth of Layers
note | ad161e71-1654-5100-9069-7a161ec3f7b1 | ○ Selected backfill material shall be placed for the full width of the bedding material to a height of 0.3m above the top of the culvert or subgrade level (whichever is lower)
note | e8db5b9b-e0e3-5b1f-919c-8ed9c0b0e892 | Frequency - Each Lot
note | 2493e2de-4a47-52f2-8d30-9dead65a01b1 | Verification Records - Visual / Pictures
note | f09e4260-484e-536d-9ab1-cd7ecaf196c9 | Action Respon. - SE/FM
date | 0fa6ffd0-a4a2-51d5-9231-4b6bce7e163f | Date:
checkpoint |  | Geotechnical Testing
note | da9fd1fc-befc-52aa-a636-3fdd4321fbbf | I
note | 2043ac61-9bcc-504d-84a2-e46f3d4e69ad | Applicable Standard / Reference - VR701.15
note | 56cf0eed-cc07-5748-8a4d-d39c55f4f2e2 | Acceptance Criteria -
textbox | d2526c1b-078f-5493-ba55-cfb04440a71d | Minimum Testing Requirements (per lot)
textbox | 314632e8-6163-5a87-ae90-bae8a087fcd4 | (1) Compaction Requirements
textbox | 32818d97-faad-59e2-8cd8-21d42cc6d9fb | (2) Moisture Requirements
note | 0d3d9fae-4329-5edb-b023-b55cf8237c89 | Frequency - Each Lot
note | 3eb2e335-0b86-51f2-837b-29b2ec22b948 | Verification Records - Visual
note | febbbf63-0cee-5804-b7e5-29daf288854e | Action Respon. - SE/FM
date | 47c8fc8c-1560-50f5-bb51-62423ff10848 | Date:
checkpoint |  | Grading & PI testing Frequency
note | 42d67e0a-1e5b-53ee-9a82-b6ec5e377ea8 | S
note | e5817e3b-0e71-565a-942e-14502174413e | Applicable Standard / Reference - VR701.23 Table 701.231
note | 993af202-e58d-5a85-a62c-2fa3e2b7092c | Acceptance Criteria -
textbox | 1b250045-57d2-56f3-ae23-0cbe945ef570 | Grading |  |  | per tonnes or part thereof
textbox | 9fe21bf9-7c07-51b9-8807-757b2930b3c9 | PI |  |  | per tonnes or part thereof
note | c2f0781b-60e3-5b71-99ad-474a2ea3f99c | Frequency - Each Lot
note | e16ff615-c009-52bb-8af9-77bb42fa906e | Verification Records - Records
note | 0c212114-7e14-5eea-a8a7-c25c26c5363a | Action Respon. - PE/SE
date | 48a5d5f2-6cc3-5f7e-b725-6a199bdc17d5 | Date:
checkpoint |  | Other Contract Specific Requirements
textbox | 535aa0d1-7c74-580f-ae3f-a9478fc339a5 | Requirement(s):
note | 25094c70-5c7c-5748-9dd6-9312726698e6 | S
note | 08d9bfe8-7df2-5714-b977-70548ca9c4f9 | Applicable Standard / Reference - ITP
date | 8f926f83-cfb2-5a40-b079-4f624fc595c6 | Date:
checklist |  | ITC - Type A Earthworks | itp | Type A Earthworks |  | ec136f18-ca9d-45e8-9b83-3b1921554e00
section |  | PRELIMINARIES
checkpoint |  | Design Issued for Construction
checkpoint |  | Drawings Issue for Construction
checkpoint |  | Material Hold Points Released
checkpoint |  | Survey Request
checkpoint |  | Traffic Management Plan Approved
checkpoint |  | Subcontractor/Provider approved?
checkpoint |  | Kick-off meeting (Subcontractor)
section |  | CONSTRUCTION
checkpoint |  | Safety; SWMS
note | 9415e8dd-9160-5c10-a2e3-a632eb147083 | Applicable Standard / Reference - HSMP
note | 4035f5d4-f53f-56b0-9323-ff20e9b82193 | Acceptance Criteria - SMWS to be written for each activity on Project and shall be reviewed by a competent person.
number | f088b165-2f4e-5313-b7ce-4413d6227e8b | Submitted to the client |  |  | days prior to commencement of Activity.
note | 072ad6c5-1035-5e3b-a93d-00fcf9ea4edf | Frequency - Each Activity
note | 7a56b41e-22da-5603-b7e8-4df243efa31c | Verification Records - Records
note | d952cc8f-bfd1-53d2-a8df-f57ab6e4ef19 | Action Respon. - PE/SE
date | 4b54a544-2054-54dd-a48d-09d5f38e5fbd | Date:
checkpoint |  | Environmental Controls
note | 53581e06-c57e-58ff-beb4-f10573d89e9a | Applicable Standard / Reference - EMP
note | afd06265-a7ed-5a63-8921-06dd9dac7842 | Acceptance Criteria - No work shall commence unless all erosion/ Sediment controls are implemented in accordance with EMP.
note | 0193d2b2-d388-56e3-8e87-48b177a76b5c | Frequency - Each Activity
note | d3c1b7aa-98da-556c-9cea-3e109f7742d6 | Verification Records - ECP
note | 28b32522-e16f-5d54-a50c-41027d7b8300 | Action Respon. - PE/SE
date | e5531418-fa7a-5d91-80ee-d8f5cb68a378 | Date:
checkpoint |  | Excavation Permit
note | d9f28b5f-6eb7-5102-a83c-24390b99d703 | Applicable Standard / Reference - OHS
note | c98599c9-b9fb-5f98-9b68-311f0a659cd8 | Acceptance Criteria - DBYD information available on site, Excavation permit issued and spotter at location befotre commencement of excavation works
note | 4e5d4b8c-f622-5e67-9b63-c333e6d480dc | Frequency - Each Lot
note | 26405409-6f8b-5d25-93ce-94397cd1e291 | Verification Records - Records
note | 1565199a-cb85-567c-8a4b-12f7a0d65beb | Action Respon. - PE/SE
date | fdc41ee0-0cc8-51d6-9b33-6c62852edd27 | Date:
checkpoint |  | Survey Control
note | ee03d035-6f3d-5235-abc3-10b01c7e34a7 | Applicable Standard / Reference - VR204.03 (a), (b, c)
note | 134fa71f-1633-5db5-8bed-6e7977abcb04 | Acceptance Criteria - All Earthworks shall be finished to conform to the levels, lines, grades and cross sections showed in the plans.
date | df1eff61-24f8-5b78-bfbe-2a258d6a0e9b | Machine GPS File Date
note | b2872c70-0c2b-59a0-8c8a-ce451018ed64 | Frequency - Each Lot
note | 0a754b5e-8945-5246-9e07-df4ff73babf0 | Verification Records - Setout
note | 078389cf-a2cc-54ec-afca-3a5980ee98c5 | Action Respon. - Surveyor
date | 01160a34-c55e-572e-b13e-1e2196fa96b8 | Date:
checkpoint |  | Material - Type A
note | 8d724c57-a193-53e3-a491-9c7187c935ac | HP
note | f8efa808-1e8b-57f8-b4dd-081c548a0eb7 | Applicable Standard / Reference - VR204.04 (b)
note | 524c7603-ed49-5692-9caf-dcb9a1d9142c | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material unless otherwise approved by the Superintendent.
note | 09df13e7-6a1b-5eba-801c-4206ce14bc6b | Frequency - Each Lot
note | 68935ef8-2adb-5dd7-9fbd-f20c49ab5ade | Verification Records - Visual
note | 59942f89-4594-5f0d-883e-1659151df715 | Action Respon. - FM
date | e0babe5c-d743-59ae-aee0-f0d32271d5a7 | Date:
signoff |  | HOLD POINT
checkpoint |  | Site excavation - Cut Floor Level
note | 4544bfa2-c2f0-5941-a977-5381a20344d5 | Applicable Standard / Reference - VR204.03 (f)
note | 3b4b68fa-da09-5b50-9d78-e2a6fb19fdbe | Acceptance Criteria - The level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level.
note | 6b568d46-1e73-5b52-9a20-21b23b5ffc38 | Frequency - Each Lot
note | 1e1743a8-dd8d-5f84-b665-a1728c5842ab | Verification Records - Visual
note | d930679c-25d3-5efc-b75c-a073aa308d04 | Action Respon. - FM
date | ebad0781-31df-5a59-84cb-dcbecd94d52a | Date:
checkpoint |  | Site excavation - material category
note | 2477480b-1cb1-50f1-90a5-3a727f8d0ed8 | HP
note | 4c007154-24cf-57f7-abcc-64ed0a133f07 | Applicable Standard / Reference - VR204.06 (c)
note | 1f0a0014-d698-5581-bf50-985a158f0033 | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
note | 2972cb8a-9e57-5658-826b-09b74c485449 | Frequency - Each Lot
note | 3b117a74-dd8a-5f17-9873-d34a7244ca4d | Verification Records - Visual
note | 36415b8a-c46d-5917-96a0-19bc45afa8b2 | Action Respon. - FM
date | 95e40526-e249-599f-85e8-7b87886d3ba1 | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - treatment of cutting at cut floor level
note | ea667864-fd29-5515-b9af-556e78420168 | Applicable Standard / Reference - VR204.06 (e) (i)
note | c5f9a34d-db31-59bf-bbe9-0874d196a44e | Acceptance Criteria - In situ material below cut floor level having an assigned CBR less than 6, or a swell of 2.5% or greater, shall be removed to a depth of 400mm below cut floor level and replaced with conforming type B material to the underside of the capping or selected material layer
note | da068320-e7a4-5b5a-9d00-42be03dd3294 | Frequency - Each Lot
note | deb63290-32c6-54a1-b5e3-6bb168cb872a | Verification Records - Visual
note | 08fe95f9-c13a-5f73-8c1a-83c424161d02 | Action Respon. - FM
date | 7683f71b-50d8-586b-81dc-bb1b44cb2c3b | Date:
checkpoint |  | Earthworks - Groundwater Seepage
note | 4c14bf23-a19b-58d6-ab95-da913518c6be | HP
note | a4bfae94-e3cc-5d42-bf76-527df8346b90 | Applicable Standard / Reference - VR204.06 (h)
note | 0a3b1e20-0567-5e8d-a621-5926382557c3 | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
note | 66b1d51c-af46-5407-beda-ad21c7c0a214 | Frequency - Each Lot
note | 683816a9-8f2f-5e3b-960c-39212eda44c4 | Verification Records - Visual
note | 38b7f3c7-d030-5735-b35a-95b9ee0ce21e | Action Respon. - FM
date | fdd3f73b-efd4-5677-865c-c84bf272c4e1 | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - treatment of Unsuitable Material
note | e52c1071-8881-5d90-94e9-924b93f88964 | HP
note | b94d4eb6-780d-5829-a6fe-26368ec07556 | Applicable Standard / Reference - VR204.07 (d)
note | 8d845dde-987c-5a17-a061-02026b86ae87 | Acceptance Criteria - Where unsuitable material is encountered the Contractor shall submit the proposed in situ treatment or extent of excavation to the Superintendent for review.
note | a67409ed-6160-55c9-8632-fdcc30fc9ac7 | Frequency - Each Lot
note | 8934766a-8859-5b76-8150-0b320e39d0d2 | Verification Records - Visual
note | a3c465ad-14ca-584f-a69e-c86aab2a04fb | Action Respon. - FM
date | 0a4b2358-dfa3-5d8b-b193-f06527beb5dd | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - Fill construction
note | 007dece1-f96b-5b2f-b49f-b71419e961df | HP
note | 0a227704-690b-5151-8992-3c907c62c944 | Applicable Standard / Reference - VR204.10 (b)
note | 9fac4637-6706-517b-abef-dbfdd30423b0 | Acceptance Criteria - The Contractor shall not commence placing of any fill on the prepared surface until the area has been reviewed by the Superintendent.
note | 27588009-f3c0-5a6f-908f-191bf6a9aa62 | Frequency - Each Lot
note | 71272720-a33d-5e16-be2c-a4ed3517618e | Verification Records - Visual
note | e21cd0aa-befd-5f10-b63b-1d60b88ef28f | Action Respon. - FM
date | 91752fd8-31c4-538a-a0ce-0bc1447de238 | Date:
signoff |  | HOLD POINT
checkpoint |  | Earthworks - Fill at Structures (wing walls, culverts >1200mm)
note | de982d79-8af2-521b-8259-24b4879edf68 | HP
note | 4790cc37-a8b9-53ee-a825-b41e3fe3ca70 | Applicable Standard / Reference - VR204.11 (b)
note | 0acaebc7-c454-5de6-81de-2d3e8f0a5e89 | Acceptance Criteria - No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent.
note | 6ffb40da-e4a2-5766-9a55-eb7ca3c43051 | Frequency - Each Lot
note | 9efb6db5-cc46-59b3-abaa-66c5ccd8873a | Verification Records - Visual
note | bc141d3b-47c3-5069-961d-17e674b78dba | Action Respon. - FM
date | 4421601b-60e6-5d9d-b93a-87b0c5e02d07 | Date:
signoff |  | HOLD POINT
checkpoint |  | Test Rolling
note | 779dd15b-4cc5-53f2-81ad-f2cc110482b4 | HP
note | e9ddd1f2-b68f-5138-879c-b82ef10087ce | Applicable Standard / Reference - VR173.03, VR204.12
note | 2b9a935d-cda9-5103-9359-df282b006968 | Acceptance Criteria - Undertake test roll prior to placement of fill/or proceeding layer. Contractor shall provide for the Superintendant to be present during all test rolling.
note | 07533b0a-1fa1-5264-936a-06ea56e8eec8 | Frequency - Each Lot
note | 2c0d6e16-e103-5b19-88f6-f30929449714 | Verification Records - Visual
note | 6c83b03d-31b5-5e2a-a89f-300d904e17c6 | Action Respon. - FM
date | dc7c1280-046f-598b-81a0-6a1ae8551490 | Date:
signoff |  | HOLD POINT
checkpoint |  | Lot size
note | 5a82d004-4bfa-5e8f-a6bc-ffc762c2e72f | Applicable Standard / Reference - VR204.13, Table 204.142
note | 98c45872-b97d-55ae-ba50-0d22d7715343 | Acceptance Criteria - Type A: max 5000m2 or one day's production, whichever is the lesser
textbox | d8846cb7-241d-5475-8a4e-18f40866ecc9 | Actual |  |  | m2
note | ce2a0e73-bb93-560a-bb78-3d36664ed5dc | Frequency - Each Lot
note | b1af837b-1c4f-53d7-a339-6ce2a33fe5f7 | Verification Records - Records
note | 72d63646-efce-58a1-b203-d528e40025c5 | Action Respon. - PE/SE
date | 07791e49-222e-504d-9d57-f2d1af950607 | Date:
checkpoint |  | Compaction & Grading
note | 1dd38155-cbd2-5540-9c3d-170f28cd7c5d | Applicable Standard / Reference - VR204.13 (b), Tables 204.042, 204.14 1
note | 6d095886-e2b8-5f6a-9cbf-48267778547c | Acceptance Criteria - Compaction:
note | cd918a48-f69b-5e2a-ab33-e9f283567a45 | ○ All Type A Material, and Type B material placed within 400mm of top of cut floor level: min. 100%
textbox | 66c42768-f31d-531c-96d9-5631f1235097 | Actual % / Minimum Frequency Testing
note | 3ccc14fe-e73c-596f-a6a4-c162c255cd3b | Grading:
note | f8ebac7f-dbbb-5822-bac5-e996cb0af915 | ○ as per Table 204.041
note | 808a51a5-d12a-5f15-9adb-b9daad2e6bac | ○ Pass/ Fail/ Minimum Frequency testing
note | 9e0a316c-ffb0-5ddb-a859-7cb63cd7bbf2 | Frequency - 1 test for each lot then reduced to 1 test for every second lot
note | edc7d9ab-e00b-54e6-8f95-b42ceebfd7bc | Verification Records - Records/Visual
note | 776aa4dd-9742-52af-bcf5-2b27a6e48fed | Action Respon. - FM
date | c5b74ca0-1e32-5128-8ada-5181a945a424 | Date:
checkpoint |  | Compaction - CBR & Swell
note | 8b82aa06-d89e-51e1-99c6-1b7626882c62 | Applicable Standard / Reference - Table 204.141 & Table 204.041
note | 2cc8114b-c4de-5ccc-b860-b6506ce000ee | Acceptance Criteria - Type A: initial 1 lot test to determine assigned CBR >6% and swell <1.5%
textbox | 9b9bf718-02b3-54fa-b367-de594ff1f60a | Assigned CBR |  |  | %
textbox | c8784b74-ca0d-5a11-b4fb-60683f143b8d | Actual |  |  | %
textbox | 096ccf84-da2f-5bfa-903f-3cb470aeb45f | Assigned Swell |  |  | %
textbox | 122ac4a0-b0de-5f21-aa11-477d9b46cc4b | Actual |  |  | %
note | 0230b259-b967-5025-aeb4-f656c20af785 | Frequency - Single CBR test to confrim assigned CBR and swell - first lot only
note | ca4df214-0d30-5838-98f3-ae4bf8f36063 | Verification Records - Records
note | 7b5f54f2-f4f4-53b8-bf1b-fe6290c13024 | Action Respon. - PE/SE
date | 53b3c648-74e6-58de-8860-6e2fd93232c2 | Date:
checkpoint |  | Compaction - PI
note | f913df10-b1a9-52e3-a0c7-599d7cbb151e | Applicable Standard / Reference - Table 204.141 & Table 204.041
note | 6f7fd32d-cec2-5a30-b8ba-9b3346527652 | Acceptance Criteria - Type A: plasticity index (PI) calculation x % Passing 0.425mm, Max. 1000
note | 1517cc68-df0d-5d70-b30c-094ad39eb302 | Frequency - 1 test per 2 lots then 1 test per 4 lots
note | 8434c12e-7266-5760-9612-b62dea660ffa | Verification Records - Records
note | c931d870-810d-5466-bc8c-d1f835c021a7 | Action Respon. - PE/SE
date | 25bb83a6-06da-56ef-8bd6-ce4b51936a00 | Date:
checkpoint |  | Compaction - LL & Permeability
note | 8ad8fb13-0a1c-541c-80bb-8e0c8ce5f2eb | Applicable Standard / Reference - Table 204.141 & Table 204.041
note | 99d4ec55-e68e-5734-9d14-8b7c4975b76c | Acceptance Criteria - Type A: liquid limit and comparison of PI against LL, Permeability <5 x 10-9m/sec
note | 87733a13-21b5-50b9-807c-40ba423e177b | Frequency - 1 test per 2 lots then 1 test per 4 lots
note | e9c1c207-8995-5ca1-a86f-d8d0db1824e1 | Verification Records - Records
note | 6031c425-be15-538b-85a9-72d07dad9831 | Action Respon. - PE/SE
date | 2350d913-7117-5757-a5ca-65e72ed6e40f | Date:
checkpoint |  | Other Contract Specific Requirements
textbox | d5b6d443-74e5-5978-a8e9-699624038ec7 | Requirement(s):
date | c80e06b6-e4f1-54fb-8006-7ace5dc2be21 | Date:
checklist |  | NCR Checklist |  | NCR No: |  | f0704521-0eed-41a3-894d-64c7a2cc0f72
checkpoint |  | Non Conformance Report
textbox | a6579d74-50f0-5b0c-9053-4fa6c346ad52 | Lot Number
tickbox | 491a55cf-aa1d-567c-ac68-0b1fd615a30f | Operational
tickbox | 7e5ad9d5-1c1f-59b4-bab3-a4fdf1d7018a | Procedural
tickbox | df55adf1-8c91-5618-905e-739290148913 | Material
dropdown | 093c16e5-b914-5ef9-b030-cdaa1528b656 | NCR raised as result of: | Inspection & Testing, Co's NC Product, Suppliers NC Product, Customer Complaint, Audit
textbox | 52bd8673-a599-5f8e-b28c-0a410c7959c9 | Non Conformance Details
date | f87d50dd-b43c-5db7-8e41-56fac938515a | Approval Date
dropdown | 68eb3b08-fec9-59fc-8cf0-6efcdf1ff742 | Proposed Method of Disposition to Non - Conformance | Accept as it is, Accept with Concession, Rework or Repair, Reject & Replace, Return to Supplier, Regrade for other use
textbox | 01a4c3ef-b34a-52f3-bbd8-dc7f32049651 | Details of Disposition
dropdown | 277c0a6a-c8df-5653-8636-38d45cc52b75 | Customer/Client Approval | Required, Not Required
date | e4001a7c-3fff-5fd3-918f-4cf9357ffab3 | Disposition Completed On
textbox | 52da77a7-217f-5967-b0af-55d41801a0c3 | Completed By
date | 91814999-c2b3-5c43-95af-7dd99597d677 | Dispoition Approved On
date | 1d14c73a-6eed-5f37-8410-698abd8220fd | Date NCR Closed
textbox | 848847e6-8ba9-541c-adc5-5428edb2ac46 | Closed By
dropdown | 2b538ff0-4ea6-5fb2-b8dd-9febf4e9a288 | Corrective Action | Required, Not Required
dropdown | c00fff82-5a25-58fb-a246-e693a8ddfc6b | Preventative Action | Required, Not Required
textbox | a93dfa0b-ed20-5fd4-87af-2bd8b8c99db7 | Details of CA/PA taken if required:
date | 468f9164-522a-5c4b-b939-c33b71432c24 | CA/PA Closed
textbox | fba489c0-7318-54f1-a4cc-6d2253d09f6a | Closed By
signoff |  | NCR Sign Off