## AC Resurfacing ITP
Product Stage or Material to be Tested or Inspected | Type |  |  | How Often? | Records Required | Responsibility | Initial on completion
| T = Test | Reference or | Method/Test
| I= Inspection | Specification | Required
H= Hold point
1.0 Pre-Work
Approved JMF for Strengthening Repairs Mix (if required) | H | Design Report | Confirm approved JMF dates in Design Report | Each site | Copy of Approved Design Report | Project Manager(AC)
Approved JMF for Pre-Level Mix (if required) | H | Design Report | Confirm approved JMF dates in Design Report | Each site | Copy of Approved Design Report | Project Manager(AC)
Approved JMF for Wearing Course Mix | H | Design Report | Confirm approved JMF dates in Design Report | Each site | Copy of Approved Design Report | Project Manager(AC)
Approved Design Report | H | Design Report | Confirm document on-site | Each site | Copy of Approved Design Report | Renewals Manager
Treatment of affected Service Covers (to be raised or protected) | H | Job sheet | Confirm plan in place | Each site | Job Sheet record | Project Manager(AC)
Stakeholder Management Requirements met | H | CSCMP | Confirm requirements followed | Each site | Copy of stakeholder notification / Photographs of VMS Boards | Renewals Manager
Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work | H | QMP | Brief all team members on day’s work plan | Each site | Daily diary | Project Manager(AC)
Confirm if any environmental protection is required | H | ESMP | Record decision | Each site | Job Sheet record | Project Manager AC/Site Supervisor
2.0 Site set up
Ambient Conditions Pavement Surface Temp ≥ 5ºC (Intermediate or structural layers) and ≥ 10ºC (wearing course) and forecast to rise | H | NZTA M10: 2020 9.5.2 | Temperature Gun Check Acceptable / Unacceptable | Each site | Job Sheet record | Site Supervisor
Job start, identify risks and controls, communicated to team | H | HSMP | Record all risks and controls on Hazard ID following Team discussion | Each site | Hazard ID form | Site Supervisor
Establish traffic management to plan | H | TMP | Site audit post set up | Each site | TTM diary | STMS
Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report | H | Design Report | Record as-built site dimensions | Each site | Job Sheet record | Site Supervisor
Identification of Services Service Plans on-site Shallow Services marked | H | SOP | Confirm document on-site / Visual check | Each site | Job Sheet record | Site Supervisor
Job Sheet record
Job Sheet record
Service Covers treated as planned | H | Job sheet | Visual check | Each site | Job Sheet record | Site Supervisor
Record & photograph environmental protection measures installed | I | ESMP | Record temporary measures | Each site | Job Sheet record & photograph | Site Supervisor / Site QA
3.0 Milling (If Required)
Milling undertaken to correct depth ±5mm nominal thickness | I | Design Report | Dip checks | Per site | Job Sheet record | Site Supervisor / Site QA
Exposed Basecourse waterproofed / levelled | I | QMP | Acceptable / Unacceptable | Per site | Job Sheet record | Site Supervisor
4.0 Membrane (If Required)
Application as per Design Requirements (Chip size / binder application rate) | I | Design Report | Spray Sheet/s | Per site | Job Sheet record | Site Supervisor / Site QA
5.0 Strengthening Repairs (If Required)
Delivery temperature ±30 degrees from recommended mixing temperature | T | NZTA M10: 2020 Notes | Temperature Gun Check Acceptable / Unacceptable | Per load | Job Sheet record | Site Supervisor
Structural Asphalt Layer Thickness Each Layer >55mm | T | NZTA M10 2020 10.1 & Table 3.1 | Dip checks during paving process / Cores | One test per patch & / or One test per 300m2 | Job Sheet record & photograph | Site Supervisor / Site QA
±10mm nominal thickness | T | NZTA M10: 2020 10.1 & Table 3.1 | Dip checks during paving process / Cores | One test per patch & / or One test per 300m2 | Job Sheet record & photograph | Site Supervisor / Site QA
Compaction and Air Voids | T | Paving SOP | NDM for Quality Control Only | One test per patch & / or One test per 50m2 | Job Sheet record & photograph | Site Supervisor / Site QA
6.0 Pre-Levelling (If Required)
Delivery Temperature +10 / -30 degrees from recommended mixing temperature | T | NZTA M10: 2020 Notes | Temperature Gun Check Acceptable / Unacceptable | Per load | Job Sheet record | Site Supervisor
-5mm / +5mm below bottom of the nominal thickness of wearing course specified in Design Report | T | Design Report | Dip checks during paving process / Cores | Every 15m | Stringline Sheet record & photograph | Site Supervisor / Site QA
7.0 Wearing Course
Delivery temperature ±30 degrees from recommended mixing temperature | T | NZTA M10: 2020 Notes | Temperature Gun Check Acceptable / Unacceptable | Per load | Job Sheet record | Site Supervisor
-5mm / +10mm nominal thickness specified in Design Report If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report | T | NZTA M10:2020 10.1 & NZTA M10:2020 Notes Table 3.3 & 3.4 or NZTA M27:2020 10.2 & NZTA M27:2020 Notes Table 3.1 | Dip checks during paving process / Stringline Sheet | Every 15m | Stringline Sheet record & photograph | Site Supervisor / Site QA
Compaction and Air Voids Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset | T | NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2 | 150mm Diameter Cores where: 1. >30tonnes 2. >=35mm lift thickness 100mm Diameter Cores where: 1. >30tonnes 2. >=35mm and <40mm lift thickness NDM (only where accepted by the Engineer in writing along with the testing plan.) | Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint. NDM (only where accepted by then Engineer as per agreed testing plan.) | IANZ Accredited Laboratory | Site Supervisor / Site QA
Compaction and Air Voids Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset | T | NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2 | NDM for Quality Control Only | Every 20m alternating wheel tracks | Job Sheet record | Site Supervisor / Site QA
Post construction surface condition | I | Design | Acceptable / Unacceptable | Per site | Job Sheet record | Site Supervisor
Supervisor/QA to provide an update regarding site completion per shift | H | Design | Acceptable / Unacceptable | Per site | Email | Site Supervisor/Site QA
8.0 Post-Construction
Linemarking and RRPM Reinstated Matches previous linemarking - within 48 hours of sealing | H | MOTSAM | Visual check | Per site | Job Sheet record & photograph | Project Manager(AC)
As-Built records – structural patches | H | Design | Record as-built patch dimensions & RPs | Per site | Job Sheet record & photograph | Project Manager AC / Site QA
Collect RAMM data | H | Comply with Waka Kotahi format | Correct data supplied | Per site | Job Sheet record + As-Builts + photographs | Project Manager AC / Site QA
9.0 Out Of Season Paving
Out of Season Paving | H | Winter Surfacing Site Note | Waka Kotahi Approval | Per Applicable Site | Copy of Waka Kotahi Approval on-site | Project Manager AC / Site Supervisor
Dispatching Temperature compliance | T | NZTA M10: 2020 Notes - Table 3.3 | As per Table N4.1: NZTA M/10: 2014 | Per Load | Job Sheet record | Asphalt Plant Manager
Arrival and Compaction Temperature: 110-170°C To be recorded when mix is tipped into the paver. Manager to be notified if temperature falls below: SMA9.5 134°C SMA12.5 134°C SMA11 134°C AC20 145°C AC14 142°C If temperature falls below 110°C mix will not be used | T | NZTA M10: 2020 Notes - Table 3.3 | Temperature Gun Acceptable / Unacceptable | Per Load | Job Sheet record | Site Supervisor / Site QA