## 24.25 CHIP Master Programme (2)
Site Ref # | jv_ID | State Highway - Route Station | State Highway | Updated Start | Updated End | Length | Lane | # of lanes | Lane Length | Avge Total Width to be Surfaced (m) | Area (m²) | Additional areas (m²) | info_extraAreaReason | Total Area (m²)
| 2061995 | 002-0034 |  | 1759 | 2280 | 521 | All | 2 | 1042 | 10.05 | 5236.05 | 500 | Intersection | 5736.05
| 59009 | 002-0037 |  | 4621 | 4979 | 358 | All | 2 | 716 | 7.5 | 2685 | 400 | Intersection | 3085
|  | 002-0048 |  | 12817 | 12867 | 50 |  | 2 | 100 | 7.5 | 375
|  | 002-0061 |  | 0 | 40 |  |  | 2 | 80 | 11.4 | 456
| 59010 | 002-0061 |  | 4369 | 4780 | 411 | All | 2 | 822 | 8.6 | 3534.6 |  |  | 3534.6
| 59514 | 002-0061 |  | 6500 | 6940 | 440 | All | 2 | 880 | 8.6 | 3784 | 300 | Intersection | 4084
| 59497 | 002-0061 |  | 7639 | 7730 | 91 | All | 2 | 182 | 8.4 | 764.4 |  |  | 764.4
| 59498 | 002-0061 |  | 7730 | 7790 | 60 | All | 2 | 120 | 8.4 | 504 | 300 | Intersection | 804
| 59597 | 002-0073 |  | 12465 | 12550 | 85 | All | 2 | 170 | 7.9 | 671.5 |  | Do we seal the carpark ? | 671.5
| 59406 | 002-0073 |  | 15865 | 16880 | 1015 | All | 3 | 3045 | 17.484 | 17746.26 |  | 4 lanes + flush median ( CAD) + intersection | 17746.26
| 59013 | 002-0073 |  | 17847 | 18199 | 352 | All | 2 | 704 | 7.5 | 2640 |  |  | 2640
|  | 002-0073 |  | 18199 | 18600 | 401 | All | 2 | 802 | 10.8 | 4330.8 | 1000 | Intersection , slip lane, (CAD) | 5330.8
| 59014 | 002-0093 |  | 98 | 254 | 156 | All | 2 | 312 | 13.07 | 2038.92 | 500 | CAD - multiple intersections. RTB, | 2538.92
| 59431 | 002-0093 |  | 2512 | 2822 | 310 | All | 2 | 620 | 7.5 | 2325 | 1000 | RTB, side road | 3325
| 59432 | 002-0093 |  | 3147 | 3633 | 486 | All | 2 | 972 | 7.5 | 3645 |  | wide centre line | 3645
| 59016 | 002-0093 |  | 4537 | 5035 | 498 | All | 2 | 996 | 11.45 | 5702.1 |  | CAD - multiple intersections. RTB, | 5702.1
| 59017 | 002-0093 |  | 5035 | 5546 | 511 | All | 2 | 1022 | 11.3 | 5774.3 |  | CAD - multiple intersections. RTB, | 5774.3
| 2062233 | 024-0000/01.08 |  | 9530 | 9880 | 350 | All | 2 | 700 | 7.6 | 2660 |  |  | 2660
| 2062353 | 025-0024 |  | 11661 | 11900 | 239 | All | 2 | 478 | 8.3 | 1983.7 |  |  | 1983.7
| 2062342 | 025-0024 |  | 7488 | 7980 | 492 | All | 2 | 984 | 8.7 | 4280.4 | 1500 | CAD - multiple intersections. Carparking area | 5780.4
| 2062374 | 025-0024 |  | 17728 | 17940 | 212 | All | 2 | 424 | 10.3 | 2183.6 |  | 3 x intersections, wide shoulder, carpark by shops (CAD) | 2183.6
| 2062376 | 025-0042 |  | 30 | 280 | 250 | All | 2 | 500 | 8.1 | 2025 |  |  | 2025
|  | 025-0042 |  | 7790 | 7890 | 100 | All | 2 | 200 | 7.8 | 780 |  |  | 780
|  | 025-0042 |  | 7890 | 8510 | 620 | All | 2 | 1240 | 7.8 | 4836 |  |  | 4836
| x | 025-0042 |  | 3630 | 3780 | 150 | All | 2 | 300 | 8.5 | 1275 |  | Raumahanga construction site | 1275
| x | 025-0042 |  | 3970 | 4140 | 170 | All | 2 | 340 | 8.5 | 1445 |  | Raumahanga construction site | 1445
| x | 025-0042 |  | 4355 | 4650 | 295 | All | 2 | 590 | 8.5 | 2507.5 |  | Raumahanga construction site | 2507.5
| 2062486 | 025-0058 |  | 8020 | 8200 | 180 | All | 2 | 360 | 7.6 | 1368 |  |  | 1368
| 58878 | 025-0058 |  | 9290 | 9700 | 410 | All | 2 | 820 | 7.9 | 3239 |  |  | 3239
| 2062528 | 025-0072 |  | 6110 | 6790 | 680 | All | 2 | 1360 | 8.1 | 5508 |  |  | 5508
| 2062542 | 025-0084 |  | 40 | 770 | 730 | All | 2 | 1460 | 8.26 | 6029.8 |  |  | 6029.8
| 2062569 | 025-0084 |  | 5500 | 6591 | 1091 | All | 2 | 2182 | 8.11 | 8848.01 | 1552.8 | Intersection | 10400.81
| 2062573 | 025-0084 |  | 7063 | 7594 | 531 | All | 2 | 1062 | 7.6 | 4035.6 | 924.4 | Intersection | 4960
| 2062592 | 025-0099 |  | 0 | 41 | 41 | All | 2 | 82 | 8.8 | 360.8 |  |  | 360.8
| 2062592 | 025-0099 |  | 41 | 641 | 600 | All | 2 | 1200 | 8.8 | 5280 |  |  | 5280
| 59001 | 025-0127 |  | 3538 | 3790 | 252 | All | 2 | 504 | 7.9 | 1990.8 |  |  | 1990.8
| 2062730 | 025-0143 |  | 3287 | 3345 | 58 | All | 2 | 116 | 8.5 | 493 |  |  | 493
| 2062730 | 025-0143 |  | 3345 | 3420 | 75 | All | 2 | 150 | 8.5 | 637.5 |  |  | 637.5
| 2062743 | 025-0143 |  | 6287 | 6610 | 323 | All | 2 | 646 | 8 | 2584 |  |  | 2584
| 58613 | 025-0143 |  | 6610 | 7020 | 410 | All | 2 | 820 | 7.7 | 3157 |  |  | 3157
| 2062826 | 025-0156 |  | 14700 | 15300 | 600 | All | 2 | 1200 | 13.8 | 8280 |  |  | 8280
| 58842 | 025-0156 |  | 14340 | 14700 | 360 | All | 2 | 720 | 7.7 | 2772 |  |  | 2772
| 2062919 | 025-0188 |  | 8349 | 8580 | 231 | All | 2 | 462 | 8.6 | 1986.6 |  |  | 1986.6
| 2062919 | 025-0188 |  | 8580 | 8740 | 160 | All | 2 | 320 | 8.6 | 1376 |  |  | 1376
| 2062990 | 025-0217 |  | 464 | 650 | 186 | All | 2 | 372 | 7.9 | 1469.4 |  |  | 1469.4
| 2062991 | 025-0217 |  | 650 | 800 | 150 | All | 2 | 300 | 7.9 | 1185 |  |  | 1185
|  | 025-0217 |  | 4940 | 5080 |  |  | 2 | 280 | 7.6 | 1064 |  |  | 1064
|  | 025-0217 |  | 5170 | 5400 |  |  | 2 | 460 | 7.6 | 1748 |  |  | 1748
| 58936 | 025-0217 |  | 6339 | 6449 | 110 | All | 2 | 220 | 8.2 | 902 |  |  | 902
| 58937 | 025-0217 |  | 6449 | 6530 | 81 | All | 2 | 162 | 7.9 | 639.9 |  |  | 639.9
| 2063028 | 025-0226 |  | 2200 | 3270 | 1070 | All | 2 | 2140 | 7.3 | 7811 | 3942 |  | 11753
| 2063045 | 025-0226 |  | 5843 | 6050 | 207 | All | 2 | 414 | 7.9 | 1635.3 |  |  | 1635.3
| 2063055 | 025-0226 |  | 8717 | 9000 | 283 | All | 2 | 566 | 7.5 | 2122.5 |  |  | 2122.5
| 2063055 | 025-0226 |  | 9000 | 9225 | 225 | All | 2 | 450 | 7.5 | 1687.5 |  |  | 1687.5
| 2063072 | 025-0226 |  | 12696 | 12775 | 79 | All | 2 | 158 | 7.5 | 592.5 |  |  | 592.5
| 58617 | 025-0226 |  | 4500 | 4590 | 90 | All | 2 | 180 | 17 | 1530 |  |  | 1530
| 59002 | 025-0226 |  | 5613 | 5843 | 230 | All | 2 | 460 | 10.4 | 2392 |  |  | 2392
| 58618 | 025-0226 |  | 7026 | 7410 | 384 | All | 2 | 768 | 10 | 3840 |  |  | 3840
| 58853 | 025-0226 |  | 8040 | 8435 | 395 | All | 2 | 790 | 7.5 | 2962.5 |  |  | 2962.5
| 58620 | 025-0226 |  | 13950 | 15090 | 1140 | All | 2 | 2280 | 11 | 12540 |  |  | 12540
| 58621 | 025-0226 |  | 15255 | 15700 | 445 | All | 2 | 890 | 10.6 | 4717 |  |  | 4717
| 58622 | 025-0226 |  | 15700 | 16070 | 370 | All | 2 | 740 | 10.6 | 3922 |  |  | 3922
| 57090 | 026-0026 |  | 711 | 980 | 269 | All | 2 | 538 | 7.5 | 2017.5 |  | CAD . Flush median, RTB, | 2017.5
| 2063191 | 026-0048 |  | 6160 | 6420 | 260 | All | 2 | 520 | 8.4 | 2184 |  |  | 2184
| 2063191 | 026-0048 |  | 6420 | 6689 | 269 | All | 2 | 538 | 8.4 | 2259.6 |  |  | 2259.6
| 2063197 | 026-0048 |  | 9900 | 10580 | 680 | All | 2 | 1360 | 8.4 | 5712 |  |  | 5712
| 2063221 | 026-0060 |  | 6064 | 6310 | 246 | All | 2 | 492 | 9.9 | 2435.4 |  |  | 2435.4
| 2063265 | 026-0070 |  | 9200 | 9650 | 450 | All | 2 | 900 | 9.04 | 4068 |  |  | 4068
| 2063276 | 026-0080 |  | 3320 | 3440 | 120 | All | 2 | 240 | 7.9 | 948 |  |  | 948
| 2063278 | 026-0080 |  | 3440 | 3920 | 480 | All | 2 | 960 | 7.9 | 3792 |  |  | 3792
| 2063284 | 026-0080 |  | 4830 | 5290 | 460 | All | 2 | 920 | 7.7 | 3542 |  |  | 3542
|  | 026-0080 |  | 7700 | 8090 | 390 | All | 2 | 780 | 8.2 | 3198 |  |  | 3198
| 2063298 | 026-0080 |  | 8849 | 9229 | 380 | All | 2 | 760 | 7.9 | 3002 |  |  | 3002
| 2063316 | 026-0080 |  | 15090 | 15350 | 260 | All | 2 | 520 | 7.5 | 1950 |  |  | 1950
| 2063321 | 026-0095 |  | 170 | 300 | 130 | All | 2 | 260 | 14.5 | 1885 |  | CAD - big area, 4 lanes, merge. | 1885
| 2063398 | 027-0021 |  | 1780 | 2170 | 390 | All | 2 | 780 | 9.72 | 3790.8 | 200 | intersection | 3990.8
| 2063398 | 027-0021 |  | 2170 | 2512 | 342 | All | 2 | 684 | 9.72 | 3324.24 |  |  | 3324.24
|  | 027-0027 |  | 4020 | 4170 |  |  | 1 | 150 | 5 | 750
| 57474 | 027-0027 |  | 16918 | 17617 | 699 | All | 2 | 1398 | 10.3 | 7199.7 |  |  | 7199.7
| 2063480 | 027-0046 |  | 10800 | 11185 | 385 | All | 2 | 770 | 10.6 | 4081 | 697.1783 | Intersection | 4778.1783
| 2063484 | 027-0046 |  | 13034 | 13275 | 241 | All | 2 | 482 | 10.6 | 2554.6 |  |  | 2554.6
| 2063502 | 027-0067 |  | 40 | 390 | 350 | All | 2 | 700 | 10.9 | 3815 |  |  | 3815
| 57711 | 029-0050 |  | 550 | 915 | 365 | All | 2 | 730 | 8.9 | 3248.5 |  |  | 3248.5
| 57714 | 029-0061 |  | 60 | 160 | 100 | All | 2 | 200 | 11 | 1100 | 200 | RTB Flush median rail | 1300
|  | 029-0061 |  | 160 | 428 | 268 | All | 2 | 536 | 10 | 2680 |  |  | 2680
Add Hauraki Intersection (Was on the AC list)
m2 figures need work.
|  | MEDIUMS = |  | in general, some minor fabs could make them a LOW
Need scrim added at some point.
[6 empty] | 27405 |  |  | 58653 |  | 257681.13 | 13016.3783 | 0 | 269047.5083
BIG Grade 2 for all flushed sites
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to add to CMR and make site start at 15870 as per SCRIM request. NEED NZTA APPROVAL Reply: Was 16167
Note on I11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Clarify
Note on F19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was 9842
Note on E27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3770 ? (RAMM TL)
Note on E37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New start RP 3538. Trimmed bit is LOW priority TL.
Note on E74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change start - don’t seal bridge deck