## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - AC Resurfacing | itp |  |  |  |  | ITP - AC Resurfacing
section | 1.0 Pre-Work
checkpoint | Approved JMF for Strengthening Repairs Mix (if required)
label | H
label | Reference or Specification - Design Report
label | Method/Test Required - Confirm approved JMF dates in Design Report
label | How Often? - Each site
label | Records Required - Copy of Approved Design Report
label | Responsibility - Project Manager(AC)
checkpoint | Approved JMF for Pre-Level Mix (if required)
label | H
label | Reference or Specification - Design Report
label | Method/Test Required - Confirm approved JMF dates in Design Report
label | How Often? - Each site
label | Records Required - Copy of Approved Design Report
label | Responsibility - Project Manager(AC)
checkpoint | Approved JMF for Wearing Course Mix
label | H
label | Reference or Specification - Design Report
label | Method/Test Required - Confirm approved JMF dates in Design Report
label | How Often? - Each site
label | Records Required - Copy of Approved Design Report
label | Responsibility - Project Manager(AC)
checkpoint | Approved Design Report
label | H
label | Reference or Specification - Design Report
label | Method/Test Required - Confirm document on-site
label | How Often? - Each site
label | Records Required - Copy of Approved Design Report
label | Responsibility - Renewals Manager
checkpoint | Treatment of affected Service Covers (to be raised or protected)
label | H
label | Reference or Specification - Job sheet
label | Method/Test Required - Confirm plan in place
label | How Often? - Each site
label | Records Required - Job Sheet record
label | Responsibility - Project Manager(AC)
checkpoint | Stakeholder Management Requirements met
label | H
label | Reference or Specification - CSCMP
label | Method/Test Required - Confirm requirements followed
label | How Often? - Each site
label | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
label | Responsibility - Renewals Manager
checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
label | H
label | Reference or Specification - QMP
label | Method/Test Required - Brief all team members on day’s work plan
label | How Often? - Each site
label | Records Required - Daily diary
label | Responsibility - Project Manager(AC)
checkpoint | Confirm if any environmental protection is required
label | H
label | Reference or Specification - ESMP
label | Method/Test Required - Record decision
label | How Often? - Each site
label | Records Required - Job Sheet record
label | Responsibility - Project Manager AC/Site Supervisor
section | 2.0 Site set up
checkpoint | Ambient Conditions - Pavement Surface Temp ≥ 5ºC (Intermediate or structural layers) and ≥ 10ºC (wearing course) and forecast to rise
label | H
label | Reference or Specification - NZTA M10: 2020 9.5.2
label | Method/Test Required - Temperature Gun Check, Acceptable / Unacceptable
label | How Often? - Each site
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor
checkpoint | Job start, identify risks and controls, communicated to team
label | H
label | Reference or Specification - HSMP
label | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
label | How Often? - Each site
label | Records Required - Hazard ID form
label | Responsibility - Site Supervisor
checkpoint | Establish traffic management to plan
label | H
label | Reference or Specification - TMP
label | Method/Test Required - Site audit post set up
label | How Often? - Each site
label | Records Required - TTM diary
label | Responsibility - STMS
checkpoint | Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
label | H
label | Reference or Specification - Design Report
label | Method/Test Required - Record as-built site dimensions
label | How Often? - Each site
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor
checkpoint | Identification of Services, Service Plans on-site, Shallow Services marked
label | H
label | Reference or Specification - SOP
label | Method/Test Required - Confirm document on-site / Visual check
label | How Often? - Each site
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor
checkpoint | Service Covers treated as planned
label | H
label | Reference or Specification - Job sheet
label | Method/Test Required - Visual check
label | How Often? - Each site
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor
checkpoint | Record & photograph environmental protection measures installed
label | I
label | Reference or Specification - ESMP
label | Method/Test Required - Record temporary measures
label | How Often? - Each site
label | Records Required - Job Sheet record & photograph
label | Responsibility - Site Supervisor / Site QA
section | 3.0 Milling (If Required)
checkpoint | Milling undertaken to correct depth: ±5mm nominal thickness
label | I
label | Reference or Specification - Design Report
label | Method/Test Required - Dip checks
label | How Often? - Per site
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor / Site QA
checkpoint | Exposed Basecourse waterproofed / levelled
label | I
label | Reference or Specification - QMP
label | Method/Test Required - Acceptable / Unacceptable
label | How Often? - Per site
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor
section | 4.0 Membrane (If Required)
checkpoint | Application as per Design Requirements (Chip size / binder application rate)
label | I
label | Reference or Specification - Design Report
label | Method/Test Required - Spray Sheet/s
label | How Often? - Per site
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor / Site QA
section | 5.0 Strengthening Repairs (If Required)
checkpoint | Delivery temperature: ±30 degrees from recommended mixing temperature
label | T
label | Reference or Specification - NZTA M10: 2020 Notes
label | Method/Test Required - Temperature Gun Check, Acceptable / Unacceptable
label | How Often? - Per load
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor
checkpoint | Structural Asphalt Layer Thickness: Each Layer >55mm
label | T
label | Reference or Specification - NZTA M10 2020 10.1 & Table 3.1
label | Method/Test Required - Dip checks during paving process / Cores
label | How Often? - One test per patch & / or One test per 300m2
label | Records Required - Job Sheet record & photograph
label | Responsibility - Site Supervisor / Site QA
checkpoint | ±10mm nominal thickness
label | T
label | Reference or Specification - NZTA M10: 2020 10.1 & Table 3.1
label | Method/Test Required - Dip checks during paving process / Cores
label | How Often? - One test per patch & / or One test per 300m2
label | Records Required - Job Sheet record & photograph
label | Responsibility - Site Supervisor / Site QA
checkpoint | Compaction and Air Voids
label | T
label | Reference or Specification - Paving SOP
label | Method/Test Required - NDM for Quality Control Only
label | How Often? - One test per patch & / or One test per 50m2
label | Records Required - Job Sheet record & photograph
label | Responsibility - Site Supervisor / Site QA
section | 6.0 Pre-Levelling (If Required)
checkpoint | Delivery Temperature: +10 / -30 degrees from recommended mixing temperature
label | T
label | Reference or Specification - NZTA M10: 2020 Notes
label | Method/Test Required - Temperature Gun Check, Acceptable / Unacceptable
label | How Often? - Per load
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor
checkpoint | -5mm / +5mm below bottom of the nominal thickness of wearing course specified in Design Report
label | T
label | Reference or Specification - Design Report
label | Method/Test Required - Dip checks during paving process / Cores
label | How Often? - Every 15m
label | Records Required - Stringline Sheet record & photograph
label | Responsibility - Site Supervisor / Site QA
section | 7.0 Wearing Course
checkpoint | Delivery temperature: ±30 degrees from recommended mixing temperature
label | T
label | Reference or Specification - NZTA M10: 2020 Notes
label | Method/Test Required - Temperature Gun Check, Acceptable / Unacceptable
label | How Often? - Per load
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor
checkpoint | -5mm / +10mm nominal thickness specified in Design Report. If applicable all mix is not more than 5mm above lip of channel unless specified otherwise in the Design Report
label | T
label | Reference or Specification - NZTA M10:2020 10.1 & NZTA M10:2020 Notes Table 3.3 & 3.4 or NZTA M27:2020 10.2 & NZTA M27:2020 Notes Table 3.1
label | Method/Test Required - Dip checks during paving process / Stringline Sheet
label | How Often? - Every 15m
label | Records Required - Stringline Sheet record & photograph
label | Responsibility - Site Supervisor / Site QA
checkpoint | Compaction and Air Voids: Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset
label | T
label | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
label | Method/Test Required - 150mm Diameter Cores where:
label | 1. >30tonnes
label | 2. >=35mm lift thickness
label | ○ 100mm Diameter Cores where:
label | 1. >30tonnes
label | 2. >=35mm and <40mm lift thickness
label | ○ NDM (only where accepted by the Engineer in writing along with the testing plan.)
label | How Often? - Mat Cores: Cores to be randomly located using ASTM D5361 in each sublot. 1 core per 300m2 sublot and a min 8 cores each lot
label | ○ Joint Cores: Cores to be randomly located using ASTM D5361 in every 100m of joint.
label | ○ NDM (only where accepted by then Engineer as per agreed testing plan.)
label | Records Required - IANZ Accredited Laboratory
label | Responsibility - Site Supervisor / Site QA
checkpoint | Compaction and Air Voids: Mat density air voids (+3 and -2) and joint density air voids (+5 and -2) as noted on JMF with the offset
label | T
label | Reference or Specification - NZTA M10: 2020 Table 9.2 + ASTM D3203 or NZTA M27: 2020 Table 9.2
label | Method/Test Required - NDM for Quality Control Only
label | How Often? - Every 20m alternating wheel tracks
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor / Site QA
checkpoint | Post construction surface condition
label | I
label | Reference or Specification - Design
label | Method/Test Required - Acceptable / Unacceptable
label | How Often? - Per site
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor
checkpoint | Supervisor/QA to provide an update regarding site completion per shift
label | H
label | Reference or Specification - Design
label | Method/Test Required - Acceptable / Unacceptable
label | How Often? - Per site
label | Records Required - Email
label | Responsibility - Site Supervisor/Site QA
section | 8.0 Post-Construction
checkpoint | Linemarking and RRPM Reinstated: Matches previous linemarking - within 48 hours of sealing
label | H
label | Reference or Specification - MOTSAM
label | Method/Test Required - Visual check
label | How Often? - Per site
label | Records Required - Job Sheet record & photograph
label | Responsibility - Project Manager(AC)
checkpoint | As-Built records – structural patches
label | H
label | Reference or Specification - Design
label | Method/Test Required - Record as-built patch dimensions & RPs
label | How Often? - Per site
label | Records Required - Job Sheet record & photograph
label | Responsibility - Project Manager AC / Site QA
checkpoint | Collect RAMM data
label | H
label | Reference or Specification - Comply with Waka Kotahi format
label | Method/Test Required - Correct data supplied
label | How Often? - Per site
label | Records Required - Job Sheet record + As-Builts + photographs
label | Responsibility - Project Manager AC / Site QA
section | 9.0 Out Of Season Paving
checkpoint | Out of Season Paving
label | H
label | Reference or Specification - Winter Surfacing Site Note
label | Method/Test Required - Waka Kotahi Approval
label | How Often? - Per Applicable Site
label | Records Required - Copy of Waka Kotahi Approval on-site
label | Responsibility - Project Manager AC / Site Supervisor
checkpoint | Dispatching Temperature compliance
label | T
label | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
label | Method/Test Required - As per Table N4.1: NZTA M/10: 2014
label | How Often? - Per Load
label | Records Required - Job Sheet record
label | Responsibility - Asphalt Plant Manager
checkpoint | Arrival and Compaction Temperature: 110-170°C. To be recorded when mix is tipped into the paver. Manager to be notified if temperature falls below:
label | ○ SMA9.5 134°C
label | ○ SMA12.5 134°C
label | ○ SMA11 134°C
label | ○ AC20 145°C
label | ○ AC14 142°C
label | ○ If temperature falls below 110°C mix will not be used
label | T
label | Reference or Specification - NZTA M10: 2020 Notes - Table 3.3
label | Method/Test Required - Temperature Gun, Acceptable / Unacceptable
label | How Often? - Per Load
label | Records Required - Job Sheet record
label | Responsibility - Site Supervisor / Site QA
checklist | ITP - CS Resurfacing Physical Works | itp |  |  |  |  | ITP - CS Resurfacing Physical Works
section | 1.0 Pre-Works (Off Site)
checkpoint | Stakeholder Management Requirements met
label | H
label | Reference or Specification - CSCMP
label | Method/Test Required - Confirm requirements followed
label | How Often? - Each site
label | Records Required - Copy of stakeholder notification / Photographs of VMS Boards
label | Responsibility - Project Manager / Renewals Manager
checkpoint | Confirm if any environmental protection is required
label | I
label | Reference or Specification - ESMP
label | Method/Test Required - Record decision
label | How Often? - Each site
label | Records Required - Pre-seal Inspection Form
label | Responsibility - Project Manager
checkpoint | Daily work briefing, confirm scope, that you have all staff, materials and plant needed to complete the work
label | H
label | Reference or Specification - QMP
label | Method/Test Required - Brief all team members on day’s work plan
label | How Often? - Each site
label | Records Required - Pre-seal Inspection Form
label | Responsibility - Project Manager
section | 2.0 Pre-Construction (On Site)
checkpoint | Job start, identify risks and controls, communicated to team
label | H
label | Reference or Specification - HSMP
label | Method/Test Required - Record all risks and controls on Hazard ID following Team discussion
label | How Often? - Each site
label | Records Required - Hazard ID form
label | Responsibility - Site Foreperson
checkpoint | Establish traffic management to plan
label | H
label | Reference or Specification - TMP
label | Method/Test Required - Site audit post set up
label | How Often? - Each site
label | Records Required - TTM Diary
label | Responsibility - STMS
checkpoint | Confirm site is on approved programme
label | H
label | Reference or Specification - Approved Programme
label | Method/Test Required - Record as-built site dimensions
label | How Often? - Each Site
label | Records Required - Pre-seal Inspection Form
label | Responsibility - Site Foreperson
checkpoint | Confirm site extents (i.e. Check what is marked on the road matches the job sheet / programme details
label | H
label | Reference or Specification - Approved Programme
label | Method/Test Required - Record as-built site dimensions
label | How Often? - Each Site
label | Records Required - Pre-seal Inspection Form
label | Responsibility - Site Foreperson / Site QA
checkpoint | Stockpiled sealing chip is clean and suitable for sealing
label | H
label | Reference or Specification - QMP
label | Method/Test Required - Acceptable/Unacceptable
label | How Often? - Each Stockpile
label | Records Required - Pre-seal Inspection Form & Photograph
label | Responsibility - Site Foreperson / Site QA
checkpoint | Stockpiled sealing chip is the same grade(s) as specified in the chipseal design
label | H
label | Reference or Specification - QMP
label | Method/Test Required - Acceptable/Unacceptable
label | How Often? - Each Stockpile
label | Records Required - Pre-seal Inspection Form
label | Responsibility - Site Foreperson / Site QA
checkpoint | Record & photograph environmental protection measures installed
label | I
label | Reference or Specification - ESMP
label | Method/Test Required - Record temporary measures
label | How Often? - Each site
label | Records Required - Pre-seal Inspection Form & Photograph
label | Responsibility - Site Foreperson / Site QA
checkpoint | Binder application rate
label | T
label | Reference or Specification - Seal Design / Spraying Insructions
label | Method/Test Required - Confirm seal design requirements from programme
label | How Often? - Per site
label | Records Required - Spray Sheet
label | Responsibility - Site Foreperson / Site QA
checkpoint | Pre-Sealing surface condition
label | I
label | Reference or Specification - QMP
label | Method/Test Required - Acceptable/Unacceptable
label | How Often? - Per Site
label | Records Required - Pre-seal Inspection Form & Photograph
label | Responsibility - Site Foreperson / Site QA
section | 3.0 Construction
checkpoint | Start spraying Temp >10°C
label | T
label | Reference or Specification - NZTA P/17
label | Method/Test Required - Start >10°C
label | How Often? - Per site
label | Records Required - Spray Sheet
label | Responsibility - Site Foreperson / Site QA
checkpoint | Binder application variation
label | T
label | Reference or Specification - NZTA P/17
label | Method/Test Required - +/- 4% (spray rate), +/- 50l (tank dip)
label | How Often? - Per site
label | Records Required - Spray Sheet
label | Responsibility - Site Foreperson / Site QA
checkpoint | Sealing chip application
label | I
label | Reference or Specification - NZTA P/17
label | Method/Test Required - Full and even coverage of sprayed area
label | How Often? - Per site
label | Records Required - Post-seal Inspection Form
label | Responsibility - Site Foreperson / Site QA
checkpoint | PTR Rolling pattern
label | I
label | Reference or Specification - NZTA P/17
label | Method/Test Required - Initial rolling completed along with traffic-rolling under controlled TTM
label | How Often? - Per Site
label | Records Required - Post-seal Inspection Form
label | Responsibility - Site Foreperson
checkpoint | Trafficating
label | I
label | Reference or Specification - Chapter 11 - Chipsealing in NZ
label | Method/Test Required - Initial rolling completed along with traffic-rolling under controlled TTM
label | How Often? - Per Site
label | Records Required - Post-seal Inspection Form
label | Responsibility - Site Foreperson / STMS
checkpoint | Tagging for line marking
label | I
label | Reference or Specification - Chapter 11 - Chipsealing in NZ
label | Method/Test Required - Pre-seal Visual check
label | How Often? - Per site
label | Records Required - Post-seal Inspection Form
label | Responsibility - Site Foreperson
checkpoint | Post-Sealing Surfacing Condition
label | I
label | Reference or Specification - QMP
label | Method/Test Required - Visual check
label | How Often? - Per site
label | Records Required - Post-seal Inspection Form & Photograph
label | Responsibility - Site Foreperson
section | 4.0 Post-Construction
checkpoint | Linemarking and RRPM Reinstated: Matches previous linemarking - within 48 hours of sealing
label | H
label | Reference or Specification - MOTSAM
label | Method/Test Required - Visual check
label | How Often? - Per site
label | Records Required - Photograph
label | Responsibility - Project Manager
checkpoint | Spray Sheet/s Checked & Supplied for Claiming
label | H
label | Reference or Specification - QMP
label | Method/Test Required - Spray sheet data verified against design/programme
label | How Often? - Per site
label | Records Required - Spray Sheet/s
label | Responsibility - Project Manager
checkpoint | Collect & Upload RAMM data
label | H
label | Reference or Specification - Comply with Waka Kotahi format
label | Method/Test Required - Correct data supplied
label | How Often? - Per site
label | Records Required - Spary Sheet/s & Photographs
label | Responsibility - Renewals Manager
section | 5.0 Out Of Season Sealing
checkpoint | Out of Season Sealing
label | H
label | Reference or Specification - Winter Surfacing Site Note
label | Method/Test Required - Waka Kotahi Approval
label | How Often? - Per Applicable Site
label | Records Required - Copy of Waka Kotahi Approval on-site
label | Responsibility - Project Manager / Renewals Manager