## DGA
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | DGA | CD85 |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | MRTS 30 March 2024, LCC Standard Specification 13 |  | Activity | Dense Grade Asphalt
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Submission of Asphalt Quality Plan |  |  |  |  | MRTS30 Cl 5.2 | Milestone
The Contractor must develop an Asphalt Quality Plan (AQP) for the asphalt work to the Administrator for consideration at least seven days prior to work commencing and must be implemented.
2 | Submission of Asphalt Quality Plan |  |  |  |  | MRTS 30 Cl 7.2.5 | Hold Point
For dense graded asphalt, the tensile strength ratio (TSR) must be ≥ 80% when determined in accordance with ATM 232 and the average tensile strength of the freeze / thaw group must be: a) ≥ 500 kPa for mixes containing SBS based polymer modified binder (e.g., A10E, A15E and A20E), and b) ≥ 600 kPa for mixes containing all other binders.
2 | Nomination of registered mix designs |  |  |  |  | MRTS30 Cl 7.3.3 | Milestone
At least seven days before asphalt is to be incorporated into the Works, the Contractor shall submit to the Administrator a copy of the mix design certificate(s) for each nominal size and type of asphalt mix to be incorporated into the Works.
3 | Asphalt Mix Properties |  |  |  |  | LCC SS 13 Part 2.6 & MRTS 30 | Check and Verify |  | N/A
The properties of asphalt mix must comply with Table 2.6.1 - Asphalt mix properties of LCC spec No. 13 Part 2.6.1 when tested in accordance with column 3, asphalt shall aslo comply with MRTS 30.
4 | General |  |  |  |  | General | Ckeck and Verify |  | N/A
All asphalt shall be placed in accordance with design drawings and as per drawings GW001 & LS001
5 | Bitumen Binder |  |  |  |  | General | Ckeck and Verify |  | N/A
All asphalt shall be placed in accordance with design drawings and as per drawings GW001 & LS002
6 | Production of Asphalt |  |  |  |  | MRTS30 Cl 7.4.1 | Hold Point 2
Asphalt shall be produced by a registered asphalt manufacturer from the nominated asphalt plant in accordance with the nominated mix design for the Works. Asphalt shall not be incorporated into the Works until the Contractor has demonstrated to the Administrator that the underlying lots conform to the specified requirements
7 | Production of Asphalt |  |  |  |  | MRTS30 Cl 8.2.2 | Witness Point 1
For asphalt placed over pavement constructed by others, the surface on which asphalt will be placed shall be tested for perceptible surface deformation by ‘proof rolling’ in the presence of the Administrator.
8 | Preparation |  |  |  |  | MRTS30 Cl 8.2.2 | Hold Point 4
Unless otherwise approved by the Administrator, asphalt shall not be placed over pavement exhibiting significant perceptible surface deformation.
9 | Preparation of pavement |  |  |  |  | MRTS30 Cl 8.2.2 | Check and Verify |  | N/A
Existing substrate shall not be wet and shall be swept thouroughly to remove and loose or deleterious material
10 | Application of Asphalt - Temperature |  |  |  |  | LCC SS 13 Part 3.1.1&2 | Check and Verify |  | N/A
The asphalt mix temperature is controlled so that it is between 135C and 175C when loaded into the delivery truck, the mix temperature is between 110C and 165C immediately behind the paver with compaction commencing before the temperature of the mix falls below a minimum of 95C.
11 | Asphalt Compaction |  |  |  |  | LCC SS 13 Part 3.4 & 3.5 | Hold Point
Compaction is commenced as soon as possible after spreading, and is completed in the shortest possible time except in the event of significant deformation or an irregularity occurring under the action of the roller in which case, rolling is delayed For compaction testing, a lot is the same as for a production lot and compaction testing is undertaken in accordance with Q302A, Q302B, Q306B and Q314. After completion of each job, core samples are taken from the compacted asphalt at the rate of one core per 1000m2 of asphalt laid, but with a minimum of three cores per job, asphalt compaction shall be greater than 95%
6 | Temporary line marking |  |  |  |  | LCC SS 10 Part 2.8.4 | Check and Verify |  | N/A
Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
5 | Access |  |  |  |  | MRTS 28 Clause 4.5.6 | Check and Verify |  | N/A
The Contractor’s site facilities shall be located to provide safe ingress and egress of traffic to the Site and public roads and shall not deteriorate the existing traffic operation.
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## RCP
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | RCP |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description | Installation of Reinforced Concrete Pipe and insitu Gully Pit |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | LCC Standatd Specification No. 3 |  | Activity | Reinforced Concrete Pipe
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
Reinforced Concrete Pipe Works
1 | General |  |  |  |  | General | Check and Verify |  | N/A
All reinforced concrete pipes and pit shall be as per drawings unless an alternitive is approved, all pipes shall be laid in location and to levels specified in drawings. - Drawings specify
2 | Construction Procedure - Submission |  |  |  |  | MRTS03 Clause 11.3.1 | MILESTONE
Construction procedure for the construction of concrete pipes shall be provide at least 14 days prior to the administrator.
3 | Construction Procedure - Approval |  |  |  |  | MRTS03 Clause 11.3.2 | Hold Point 2
The contractor shall not commence construction of any culverts until the construction procedure has been submitted
2 | Material Conformance |  |  |  |  | LCC SS No.3 Part 2.1 | Check and Verify |  | N/A
Unless otherwise noted on the approved drawings all pipes are Class 2 and comply with the requirements of AS 4058–2007 and all matrial conformnace data shall be included in the lot submission to the administrator.
3 | Construction |  |  |  |  | LCC SS No.3 Part 6.3 | Check and Verify |  | N/A
All RCP will be constructed as per IPWEA-STD-DS-030 which covers excavation, bedding material and backfilling - Bottom of excavation shall be compacted to a 95% standard compaction unless insitu material is rock for all excavations. - Backfill material shall be either 5 or 10mm aggregate.
4 | Pipe Laying |  |  |  |  | LCC SS No.3 Part 4.2 | Check and Verify |  | N/A
Pipes are laid true to line and grade, and are free draining and firmly bedded and are laid from the discharge end upstream to the following tolerances: - invert levels - ±50mm; - gully locations - within 300mm of design. For pipes up to and including 600mm diameter, the socketed end of the pipe is laid upstream and a shallow excavation is made under the socket of each pipe so that the pipe fully rests for its full length of barrel upon the bedding material in the trench.
5 | Construction - Backfilling |  |  |  |  | LCC SS No.3 Part 5.1 | Hold Point
Pipe is not to be backfilled without being inspected and approved by administrator.
6 | Backfilling Material |  |  |  |  | LCC SS No.3 Part 4.1 | Hold Point/ Witness Point
Prior to incorporating any Backfill material into the Works, the Contractor shall submit stockpile or source tests results as specified in part 4 of Standard specification 3 and conforms with table 4.1.1 Bedding Material
7 | Backfilling Under Proposed Pavements |  |  |  |  | LCC No.3 Part 5.2.1.(a) | Check and Verify |  | N/A
backfilled with approved material of minimum 4 day soaked California bearing ratio of 15 and compacted to 100 percent standard compaction.
9 | Bedding |  |  |  |  | LCC SS No3 Part 5.5 | Check and Verify |  | N/A
The pipe bedding or box culvert bedding and the lower layers of backfill up to a point 300mm above the crown of the pipe or box culvert are carefully packed and rammed solidly in layers of 150mm, to 95 percent standard compaction as determined by AS 1289.1.1 - 2001 and Amendment 1- 2002 and Amendment 2 - 2008 Methods of testing soils for engineering purposes - General requirements and list of methods.
8 | Pipe Laying Compliance Testing |  |  |  |  | LCC SS No.3 Part 4.4 | Hold Point
All pipes lines are subject to internal inspection and approval, the inspection of all pipes is carried out using a remote controlled video camera and is submitted to the local government before being accepted on-maintenance. A report on the findings of a remote controlled video camera inspection is to be submitted to the local government in an electronic format suitable for utilisation in “Sewer Rat” compatible applications. Pipes must not show clearly visible cracks of more than one millimetre for a length of 300mm or more on the inside.
Insitu Gully Pit Works
9 | General |  |  |  |  | LCC SS No.3 Part 6.1 | Check and Verify |  | N/A
A drainage structure includes all work and materials necessary for the construction of gullies, inlet pits and manholes, including excavation, concrete rendering and all necessary frames, curves, gratings, precast units and surrounds, precast troughs, chambers, lintels and shafts for side entry gullies, as specified in the approved drawings and standard drawings. -IPWEA-STD-DS-60
10 | Materials - Gully Pit |  |  |  |  | LCC SS No.3 Part 6.2 | Check and Verify |  | N/A
All materials used in insitu drainage structure will the N32 class concrete or otherewise specified. Concrete mix used - _________________
11 | Formwork Approval |  |  |  |  | LCC SS No.7 Part 4.1.1 | Hold Point
All concrete is placed in dry conditions and no concrete is placed until the formwork, falsework, and reinforcing materials have been inspected and approved by the local government.
12 | Construction of Gully Pit |  |  |  |  | LCC SS No.3 Part 6.3 | Check and Verify |  | N/A
Where the sides of the excavation are deemed to be in solid ground shafts may be constructed without the use of backforms, where concrete is placed without backforms the specified wall thickness is increased by 50mm minimum and not greater than 300mm of the design thickness. The finished concrete surface shall have smooth even and neat edges and will be shaped per the design intent.
13 | Subsoil Drainage |  |  |  |  | LCC SS No3 Part 3.2 | Check and Verify |  | N/A
Upstream of each headwall, manhole, or gully (other than an end of line gully), a 3.0 metre length of 100mm diameter sub−soil drainage pipe is laid in the bedding material. (2) The sub−soil drainage pipe is: (a) Class 400 perforated corrugated PVC pipe Type 1 that complies with AS 2439.1−2007 Perforated plastics drainage and effluent pipe and fittings—Perforated drainage pipe and associated fittings and AS 2439.2−2007 Perforated plastics drainage and effluent pipe and fittings—Perforated effluent pipe and associated fittings for sewerage applications; (b) fitted with an approved geotextile filter sock where sand bedding is used.
Inspection and Test Plan
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date
Hamish Hewitt

## CP
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | CP |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | MRTS 91 July 2024 |  | Activity | Conduits and Pits
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | General |  |  |  |  | MRTS 91 Clause 5.3 | Witness Point & Hold Point
A construction procedure for the installation of all conduits and pits shall be submitted to the Administrator at least 14 days prior to the commencement of installation. No excavation activity associated with the installation of conduits and pits shall commence until the expiration of the 14-day period.
2 | Asbestos Assessment |  |  |  |  | MRTS 91 Clause 6.1 | Hold Point
Asbestos is suspected or found in existing installation, work at this site must be stopped immediately, and the finding must be reported to the principal immediately for their decision and instruction on the work to be carried out at the site.
3 | Material Certification |  |  |  |  | MRTS 91 Clause 7.1 | Hold Point
All materials must comply strictly with the requirements of this Technical Specification. For all materials, a certificate of such compliance shall be provided to the Administrator before the materials are incorporated into the works
4 | Excavation for underground conduits and pits |  |  |  |  | MRTS 91 Claus 8.1 | Witness Point & Hold Point
Conduit runs and pit locations shall be set out and notice of such set out shall be provided to the principal at least 48 hours prior to the commencement of excavation. Construction shall not commence before the expirations of the period of notice.
5 | Bottom of trench |  |  |  |  | MRTS 91 Clause 8.4 | Witness Point
The bottom of the trench shall be compacted as per Standard Drawing 1149 to form a firm uniform surface free from loose material.
6 | Boring and Jacking |  |  |  |  | MRTS 91 Clause 8.7 | Hold Point
Work shall not commence until it has been demonstrated to the Administrator that the proposed equipment can accurately install the conduit in accordance with MRTS140 Horizontal Directional Drilling (HDD) and Standard Drawing 1149 Installation of Underground Electrical and Communication.
7 | Installation of conduits |  |  |  |  | MRTS 91 Clause 9.1 | Hold Point
The installation of conduits shall conform to the requirements of Standard Drawing 1149. The installation of communications conduits shall also comply with the requirements of AS/CA S009. Prior to installation, the Contractor shall inspect all conduit and conduit fittings to ensure that they are free of any defects that could damage the cables during installation. Conduits to be installed without dips/low points to ensure that drainage at pits operates as intended. The conduits are not to be lower than the pit it connects to unless approved by the Principal. Road crossing installed by ‘boring’ conduit to be installed level to facilitate correct drainage of conduit.
8 | Mandrel |  |  |  |  | MRTS 91 Clause 9.1 | Hold Point
After installation and backfilling, the conduit and conduit fittings shall be proved by drawing a mandrel having a diameter of at least 95% of the internal diameter of the conduit. The mandrel shall have a length sufficient to allow it to pass around any bends in the conduit, but not shorter than 95% of the diameter of the conduit being tested
9 | Draw rope |  |  |  |  | MRTS 91 Clause 9.13 | Witness point
Any joints made in the draw rope shall be capable of resisting the same tensile load as the draw rope without such a joint. The joint shall not appreciably increase the diameter of the rope.
10 | Vermin proofing of conduits |  |  |  |  | MRTS 91 Clause 10.9 | Hold Point
Any alternative proposed conduit sealing system shall be fit for purpose, and a proprietary system, and shall be submitted to the Administrator for consideration and approval prior to commencement of the installation of any cabling.
11 | Bedding of pit |  |  |  |  | MRTS 91 Clause 10.4 | Hold Point
The bottom of an excavation for a pit shall be compacted to at least 95% relative compaction.
12 | Compact bedding material |  |  |  |  | MRTS 91 Clause 10.4 | Check & Verify |  | N/A
Compact bedding material to density index 60.
13 | Drainage Holes |  |  |  |  | MRTS 91 Clause 10.11 | Witness Point
The lowest open end of conduits installed in poles and other field equipment enclosures shall be at least 50 mm higher than the surrounding finished surface level.
14 | Backfilling |  |  |  |  | MRTS 91 Clause 13.1 | Hold Point
Backfilling of trenches for conduits shall not commence until the conduit system has been inspected by the Administrator Backfilling shall not commence until all the conformance and As Constructed survey requirements have been met as specified in Clause 11 and 12 of MRTS91, and notice of such works provided to the Administrator
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## LS
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | LS | CD70 |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | LCC Standard Specification No. 2 (Landscaping) |  | Activity | Landscaping
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
Topsoil & Turf
1 | Soil Type |  |  |  |  | LCC SS No. 2 Part 6.2.1 | Check and Verify |  | N/A
Alll topsoil imported to site shall comply wiht the following below (a) is a fine soil type in accordance with Table 6.2.1–Soil type by texture of this standard specification; (b) is friable; (c) is moderately free draining; (d) complies with AS 4419–2003 Soils for landscaping and garden use; (e) is free of fire ants; (f) is free from Nut Grass (Cyperus rotundus);
2 | [5 empty] | LCC SS No. 2 Part 6.2.3 | Check and Verify |  | N/A
3 | [5 empty] | LCC SS No. 2 Part 6.2.4 | Check and Verify |  | N/A
2 | Topsoil Provider |  |  |  |  | LCC SS No. 2 Part 6.2.2&3 | Hold Point
Soil is imported from a source approved by the local government or is provided from material upon the premises where approved by the local government. Soil from the premises which is improved to comply with Table 6.2.1–Soil type by texture of this standard specification by the use of additives such as Gypsum, may be used as topsoil where approved by the local government.
3 | Spreading Topsoil |  |  |  |  | LCC SS No. 2 Part 6.2.5 | Check and Verify |  | N/A
Soil is spread such that: (a) the finished surface of the soil is smooth, free of lumps and free draining; (b) the finished surface levels allows for the settling and spreading of mulch; (c) the soil is lightly compacted over the prepared sub-grade; (d) in a grassed area the edge of the soil is feathered into undisturbed ground.
4 | Topsoil Finish |  |  |  |  | LCC SS No. 2 Part 6.2.6 | Check and Verify |  | N/A
Where soil is next to a kerb, a path, a mowing strip or other hard paved surface: (a) the soil is finished flush for a seeded grass area and bevelled below the abutting finished grade to allow for turf or mulch; (b) the finished grade of the mulch is approximately 10mm below the abutting finished surface level; (c) the finished surface level of the turf is flush with the abutting finished surface level; (d) the finished surface level of a grass area, turf and a garden bed adjacent to a building or other structure is 125mm below the weepholes in the building or the structure.
5 | Topsoil Depth |  |  |  |  | Contract Drawings | Check and Verify |  | N/A
Topsoil depth is 75mm as per contract drawing GW001
6 | Fertiliser |  |  |  |  | LCC SS No. 2 Part 6.4.1 | Check and Verify |  | N/A
Fertiliser is to be applied as per manufacturer's specification to ensure healthy long term growth.
7 | Turfed Area |  |  |  |  | LCC SS No. 2 Part 6.4.3 | Check and Verify |  | N/A
A turf roll has a minimum soil thickness of 20mm. (2) The turf is delivered to the premises within 24 hours of being cut. (3) The turf is laid within 36 hours of being cut. (4) Where the laying of the turf is delayed, the turf is: (a) protected and watered to maintain its condition; (b) not allowed to dry out at any stage from cutting to laying.
Maintenance
8 | General Maintenance |  |  |  |  | LCC SS No.3 Part 7.1 | Check and Verify |  | N/A
The premises is to be kept free of weeds and rubbish and any damaged, defective or stolen landscaping item is to be repaired or replaced.
9 | Maintenance Period |  |  |  |  | LCC SS No.3 Part 7.3 | Check and Verify |  | N/A
All turfef areas are maintained through the maintenance period such that at the end of the establishment period a turfed area has 100 percent of turf coverage, the plant estabblishment period is a minimum period of 12 weeks from the date that PC is approved.
10 | Maintenance of Turf |  |  |  |  | LCC SS No.3 Part 7.4.2 | Check and Verify |  | N/A
A grassed area is maintained during the maintenance period by: (a) mowing grass to 50mm height when grass has grown no higher than 75mm and removing grass clippings from the landscape area or as otherwise approved by the local government; (b) applying water at regular intervals to ensure ongoing healthy growth
11 | Maintenance Program |  |  |  |  | LCC SS No.7 Part 8.3.4 | Milestone/ Hold Point
The Maintenance Program is to be prepared by the Contractor and submitted to the Superintendent for approval prior to commencement of work under the Contract and is to contian details about the frequency which the contractor proposes to carry out its obligation under section 7.4 SS 2
Inspection and Test Plan
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date
Hamish Hewitt

## KRB
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council | [6 empty] | Chainage | From | To
Contract No |  | CD70 |  | Description
Specification |  | Standard Specification No. 8 (Minor Concrete works) |  | Activity | Installation of Kerb and Channel
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Kerb type |  |  |  |  | LCC SS No.8 Part 2.1 | Check and Verify |  | N/A
Kerb and channel complies with standard drawing number R-0080 and is one of the following profiles: B1, B2, SM5, M3, Median and Invert, and must be wet mix unless otherwise approvd by local government
2 | Design and Set-Out Locations |  |  |  |  | LCC SS No.8 Part 2.3 | Check and Verify |  | N/A
Concrete for kerb and kerb and channel is 32 MPa strength grade complying with the requirements of AS 1379-2007: The slump values of the concrete are machine finished (wet kerb)—12mm minimum—40mm maximum.
3 | Compaction of Materials |  |  |  |  | LCC SS No.8 Part 2.2 | Hold Point
Where pavement thickness exceeds 175mm in depth, the pavement extends under the kerb where the pavement thickness does not exceed 175mm in depth, the kerb and channel is firmly bedded on 100mm road base aggregate compacted to 95 percent modified dry density as required under AS 1289.0-2000 Methods of testing soils for engineering purposes - General requirements and list of methods. No concrete is placed until the foundations have been approved by the local government.
4 | Manual Construction |  |  |  |  | MRTS03 Clause 20.4 | Check and Verify |  | N/A
Manually-placed concrete shall be in accordance with Clause 6.1. Exposed surfaces shall have a steel-trowelled finish.
5 | Extruded Construction |  |  |  |  | MRTS03 Clause 20.5 | Check and Verify |  | N/A
Where kerb, channel and/or kerb and channel is constructed by an extrusion process, concrete shall comply with a maximum aggregate size not exceeding 20 mm and a minimum of 320 kg of cement per cubic metre of concrete. The extrusion machine shall be fitted with a tamper and an automatic control which allows adjustment of the position of the forming mould while the machine is in operation.
4 | Joining existing Kerb |  |  |  |  | LCC SS No.8 Part 2.5 | Check and Verify |  | N/A
The concrete kerb or kerb and channel joins neatly with the existing kerb or kerb and channel over a minimal transitional length of 2 metres
5 | Expansion Joints |  |  |  |  | LCC SS No.8 Part 2.4 | Check and Verify |  | N/A
In the case of kerb, a joint is cut and cork jointing is inserted every 20 metres with a cut joint midway between cork joints and jointing is placed in such a manner as to dissect the kerb for its full thickness.
6 | Contraction Joints |  |  |  |  | LCC SS No.8 Part 2.4 | Check and Verify |  | N/A
A contraction joint is provided at 4 metre centres which is finished square and at right angles to the section of kerb or kerb and channel. The kerb or kerb and channel at a contraction joint is guillotined to the full depth of the concrete and re-finished with a jointing tool to form neat joint lines not exceeding 3mm in width and 6mm in depth
9 | Curing |  |  |  |  | LCC SS No.8 Part 2.4 | Check and Verify |  | N/A
Concrete shall be cured for a period not less than seven days before any other roadworks operations are carried out adjacent to the kerb, channel or kerb and channel.
7 | Tolerances |  |  |  |  | LCC SS No.8 Part 2.4 | Check and Verify |  | N/A
The horizontal and vertical alignments of kerb, channel and/or kerb and channel shall not vary from those specified by more than ± 10 mm provided that the difference between the deviations from the correct levels at any two points 30 metres apart does not exceed 30mm. Crossfall is maintained within +/- 0.50 percent of the design
8 | Water Test |  |  |  |  | LCC SS No.8 Part 2.4.10 | WITNESS POINT
Notwithstanding the allowable tolerances, the invert of the channel is finished true to grade and alignment and channelling in which water is found to pond is not accepted and is removed immediately
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## GEO
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council | [6 empty] | Chainage | From | To
Contract No |  | CD70 |  | Description
Specification |  | MRTS57 July 2017 Geotextiles for Paving application |  | Activity | Geotextiles for paving applications
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Geotextile Filtration & Strength Class |  |  |  |  | Drawing Notes | Check and Verify |  | N/A
Geotextile to be used as specified in approved drawings
2 | Storage, packaging and identification on site |  |  |  |  | MRTS27 Clause 7 | Check and Verify |  | N/A
Geotextiles shall be stored under protective cover or wrapped with a waterproof, opaque UV protective sheeting to avoid any damage prior to installation. Geotextiles shall not be stored directly on the ground or in any manner in which they may be affected by heat. The method of storage shall be in accordance with any other recommendations set by the manufacturer. The protected geotextile rolls shall be clearly labelled showing manufacturer, type of geotextile and batch number identification number
3 | Geotextile Construction Procedure |  |  |  |  | MRTS57 Clause 5.2 | Milestone
A construction procedure detailing all work described in this Technical Specification shall be prepared. The construction procedure shall be consistent with the guidelines set out in the Transport and Main Road’s Pavement Rehabilitation Manual April 2012, Sections 4.4.6 to 4.4.6.8. The proposed construction procedure shall be submitted to the Administrator at least 14 days prior to the commencement of any works related to the placement of paving geotextile(s)
4 | Approval of construction Procedure |  |  |  |  | MRTS57 Clause 5.2 | Hold Point 1
No works related to the placement of paving geotextile(s) shall commence until the construction procedures have been approved by the Administrator and the Administrator has given the Contractor permission to proceed.
3 | Ordering - Technical Data |  |  |  |  | MRTS57 Cl 8.2 | Milestone
At least 14 days prior to the proposed ordering date of any geotextile, the Contractor shall submit to the Administrator a copy of the proposed manufacturer’s technical data sheet and a sample of the proposed geotextile from the manufacturer demonstrating compliance with this Technical Specification
4 | Ordering |  |  |  |  | MRTS57 Cl 8.2 | Hold Point 2
The Contractor shall not order any geotextile prior to the acceptance of that geotextile by the Administrator.
5 | Delivery |  |  |  |  | MRTS57 Cl 8.4 | Check and Verify |  | N/A
With each batch of geotextile incorporated in the Works, a certificate of compliance stating that the geotextile complies with all the requirements of this Technical Specification as appropriate to the application, together with test results reported on NATA endorsed test documents, shall be included in the Quality Records
5 | Surface Terperature |  |  |  |  | MRTS57 Cl 9.3 | Witness Point
Spraying of bitumen or placement of geotextile shall not commence until the temperature of the surface of the pavement is above the temperature specified in MRTS11 Sprayed Bituminous Surfacing
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## Subsoil
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | SD |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council | [6 empty] | Chainage | From | To
Contract No |  | CD70 |  | Description
Specification |  | LCC Standard Specification 12 (Subsoil Drain) |  | Activity | Subsoil Drains
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Material Requirements - Perforated drainage pipes for Type B subsoil drains |  |  |  |  | MRTS03 Clause 22.2 | Check and Verify |  | N/A
Perforated drainage pipes used in Type B subsoil drains and associated fittings and jointing procedures shall comply with AS 2439.1. The pipe shall have a minimum diameter of 100 mm.
1 | Material Requirements - Standard subsoil drains |  |  |  |  | LCC SS 12 Part 2.5 | Check and Verify |  | N/A
A sub-soil drainage pipe is a class 400 perforated corrugated PVC pipe Type 1 in accordance with AS 2439.1-2007 Perforated plastics drainage and effluent pipe and fittings - Perforated drainage pipe and associated fittings. The diameter of a sub-soil drainage pipe is a minimum of 100mm and the perforations do not exceed 1.1mm in width and 7.4mm in length.
2 | Longitudinal subsoil drain in pavement |  |  |  |  | LCC SS 12 Part 2.2 | Check and Verify |  | N/A
Where a kerb and channel is constructed a sub-soil drainage pipe is constructed Ss12-2 (a) immediately below the back of the kerb in accordance with standard drawing IPWEAQ R-0140, (b) at least 150mm below the finished sub-grade level
3 | Subsoil Drain Excavation |  |  |  |  | LCC SS 12 Part 2.4 | Check and Verify |  | N/A
A trench for a sub-soil drainage pipe is excavated to 50mm below the invert level of the sub-soil drainage pipe and have a gradient which is specified in the approved drawings or which is a minimum of 1 percent. the excavated trench is to be a minimum of 100mm wider than the outside diameter of the sub-soil drainage pipe.
4 | Filter Material |  |  |  |  | IPWEA-RS-030 | Check and Verify |  | N/A
Fileter material shall be either 5mm or 10mm drainage aggregate as per standard drawing IPWEA - RS - 140
5 | Subsoil drain outlet |  |  |  |  | LCC SS 12 Part 4.3 | Check and Verify |  | N/A
A sub-soil drainage pipe: shall be connected to a gully pit, as specified in standard drawing IPWEAQ R-0140; or discharges to a culvert head wall or an open channel below the edge of the road shoulder or at the edge of an embankment. (a) If a sub-soil drainage pipe is not connected into a gully pit or a culvert headwall, a concrete headwall is provided to the sub-soil drainage pipe. (b) The headwall is at least 100mm thick and extends for a minimum of 150mm on all sides of the pipe. (c) Where the outlet is through a batter, the surface of the headwall conforms to the batter slope.
6 | Poor Ground Conditions |  |  |  |  | LCC SS 3 Part 3.3 | Check and Verify |  | N/A
Add below: (1) Where the excavation encounters ground water or other poor ground conditions, the depth of the bedding and surround material is increased to provide adequate support for the pipe as approved by the local government. (2) If poor trench conditions exist, the pipe, or structure is supported by rock ballast which is: (a) sound igneous or metamorphic material that does not disintegrate in water; (b) of a 50mm nominal size; (c) completely wrapped in a non−woven geotextile fabric 1.9mm minimum thickness; (d) tamped into place.
Inspection and Test Plan
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## EXC
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council | [6 empty] | Chainage | From | To
Contract No |  | CD70 |  | Description | Excavation, all materials (cut)
Specification |  | MRTS04 June 2023, LCC Specification No. 1 (Earthworks) |  | Activity | General Excavation
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Lot Boundries |  |  |  |  | General | Check and Verify |  | N/A
Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
2 | Services: |  |  |  |  | DBYD | Check and Verify |  | N/A
All services identified – shall be marked, potholed and/or protected as required - Permit to excavate issued by Project Engineer
3 | Testing Frequencies |  |  |  |  | MRTS04 Clause 5.6 | Check and Verify |  | N/A
The minimum testing frequencies shall be as stated in Tables A.1 and A.2 of Appendix A.
4 | Erosion Sediment Control |  |  |  |  | MRTS51 Cl 10.3 | Check and Verify |  | N/A
Erosion and sediment controls in place - Due care taken to ensure native fauna is not harmed - Vibration and Air quality to be monitored as a direct result of construction activities
5 | Excavation Cutting |  |  |  |  | LCC SS No.1 Part 9.1 | Check and Verify |  | N/A
The bottom of excavations shall be trimmed to the tolerances specified in Clause 6 and any loose material removed from the surface. The existing soil is compacted to 95 percent relative dry density standard compaction, for a depth of 300mm below the sub-grade and care is taken to ensure that the topsoil and organic material is removed and replaced with approved selected material for a depth of 500mm and compacted to 95 percent relative dry density standard compaction where the sub-grade passes through the natural surfaceat the ends of the excavation or anywhere in cross-section.
6 | Unsuitable Material in Excavtion |  |  |  |  | LCC SS No.1 Part 9.3 | Check and Verify |  | N/A
Unsuitable material below the level of the sub-grade in an excavation is: (a) removed and run to spoil in accordance with section 12.1 of Specification 1,or replaced with select backfill in accordance with section 8.3–Selected gravel fill or selected backfill of this standard specification; (b) compacted to 95 percent relative dry density standard compaction
7 | Unsuitable Material Below Lines of Cuttings |  |  |  |  | MRTS04 Clause 13.3.2.2 | Check and Verify |  | N/A
Material below the finished lines and levels of cuttings, which is Unsuitable Material in accordance with the provisions of Clause 9.2, shall be removed and disposed of in accordance with the provisions of Clause 9.4. Where Unsuitable Material has been removed, the excavation shall be backfilled to the finished surface level with appropriate fill material as specified on the drawings or in accordance with Clause 18 and 19.
8 | Finished Cut Surface & Foundation |  |  |  |  | MRTS04 Clause 13.3.2.1 | HOLD POINT
When the level of excavation has reached Subgrade Level plus a nominal allowance determined by the Contractor, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the Subgrade treatment type has been determined in accordance with Clause 18.3.3. At the foundation surface of the Mass Block Retaining, the bearing capacity shall be confirmed in accordance with the Drawings (150 kPa) via Dnynamic Cone Penetration. Improvement of the foundation is required if the allowable bearing pressure is found to be less than the calcualted bearing pressure. Following the above confirmation the founding surfaces for all structures, including base slab are to be inspected and approved by a suitably qualified Geotechnical Enginee and any necessary treatment is completed prior to any Drain works taking place.
8 | Finished Cut Surface Survey |  |  |  |  | MRTS04 Clause 13.3.2.1 | Check and Verify |  | N/A
Once Works are completed to Subgrade Level (including all Subgrade treatments), an As Constructed Survey of the bottom of the excavated area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
9 | Lot Acceptance | [5 empty] | Check and Verify |  | N/A
Lot closure requires all relevant information to be attached to the Conformance Report this includes a Lot Plan, Survey Report, Hold Points/Approvals & any supporting documentation
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## HPC
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | HPC | CD85 |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | LCC Standard Specification 7 (Concrete) & LCC Standard Specification 8 (Minor concrete works) |  | Activity | Hand Placed Concrete
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Design location |  |  |  |  | IFC Design Drawings | Check and Verify |  | N/A
All concrete works are to be intalled in location and noted on a lot map attached to this document and accordance with the spcified drawings: Specified Drawing:
2 | Concrete Mix Design Submission |  |  |  |  | LCC SS No. 7 Part 2.3 | Milestone
All mix designs shall be submitted to the administrator prior to works beginning if insufficient testing history is available for the specified mix from an approved supplier, preliminary mixes for all grades of concrete are designed, made and tested.
3 | Concrete Mix Design Approval |  |  |  |  | LCC SS No. 7 Part 2 | Hold Point
Concrete Mix designs are approved prior to the usage in any works.
4 | Concrete Mix Design Approval |  |  |  |  | LCC SS No. 1 Part 9.1.1 | Check and Verify |  | N/A
Where the bottom of an excavation is free of rock or a rock bar the existing soil is compacted to 95 percent relative dry density standard compaction, for a depth of 300mm below the sub-grade
4 | Formwork Approval |  |  |  |  | LCC SS No. 7 Part 5.3.11 | Hold Point
All steel reinforcement that will be used in concrete works shall be inspected and approved by the local government prior to the placement of concrete, all formwork shall be inspected and checked against formwork checklist. When forms appear to be unsatisfactory in any way, either before or during the placing of concrete, the work does not proceed until the defects have been corrected to the approval of the local government.
5 | Footpath Contraction Joint |  |  |  |  | LCC SS No. 8 Part 3.1.4 | Check and Verify |  | N/A
Contraction joints: (a) are provided at centres matching the width of the footpath and not more than 3.0 metres; (b) are formed by a jointing tool; (c) do not exceed 35mm in depth or 6mm in width; (d) are at right angles to the edge of the path.
6 | Footpath Expansion Joint |  |  |  |  | LCC SS No. 8 Part 3.1.5 | Check and Verify |  | N/A
Expansion joints: (a) are placed at 15 metre centres except for 2.0m footpath which can be 16m to match dimension multiplier; (b) are at right angles to the edge of the path; (c) extend for the full depth of the concrete path and are 10mm in width. All expansion joints shall be as per LCC specifcations or where specified in standard darwings.
7 | Formwork
7 | Slump & Testing |  |  |  |  | LCC SS No. 7 Part 2.4 | Check and Verify |  | N/A
All concrete poured on site shall be slump tested by a NATA certified testing contractor, all slump testing values shall be recorded by a pour record sheet and provided to the administrator with the submission of the lot. All slump values shall comply with table 2.4.1 under Standard Specification 7. All concrete shall be tested for strength, concrete is sampled and tested in accordance with AS 1012.1-1993 Methods of testing concrete - Sampling of fresh concrete, by an approved NATA registered laboratory and the results are provided to the local government.
8 | Temperature and Timing |  |  |  |  | LCC SS No. 7 Part 4.2&4.3 | Check and Verify |  | N/A
Where the ambient temperature is likely to exceed 30°C, all practical precautions are taken to maintain the concrete at a temperature not exceeding 30°C at the time of placing to prevent shrinkage, settlement and presetting cracks. No concrete with a temperature higher than 30°C is placed unless otherwise approved by the local government. Ready mixed concrete is placed and compacted within 1 hour 15 minutes of charging the mixer for concrete temperatures up to 30°C and within 30 minutes of charging the mixer.
9 | Finishing |  |  |  |  | LCC SS No. 7 Part 6.1.2 | Check and Verify |  | N/A
All surfaces of concrete that are exposed to view in the completed structure are finished such that: (a) Immediately after the removal of forms, all fins and other projections are ground off, all pockets and honeycombs are cleaned and filled with a stiff cement mortar having the same proportion of cement and sand as the original concrete, and the surface of the patch is ground flush; (b) Decks are roughened slightly by brooming or other approved method before initial set; (c) Kerb and channel, invert crossings, vehicle crossings and industrial crossings are finished with an approved steel finishing tool; (d) Footpaths and pram ramps are finished with a wooden float and broomed.
10 | Curing |  |  |  |  | LCC SS No. 7 Part 6.3 | Check and Verify |  | N/A
Concrete surfaces are kept moist by spraying with an approved curing compound, or water sprays or wet sand in which case the surfaces are kept moist 24 hours a day for the full period specified without any breaks at weekends or holidays. Curing is commenced immediately on completion of the finishing of exposed surfaces or within 30 minutes of removal of the forms from other surfaces.
11
6 | Temporary line marking |  |  |  |  | LCC SS 10 Part 2.8.4 | Check and Verify |  | N/A
11 | Dimension Tolerances |  |  |  |  | LCC SS No. 7 Part 6.4 | Check and Verify |  | N/A
Where tolerances are not stated in the approved drawings for any individual structure or feature thereof, deviations from established lines, grades and dimensions are not greater than the tolerances listed in Table 6.4.1–Tolerances of this standard specification and are applied to the completed work. Size of member or thickness of slab: +7mm, -0 Cover of Concrete Over Reinforcement: +7mm, -3mm Contract dimensions: 0-20meters: +7mm Over 20meters: +13mm
12 | Addded Water |  |  |  |  | LCC SS No.7 Part 2.4 | Check and Verify |  | N/A
No extra water is added to the concrete on site unless: (a) the amount of the water being added is measured and recorded; (b) the concrete is thoroughly remixed and a slump test taken to ensure the consistency is still within the specified limits in this standard specification.
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date