## Sheet1
Homi Train Station - Inspection and Test Plan
Project Area |  | Homai Train Station |  |  |  | Rev | 4 |  | Inspection and Test Codes:
Activity Title |  | Staircase |  |  |  | Date | 2024-12-04 |  | [R] Review | Review of reports, records or other evidence of compliance.
Location | [5 empty] | Lot No. |  |  | [I] Inspection | In process check, work proceeds. Record the check if required.
Ref # |  | DN1212-ITP-005 | [6 empty] | [W] Witness | Inspection to be witnessed on site and recorded. Record to be filed.
DNZ Project Manager: |  | Dan Trotman | [6 empty] | [H] Hold | No work to proceed past Hold Point until this is completed, recorded and released
AT Project Manager: |  | Mike Robertson
DNZ Project Engineer: |  | Grant Wallace
Drawings/Reference Documents: |  | 3235599-SP03-CA-1024 - Rev 1 New Staircase Layout Plan and Long Section 3235599-SP03-CA-1025 - Rev 1 New Staircase Details 3235599-SE-3001 - Rev 1 General Notes 3235599-SE-3002 - Rev 1 General Notes - Reinforced Concrete 3235599-SE-3003 - Rev 1 General Notes - Reinforced Concrete
Specifications: |  | NZS3910:2013 746-24-874-AC 746-22-052-PS NZS 3114:1987, part 2 Exposed Aggregate surfaces. TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction Transport New Zealand ATCOP Chapter 12: Footpaths AND Pedestrian Facilities, and RTS14 “Guidelines for Facilities for Blind and Vision-impaired Pedestrians”
ITP Item # | Construction Activity or Material Element |  | Standard, Drawing or Specification Reference | Construction Activity Description, Test Type and Acceptance Criteria |  | Test Frequency |  | QA Record | Verification Method and On Site Responsibilities |  |  | DNZ Rep Sign and Date
[9 empty] | DNZ Engineer | Engineer's Rep | Designer Rep
1 | PRELIMINARY AND GENERAL
1.1 | IFC Drawings and Specification |  | ACC | A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction Works done in accordance with Project specification |  | Once |  | N/A | R |  | H | Sign | Date
1.2 | Method Statement & JSEA Development |  | The Downer Standards (TDS) | Prior to construction: document review. |  | Once |  | Method Statement & JSEA Completed & signed by relevant authority | H | R | R | Sign | Date
1.3 | Permit to Dig |  | DN-ZH-ST043 Ground Disturbance | Prior to construction. Permit in work package |  | Permit issued each week |  | Permit number ....................... | H |  |  | Sign | Date
1.4 | Survey Model |  | N/A | Model Review. |  | Once |  | Visual Inspection & measurement Survey Check set out as per design | H |  |  | Sign | Date
1.5 | Lift Plan |  | DG-ZH-ST047 Cranes and Lifting Equipment Standard | Prior to construction. For lifting of reinforcing cages, lift plan shall be in place ahead of construction, a Complex lift plan for the Crane and lift card for lifting with Excavators. Lift plan included in the work package. |  | Prior to Construction when required |  | Permit number …................ | H |  |  | Sign | Date
2 | MATERIAL APPROVALS
2.1 | Concrete Mix Design |  | 746-22-052-PS Section 5.2 NZS 3114:1987, part 2 Exposed Aggregate surfaces. | Mix Design approved by designer. 40Mpa Concrete with maximum 19mm aggregate Slump 120mm-160mm 4kg/m³ of black oxide to be used as per AT spec, exposed aggregate finish to be installed.. |  | Once |  | Approved Mix InEight Reference ................. | R |  | H | Sign | Date
2.2 | ATAP65/GAP65 - Material Source property testing and sampling |  | TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986 (Oringinal detail was concrete blinding but changed by site to GAP 65 for easier bulidability) | The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for crushing resistance, wethering quality Index and California bearing ratio ( Class 3 & 4) |  | Once Per Year Or Every 10 000 m³ |  | IANZ Test Report | H |  | R | Sign | Date
2.3 | ATAP65/GAP65 - Production property testing and sampling |  | TNZ M/4: 2006 - 4 NZS 4407 : 1991 (Oringinal detail was concrete blinding but changed by site to GAP 65 for easier bulidability | The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for Quality of fines as per M/4 fiqure 1, Broken Face content and WET particle size distribution Limits and shape control |  | Once Per Year Or Every 10 000 m³ |  | IANZ Test Report | H |  | R | Sign | Date
2.4 | ATAP65/GAP65 - Testing for layor compaction - MDD |  | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 (Oringinal detail was concrete blinding but changed by site to GAP 65 for easier bulidability | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Average MDD 95% with a minimum of 92%. |  | Once Per Year Or Every 5 000 m³ |  | IANZ Test Report | H |  | R | Sign | Date
2.5 | Reinforcing Steel |  | 24-178_FC_201124 | Supplied by pre-cast sub contractor as per drawing 24-178_FC_201124. Original detail was insitu but all work will be pre-cast. |  | Once |  | Mill Certificates & Shop Drawing Approval | S |  | H | Sign | Date
2.6 | Tactile Indicators |  | TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11 | 300mm x 300mm x 60mm thick yellow anti-slip will be installed in the insitu stitch pour section. |  | Once |  | MDS & Approval | R |  | H | Sign | Date
2.7 | Tactile Cement Blinding |  | TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 12 | Minimum 50 Mpa cement to be used according to supplier installations. |  | Once |  | MDS & Approval | R |  | H | Sign | Date
2.8 | Joint Filler |  | 3235599-SP03-CA-1025 - Rev 1 | Sika BlackSeal-1 Bitumionous joint filler or alternativly approved material. |  | Once |  | MDS & Approval | H |  | R | Sign | Date
2.9 | Moddex Handrail |  | 3235599-SP03-CA-1024 - Rev 1 3235599-SP03-CA-1025 - Rev 1 Note 1.11 | Moddex AR10 or Similar approved handrail. |  | Once |  | PS1 & Approval | H |  | R | Sign | Date
CONSTRUCTION ACTIVITIES
3.1 | Staircase set out and excavation to subgrade |  | 3235599-SP03-CA-1024 - Rev 1 746-22-052-PS Page 9 Table 1 | Excavated as per IFC long section. |  | Once |  | As-Built | H |  |  | Sign | Date
3.2 | Installation of benching |  | As Per CAN 033 | Installation of benching for backfill of GAP 65 as per CAN 033 |  | Once |  | Photos | H |  | R | Sign | Date
3.3 | Subgrade Testing (Scala) |  | 3235599-SP03-CA-1025 - Rev 1 Note 2.3a 746-22-052-PS Page 9 Table 1 | If clay based material is encountered - ensure subgrade has a minimum CBR of 3 Test to a depth to 1m, not less than 3 blows per 150mm for CBR 3.5% and 3 blows per 200mm for CBR 2%. |  | 1 per unit |  | Scala Test Results CBR of 3 | R |  | H | Sign | Date
3.4 | Undercut (If required) |  | 3235599-SP03-CA-1025 - Rev 1 Note 2.3c 746-22-052-PS Page 10 Table 2 NZS 4407:2015 4.1.2 | Prior to subgrade undercutting, the Engineer shall confirm the extent and depth of subgrade undercut. Replace with compacted AP/GAP 65, compact to a minimum 95% MDD. Minimum two NDM tests per footing location. |  | As required |  | NDM Results | I |  | H | Sign | Date
3.5 | Precast Units Pre-Pour |  | 3235599-SP03-CA-1024 - Rev 1 | Supplier to fabricate precast units as per the approved shop drawings. Pre-Pour inspection to be completed by DNZ and BECA Representative. |  | Every Unit |  | Supplier QA Report Concrete Test Results Mill Certificates | I |  | H | Sign | Date
3.6 | Precast Units Post-Pour |  | 3235599-SP03-CA-1024 - Rev 1 | Before site delivery, a post-pour inspection must be completed by the DNZ Engineer or Precast Supplier to check for any defects and to confirm that the exposed aggregate finish meets the design intent. |  | Every Unit |  | Supplier QA Report Photos | I |  |  | Sign | Date
3.7 | Insitu Stitch Works |  | 24-178_FC_201124 3235599-SP03-CA-1031 | Required at the top and the bottom of stairs. As per RFI 012 - Staircase Detail. Starter bars will project into the top landing only. Starter bars from the precast section shall be lapped with DH12 bars which extend (and terminate with cover) to the end of the insitu portion of the stairs landing. Cover of reinforcement will be checked with minimum 75mm cover at the base of reinforcement with 50mm cover on the side. Concrete will also be poured as per AT finish with exposed aggregate finish and 4kg/m³ of black oxide present. Precast to be shrink wrapped to allow 7 Days curing time. |  | Every Stitch |  | Concrete Dockets Pre-pour checklist Photos | I |  |  | Sign | Date
3.8 | Place Tactilies |  | TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11 | Note that per CAN 2, the middle landing of staircases will not have tactiles. Only the pre-cast units that will be installed on top and bottom landing. The horizontal tolerence should be between 3mm and 5mm. Vertical tolerance -10mm max. Orientation and set out shall be approved by the Engineer and or ATOC Representative prior to concrete placement. A one coat sealer with UV stabiliser is to be applied for maintenance and durability reasons |  | Per installation |  | Delivery Dockets Photos | H | I | I | Sign | Date
4 | FINAL RECORDS
4.1 | Construction Record Compilation |  | N/A | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. |  | Once |  | QA Records | H |  | R | Sign | Date
4.2 | Survey Records |  | N/A | Ensure all items have been surveyed and records are assembled for asbuilting |  | Once |  | As-Built | H |  | R | Sign | Date
4.3 | Redline Drawings |  | IFC Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. |  | Once |  | IFC Mark-Up | H |  | R
4.4 | Defect, Snag and Punch List |  | DN1212-DOW-PLA-PM-0005 QMP | Update the project Defect, Snag and Punch List Register |  | If required |  | Snag Register | H |  | R | Sign | Date
4.5 | Non-conformances |  | DN1212-DOW-PLA-PM-0005 QMP | Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report. NCR Reference ….................. |  | When Required |  | NCR Forms on InEight | H |  | R | Sign | Date
Comments:
ITP APPROVAL PROCESS
Prepared By: Quality Engineer |  |  | Nas Matar |  | Signed: |  | Date:
Reviewed By: Project Manager |  |  | Dan Trotman |  | Signed: |  | Date:
Reviewed By: Design Engineer |  |  | Daniel Cvitanich |  | Signed: |  | Date:
Reviewed By: AT Project Manager |  |  | Mike Robertson |  | Signed: |  | Date:
FINAL ITP CLOSE-OUT
Downer Project/Site Engineer |  |  |  |  | Signed: |  | Date:
QA Mgr./Engineer |  |  |  |  | Signed: |  | Date:
Designers Rep(Assistant) |  |  |  |  | Signed: |  | Date:
Note on A50: Kelsey Wong: ITP Revision to be signed and approved the Project Lead prior to construction. Final version issued to Quality Engineer / Engineer's Rep for Comment and Acceptance of ITP.