## Sheet1
Homai Train Station - Inspection and Test Plan
Project Area |  | Homai Train Station Structures |  |  |  | Rev | 1 |  | Inspection and Test Codes:
Activity Title |  | Pier 5 Column and Headstock Construction |  |  |  | Date | 2024-12-15 |  | [R] Review | Review of reports, records or other evidence of compliance.
Location | [5 empty] | Lot No. |  |  | [I] Inspection | In process check, work proceeds. Record the check if required.
Ref # |  | DN1212-ITP-012 | [6 empty] | [W] Witness | Inspection to be witnessed on site and recorded. Record to be filed.
DNZ Project Manager: |  | Dan Trotman | [6 empty] | [H] Hold | No work to proceed past Hold Point until this is completed, recorded and released
AT Project Manager: |  | Werner Nel
DNZ Project Engineer: |  | Grant Wallace
Drawings/Reference Documents: |  | 3235599-SP03-ST-3001 - PROPOSED ACCESS RAMP- GENERAL NOTES 3235599-SP03-ST-3002 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET1 OF 2) 3235599-SP03-ST-3003 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET2 OF 2) 3235599-SP03-ST-3004 - PROPOSED ACCESS RAMP- GENERAL NOTES- STRUCTURAL STEELWORK 3235599-SP03-ST-3100 - PROPOSED ACCESS RAMP- GENERAL ARRANGEMENT- PLAN AND ELEVATION 3235599-SP03-ST-3101 - PROPOSED ACCESS RAMP- GENERAL ARRANGEMENT- TYPICAL SECTIONS- SHEET1 3235599-SP03-ST-3150 - PROPOSED ACCESS RAMP- SETOUT 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3210 - PROPOSED ACCESS RAMP- PIER REINFORCEMENT DETAILS- SHEET1 3235599-SP03-ST-3211 - PROPOSED ACCESS RAMP- PIER REINFORCEMENT DETAILS- SHEET2 3235599-SP03-ST-3250 - PROPOSED ACCESS RAMP- ABUTMENT DETAILS- SHEET1 Temporaray Works Drawings - Pier 5. (Scaffolding and & Formwork) Reinforcement Steel Detail Sheets - Pier 5
Specifications: |  | NZS 3104: Specification for Concrete Production NZS 3109: Concrete Construction NZS 3101: Concrete Structures Standard NZS 3121: Specification for Methods of test for Concrete NZS 3114: Specifications for Concrete Surface Finishes App 1C - 746-24-847-AC - Tech Spec - Geo & Struc NZS 3101:2006 Concrete Structures Standard NZS 3104:2021 Specification for Concrete Production AS/NZS 4671:2019 Steel for the Reinforcement of Concrete Waka Kotahi NZ Transport Agency Bridge Manual Third Edition, Amendment 4 AS/NZS 4671 - Steel for the reinforcement of Concrete
ITP Item # | Construction Activity or Material Element |  | Standard, Drawing or Specification Reference | Construction Activity Description, Test Type and Acceptance Criteria |  | Test Frequency |  | QA Record | Verification Method and On Site Responsibilities |  |  | DNZ Rep Sign and Date
[9 empty] | DNZ Engineer | Engineer's Rep | Designer Rep
1 | PRELIMINARY AND GENERAL
1.1 | Method Statement Development & Safety Analysis |  | The Downer Standards (TDS) | Prior to Construction: Document Review Method Statement & JSEA Completed & signed by relevant authority |  | Once |  | Work pack (MS,JSEA,ITP) | H | R | R | Sign | Date
1.2 | IFC Drawings and Specification |  | ACC | A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction Works done in accordance with KiwiRail specification |  | Once |  | N/A | R |  |  | Sign | Date
1.3 | Permit to Dig |  | DG-ZH-ST004 Ground Disturbance | Prior to construction. Permit in work package |  | Permit issued each week |  | FlowForm Permit Register/Permit Number …...... | H |  |  | Sign | Date
1.4 | Lifting Permit |  | DG-ZH-ST047 Cranes and Lifting Equipment Loads | Prior to construction. Permit in work package |  | Prior to Construction when required |  | FlowForm Permit Register/Permit Number …...... | H |  |  | Sign | Date
1.5 | Working at Heights Permit |  | DG-ZH-ST042 Working at Height | Prior to construction. Permit in work package |  | Permit issued each week |  | FlowForm Permit Register/Permit Number …...... | H |  |  | Sign | Date
1.6 | Permit to Load - Scaffolding |  | DG-DM-PR036 Temporary Works Procedure DG-DM-FM066 | Prior to construction. Permit in work package |  | Permit Issued prior to construction |  | Temp Works Certification ITP Permit to Load - PtL …...... | H |  |  | Sign | Date
2 | MATERIAL APPROVALS
2.1 | Concrete Mix Design |  | NZS 3104 SP-NIMT-ST-AD-00001, Section 2.3.10 | Concrete mix details shall be provided to the Engineer for review and approval. 40MPa @ 28 Day Compressive Strength. |  | Once |  | Mix Certification InEight Response .................. | R |  | H | Sign | Date
2.2 | Reinforcing Cages |  | Reinforcing Cage Drawings - Pier 5 datail sheet | As per Column Reinforcing IFC detail drawings. Shop Drawings shall be provided to the Engineer for review and approval. Note any changes undertaken to reinforcing to be captured as per item 4.2 |  | Every Reinforcement Cage |  | Mill Test Certificates Delivery Dockets In Eight Response ................... | I |  | H | Sign | Date
2.3 | Formwork |  | Material Data Sheet Temporaray works drawings Piers 3 and 4. | Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules Rigid hollow-section steel frame High-grade hot dip galvinising for durability & long life Gang forms and lifting applications available Full range of safety features High Quality plywood 60kN/m2 permissible fresh concrete pressure To be captured on temp works drawings. Inclusive of structural shore loading for super structure |  | Once |  | MDS | I |  | R | Sign | Date
2.4 | Formwork Curing Agent |  | Material Data Sheet | Chemical curing agent. |  | Once |  | MDS | R |  | R | Sign | Date
2.6 | Reid Bars Products |  | Material Data Sheet 3235599-SP03-ST-3002 | RB 25 Couplers & RB25FNS Reidbar Steel Flange nut, as per noted 8 & 9 on drawing 3235599-SP03-ST-3002. Proposed epoxy will be per manufacturers recommendations to use C8 extreme epoxy. Superstructural couplers will be covered under PFS installation methodology and ITP. This is only for column / headstock construction. |  | Once |  | MDS, Delivery Dockets, mill certs ---------- | R |  | R | Sign | Date
3 | CONSTRUCTION ACTIVITIES
3.1 | Column Set-Out |  | 3235599-SP03-ST-3100 3235599-SP03-ST-3150 3235599-SP03-ST-3202 | Before commencing formwork installation, survey set out column position based on drawings with RL supplied. Set out to include; Column centre, height and offset. Tollerances for insitu concrete pour taken from NZS 3109 table 5.2 |  | Once |  | As-Built | W |  |  | Sign | Date
3.2 | Formwork Installation |  | Material Data Sheet Temporaray works drawings Pier 5 | As per Temporaray works drawings for Piers 5. Inclusive of shoreloading requirements for the support of the bridge superstructure around Pier 5. |  | Once |  | Photos plus signed off temporaray works inspection of shuttering and formwork. | W |  |  | Sign | Date
3.3 | Steel Cage Installation |  | As per detail Sheets for Pier 5 3235599-SP03-ST-3210 | Cage installation will be checked prior to placement to ensure that cage inspection requirements identified by BECA and DNZ will install cage and secure with RB 25 couplers that will be installed between the pier and pile starter bars. Couplers will be installed and epoxied in place using manufac turer recommended C8 extreme epoxy and photos of coupler will be supplied a spart of installation QA. Surveyors will also survey cage to ensure verticality and correct height of steel has been achieved prior to epoxying. |  | Once |  | Photos, | H |  | R
3.4 | Concrete Pre-Pour Inspection |  | 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc | Reinforcing cage as per IFC and shop drawings. Correct number of bars and grade. Correct steel lapping. Earthing and Earth terminal tested and inspected. Formwork installed as per the temporaray works drawings. Minimum 40mm cover achieved. Test specimens to be supplied by plant for every 75m³ for each shift of conncrete ordered. |  | Once |  | Survey Check Structural Engineer Inspection MSQA SVR Pre-Pour Checklist Photos | I |  | H | Sign | Date
3.5 | Concrete Pour |  | 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc | Concrete: 40MPa - Self Compacting Concrete - WS4010FS Cylinder test taken at supply Yard only. Spread Test to be completed on site prior to concrete pour. Target Spread Test - 680mm +/- 60mm |  | Once |  | Delivery Dockets Compressive Test Results Photos | H |  | W | Sign | Date
3.6 | Structural Surface Finish |  | App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003 NZS 3114 NZS 3109 | F1 Surface Finish - Concealed Formed faces F5 Surface Finish - Exposed and Visible Faces |  | Each joint and surface. |  | Visual Inspection Photos cylinders for blinding | H |  | I | Sign | Date
3.7 | Concrete Curing |  | App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3200 | Concrete to be cured for a minimum of 3 days as per drawing st-3200, curing methodology will be formwork curing. Cylinder to be taken at 3 days to verify strength of 30 Mpa has been achieved prior to stripping of formwork if required. Intention is to leave formwork on to 7 days max if possible. |  | Once |  | Concrete strength results, concrete pour checksheet notifying date of formwork striking. | H |  | R
3.8 | Post Pour Inspection |  | App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003 NZS 3114 | Joint inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/ check dimeniosn of structure have acieved stipulated tollarences stated in drawing suite and NZS 3109 |  | Once |  | Visual Inspection Photos | H |  | W
4 | FINAL RECORDS
4.1 | As-Built |  | N/A | Installed as per design drawings. All compliance recorded CAD files |  | Once |  | As-Built | H |  | R | Sign | Date
4.2 | Redline Mark-Up |  | IFC Drawings | IFC Drawings mark-Up on ACC sheets dated and signed. |  | Once |  | IFC Drawings Mark-Up on ACC | H |  | R | Sign | Date
4.3 | Non-conformances |  | DN1212-DOW-PLA-PM-0005 QMP | Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report. NCR Reference ….................. |  | Each NCR |  | NCR forms on InEight | H |  |  | Sign | Date
Comments: Please note that the inclusion of cast in items such as bolts, couplers etc for super structure will be supplied under separate ITP and MS. The same also with the pre cast deck which manufacturing and installation will be covered under a separate method statement and ITP.
ITP APPROVAL PROCESS
Prepared By: Project Engineer |  |  | Grant Wallace |  | Signed: |  | Date:
Reviewed By: Project Manager |  |  | Dan Trotman |  | Signed: |  | Date:
Reviewed by: Quality Manager |  |  | Cordelia Girdler-Brown |  | Signed: |  | Date:
Reviewed By: Design Engineer |  |  | Daniel Cvitanich |  | Signed: |  | Date:
Reviewed By: AT Project Manager |  |  | Werner Nel |  | Signed: |  | Date:
Reviewed By: AT Engineer to Contract |  |  | Mike Robertson |  | Signed: |  | Date:
FINAL ITP CLOSE-OUT
Downer Project/Site Engineer |  |  |  |  | Signed: |  | Date:
QA Mgr./Engineer |  |  |  |  | Signed: |  | Date:
Engineer Rep(Assistant) |  |  |  |  | Signed: |  | Date:
Note on A45: Kelsey Wong: ITP Revision to be signed and approved the Project Lead prior to construction. Final version issued to Quality Engineer / Engineer's Rep for Comment and Acceptance of ITP.