## Sheet1
Homai Train Station - Inspection and Test Plan
Project Area |  | Homai Train Station |  |  |  | Rev | 1 |  | Inspection and Test Codes:
Activity Title |  | Pre Cast Cantilever Fabrication |  |  |  | Date | 2024-12-17 |  | [R] Review | Review of reports, records or other evidence of compliance.
Location |  | Pier 1 Span to Browns Road |  |  |  | Lot No. |  |  | [I] Inspection | In process check, work proceeds. Record the check if required.
Ref # |  | DN1212-ITP-013 | [6 empty] | [W] Witness | Inspection to be witnessed on site and recorded. Record to be filed.
DNZ Project Manager: |  | Dan Trotman | [6 empty] | [H] Hold | No work to proceed past Hold Point until this is completed, recorded and released
AT Project Manager: |  | Werner Nel
DNZ Project Engineer: |  | Grant Wallace
Drawings/Reference Documents: |  | 3235599-SP03-ST-3001 - PROPOSED ACCESS RAMP- GENERAL NOTES 3235599-SP03-ST-3002 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET1 OF 2) 3235599-SP03-ST-3003 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET2 OF 2) 3235599-SP03-ST-3004 - PROPOSED ACCESS RAMP- GENERAL NOTES- STRUCTURAL STEELWORK 3235599-SP03-ST-3100 - PROPOSED ACCESS RAMP- GENERAL ARRANGEMENT- PLAN AND ELEVATION 3235599-SP03-ST-3101 - PROPOSED ACCESS RAMP- GENERAL ARRANGEMENT- TYPICAL SECTIONS- SHEET1 3235599-SP03-ST-3150 - PROPOSED ACCESS RAMP- SETOUT 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3210 - PROPOSED ACCESS RAMP- PIER REINFORCEMENT DETAILS- SHEET1 3235599-SP03-ST-3211 - PROPOSED ACCESS RAMP- PIER REINFORCEMENT DETAILS- SHEET2 3235599-SP03-ST-3550 - PROPOSED ACCESS RAMP- GRP DECK AND BALUSTRADE DETAILS- SHEET 1
Specifications: |  | NZS 3104: Specification for Concrete Production NZS 3109:1997 Concrete Construction NZS 3101: Concrete Structures Standard NZS 3121: Specification for Methods of test for Concrete NZS 3114: Specifications for Concrete Surface Finishes App 1C - 746-24-847-AC - Tech Spec - Geo & Struc NZS 3101:2006 Concrete Structures Standard NZS 3104:2021 Specification for Concrete Production AS/NZS 4671:2019 Steel for the Reinforcement of Concrete Waka Kotahi NZ Transport Agency Bridge Manual Third Edition, Amendment 4 AS/NZS 4671 - Steel for the reinforcement of Concrete
ITP Item # | Construction Activity or Material Element |  | Standard, Drawing or Specification Reference | Construction Activity Description, Test Type and Acceptance Criteria |  | Test Frequency |  | QA Record | Verification Method and On Site Reponsibilities |  |  | DNZ Rep Sign and Date
[9 empty] | DNZ Engineer | Wilco PM | Designer Rep
1 | PRELIMINARY & GENERAL
1.1 | IFC Drawings and Specification |  | IFC Drawings Wilco Shop Drawings | A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per the instruction. Work is done in accordance with IFC design and specification. |  | Once |  | Reviewed Shop Drawings InEight Reference ............ | R | R | R | Sign | Date
2 | MATERIAL APPROVALS
2.1 | Concrete Mix Design |  | 3235599-SP03-ST-3001 - PROPOSED ACCESS RAMP- GENERAL NOTES 3235599-SP03-ST-3002 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET1 OF 2) 3235599-SP03-ST-3003 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET2 OF 2) App 1C - 746-24-847-AC - Tech Spec - Geo & Struc | Concrete mix details shall be provided to the Engineer for review and approval. 50MPa @ 28 Day Compressive Strength. Maximum Aggregate Size 20mm. Maximum Water/Cement Ratio 0.43 (drawing/ notes state 40 Mpa but concrete increased to 50 Mpa mix to reach target strength quicker for demoulding). |  | Once |  | Mix Certificate Plant Certification InEight Reference Approval .................. | R | R | H | Sign | Date
2.2 | Reinforcement |  | IFC Reinforcement Detail Sheets | As per Cantilever Reinforcement shop drawing detail. Shop Drawings shall be provided to the Engineer for review. Grade 500. |  | Once |  | Mill Test Certificates Delivery Dockets Wilco Shop Drawings InEight Reference ................... | R | R | H | Sign | Date
2.3 | Lifting And Handling |  | REIDS Lifting Manual | Lifting Design added to the shop drawings. |  | Once |  | Lift Design Approval | R | H |  | Sign | Date
2.4 | Curing Method |  | C0602.7 NZS 3109:1997 Section 7 | Curing method shall be by wrapping of the precast concrete with shrink wrapping for a minimum of 7 days. |  | Once |  | Photos InEight Reference .................... | H | R | R | Sign | Date
2.5 | Cast in Plate |  | 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS | Stainless Steel: 1) M10 SS Grade 316 Bolts with Nylon Washers 2) M10 SS Grade 316 TCM threaded inserts Hot Dipped Galvanised: 1) 450 x 10mm thick HDG 600 plate with approved surface treatment. Colour matched to concrete. |  | Once |  | Material Certificate & Photos | R | R |  | Sign | Date
3 | PRE-CAST FABRICATION ACTIVITIES
3.1 | Mould assembly / set-up |  | Approved Shop Drawings | Mould shall be set-up as per IFC Shop Drawings. |  | Once |  | Wilco QA Report | W | I | W | Sign | Date
3.2 | Reo Assembly & Placement |  | Approved Shop Drawings | Reinforcement cage assembled & installed as per IFC Shop Drawings. Threaded rods shall be wrapped with 2 layers of Denso tape at the interface. Stainless steel 50EA6 Studs to have 100mm embedment and to be flush with the surface of headstock. |  | Once |  | Wilco QA Report | W | I | W | Sign | Date
3.3 | Corners and edges |  | 3235599-SP03-ST-3200 3235599-SP03-ST-3001 3235599-SP03-ST-3002 3235599-SP03-ST-3003 | All external corners and edges to concrete surfaces shall have a 20x20mm CHAMFER unless shown otherwise on the drawings. |  | Once |  | Wilco QA Report | W | I | I | Sign | Date
3.4 | Dimensional Tolerances |  | NZS 3109: 1997, Table 5.1 | As per Table 5.1 – Tolerance for precast components NZS 3109: 1997. |  | Once |  | Wilco QA Report | W | I | W | Sign | Date
3.5 | Cast-in Installation & Inspection |  | Approved Shop Drawings | Set-up as per IFC Shop Drawings. |  | Once |  | Wilco QA Report | W | I | W | Sign | Date
3.6 | Approval to cast (Pre-Pour) |  | Approved Shop Drawings | DNZ/Beca to be notified of the cast date for a Pre-pour inspection. PS3 to be supplied by Wilson. |  | Once |  | Wilco QA Report DNZ/Beca Pre-Pour Inspection Photos | I | H | I | Sign | Date
3.7 | Concrete Testing |  | NZS3104:2021 | 3 x Cylinders for 28 Days Compressive Strength Testing. |  | Once |  | One set of samples 28 Days Concrete Compressive Results | R | H | R | Sign | Date
3.8 | Concrete Placement and Finish |  | NZS 3114:1987 | 50Mpa Concrete. Finish as per Shop Drawings. U3/F5 finish class. Tolerance on Cover: -0, +5mm |  | Once |  | Wilco QA Report Concrete Dockets | W | I | W | Sign | Date
3.9 | Demoulding |  | Reid Lifting Manual Reid Lift Plan | Minimum demoulding strength achieved. Lift plan shall be followed. |  | Once |  | Lift Plan Compressive strength Test Results Reid lifting manual Reid Lift Plan | R | H | R | Sign | Date
3.1 | Post Pour Inspection |  | Approved Shop Drawings | Cantilever to be inspected to ensure are free of defects prior to site delivery. Confirmation that F5 finish has been acieved for the pre cast unit and the U5 broom finish has been applied to the top deck as per shop drawings. |  | Once |  | Wilco QA Report | I | I | I | Sign | Date
3.11 | Unit Marking |  | Approved Shop Drawings | Product marked with the correct information. (Date of cast, Unit ID, Weight) |  | Once |  | ID Label | R | I | R | Sign | Date
3.12 | Curing |  | NZS 3101.1&2:2006 | Standard 7 days curing with concrete unit remaining shrink wrapped to provide membrane for curing. |  | Once |  | N/A | R | I | R | Sign | Date
4 | FINAL RECORDS
4.1 | Compiled QA |  | DN1212-DOW-PLA-PM-0005 QMP | Quality Assurance documents are compiled as per the ITP acceptance criteria. |  | Once |  | Wilco QA Report | R | H | R | Sign | Date
4.2 | Producer Statement (PS3) |  | NZS 3916:2013 Schedule 6 | Completed and signed PS3 by Wilco Confirming Compliance with the IFC drawings and specification for the fabrication of Cantilever Deck. |  | Once |  | Signed PS3 | R | H | R | Sign | Date
4.3 | Non-conformances |  | DN1212-DOW-PLA-PM-0005 QMP | Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report. NCR Reference ….................. |  | Each NCR |  | NCR forms on InEight | H | R | R | Sign | Date
Comments: This ITP is purely for the Pre Cast Manufacturing and Placement, the corbels and stitch pour will be addressed in a separate ITP.
ITP APPROVAL PROCESS
Prepared By: Project Engineer |  |  | Grant Wallace |  | Signed: |  | Date:
Reviewed By: Project Manager |  |  | Dan Trotman |  | Signed: |  | Date:
Reviewed by: Quality Eng./Mgr. |  |  | Nas Matar |  | Signed: |  | Date:
Reviewed By: Design Engineer |  |  | Daniel Cvitanich |  | Signed: |  | Date:
Reviewed By: AT Project Manager |  |  | Werner Nel |  | Signed: |  | Date:
Reviewed By: AT Engineer to Contract |  |  | Mike Robertson |  | Signed: |  | Date:
FINAL ITP CLOSE-OUT
Downer Project/Site Engineer |  |  |  |  | Signed: |  | Date:
QA Mgr/Engineer |  |  |  |  | Signed: |  | Date:
Engineer Rep(Assistant) |  |  |  |  | Signed: |  | Date:
Note on A44: Kelsey Wong: ITP Revision to be signed and approved the Project Lead prior to construction. Final version issued to Quality Engineer / Engineer's Rep for Comment and Acceptance of ITP.