## Sheet1
Homai Train Station - Inspection and Test Plan
Project Area |  | Homai Train Station |  |  |  | Rev | 1 |  | Inspection and Test Codes:
Activity Title |  | Pre Cast Cantilever Deck Install & Stitch Pour |  |  |  | Date | 2024-12-18 |  | [R] Review | Review of reports, records or other evidence of compliance.
Location |  | Pier 1 Cantilever |  |  |  | Lot No. |  |  | [I] Inspection | In process check, work proceeds. Record the check if required.
Ref # |  | DN1212-ITP-014 | [6 empty] | [W] Witness | Inspection to be witnessed on site and recorded. Record to be filed.
DNZ Project Manager: |  | Dan Trotman | [6 empty] | [H] Hold | No work to proceed past Hold Point until this is completed, recorded and released
AT Project Manager: |  | Werner Nel
DNZ Project Engineer: |  | Grant Wallace
Drawings/Reference Documents: |  | 3235599-SP03-ST-3001 - PROPOSED ACCESS RAMP- GENERAL NOTES 3235599-SP03-ST-3002 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET1 OF 2) 3235599-SP03-ST-3003 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET2 OF 2) 3235599-SP03-ST-3004 - PROPOSED ACCESS RAMP- GENERAL NOTES- STRUCTURAL STEELWORK 3235599-SP03-ST-3100 - PROPOSED ACCESS RAMP- GENERAL ARRANGEMENT- PLAN AND ELEVATION 3235599-SP03-ST-3101 - PROPOSED ACCESS RAMP- GENERAL ARRANGEMENT- TYPICAL SECTIONS- SHEET1 3235599-SP03-ST-3150 - PROPOSED ACCESS RAMP- SETOUT 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3210 - PROPOSED ACCESS RAMP- PIER REINFORCEMENT DETAILS- SHEET1 3235599-SP03-ST-3211 - PROPOSED ACCESS RAMP- PIER REINFORCEMENT DETAILS- SHEET2 3235599-SP03-ST-3550 - PROPOSED ACCESS RAMP- GRP DECK AND BALUSTRADE DETAILS- SHEET 1
Specifications: |  | NZS 3104: Specification for Concrete Production NZS 3109:1997 Concrete Construction NZS 3101: Concrete Structures Standard NZS 3121: Specification for Methods of test for Concrete NZS 3114: Specifications for Concrete Surface Finishes App 1C - 746-24-847-AC - Tech Spec - Geo & Struc NZS 3101:2006 Concrete Structures Standard NZS 3104:2021 Specification for Concrete Production AS/NZS 4671:2019 Steel for the Reinforcement of Concrete
ITP Item # | Construction Activity or Material Element |  | Standard, Drawing or Specification Reference | Construction Activity Description, Test Type and Acceptance Criteria |  | Test Frequency |  | QA Record | Verification Method and On Site Reponsibilities |  |  | DNZ Rep Sign and Date
[9 empty] | DNZ Engineer | Engineers Rep | Designer Rep
1 | PRELIMINARY & GENERAL
1.1 | IFC Drawings and Specification |  | IFC Drawings | Work is done in accordance with IFC design and specification. |  | Once |  | DN1212-ITP-013 | R | R | R | Sign | Date
1.2 | Method Statement Development & Safety Analysis |  | The Downer Standards (TDS) | Prior to construction: document review. |  | Once |  | Method Statement & JSEA Completed & signed by relevant authority | H | R | R | Sign | Date
1.3 | Model |  | ACC | Model reviewed and confirmed with correct location; depth, height and orientation |  | Once |  | N/A | R |  |  | Sign | Date
2 | MATERIAL APPROVALS
2.1 | Concrete Mix Design (Stitch) |  | 3235599-SP03-ST-3001 - PROPOSED ACCESS RAMP- GENERAL NOTES 3235599-SP03-ST-3002 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET1 OF 2) 3235599-SP03-ST-3003 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET2 OF 2) App 1C - 746-24-847-AC - Tech Spec - Geo & Struc | Concrete mix details shall be provided to the Engineer for review and approval. 50MPa @ 28 Day Compressive Strength. Maximum Water/Cement Ratio 0.43 (drawing/ notes state 40 Mpa but concrete increased to 50 Mpa mix to reach target strength quicker). Samples to be taken at 1, 2,3, 7 and 28 day strengths. |  | Once |  | Mix Certificate Plant Certification InEight Reference Approval .................. | R | R | H | Sign | Date
2.2 | Reinforcement (corbel steel and Stitch pour Steel) |  | IFC Reinforcement Detail Sheets | As per NTC 058 Installation of DH12 bars on precast edges to create corbels.. Grade 500. Also includes the structural steel required for the stitch pour. |  | Once |  | Mill Test Certificates Delivery Dockets InEight Reference ................... | R | R | H | Sign | Date
2.3 | Formwork |  | Material Data Sheet Temporary works drawings Piers 1 and 2. | Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules Rigid hollow-section steel frame High-grade hot dip galvanising for durability & long life Gang forms and lifting applications available Full range of safety features High Quality plywood 60kN/m2 permissible fresh concrete pressure To be captured on temp works drawings. Inclusive of structural shore loading for super structure |  | Once |  | MDS | H | R | R | Sign | Date
2.4 | Formwork Curing Agent |  | Material Data Sheet | Chemical curing agent. |  | Once |  | MDS | R | R | R | Sign | Date
2.5 | Installation - Lift Plan |  | DNZ Lift Plan for GMK 300 L | Lifting plan for the installation of the pre cast cantilever deck. |  | Once |  | Lift Design Approval | H | R | R | Sign | Date
2.6 | Epoxy for corbel Installation |  | As per NTC 058 | R12 bars to be installed and epoxied into place using C8 epoxy. Requires designer approval. |  | Once |  | MDS In Eight Reference …......... | H | R | R | Sign | Date
2.7 | Concrete Bags |  | MDS | 40Mpa Concrete Dricon High Strength Handicrete or similar approved product. |  | Once |  | MDS | H | R | R | Sign | Date
2.8 | Column and Headstock ITP Sign Off |  | Signed ITP | Sign off of Column and headstock construction |  | Once |  | Signed ITP | H | R | R | Sign | Date
2.9 | Structural Steel Deck Installation ITP Sign Off |  | Signed ITP | Required before pouring of concrete stitch pour. |  | Once |  | Signed ITP | H | R | R | Sign | Date
3 | CONSTRUCTION ACTIVITIES
3.1 | Setout |  | 3235599-SP03-ST-3100 3235599-SP03-ST-3150 3235599-SP03-ST-3202 | Before commencing formwork installation, survey set out top of cantilever position based on drawings with RL supplied. Tolerances for insitu concrete pour taken from NZS 3109 table 5.2. Required to check and confirm that the position of the slab has the correct clearance from the bridge structure of 160mm and that the Macalloy bars are installed per the correct place. |  | Once |  | As-Built | H |  | R | Sign | Date
3.2 | Type B Construction Joint Corbels |  | As per CAN 69 | As per CAN 069 Type B construction joint to be formed on the vertical faces of the corbels to ensure connection when concrete poured. |  | Each Corbel |  | Photos | H |  | R | Sign | Date
3.3 | Formwork Installation |  | Material Data Sheet Temporary works drawings Piers 1 and 2. | As per Temporary works drawings for Piers Stitch Pour. |  | Once |  | Photos plus signed off temporary works inspection of shuttering and formwork. | H |  | R | Sign | Date
3.4 | Steel Installation for Corbel |  | As per NTC 058 | R12 U bars to be installed within concrete corbel as per NTC 058. 40mm cover to be obtained surrounding steel. All bars must be epoxied into place with visual evidence to support that approved epoxy has been installed. Epoxy to be installed as per manufacturers installation instructions. Refer to CAN 069 |  | Once |  | Photos | H |  | R | Sign | Date
3.5 | Concrete Corbel Pre-Pour Inspection |  | 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc | Reinforcing installed as per NTC 058. Correct number of bars and grade. Correct steel lapping. Minimum 40mm cover achieved. 40Mpa Bagged Concrete to achieve 28 Days Compressive Strength. Mixing as per manufactures guidelines. Refer to CAN 069 |  | Once |  | Survey Check Structural Engineer Inspection MSQA SVR Pre-Pour Checklist Photos | I |  | H | Sign | Date
3.6 | Corbel Concrete Pour |  | 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc | Minimum 40mm cover achieved. 40Mpa Bagged Concrete to achieve 28 Days Compressive Strength. Mixing as per manufactures guidelines. |  | Once |  | Survey Check Pre-Pour Checklist Photos | H |  | W | Sign | Date
3.7 | Concrete Stitch Pre-Pour |  | 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc | Reinforcing installed as per IFC drawings. Minimum cover 50mm. |  | Once |  | Survey Check Structural Engineer Inspection MSQA SVR Pre-Pour Checklist Photos | I |  | H | Sign | Date
3.8 | Concrete Stitch Pour |  | 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc | Concrete: 50MPa - Self Compacting Concrete Cylinder test taken at supply Yard only. Spread Test to be completed on site prior to concrete pour. Target Spread Test - 680mm +/- 60mm |  | Once |  | Delivery Dockets Compressive Test Results Photos | H |  | W | Sign | Date
3.9 | Surface Finish/Construction Joint |  | App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003 NZS 3114 | F1 Surface Finish - Concealed Formed faces F5 Surface Finish - Exposed and Visible Faces Type B Construction Joint to be used between insitu and pre-cast deck placement, as well as headstock placement on existing column. Insitu Concrete Stich Pour on Pier 1 - surface to have U2 broomed finish for slip resistance in both rain and dry as per NZBC D1 requirements. |  | Once |  | Visual Inspection Photos | H |  | I | Sign | Date
3.1 | Concrete Curing |  | App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3200 | Concrete to be cured for a minimum of 3 days as per drawing ST-3200, curing methodology will be formwork curing. Cylinder to be taken at 3 days to verify strength of 30 Mpa has been achieved prior to stripping of formwork. |  | Once |  | Concrete strength results, concrete pour checksheet notifying date of formwork striking. | H |  | R | Sign | Date
3.11 | Post Pour Inspection |  | App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003 NZS 3114 | Joint inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/ check dimension of structure have achieved stipulated tolerances stated in drawing suite and NZS 3109 |  | Once |  | Visual Inspection Photos | H |  | W | Sign | Date
4 | FINAL RECORDS
4.1 | As-Built |  | N/A | Installed as per design drawings. All compliance recorded CAD files |  | Once |  | As-Built | H |  | R | Sign | Date
4.2 | Redline Mark-Up |  | IFC Drawings | IFC Drawings marked up and signed. |  | Once |  | IFC Drawings Mark-Up | H |  | R | Sign | Date
4.3 | Non-conformances |  | DN1212-DOW-PLA-PM-0005 QMP | Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report. NCR Reference ….................. |  | Each NCR |  | NCR forms on InEight | H | R | R | Sign | Date
Comments: This ITP is purely for the corbels, pre cast placement and stitch pour. Bearing pads and Grouting will be covered under another ITP.
ITP APPROVAL PROCESS
Prepared By: Project Engineer |  |  | Grant Wallace |  | Signed: |  | Date:
Reviewed By: Project Manager |  |  | Dan Trotman |  | Signed: |  | Date:
Reviewed by: Quality Eng./Mgr. |  |  | Nas Matar |  | Signed: |  | Date:
Reviewed By: Design Engineer |  |  | Daniel Cvitanich |  | Signed: |  | Date:
Reviewed By: AT Project Manager |  |  | Werner Nel |  | Signed: |  | Date:
Reviewed By: AT Engineer to Contract |  |  | Mike Robertson |  | Signed: |  | Date:
FINAL ITP CLOSE-OUT
Downer Project/Site Engineer |  |  |  |  | Signed: |  | Date:
QA Mgr./Engineer |  |  |  |  | Signed: |  | Date:
Engineer Rep(Assistant) |  |  |  |  | Signed: |  | Date:
Note on A49: Kelsey Wong: ITP Revision to be signed and approved the Project Lead prior to construction. Final version issued to Quality Engineer / Engineer's Rep for Comment and Acceptance of ITP.