## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
8eb822b5-a279-45f8-b187-326dc5d71aee | checklist | DN1212-ITP-001 Concrete Footpath Rev2 | itp | DN1212-ITP-001 Concrete Footpath
38820775-d13e-4983-a44e-287170916540 | section | 1 - PRELIMINARY AND GENERAL
9c5620dd-712e-4602-ac4c-60657b8854b7 | checkpoint | 1.1 - IFC Drawings and Specification
3880bc4b-7b5c-5a63-b1cc-69676c84ed1c | note | Standard, Drawing or Specification Reference - ACC
80f1154b-b0bf-54d8-b4a9-d17b2c954847 | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
c12c78b0-8954-55c9-a9d8-1990c10e2f3d | note | ○ Works done in accordance with Project specification
7d68c84c-dc5c-506a-90b2-d8cf32da1f2e | note | Test Frequency - Once
056f39eb-47c7-5fe5-b52f-465b0b02af1d | note | QA Record - N/A
96080ce2-5c4d-5bdb-ae1c-90e8ae915ef6 | note | DNZ Engineer - R
0e93766c-2956-57ee-b8e6-aa8d4e896ac9 | note | Designer Rep - H
ae3fc8b0-3ba8-4eb6-a6a8-9dd8fba4b280 | signoff | AUTHORITY HOLDPOINT
6823f7f0-4a97-4ac1-897a-be92d459fb8e | checkpoint | 1.2 - Method Statement & JSEA Development
8a86e831-ca46-5559-a815-96aba75a6ea4 | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
847851fa-0f23-540d-a7e7-bc35ab9af9f3 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
6fd867de-e380-5f30-91c0-a47bea6a1d3a | note | Test Frequency - Once
2d49cb81-5084-50df-b4f4-911ce41f9db1 | note | QA Record - Method Statement & JSEA Completed & signed by relevant authority
89770c9a-5917-5dae-b54f-7f9013c08904 | note | DNZ Engineer - H
f03b0de3-64f8-54a9-94a8-d26e9089536d | note | Engineer's Rep - R
d4b1de8b-3154-5630-8c70-35ac345083ff | note | Designer Rep - R
34aca323-6f82-4a76-bec0-7078cac31b3f | signoff | AUTHORITY HOLDPOINT
72f29a71-cf7c-42f7-b303-21ccad757177 | checkpoint | 1.3 - Permit to Dig
030d367e-2d62-574f-b800-a00a48287811 | note | Standard, Drawing or Specification Reference - DN-ZH-ST043 Ground Disturbance
de6323e4-6afe-59ef-add0-6cfc4184350f | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
810b68ab-9254-5fb7-a351-bc6357b89664 | note | Test Frequency - Permit issued each week
f916783b-dc8b-5963-ad65-e7725f13acd0 | textbox | QA Record - Permit number
833dbe8b-5134-57ad-9290-c995e210d754 | note | DNZ Engineer - H
d3ea1e69-e11e-4924-ab55-4b377de46530 | signoff | AUTHORITY HOLDPOINT
09b621a1-cd59-4a98-875a-7caf42c9a638 | checkpoint | 1.4 - Survey Model
29c2e033-8b83-5b4d-b2e4-4a26fda7ce6e | note | Standard, Drawing or Specification Reference - N/A
440d57be-7453-5787-a9c9-e3c4d7adc731 | note | Construction Activity Description, Test Type and Acceptance Criteria - Model Review.
9b4dfe3f-cc65-5100-83a0-3fabe89f9065 | note | Test Frequency - Once
fdd9f306-fb9c-500f-bd98-092453e1774a | note | QA Record - Visual Inspection & measurement Survey Check set out as per design
3c333d29-680d-5e37-a019-859501b763b7 | note | DNZ Engineer - H
f4a8dbc3-c031-4cad-8c01-1a6f7f5b8a6e | signoff | AUTHORITY HOLDPOINT
9c858345-b5fd-4d2a-ba9b-c750259939f9 | section | 2 - MATERIAL APPROVALS
f1f3e5c0-1a3f-43b1-ab6b-687c372bc22f | checkpoint | 2.1 - Concrete Mix Design
3a2786d5-c548-5ed2-a77f-b61ce1283669 | note | Standard, Drawing or Specification Reference - 746-22-052-PS Section 5.2, NZS 3114:1987, part 2 Exposed Aggregate surfaces.
2c7bef63-4b6a-571c-b84e-166620647da2 | note | Construction Activity Description, Test Type and Acceptance Criteria - Mix Design approved by designer.
69a9d6dc-7475-52b7-8441-cf2d993f4e22 | note | ○ 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates.
3feb15aa-c13e-5252-b5fa-5d9901a605db | note | Test Frequency - Once
cb1a8b53-a30a-5936-bee4-23b5218c2ad3 | note | QA Record - Approved Mix
7020b0df-78f9-57e4-9a93-14aa2b6f11d6 | textbox | InEight Reference
5f7d19af-c9df-52cb-8ca2-3a1289c97580 | note | DNZ Engineer - R
cf328b58-8d3b-5c74-96ec-a0c8eda72ae7 | note | Designer Rep - H
d563f239-b6fa-4e1f-b1b5-ba7ed61ea19b | signoff | AUTHORITY HOLDPOINT
03678886-ca6f-4781-a4f3-6557f87e38e9 | checkpoint | 2.2 - ATAP40/GAP40 - Material Source property testing and sampling
a53dcabc-5e7b-55bb-a9d2-84abc8de421f | note | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 3, NZS 4407 : 1991, NZS 4402 : 1986
05ead482-f56d-5c59-a325-fd8342fdb191 | note | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for crushing resistance, wethering quality Index and California bearing ratio ( Class 3 & 4)
6ba4b2cb-08aa-5c51-88a6-77b85140c0d2 | note | Test Frequency - Once Per Year Or Every 10 000 m³
fdce9ef3-db5b-5014-be92-6d6d726fc754 | note | QA Record - IANZ Test Report
3d1bda34-b848-56dc-aeac-dae0af934ae2 | note | DNZ Engineer - R
3181b171-cab8-59ba-b585-fc24dbe1e178 | note | Designer Rep - H
72136807-03ad-4b03-820f-1535199c0c2a | signoff | AUTHORITY HOLDPOINT
2a7b8e83-27a4-4ee1-a6d7-3f43f579b685 | checkpoint | 2.3 - ATAP40/GAP40 - Production property testing and sampling
df2671eb-df11-5e84-ba35-6a18413110e2 | note | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 4, NZS 4407 : 1991
4814780a-ae05-5c0d-83d6-635f0214759b | note | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for Quality of fines as per M/4 fiqure 1, Broken Face content and WET particle size distribution Limits and shape control
c59c4503-49bf-555e-b715-4737c9feb2e2 | note | Test Frequency - Once Per Year
41b4205e-a2b0-5267-87f5-2ca6da5684a8 | note | ○ Or Every 10 000 m³
a3287230-1b97-5bab-b4b9-45bcd8d43f1f | note | QA Record - IANZ Test Report
5f721988-ceb3-559c-9ca3-c5bd9b83d681 | note | DNZ Engineer - R
678a1825-bf79-57fb-a335-fd0c0e984e28 | note | Designer Rep - H
61aa58c3-7ab7-468c-bc7b-cd2b2cf0973b | signoff | AUTHORITY HOLDPOINT
6c8567b6-4dd8-43e7-af8b-5d29c04a51bf | checkpoint | 2.4 - ATAP40/GAP40 - Testing for layor compaction - MDD
c12c79cf-d444-5841-a820-578d0a1d0943 | note | Standard, Drawing or Specification Reference - TNZ B/02: 2005 - 7.5, NZS 4402:1986 - 4.1.3
8979071b-bbb5-5687-8099-67b53e76cb23 | note | Construction Activity Description, Test Type and Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
b686ed6b-57bc-5ed0-80c4-e650238014f9 | note | ○ Average MDD 95% with a minimum of 92%
2157fe88-99ce-56fc-a41c-33e5ea8b0760 | note | Test Frequency - Once Per Year Or Every 5 000 m³
04220e3c-9509-5d6c-902c-3f377a72ee80 | note | QA Record - IANZ Test Report
cc51ba3a-b8a2-5b47-93d1-97e34cac9fa8 | note | DNZ Engineer - R
5eebe1b6-1822-5dd0-a7ac-7d1f7e6a8645 | note | Designer Rep - H
bfc958cb-d185-400d-8dbc-5cb8ad8e0646 | signoff | AUTHORITY HOLDPOINT
cc1d560c-12b1-4056-980f-cf4f8817254f | checkpoint | 2.5 - Reinforcing Steel
4f03de88-55bd-5a7e-8fd1-57eb302507b4 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
586a8600-94d1-5075-a207-12d0db8daae9 | note | Construction Activity Description, Test Type and Acceptance Criteria - SE62 - 665 Mesh Grade 500E.
c4c8a037-aefd-52c4-8bb6-827691bfb7e8 | note | Test Frequency - Once
26ce066a-146a-5ab6-835b-03caae60b26c | note | QA Record - Mill Certificates & Approval
b3da3a6d-85cc-5771-ae0a-ef0f6b02d556 | note | DNZ Engineer - H
51f80e34-4184-5a68-8ca2-d9f4d295e0af | note | Designer Rep - R
412b4ddb-b9b9-41c8-a2e5-910db9af75dd | signoff | AUTHORITY HOLDPOINT
88cdbabf-2b27-47a5-be15-f0afc4c02fcf | checkpoint | 2.6 - Contraction Joints
fb91dcd4-153b-589d-9b84-bb751693bbac | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
7fd869c2-e59a-580b-9e82-f15bfb73fa5b | note | Construction Activity Description, Test Type and Acceptance Criteria - 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres.
6d6d2d08-c2a1-5b1e-a526-7e2d3240875a | note | Test Frequency - Once
d6a0b2c5-0f41-5a0e-8ba7-f2f7a302089c | note | QA Record - Mill Certificates & Approval
0aaa7ebd-2ac8-5349-b185-f020993dea99 | note | DNZ Engineer - H
c57599a1-aab1-512e-9649-452382d3f9ac | note | Designer Rep - R
319f5f0e-b80a-48e3-9ed1-e5026b2ca879 | signoff | AUTHORITY HOLDPOINT
728d4893-7f89-4b42-a47b-603ea57f0d80 | checkpoint | 2.7 - Tactile Indicators
47d11475-5e4a-5a78-bbed-040180f34e7a | note | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction, FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11
ac05919e-815c-5aa6-994b-0385ca263f10 | note | Construction Activity Description, Test Type and Acceptance Criteria - 300mm x 300mm x 60mm thick yellow anti-slip precast concrete.
92cda185-11da-5db8-8af3-99aa7c825c35 | note | Test Frequency - Once
cbbf4f35-776c-5084-93b2-356c2a99d4b9 | note | QA Record - MDS & Approval
df618c67-afdd-5c12-8963-e0297c1f4e05 | note | DNZ Engineer - H
7162d791-67ad-5a5d-9730-312d7808ba4e | note | Designer Rep - R
edeefd9b-7562-40a4-b996-666134167dd4 | signoff | AUTHORITY HOLDPOINT
3b134f08-338d-4bf8-acae-c151fc5f6609 | checkpoint | 2.8 - Joint Sealer
3bcd87d3-94d7-5536-9e05-2f7e86041a8b | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
04ae746b-c84f-5b91-afca-0ad1a9616e76 | note | Construction Activity Description, Test Type and Acceptance Criteria - SIKAFLEX 11FC or similar approved product.
75917124-52e1-500d-9fb5-d0267df91763 | note | Test Frequency - Once
02b8f67d-6080-5e64-8ccb-7d9c72581995 | note | QA Record - MDS & Approval
0483b9a2-b80b-5bec-9aeb-843f8889e16b | note | DNZ Engineer - H
8fe434c9-dadb-5814-94ff-17c436aee7e3 | note | Designer Rep - R
6ef60587-60c7-4878-8ffa-0829d5bed5ce | signoff | AUTHORITY HOLDPOINT
2a17166c-3d29-44f9-877b-ed5467fb28c0 | checkpoint | 2.9 - Joint Filler
cac3bb19-08e7-5441-9af6-1e88b0901d64 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
e4fbe897-5d32-5f36-a4cc-1e7e2fcb0d35 | note | Construction Activity Description, Test Type and Acceptance Criteria - 8mm Polystyrene joint filler .
e42ee09b-4576-50b4-a72c-38bebc4a0020 | note | Test Frequency - Once
fe7fa4b6-761b-57cd-b906-1fe5ef46442d | note | QA Record - MDS & Approval
365bab6b-35db-55e2-a685-002b491d3cc2 | note | DNZ Engineer - H
a90d3690-89df-58b0-8559-7b1fdef8a466 | note | Designer Rep - R
81892fd5-15df-4680-857b-1f95a929656a | signoff | AUTHORITY HOLDPOINT
ca6fb8fe-d095-48c9-9ebc-d2a8641bef35 | checkpoint | 2.10 - Stitching Reinforcing Bars
530285e2-8abd-53f5-b104-fb43dbdde24d | note | Standard, Drawing or Specification Reference - AT Detail FP002
10f0e9e5-6a27-52ba-bb90-69b36abe7a43 | note | Construction Activity Description, Test Type and Acceptance Criteria - 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300
a545b410-6206-50b9-98e0-1d4a92a1de8b | note | Test Frequency - As required
33cf44a1-8e70-52ff-a3e3-ac07e955b9ee | note | QA Record - Mill Certificates & Approval
b32dfb10-362f-56df-b32c-b372e3cf115b | note | DNZ Engineer - H
61dbee1a-db61-5453-a492-5a9359ea35fa | note | Designer Rep - R
b77fd9fc-3d19-4f52-8066-83d9675fe605 | signoff | AUTHORITY HOLDPOINT
d9c571c2-fe6a-4944-a246-865e6aef0f6e | checkpoint | 2.11 - Geotextile
df409957-12dd-59e7-8389-a9cf211ef99c | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
35f5173d-e615-5019-b4e4-bef949657160 | note | Construction Activity Description, Test Type and Acceptance Criteria - A29 Geotextile Bidim, or similar approved product.
4eb028d5-a0d2-52cd-b080-a0567242c404 | note | Test Frequency - As required
d5aa7822-9031-5a05-92a9-fe2d9b0d8392 | note | QA Record - MDS & Approval
623d2c14-1736-57bc-a328-66eed502ca7c | note | DNZ Engineer - H
66d31ba2-9bc0-5866-82b4-faf1d2f5626b | note | Designer Rep - R
96fc0178-240e-48fa-a739-2ef19b7c7421 | signoff | AUTHORITY HOLDPOINT
498f2c53-a991-4f73-89de-490813bd0563 | checkpoint | 2.12 - Geogrid
e66b031a-65fa-5c52-b104-5ae9511ee74b | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
981da877-d527-5657-9c3d-0ba907caae6b | note | Construction Activity Description, Test Type and Acceptance Criteria - Tensar Triax 170 Geogrid or similar approved product.
c5339f99-244d-579a-a2db-353465d6dd78 | note | Test Frequency - As required
3a737c87-792b-5944-9b2a-32c44d8b7556 | note | QA Record - MDS & Approval
cd5e77b7-3569-587b-b944-b5e7f6f4f4da | note | DNZ Engineer - H
6ec924df-ee5e-5e63-b814-e43e68be9da4 | note | Designer Rep - R
6495eba6-b87c-4914-a61c-f81530e161e7 | signoff | AUTHORITY HOLDPOINT
acac2160-d80a-46d3-b4f3-68b899ea04d0 | section | 3 - CONSTRUCTION ACTIVITIES
759a03ce-8fb8-4ca5-9e69-32e15a64fa7f | checkpoint | 3.1 - Footpath set out and excavation to subgrade
b0a29b30-764c-5f2b-97a8-0e8d5d528c7c | note | Standard, Drawing or Specification Reference - IFC drawings and Models 746-22-052-PS Page 9 Table 1
5ac1d67d-beb7-59c3-b5f3-4838f4eaeb7e | note | Construction Activity Description, Test Type and Acceptance Criteria - Straight edge check ensure it is within 20mm from 3m straight edge, parallel or across each lane.
0abf8ba5-0979-5296-bb29-a85fd886b107 | note | ○ NO WATER PONDING ON SUBGRADE.
8ca207d6-8f28-5c23-b81f-13b5b3b215f6 | note | Test Frequency - Every 5m
787f297d-d029-55d0-8c7c-b709da0a714b | note | QA Record - As-Built or Stringline checksheet
6a8e29b1-e644-57ca-b118-e1d3eee85c25 | note | DNZ Engineer - H
aadb307f-568d-4b66-a396-9066b173bad4 | signoff | AUTHORITY HOLDPOINT
7d29143f-2879-4a5f-b098-2ebd8e53c841 | checkpoint | 3.2 - Foundation - Subgrade Testing (Scala)
5af1b157-b42b-5c03-8736-74e84a2bceda | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12 746-22-052-PS Page 9 Table 1
5c492b44-f10d-53b2-85af-9f1784687eb4 | note | Construction Activity Description, Test Type and Acceptance Criteria - If caly based material is encountered - ensure subgrade has a minimum CBR of 3
f2215280-1a3e-54a9-9667-74ef5adc0fea | note | ○ Test to a depth to 1m, not less than 3 blows per 150mm for CBR 3.5% and 3 blows per 200mm for CBR 2%.
1368d29c-59bb-524a-983c-e85d734e7aea | note | Test Frequency - Every 25m²
c6305a30-9e8b-59f1-8483-deaff92830e5 | note | QA Record - Scala Test Results - CBR of 3
4d3c21aa-4e06-5ccd-b4a8-f476ec9acf8f | note | DNZ Engineer - H
5e4f218c-c5d0-5d0a-b1b4-371b841bce01 | note | Designer Rep - R
6eb7586f-b4be-40a0-a5b5-1354a6587cd2 | signoff | AUTHORITY HOLDPOINT
7af87028-ec5b-4465-8104-4964844502d5 | checkpoint | 3.3 - Foundation - Subgrade Testing (Existing footpath) (Clegg)
b10c4ee1-ab94-560f-b935-cc8e47d8b968 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12 746-22-052-PS Page 9 Table 1
a1f3a1f0-ab35-5bb6-a8ba-4905dd9b5e6f | note | Construction Activity Description, Test Type and Acceptance Criteria - If granular material is encountered - Minimum CIV of 12
feb0fcf3-a171-5ac9-b74c-5a4c2aa9d4fd | note | Test Frequency - Every 10m
3e6aa958-2567-5052-9ee4-69bfc8580b0f | note | QA Record - Clegg Test Results - min CIV 12
3484f796-2011-5659-8b60-3c294dc52706 | note | DNZ Engineer - H
182a9543-f496-5b30-908a-cf8b2aaf7a47 | note | Designer Rep - R
622373aa-f964-4e72-a887-c0ca089c45c0 | signoff | AUTHORITY HOLDPOINT
0a7c41cf-11fd-4909-9597-a5b708c3d4e2 | checkpoint | 3.4 - Place Geotextile
8a0a2562-ac45-5650-9ddc-5b0c96373616 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12
4f9e1ad4-4332-534f-9941-915251e5fb84 | note | Construction Activity Description, Test Type and Acceptance Criteria - An underlying geotextile layer is to be laid between the granular material (GAP40) and the Subgrade.
68ee8095-7202-5f4c-888a-a568dba0b347 | note | ○ A29 Bidim, ensure top, bottom and sides are coverd.
4d94397b-48fe-5304-b627-8e6343757119 | note | Test Frequency - Per inpsection
c8e8b86a-b714-5769-a883-e4fce2720ed6 | note | QA Record - Checksheet, Photos
a42a9daa-3096-511a-be4b-e507b0aacbce | note | DNZ Engineer - I
d5dd85aa-638e-4904-bd50-b47da07a3aee | checkpoint | 3.5 - Undercut (If required)
2594a804-7c38-530c-a911-0b543d68e43e | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12 746-22-052-PS Page 10 Table 2
df0cbd44-43e6-5aa4-b11b-7d26fb756fec | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to subgrade undercutting, the Engineer shall confirm the extent of subgrade undercut and the colume if in-situ material to be removed.
9d3812b4-c5fb-5b1b-8110-49dfb802a7f4 | note | Test Frequency - As required
45684d06-dbbf-51e9-9c2d-deae9ef2e3a8 | note | QA Record - HP Release
993a379b-f344-5a2c-868f-22e24217949e | note | DNZ Engineer - I
ecc4e3d0-ab74-5b42-a5c2-28362f017aad | note | Designer Rep - H
84e61d4d-dfdf-4e72-8a19-a0bfcef0c768 | signoff | AUTHORITY HOLDPOINT
36893440-f90b-409f-a32f-7c3a94f08ba5 | checkpoint | 3.6 - Place Geogrid (Only required for undercuts)
7269be83-ac0e-5950-8a0a-f496ea5850a1 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12 746-22-052-PS Page 10 Table 2
f98456a0-40c5-509c-847d-2d09699a2775 | note | Construction Activity Description, Test Type and Acceptance Criteria - Placed above the geotextile prior to backfilling.
43d493f3-df6e-5f68-8600-c000f02c95c3 | note | Test Frequency - As required
67eeca39-ad2e-5fa7-a166-129a4bf7c231 | note | QA Record - Checksheet, Photos
6f74799b-b6c7-57b8-8874-61959534a19d | note | DNZ Engineer - I
9efc3886-90d6-4b98-91d0-301c856f0a0f | checkpoint | 3.7 - Place and compact Basecourse GAP40
b8b4e6e6-4fc8-505a-9112-63d2a3d0f55d | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 9
92ee5142-2d13-5e0c-9c21-376185964a2f | note | Construction Activity Description, Test Type and Acceptance Criteria - 100mm thick layer compacted where no undercut is required
131c967e-0aee-5d65-bc8c-e33640d0fdc9 | note | ○ Where undercut is required: Contractor to notify Engineer.
dc648beb-95cf-51b9-b11e-daa9ae6c822a | note | ○ Minimum CLEGG CIV - 12.
814d2ed4-e7ae-519c-898b-ce4f6450fcff | note | Test Frequency - Every 10 m
0db29abc-0291-5be5-926d-56f2df7bee0d | note | QA Record - Clegg Test Results and photos
8b9b0c73-38d5-5f5b-b960-00908edb33ca | note | DNZ Engineer - I
b474359c-6449-4c59-b690-ef2d44ae03bc | checkpoint | 3.8 - Timber edging
b8ec62fc-633f-514d-ba03-9cf3dfa30908 | note | Standard, Drawing or Specification Reference - IFC Set out
6a55691d-2d98-55a3-86ac-a4fa170e4c25 | note | Construction Activity Description, Test Type and Acceptance Criteria - All footpaths shall be contained by either a concrete kerb or edging, or by treated timber edge boards, which shall form part of the finished work. Minimum width 1800mm and maximum 3000mm 150mm thick.
0e1645c4-1add-527f-848d-63759c7c434c | note | Test Frequency - As required
43f142db-b542-5ec3-bd37-48737eda1bad | note | QA Record - Checksheet, Photos
4d6912d8-5b08-5536-84c6-6b004b29b952 | note | DNZ Engineer - I
b1b4a5cf-d92a-4d6d-a5ac-8cfbe751c599 | checkpoint | 3.9 - Place Reinforcing Mesh
13d80696-806d-576f-90fe-3b69ac213082 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1, 3235599-SP03-ST-3002 Note 6.1
ed2c833c-daab-5435-b5ad-885638385bf6 | note | Construction Activity Description, Test Type and Acceptance Criteria - 665 mesh, centrally placed.
028e2bab-1830-50cf-9849-4f3b66446636 | note | ○ Minimum overlap of 200mm between outermost cross wires.
c290e1c8-00aa-56c6-bdd6-0eff611eb7a7 | note | Test Frequency - Every pour
8aba9b19-659b-5993-962c-b92fd628bed2 | note | QA Record - Checksheet, Photos
1411f7dd-02cd-5189-b797-c6858e8e8551 | note | DNZ Engineer - I
1940521d-1781-47f8-86c5-59f45135b8a3 | checkpoint | 3.10 - Place Contraction Joints
66384c3e-54ba-541c-bd0f-88ddc5040780 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
b735b860-6eb0-5a11-ae0d-cdc152e6667a | note | Construction Activity Description, Test Type and Acceptance Criteria - 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres.
a9517bef-0b60-512d-93cf-7b3bb2ea7382 | note | ○ Installed every 15m.
868903d2-2265-5cfa-9de8-96addae91246 | note | Test Frequency - Every 15m
5de791d4-af7f-5186-ba77-977d69604c43 | note | QA Record - Checksheet, Photos
095055f3-c905-5e08-81c6-0b9c3bc61751 | note | DNZ Engineer - I
11b08d43-00bd-46e6-8867-3f7989be57fc | checkpoint | 3.11 - Place Tactilies
b9f123a7-f877-58ed-bab1-d389ad3d501e | note | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction, FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1, Note 11
3e679336-e140-56ff-b28b-ee202f403ad0 | note | Construction Activity Description, Test Type and Acceptance Criteria - Tactile pavers shall be bedded on 100mm thick 20Mpa concrete.
fbabf4db-517b-5fec-9c29-c3bc4f8877b0 | note | ○ Orientation and set out shall be approved by the Engineer and or ATOC Representative prior to concrete placement.
b0f879d7-c7f8-5c7a-99df-d3a0ee1cda3a | note | ○ A one coat sealer with UV stabiliser is to be applied for maintenance and durability reasons
50925fd8-0ca4-5e7e-b6f7-9bfc6ce5a2c6 | note | Test Frequency - Per installation
5a4397d5-25f5-5ff5-9fdb-ba85fb38bfa1 | note | QA Record - Delivery dockets, Checksheet, Photos
46d92927-160b-5031-abe9-9f014f9f2ec2 | note | DNZ Engineer - H
936b6d09-85b3-5b30-b865-968449c2112f | note | Designer Rep - I
a0763c65-c674-44e6-a40a-3571626c3b20 | signoff | AUTHORITY HOLDPOINT
40a579ba-92c8-45d3-9713-82224eb1f136 | checkpoint | 3.12 - Place reinforcing Stitching Bars
719eb90e-4c10-59e2-878b-ee57838a3dd1 | note | Standard, Drawing or Specification Reference - AT Detail FP002
f977906d-d7aa-59e7-ada4-e716b6351743 | note | Construction Activity Description, Test Type and Acceptance Criteria - Stitching bars to be included around Manholes chambers, valves, hydrants and lightpoles to prevent cracking at the re-entrant corners.
4947920b-59fc-5d17-8ad3-2077876ea10f | note | ○ 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300
00b6327d-1696-584b-b806-2ce1787e93a9 | note | Test Frequency - As required
645ee32f-e56a-5d1d-9e30-7112845d6f9e | note | QA Record - Mill certificates and photos
8aef3e91-d532-5606-a65c-fbccf84bf9e0 | note | DNZ Engineer - I
a4292d1c-f1ac-49e8-a1ad-57b19e81f11c | checkpoint | 3.13 - Concrete Pre-Pour
4768b0b7-eafd-5e6f-bd62-2a8d57d64f1f | note | Standard, Drawing or Specification Reference - AT Detail FP001, 3235599-SP03-CA-1031 - Rev 1
22ebdfe0-ef22-51c7-8123-12820771bc24 | note | Construction Activity Description, Test Type and Acceptance Criteria - Ensure pre-pour checks has been completed with the Engineer prior to concrete pour, target concrete cover 50mm around each edge
0ddc06c0-da4e-5a84-8ef6-4434338aa58c | note | Test Frequency - Every Pour
e812e26b-4612-5442-ab4c-eaea58afd916 | note | QA Record - Pre-Pour Checklist
2745c096-e837-56d3-9b5c-d0e711d98da4 | note | DNZ Engineer - H
35ae51e8-f796-5d9e-9c43-13a2b25412a8 | note | Designer Rep - I
3089a663-1869-4562-a7a2-3f2c9270e61b | signoff | AUTHORITY HOLDPOINT
61fddb97-0d8c-4dc2-9a6f-3236427a4d86 | checkpoint | 3.14 - Concrete Pour
64345507-8741-5fa3-aba3-22bb2664c4c1 | note | Standard, Drawing or Specification Reference - AT Detail FP001, 3235599-SP03-CA-1031 - Rev 1
dfe48f8b-5140-5b9d-9db6-4a2708549e64 | note | Construction Activity Description, Test Type and Acceptance Criteria - 2% Cross Fall Towards Carriageway. (1% min. 3% max.)
72c1117b-fed4-5850-88f1-371a20a8631c | note | ○ 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates.
3f62ba45-22a3-5489-ab29-8c83c3b89451 | note | ○ Slump 120mm (±30mm)
b461f654-8d5d-59ad-8706-ef418acd9d4c | note | Test Frequency - Every Pour
f2411308-3701-5f21-a189-618acadb2488 | note | QA Record - 7 day and 28 day Concrete Test Results from supplier, Slump Test Results (onsite)
10edeb23-41ab-5fa4-be4c-ee733051cf62 | note | DNZ Engineer - W
f0d63463-59d5-5dcf-af3c-e71290612f74 | note | Designer Rep - W
7998bdd6-290b-4721-9aef-3d8936f22b71 | checkpoint | 3.15 - Concrete Finish
7306a334-fefd-528a-a973-079e45bea852 | note | Standard, Drawing or Specification Reference - AT Detail FP001, 3235599-SP03-CA-1031 - Rev 1
44b61a99-9199-5d05-a35f-d7bc3eecb5fd | note | Construction Activity Description, Test Type and Acceptance Criteria - 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates.
2bc38c51-1192-5f9e-9b22-455236fb89e8 | note | ○ Exposed finish apply surface with Rugasol C.
88753f82-94fd-5891-a4af-0948c7cf709b | note | ○ Exposure of the aggregate should begin when the surface can bear the weight of the paviour without making a surface impression deeper than 2mm. The surface shall be sprayed and brushed across the entire surface using a medium-bristle broom (U5 finish) and a continuous water spray to wash away the cement paste, exposing the aggregate evenly to an average depth of 2-3 mm.
2a96ad23-9bec-5006-847f-3e7c30a2d760 | note | Test Frequency - Every Pour
7e73733d-48a5-559c-ae07-9224b0d14800 | note | QA Record - Post pour inspection checksheet
15103c68-d895-57cb-8c6c-93da9a9a1256 | note | DNZ Engineer - W
bd05377f-f6a1-400a-a56b-70c94bff16ce | checkpoint | 3.16 - Saw Cut Joints
bd847148-e5e6-57f3-a4ea-db48a2084bd3 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 5, AT TDM
e2033d7b-4d99-5fc2-bd43-7a3265cb73f9 | note | Construction Activity Description, Test Type and Acceptance Criteria - Saw cut joints to be constructed to 1/3 of the concrete depth at a spacing of no greater than 3m.
d80d09c0-f2a6-5cdf-8943-5482b9665ce7 | note | Test Frequency - Every 3m
feca5fdc-8e82-5661-bc8e-b6f8b9874f27 | note | QA Record - Photos
30e4dcf5-b718-543d-acba-d819daf84539 | note | DNZ Engineer - W
f742da13-72a5-49d3-9916-9be496aea094 | section | 4 - FINAL RECORDS
57b3bf18-4684-4653-9818-3cde7511ea1d | checkpoint | 4.1 - Construction Record Compilation
2c07629d-8a2b-54fe-8e52-eb1324e58252 | note | Standard, Drawing or Specification Reference - N/A
b0af1e1a-dd4c-5257-9b6d-e72b13230831 | note | Construction Activity Description, Test Type and Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
af1865dc-f3c4-5492-817a-46929205a2b4 | note | Test Frequency - Once
126fb380-39cf-5a9f-b6dd-b4ec95c5f6af | note | QA Record - QA Records
bca13338-a5f9-50a0-a988-28c348217b46 | note | DNZ Engineer - H
65793536-0d34-5505-a8b0-71fa31f09e18 | note | Designer Rep - R
3d4a84aa-72de-41c1-a993-63ba557b828d | signoff | AUTHORITY HOLDPOINT
bbbf3776-1bd8-4c04-b49f-f23aea6f7379 | checkpoint | 4.2 - Survey Records
d87ca04e-a24c-5e60-b7ed-9d594345074f | note | Standard, Drawing or Specification Reference - N/A
ba290f35-7e92-5b07-be53-04c12050197a | note | Construction Activity Description, Test Type and Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
2c19a64f-d74a-5f5b-96ec-11f241d4e53a | note | Test Frequency - Once
d81443bb-0702-5e4d-8d83-3652ba47472b | note | QA Record - As-Built
55efd879-998a-5868-aa35-3b4615849a64 | note | DNZ Engineer - H
553152bc-74e9-536b-9b27-177a83675e2f | note | Designer Rep - R
64f608a4-734c-4f6a-84f9-0cfba9742575 | signoff | AUTHORITY HOLDPOINT
1ded465c-067a-446b-ba99-f4a73cdf612c | checkpoint | 4.3 - Redline Drawings
0b6fce22-0017-5f47-9de0-ff53353c5775 | note | Standard, Drawing or Specification Reference - IFC Drawings
3e5d028b-a688-5459-a157-0e086149454c | note | Construction Activity Description, Test Type and Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
3e42d55b-7fc6-56fa-b69d-cd0dfc653be0 | note | Test Frequency - Once
ed938605-2786-5f7a-a51b-462110e0883b | note | QA Record - IFC Mark-Up
a868f4a2-548d-5ab6-b053-eef2eb439664 | note | DNZ Engineer - H
a42ce858-1b42-5f3b-8dd6-d3f039632a58 | note | Designer Rep - R
3c296b0b-fc34-4569-9c68-fb829f2803d8 | signoff | AUTHORITY HOLDPOINT
17650747-28fc-4c0c-9779-581decf71b04 | checkpoint | 4.4 - Defect, Snag and Punch List
e0372f88-056f-50ec-a68c-0c92a8f879f2 | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
298a2902-547a-5754-ac12-72295a08aece | note | Construction Activity Description, Test Type and Acceptance Criteria - Update the project Defect, Snag and Punch List Register
e6d58a23-1f22-572d-b418-adf4f81ca483 | note | Test Frequency - If required
0bb32fa6-b105-5cf7-9049-c64c3b566071 | note | QA Record - Snag Register
8191f135-b4f6-53a2-ae8f-ffb1b42254df | note | DNZ Engineer - H
53fc376e-a875-559e-aa34-61e13ca21022 | note | Designer Rep - R
252f6ab3-cf0b-417a-925b-ade7c1d4866c | signoff | AUTHORITY HOLDPOINT
2e78b82b-cd43-4c6b-a16f-65f253533843 | checkpoint | 4.5 - Non-conformances
20834ce1-be45-5453-9654-c681313e2c9a | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
998e97b6-c635-5dfd-97fc-33281ada41ce | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
0b946165-2454-5e24-ad14-d5710186e997 | textbox | NCR Reference
1d3d1992-bf41-5ab9-aba2-be0401483f57 | note | Test Frequency - When Required
6a366753-8173-5011-9cfd-a56ef14ab363 | note | QA Record - NCR Forms on InEight
a7fca9fd-1980-5db5-a09a-079a606141c4 | note | DNZ Engineer - H
0f9321e0-7e2b-51a8-8f9b-6638b5d1fedf | note | Designer Rep - R
0bf85f53-a0b9-4731-a5c7-861b773067f1 | signoff | AUTHORITY HOLDPOINT
bacc6ad1-527f-40e9-9629-055a96bd7b8f | section | ITP APPROVAL PROCESS
a5a15efd-c190-42a4-901f-a8519390c8cc | checkpoint-no-value | ITP APPROVAL PROCESS
0233959a-8503-58b6-b606-ccccb0c892d2 | note | Prepared By: Quality Engineer - Nas Matar
db59bec0-4ac7-59ab-b396-92170a58fe82 | note | Reviewed By: Project Manager - Dan Trotman
bf7ee570-795a-5ac3-811d-909a41e60090 | note | Reviewed By: QA Manager - Cordelia Gridler-Brown
efdcecdb-2249-5a11-b1d7-f928a1f8648d | note | Reviewed By: Design Engineer - TBC
56648f48-eea6-5cea-ba06-339dcd6abc9a | note | Reviewed By: AT Project Manager - Mike Robertson
86fa02dc-9659-572d-8557-938861e3d0fd | date | Date:
7f52a519-fb14-43bd-bc63-d1ed59a6fe31 | section | FINAL ITP CLOSE-OUT
c200d87f-d3e1-4bea-84f5-355bd68d7827 | checkpoint | FINAL ITP CLOSE-OUT
5fb7b146-c587-51f3-be06-681b229b5635 | textbox | Downer Project/Site Engineer:
1fdff931-cfb6-5a29-a8c7-d78ebd33837c | textbox | QA Mgr./Engineer:
72fa00e5-b3ad-501f-857e-7e3226e0dda4 | textbox | Designers Rep(Assistant):
3004942d-c363-5e9e-8b40-c88a93bc7019 | date | Date:
56c16199-844e-4241-bfe5-0ff00677c155 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b2d33f8e-a610-5e26-b317-8d1c24480443 | textbox | Contractor's Rep Name:
1aa3abaf-132b-5fa2-99b0-3ffd428483be | textbox | Engineer's Rep. Name:
94fa42c2-3074-5d8e-8e21-dd82d3fc795d | date | Date:
92bd5454-ad17-432b-b5cb-e17c16463c71 | signoff | Add Signature
f5099d7b-faa4-49e2-92f0-ca8eb2463e82 | checklist | DN1212-ITP-002 Pilling Rev5 | itp | DN1212-ITP-002 Pilling
6230ea6e-e84b-41e0-bc06-077189e51a06 | section | 1 - PRELIMINARY AND GENERAL
04424eaf-7ec1-4905-87a1-c1274a719de8 | checkpoint | 1.1 - IFC Drawings and Specification
d52ba76f-2dfe-5767-a94c-6a3630659d46 | note | Standard, Drawing or Specification Reference - ACC
c5283fea-dbea-5c99-9b46-fa28cdd09322 | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
53fe6c38-9d40-5414-be2e-97e7cb339c39 | note | ○ Works done in accordance with Project specification
3c795a21-2f09-533a-b64f-5c062eae623a | note | Test Frequency - Once
64079b46-e3a6-5674-aa27-76d8216c42fa | note | QA Record - N/A
384b99c1-2d18-5e2b-9a06-a7060a28d0c8 | note | DNZ Engineer - R
2d1d7174-22fc-526b-a8dc-799a51372c62 | note | Designer Rep - H
0984bd00-e098-4d7f-8404-a8baf0711411 | signoff | AUTHORITY HOLDPOINT
2e958160-694a-41ea-a790-4dc8de8cffd1 | checkpoint | 1.2 - Method Statement & JSEA Development
8d7a94ee-bd4f-5dff-a202-129978656cb1 | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
e1e5f04c-90a7-5e3a-8c9a-96238ad5e6c8 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
8d1473d3-b298-5c08-ba33-bf6c97d2f2dc | note | Test Frequency - Once
d7e6530e-5fb7-50db-a3ff-bfc3902709c1 | note | QA Record - Method Statement & JSEA Completed & signed by relevant authority
578d429f-0722-5904-86b9-0907e153122f | note | DNZ Engineer - H
8ac9b53e-63ac-5c20-ba3a-93ee74ddcb7c | note | Engineer's Rep - R
71fa31be-3994-5694-ba0d-42e22613ca5c | note | Designer Rep - R
be0322bc-193c-4f30-b105-ef44f4ba5c81 | signoff | AUTHORITY HOLDPOINT
ac535b3b-e8c5-4150-a0c2-1edc99d6957e | checkpoint | 1.3 - Permit to Dig
8fae22b0-5474-5f09-8f26-7bb59e4016db | note | Standard, Drawing or Specification Reference - DN-ZH-ST043 Ground Disturbance SP03-ST-3150
d9c27ffe-49cc-5f53-8f77-6eb11593fcc7 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction, all services shall be located ahead of construction.
df004eaa-9379-58a5-9d65-e3771e21804f | note | ○ Permit in the work package.
9fa9e705-33d9-54d4-88ae-864c989636aa | note | Test Frequency - Permit issued each week
79b8a620-1c66-5658-84ff-d9a48c2efa64 | textbox | QA Record - Permit number
fd74c72d-9bbe-5734-a59d-e39833ccfa31 | note | DNZ Engineer - H
25eb8ea3-14a6-4f71-8e7d-57e710ecd207 | signoff | AUTHORITY HOLDPOINT
a45999e7-af9b-441c-800a-0d1d2e238fe1 | checkpoint | 1.4 - Survey Model
bcec3c14-f1d6-5720-80ab-598002d470bc | note | Standard, Drawing or Specification Reference - N/A
bc82d445-66e7-5212-8375-c69f2b7333da | note | Construction Activity Description, Test Type and Acceptance Criteria - Model Review.
754d3252-0191-5b40-ac4c-062d53c00a46 | note | Test Frequency - Once
94996765-a5ce-59a0-817c-bab885d5a50e | note | QA Record - Visual Inspection & measurement Survey Check set out as per design
55ca2b8c-e404-512a-a453-f029866b7f0d | note | DNZ Engineer - H
22709567-94c6-41be-a8d8-d1b2b1da3db9 | signoff | AUTHORITY HOLDPOINT
ee4ffc79-ec12-46a6-b918-67bd01aad9cd | checkpoint | 1.5 - Lift Plan
5a27eae7-eb2f-5f01-9be1-5c2cc00ddb48 | note | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Standard
9f90b723-e720-5296-bf12-398b347705d3 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. For lifting of casing, reinforcing cages, tremmie pipes etc shall be in place ahead of construction, a Complex lift plan for the Crane and lift card for lifting with Excavators.
47438308-9bfa-5475-bfac-da8b08a25adb | note | ○ Lift plan included in the work package.
18d359c0-9783-58f6-ae27-a458be9203bd | note | Test Frequency - Prior to Construction when required
8a4f9599-2a38-5e43-abd3-4a013c6247a1 | textbox | QA Record - Permit number
7be9df51-662b-5d62-894f-c48cba450ca9 | note | DNZ Engineer - H
d91ab962-330a-44f5-9b50-8dbe194fd769 | signoff | AUTHORITY HOLDPOINT
96b3e7b7-1e9f-439a-b9b2-da13db0adeea | checkpoint | 1.6 - Hot Works
84a7c0af-d4e7-543e-9487-4a14602aab58 | note | Standard, Drawing or Specification Reference - DG-ZH-ST041 Hot Work Standard
0ca3e4f8-46c4-599d-b452-63eb02969384 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction,for welding, gas cutting, grinding etc a Hot work permit shall be in place ahead of construction.
83d13bda-4a36-5b75-ab66-1d41942c9914 | note | ○ Permit in the work package.
8e9ff973-0030-533c-8e81-648c0a13d4cb | note | Test Frequency - Prior to Construction when required
57912fcb-4b70-598e-a5ce-5d181563ba26 | textbox | QA Record - Permit number
9228dac7-a1d2-58d6-8fed-7b32438652ce | note | DNZ Engineer - H
42a8ea4c-82ae-4868-a28b-bba746ecc679 | signoff | AUTHORITY HOLDPOINT
7b70bd6e-019d-4b52-8fe8-56642bfbb41d | checkpoint | 1.7 - Working at Heights
2033e872-d66d-5997-a6d0-46669298d833 | note | Standard, Drawing or Specification Reference - DG-ZH-ST042 Working at Heights Standard
d43b20e9-11bf-5b12-86b9-21c2886fca2a | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction, permit in work package.
d4cb3525-cf12-5fbe-9a5a-c4a52ed00f5c | note | Test Frequency - Prior to Construction when required
0d3824ea-b2e5-5396-9de8-26896245a192 | textbox | QA Record - Permit number
602ec510-e3c4-5dfa-81b3-2d6b5075c8c2 | note | DNZ Engineer - H
92a583dd-e025-4b29-87ac-729f3c9d180f | signoff | AUTHORITY HOLDPOINT
86f7874e-d681-468a-8487-17dc53e3ff79 | checkpoint | 1.8 - Permit to Pump Concrete
c33f9c49-bd14-59ff-bc8f-01d60b6a64d6 | note | Standard, Drawing or Specification Reference - NZ Concrete Contractors Association
820a9052-318b-5679-906a-e3ca4fe9ccde | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction, permit in work package.
8ce5846e-36c0-5410-be61-97face863596 | note | Test Frequency - Prior to Construction when required
13b630f8-2cf7-5bd5-ba5b-1e2122de6111 | textbox | QA Record - Permit number
ec6052dc-38a0-50c7-a722-5ca3b0df00c7 | note | DNZ Engineer - H
cf897af2-8a55-418a-bb51-0ce8b16ccd16 | signoff | AUTHORITY HOLDPOINT
14b4c0a5-4bcd-4bea-b91a-8ccc3818ad0d | checkpoint | 1.9 - Permit to Enter (Rail Corridor)
019fed5f-1d87-5684-bb23-8488117ab4c4 | note | Standard, Drawing or Specification Reference - DG-ZH-ST010-NZ Working in the Rail Corridor
9a492842-d16d-5c6c-b04d-a33958acff06 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction, permit in work package.
ab1464d6-6ad5-5c81-8472-f35dda92ace2 | note | Test Frequency - Prior to Construction when required
0da4d932-7c27-547e-98f4-399de7c8afb8 | textbox | QA Record - Permit number
11ab2258-1337-59ca-826a-9ada2b00c9f9 | note | DNZ Engineer - H
c1268762-8b30-4e1d-838d-9cc3d5af985a | signoff | AUTHORITY HOLDPOINT
23591cc3-7826-4d13-a337-9d41f106d650 | section | 2 - MATERIAL APPROVALS
a13b62ce-30ed-41e8-820d-1cbe655acfcc | checkpoint | 2.1 - Concrete Mix Design
d5fd79c0-6a4f-5b1c-a0f0-46b4e22faee0 | note | Standard, Drawing or Specification Reference - 746-24-874-AC Table 4 C0601.4.4, C0610.2
30c43346-c30f-5523-b0d2-70cc4e5d7033 | note | Construction Activity Description, Test Type and Acceptance Criteria - 40 Mpa, 11mm Aggregate size. Self Compacting.
6f0d3157-f3a4-561d-9053-57736e2516ef | note | ○ Target Slump 550mm ±50mm
b7d41079-8da4-5284-8836-7eb75b3666e1 | note | Test Frequency - Once
4f18fe30-1bbe-50e3-8631-072edce7f726 | note | QA Record - Approved Mix
f2a36a82-3f6b-5ae8-9ff4-6a2ee5add953 | textbox | InEight Reference
0420d78f-0355-5bb2-b2af-489391b3c90b | note | DNZ Engineer - R
e54078c2-6d4d-5fe6-99a5-f31b4584955c | note | Designer Rep - H
81110b79-0ea8-45c4-b939-c913e3c8814e | signoff | AUTHORITY HOLDPOINT
b7ab0ccc-e3c4-43cd-b044-ba8773bcd0a0 | checkpoint | 2.2 - Steel Casing
6ebf6311-3146-5cab-9f00-b6202de19985 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1 Note 4.0
9a0b1002-3289-50ce-9c0c-4dd902e242d4 | note | Construction Activity Description, Test Type and Acceptance Criteria - Details of the proposed casings shall be submitted to the Engineer for review and approval.
730e45ef-14c9-5d67-a343-c3697b61b952 | note | ○ 1219 OD permanent steel casing grade API 5L X52, thickness 16mm.
141e58e8-ed30-5c87-a28f-da081de47343 | note | Test Frequency - Each Casing
bde4a1d2-8952-5c02-a0a2-5b69e1fea656 | note | QA Record - Mill Certifcates, QA Report
1e440670-ced1-54a0-b8a8-4158a981c457 | note | DNZ Engineer - R
cbbdfd82-46c0-5d62-bb3c-6169388ec4d6 | note | Designer Rep - H
d398a49d-35a0-4bbe-824f-606a394d5b22 | signoff | AUTHORITY HOLDPOINT
02625370-1f2f-4dc5-9939-50cef2a8b8ab | checkpoint | 2.3 - Reinforcing Steel
59254380-9a73-5ce1-9236-486b8541bad4 | note | Standard, Drawing or Specification Reference - AS/NZS 4671, 746-24-874-AC C0600.17
9b8e28f6-d6b2-527d-ad5f-da1b4664c05e | note | Construction Activity Description, Test Type and Acceptance Criteria - Grade 500E MA
8fa0b78d-33ca-5aeb-a1f1-a5b6fb69d471 | note | ○ Reid Bars to Column Starter Cage
c9ae2282-23f8-51fa-8591-f3c2c72d8438 | note | ○ Reid Bars for hanging pile cage
6dc4395a-7cee-54ac-a01e-96b790987630 | note | ○ Sonic Tubes for CSL
f273da99-2aee-5bc8-aa83-a4f35dd7f80f | note | ○ Shop drawing and shop drawing check form to be provided to the Engineer for review.
1c996ef1-ce02-50f0-a142-8060cca1c8d3 | note | Test Frequency - Each Cage
fc53ca96-6796-5675-b74c-32849d768153 | note | QA Record - Shop Drawing Approval, Pile Cage inspection
69e5cff5-55b9-50d9-9153-0d36482a5865 | note | DNZ Engineer - R
32490a39-6ffa-5c35-9e47-321f6c8031fc | note | Designer Rep - H
727f3fb3-aee1-4685-b327-449d5d4e95b9 | signoff | AUTHORITY HOLDPOINT
5d9ef48e-b3e7-4b65-aaf0-9205d6721d3e | section | 3 - Construction Activities
4b78ef41-6247-4ee7-905b-364880edf9f5 | checkpoint | 3.1 - Pile Set-Out
ba9fe811-a74e-5be7-a92a-6c5e4a95f75f | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1
c176710b-7abf-51f9-89c1-7c01ba9dfee7 | note | Construction Activity Description, Test Type and Acceptance Criteria - Before commencing pile drilling operations, survey set out pile position based on model. Set out to include; pile centre, height and offset.
7a1ea9b5-ab91-569e-bbd2-028464828d0c | note | Test Frequency - Each Pile
4a790d3f-64e7-5866-a986-12a9599514c1 | note | QA Record - As-Built
30bc087b-f9b0-5b82-8bf9-159d8ff50ab0 | note | DNZ Engineer - W
aa19a500-ff9d-4b3a-acb7-a1d32ce1b6b1 | checkpoint | 3.2 - Pile Casing Installation
5b5eaeca-dafa-5922-b2de-ffeecd75475e | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1
01086716-399b-5c87-b634-ca02cdf76dbc | note | Construction Activity Description, Test Type and Acceptance Criteria - Pile casing to be installed into a shallow pre drilled hole. Pile casing to be as per submitted methodology and correspondence. Pile casing verticality to be checked using a spirit level.
d50bcfc5-d73d-5675-8820-3b5a5c98caf4 | note | Test Frequency - Each Pile
45b1d941-6351-5124-bc8e-7c9b825eb944 | note | QA Record - As-Built
b5df45cc-8dfb-5962-95ca-f403d73876cb | note | DNZ Engineer - I
32755e78-086c-4126-9e77-28805d84d598 | checkpoint | 3.3 - Welding of pile cages
1912483b-19c5-560f-a61b-bb2b6f1b086e | note | Standard, Drawing or Specification Reference - C0602.5.6, C0602.5.7
8e762757-c30a-5f86-bc80-af4d577a3deb | note | Construction Activity Description, Test Type and Acceptance Criteria - All welding of reinforcement shall be carried out in accordance with AS/NZS 1554.3.
4c7b1d43-d171-5be1-a3f9-10ee49856c97 | note | ○ The welding procedure shall be made available to the Engineer upon request.
cfd4c57a-b532-5d19-a52f-b10e5ae7da02 | note | ○ All welds shall be category SP in accordance with AS/NZS 1554.3
d5453b19-5420-5243-a8bf-d87ba61024d6 | note | ○ 100% visual examination by independent welding inspector.
c408f5cf-06e1-5de9-a488-a08478709aa6 | note | Test Frequency - As required
39cf82da-d198-5e63-91c0-67d854733ecc | note | QA Record - Welder Qualification, Weld Procudure, NDE Report
9e39831f-e707-5188-b4eb-bd26d7ec6c6a | note | DNZ Engineer - R
827cb397-f51c-5b08-8b50-5d78997bb5ff | note | Designer Rep - H
c75aef8d-1493-4cbf-a4ef-03885dae3c70 | signoff | AUTHORITY HOLDPOINT
4a57dba6-c60b-4337-b852-897dd43e6f74 | checkpoint | 3.4 - Pile Auger / Excavation
4f5ddb98-8801-5651-a2f0-e954cdb019b7 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1 Note 3.9
7ae53e2c-be64-5871-bbb9-169a85382215 | note | Construction Activity Description, Test Type and Acceptance Criteria - Depth to be checked and recorded after auger/excavation.
00469501-3c76-5981-a47d-c07f8abd6a0d | note | ○ Diameter of pile shall not be less than the specified diameter.
a94f1292-acdd-5984-b0f8-cbe8e346842e | note | ○ ±75mm positional tolerance, Max 1:75 (H:V) verticality tolerance.
9c49fa9f-e8d1-5474-8004-3351a4078c7c | note | Test Frequency - Each Pile
bb381810-5727-5717-bfef-d944fb293d74 | note | QA Record - Survey Checks, Pile Card, Photos
f6c0f5df-e67b-53db-bccf-493302b288f5 | note | DNZ Engineer - I
29a51f0c-f8cb-5f47-8e73-0bfa1dcf834b | note | Designer Rep - W
ea73f6ef-436a-41ee-bde5-3c0362a48f62 | checkpoint | 3.5 - Geotechnical Engineer Pile Inspection
ac9536d7-8f83-5152-8c59-a7afb86e6caf | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1 Note 2.3, 3.2, 3.8, C0500 A3.0.5
fb9da19e-af56-5f56-82ec-e41b75821363 | note | Construction Activity Description, Test Type and Acceptance Criteria - Geotechnical Engineer to confirm top of rock during the pile boring operation. And to inspect the material at the base and side of the rock socket complies with the design requirements (Bearing) at least equal to or greater than that nominated on the drawings.
6e2c372b-bba8-578c-97b2-24e95a3e9089 | note | ○ The pile card shall be signed by the inspecting Engineer confirming inspection has taken place and the founding stratum meets the relevant design requirements.
6acd91a1-aa6a-590f-a4d0-be044f4e6470 | note | ○ Tolerance on Top of Rock level variance of ±2m from anticipated level is acceptable.
d132c757-975d-5744-b087-4f15d6fd39a9 | note | Test Frequency - Each Pile
90110fbf-a256-555f-a246-49a6f8ea1650 | note | QA Record - MSQ SVR Pile Card
25b41a7a-7d00-5f21-9209-5c838e99e043 | note | DNZ Engineer - I
f09e90ea-b8d6-5a0a-886e-c1f26141084e | note | Designer Rep - H
0f2086f7-1888-493b-8b6c-ce60b447baf8 | signoff | AUTHORITY HOLDPOINT
135e843d-a60e-4538-8536-6c146d52071b | checkpoint | 3.6 - Geotechnical Engineer Pile Toe Inspection
be5fb248-3a56-5d4b-aae0-ee5c0cb48de1 | note | Standard, Drawing or Specification Reference - C0500 A6.0.2 Table 2
1378323a-2c71-59a8-9cf3-b1893f030236 | note | Construction Activity Description, Test Type and Acceptance Criteria - Geotechnical Engineer to inspection base cleanliness prior to reinforcing cage placement.
f2948e30-63ca-5e77-9389-0eb562c1628e | note | Test Frequency - Each Pile
4859e95a-aff7-5d3a-ae54-df5735da7ce5 | note | QA Record - MSQ SVR Pile Card
40b8ffd3-cd7d-5f4f-b0df-51f7bcd17d69 | note | DNZ Engineer - I
aa31e3c5-2461-59cc-bc91-b1d9076fffb5 | note | Designer Rep - H
f452816f-bc4e-4119-8970-e086a228fd8f | signoff | AUTHORITY HOLDPOINT
1902f08c-1740-4623-88ac-106550f6f64c | checkpoint | 3.7 - Structural Engineer Reinforcing Cage Inspection
c674374e-d346-528f-a2f2-121a6369ace2 | note | Standard, Drawing or Specification Reference - C0700
83a83c28-a3ee-5531-a0fb-8f9671c74d38 | note | Construction Activity Description, Test Type and Acceptance Criteria - Structural Engineer to inspect the reinforcing cages that it comply with the design requirements.
73062417-a181-558a-a591-1081fd19df15 | note | Test Frequency - Each Cage
42937d83-e014-58ca-b1de-25d5f1732d7f | note | QA Record - MSQA SVR
6b404351-0e59-534d-81ee-58534a67b054 | note | DNZ Engineer - I
ee40a366-e570-552b-96fb-eb3537a46085 | note | Designer Rep - H
6422878e-fb25-4a16-9ff9-71e34cfab7c8 | signoff | AUTHORITY HOLDPOINT
7c8638c9-cd17-429a-8f75-6cce6940cfb9 | checkpoint | 3.8 - Pile Reinforcing Installation
b4d61070-2348-5f4e-aedf-faa10ddc2f74 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3151-1 Note 2.4 & 2.7, 3.3, 746-24-874-AC C0601.8
f60c1d4e-4935-54ec-9be5-b0518a393ebc | note | Construction Activity Description, Test Type and Acceptance Criteria - Once the Geotechnical Engineer has accepted the founding conditions, and the Structural Engineer has inspected the reinforcing cage, placement of the cage shall occur as soon as possible.
eab73055-dc02-5afb-82cc-4a4c790dda08 | note | ○ Minimum concrete cover 75mm at any location.
e78bf431-0252-51e9-ba87-45f0e6016272 | note | ○ Tolerance on Spiral Spacing +10mm for 150mm Spiral.
ec16b6de-c4c1-563d-8604-9806a3de2bec | note | Test Frequency - Each Pile
73d407f5-c953-5f4e-b30e-9ef0484f2f83 | note | QA Record - Survey Checks before and after pour. As-Built, Pile Card
e4e23dc1-67e4-5ff6-816b-01d28314dcd9 | note | DNZ Engineer - I
fd378f03-9697-5a40-9f04-e83f7d3ee695 | note | Designer Rep - W
b186878b-34ce-456d-9b83-14f786bd5965 | checkpoint | 3.9 - Steel Tube Installation
c3fc4caf-7e2a-542c-a9e0-519d1addd790 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3151-1 Note 1.7
f6b5854e-d47c-5ceb-81fd-036dc4664062 | note | Construction Activity Description, Test Type and Acceptance Criteria - 4 x 40mm ID Integrity testing steel tube shall be installed at equal distance around the inside of the reinforcing cage for the full length of the pile.
6974aa8c-1d0d-55ce-83ae-5ff282b7976f | note | Test Frequency - Each Pile
d917939a-d15b-5100-8cfc-ffa108177da8 | note | QA Record - Photos, Structural Eng. Inspection, As-Built, Pile Card
fad9c700-91af-5d4c-aae5-649edd35947a | note | DNZ Engineer - H
5fc0cf91-46cb-529c-9aca-75323259bd54 | note | Designer Rep - W
d8f3de78-8702-43e8-9c47-47fd8da03d7a | signoff | AUTHORITY HOLDPOINT
253945af-8653-4baf-b373-57e0337c2069 | checkpoint | 3.10 - Pre-Pour Inspection
a571792f-7366-58a5-8317-b922700b6c0b | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1 Consent Inspection Schedule
933fe8f1-b2db-5f69-913e-db6385130556 | note | Construction Activity Description, Test Type and Acceptance Criteria - 2 Days notice to the Design Engineer. Pre-Pour inspection to be completed by DNZ Engineer, Auckland Council Inspector and Design Engineer.
aa55e448-2007-5f67-9c58-b7c5ba32514a | note | Test Frequency - Each Pile
2197129b-608f-5ccf-b4a0-97ec523f16db | note | QA Record - MSQA SVR, Pile Card, Building Consent Booklet
81a872f1-fe96-5af1-b28e-de423ee063ca | note | DNZ Engineer - I
0cf99f18-96fa-51f8-b91e-0f50e020b6bb | note | Designer Rep - H
612ca147-4180-41e3-8102-e4deb6f3f380 | signoff | AUTHORITY HOLDPOINT
b04a242b-cd72-4697-91c5-c16e10bcb86d | checkpoint | 3.11 - Pile Concrete Pour
598a2df7-65b9-593f-bfb7-06df0f745445 | note | Standard, Drawing or Specification Reference - 746-24-874-AC C0601.4.6, C0601.10.4, 3235599-SP03-ST-3151-1 Note 3.6
0f9d4240-c258-5317-9482-058245400fc0 | note | Construction Activity Description, Test Type and Acceptance Criteria - 40Mpa Concrete.
a414b03c-6a75-57ec-a4bf-ab93106887d0 | note | ○ 3 Specimens tested 1 x 7 Days & 2 x 28 Days.
2580703f-24c2-56dd-834f-e70c75bc6373 | note | ○ Spead test shall be completed on each sample taken from the chute.
b7100780-0467-5d14-85ce-cb73740b8444 | note | ○ Column and pile cage to be suspended for a minimum of 8 hours after placement of concrete.
0ffd7ec0-99ed-5042-9baa-a0e3f1398c06 | note | ○ Pile concrete is to be over-poured.
19c724c4-7417-5012-b6a9-6c03e0647600 | note | Test Frequency - Each Pile
9f8568f4-a11e-5e7f-ab56-1cca3451fab5 | note | QA Record - Concrete Dockets, Compressive Test Results, Slump Test Results, Photos
02e2edc1-f1f5-5a6a-a73a-26148c2f4868 | note | DNZ Engineer - I
0e30bb03-c315-53d3-95eb-6810b27523d5 | note | Designer Rep - H
1420d106-c020-47af-8e6f-521763ed6d40 | signoff | AUTHORITY HOLDPOINT
9cceb561-d074-45fa-8104-6128a1d06f75 | checkpoint | 3.12 - Pile Surface Finish / Construction Joint
9d11e19c-ca9d-58d7-9b1a-349a5634c9c2 | note | Standard, Drawing or Specification Reference - 746-24-874-AC C0602.6, 3235599-SP03-ST-3151-1 Note 3.6 NZS 3109
3a90fb08-9434-5e19-af46-153c16bf19c2 | note | Construction Activity Description, Test Type and Acceptance Criteria - Over-Poured concrete shall be removed carefully without damaging the reinforcing cage to form a Type B Construction Joint at the top of pile.
4e398574-270c-5ad2-b528-03cdb4dfb454 | note | Test Frequency - Each Pile
335aa576-aad2-571b-82bf-5aa71a3a5b36 | note | QA Record - Photos
19d5be92-7402-5456-8c29-92cb4d7e71b6 | note | DNZ Engineer - I
5f313f44-1c5a-53e3-a206-dc3758200663 | note | Designer Rep - W
cc4eb903-a97a-4b4b-bbef-257d4991540d | checkpoint | 3.13 - Post-Pour Inspection Cross Hole Sonic Loggging
5a36ef88-c5ba-5219-8add-ee686e80d088 | note | Standard, Drawing or Specification Reference - 746-24-874-AC C0500.2 A5.0
d15564d2-4f86-5dfd-90ed-5974b0ecacbb | note | Construction Activity Description, Test Type and Acceptance Criteria - Testing to be undertaken at 8 days
44d5b562-cf0a-52ba-bf8b-d5033ba4ffd1 | note | ○ Preliminary results shall be submitted to the Engineer within 1 day of completion of the test results. The Final results and findings shall be submitted to the Engineer within 3 days of completion to the test. Once the Engineer has reviewed the results of the tested piles, and are satisfactory the tubes shall be grouted with a 40Mpa Cementitious grout.
77b4dd25-085a-5fa5-b190-6558c21e1b64 | note | Test Frequency - Once
c01aa085-5c85-5ae4-9b51-371cc37537e0 | note | QA Record - Test Reports
a9cde838-1ce5-5c01-9953-e80976abb0d8 | note | DNZ Engineer - H
2d9297e2-f131-575b-882d-bf7bfddddf6a | note | Designer Rep - R
578dbb9c-9021-46b1-8779-9cb02e2381d1 | signoff | AUTHORITY HOLDPOINT
eb094b48-28e4-479c-9bb1-9f6658109c0b | section | 4 - FINAL RECORDS
052842e8-530c-42cf-b20e-558f18532cfc | checkpoint | 4.1 - Survey Records
c89d24c3-5d36-5eb7-9788-636333254cf7 | note | Standard, Drawing or Specification Reference - N/A
2f84749b-db64-55dc-8adb-4e0e9ca408f0 | note | Construction Activity Description, Test Type and Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
a9b4b483-b2e0-52bb-99a1-582c37e47924 | note | Test Frequency - Once
4fe63e2a-3e81-518b-82c7-6826cf47b0bd | note | QA Record - As-Built
c8bc61dc-d81e-5aa6-9555-ec296ae55621 | note | DNZ Engineer - H
79585f40-3f9c-5b71-b1bc-746d5f911654 | note | Designer Rep - R
cca09936-8fcf-479e-92a6-ae7e1090f814 | signoff | AUTHORITY HOLDPOINT
161a1a88-4f8c-4cce-9554-68d5c6c33c03 | checkpoint | 4.2 - Redline Drawings
ee2f5cc9-754f-5916-9cae-f84243cd709f | note | Standard, Drawing or Specification Reference - IFC Drawings
2fc44fd0-3e55-5fd5-8739-280f986c8d30 | note | Construction Activity Description, Test Type and Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
902ef243-2a34-5a65-9167-fd109ae9daf8 | note | Test Frequency - Once
faa34484-4bfa-5dd4-bc2e-7ff055b69c5f | note | QA Record - IFC Mark-Up
a8580204-45af-5f56-879f-25a9294005bd | note | DNZ Engineer - H
cdc44bb4-1ffb-5141-a113-0cdfc1d1c1ab | note | Designer Rep - R
2b67b62b-e426-4834-8ec4-1283e7de2727 | signoff | AUTHORITY HOLDPOINT
2e2f5efe-e9b3-4914-bf1b-36f1b4da383c | checkpoint | 4.3 - Defect, Snag and Punch List
a13ed3ba-7f87-5b01-8b91-e62210f4c3f5 | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
cb328779-affb-54b3-811a-8fb1870331a6 | note | Construction Activity Description, Test Type and Acceptance Criteria - Update the project Defect, Snag and Punch List Register
4a852843-622b-5cde-b234-9b14dc738e35 | note | Test Frequency - If required
b393a8fa-29e3-5c14-933c-ae5f2582d4e4 | note | QA Record - Snag Register
239e85ac-0f7b-5aa3-a91e-7873bd586665 | note | DNZ Engineer - H
1e246544-10ee-5d57-b2b8-3d15bb159eae | note | Designer Rep - R
3c84c0a1-3cc3-47c0-bf92-a581d912e3c4 | signoff | AUTHORITY HOLDPOINT
6f440c47-69ac-482f-b323-85c5bcdeb68e | checkpoint | 4.4 - Non-conformances
33477c1b-0efd-5ee9-9a20-ff863f872f1a | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
79de7f0d-9ea6-5e64-9bc8-f19a960ec5e2 | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
e39fa22e-992a-5445-a2d2-27e3556805a0 | textbox | NCR Reference
b349fdb9-305f-542a-b727-fcc28aa8614e | note | Test Frequency - When Required
ff5aab1c-2d6e-5f19-b12f-a7ff275d7318 | note | QA Record - NCR Forms on InEight
a3a7bb93-7237-5aa0-b6ee-2434736a6fd3 | note | DNZ Engineer - H
db01fca5-6cbd-59f9-b08d-21c84465aff6 | note | Designer Rep - R
75ae5e04-5b92-4904-81fb-6b085e416cc2 | signoff | AUTHORITY HOLDPOINT
471bd145-c4aa-4a86-889c-293407ab6d07 | section | ITP APPROVAL PROCESS
4bd14162-3b4d-45ef-8b76-4e31cc07b987 | checkpoint-no-value | ITP APPROVAL PROCESS
80ff22ed-af11-5a26-afb3-b4fc96eae3e1 | note | Prepared By: Quality Engineer - Nas Matar
2b29f868-5f5b-5f9f-9e1c-043204b6bfe4 | note | Reviewed By: Project Manager - Dan Trotman
379afbbe-5c7c-5aa5-afe9-3fdca2e63e72 | note | Reviewed By: QA Manager - Cordelia Gridler-Brown
2eda7883-2cb5-5f23-9ea1-d3401e467a6b | note | Reviewed By: Design Engineer - TBC
919205a4-5d9b-58f3-a973-46943f95fdc6 | note | Reviewed By: AT Project Manager - Mike Robertson
6cbb5d29-0d3c-5c26-9611-0ad875024473 | date | Date:
85f7c76d-1385-4c02-ba7e-a0b7571da052 | section | FINAL ITP CLOSE-OUT
c826fb7a-8684-4a6c-9bcb-9a6691ed4c18 | checkpoint | FINAL ITP CLOSE-OUT
5fbda94c-b590-5e25-8040-fd6038e9c11e | textbox | Downer Project/Site Engineer:
c80f91ba-5c37-5939-af4b-c663cd5308de | textbox | QA Mgr./Engineer:
d65a5fec-fc50-5a46-b0f3-bce45332ae80 | textbox | Designers Rep(Assistant):
4ae24214-9af7-5de8-ba97-277de4a374ef | date | Date:
70c444f2-5369-4f6d-a286-1932cff82803 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b5d8e742-17a6-5299-abdc-7f1baaf6c788 | textbox | Contractor's Rep Name:
13014c33-c214-5885-b6d3-58b529d4be73 | textbox | Engineer's Rep. Name:
5f7f7333-3642-5efc-9d71-c8004288b751 | date | Date:
ed9a0f0d-8f29-4b78-8f6f-75f31372dcdd | signoff | Add Signature