## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1212-ITP-005 Stair Case | itp |  |  |  |  | DN1212-ITP-005 Stair Case Rev4
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - IFC Drawings and Specification
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
label | ○ Works done in accordance with Project specification
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Method Statement & JSEA Development
label | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
label | Test Frequency - Once
label | QA Record - Method Statement & JSEA Completed & signed by relevant authority
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Permit to Dig
label | Standard, Drawing or Specification Reference - DN-ZH-ST043 Ground Disturbance
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit issued each week
textbox | QA Record - Permit number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Survey Model
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Model Review.
label | Test Frequency - Once
label | QA Record - Visual Inspection & measurement Survey Check set out as per design
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Lift Plan
label | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Standard
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. For lifting of reinforcing cages, lift plan shall be in place ahead of construction, a Complex lift plan for the Crane and lift card for lifting with Excavators.
label | ○ Lift plan included in the work package.
label | Test Frequency - Prior to Construction when required
textbox | QA Record - Permit number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Concrete Mix Design
label | Standard, Drawing or Specification Reference - 746-22-052-PS Section 5.2, NZS 3114:1987, part 2 Exposed Aggregate surfaces.
label | Construction Activity Description, Test Type and Acceptance Criteria - Mix Design approved by designer.
label | ○ 40Mpa Concrete with maximum 19mm aggregate
label | ○ Slump 120mm-160mm
label | ○ 4kg/m³ of black oxide to be used as per AT spec, exposed aggregate finish to be installed..
label | Test Frequency - Once
textbox | QA Record - Approved Mix InEight Reference
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - ATAP65/GAP65 - Material Source property testing and sampling
label | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 3, NZS 4407 : 1991, NZS 4402 : 1986 (Original detail was concrete blinding but changed by site to GAP 65 for easier bulidability)
label | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for crushing resistance, wethering quality Index and California bearing ratio ( Class 3 & 4)
label | Test Frequency - Once Per Year Or Every 10 000 m³
label | QA Record - IANZ Test Report
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - ATAP65/GAP65 - Production property testing and sampling
label | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 4, NZS 4407 : 1991 (Original detail was concrete blinding but changed by site to GAP 65 for easier bulidability
label | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for Quality of fines as per M/4 fiqure 1, Broken Face content and WET particle size distribution Limits and shape control
label | Test Frequency - Once Per Year Or Every 10 000 m³
label | QA Record - IANZ Test Report
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - ATAP65/GAP65 - Testing for layor compaction - MDD
label | Standard, Drawing or Specification Reference - TNZ B/02: 2005 - 7.5, NZS 4402:1986 - 4.1.3 (Original detail was concrete blinding but changed by site to GAP 65 for easier bulidability
label | Construction Activity Description, Test Type and Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | ○ Average MDD 95% with a minimum of 92%.
label | Test Frequency - Once Per Year Or Every 5 000 m³
label | QA Record - IANZ Test Report
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Reinforcing Steel
label | Standard, Drawing or Specification Reference - 24-178_FC_201124
label | Construction Activity Description, Test Type and Acceptance Criteria - Supplied by pre-cast sub contractor as per drawing 24-178_FC_201124. Original detail was insitu but all work will be pre-cast.
label | Test Frequency - Once
label | QA Record - Mill Certificates & Shop Drawing Approval
label | DNZ Engineer - S
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Tactile Indicators
label | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction, FP009 Pram Crossing, 3235599-SP03-CA-1001 - Rev 1, Note 11
label | Construction Activity Description, Test Type and Acceptance Criteria - 300mm x 300mm x 60mm thick yellow anti-slip will be installed in the insitu stitch pour section.
label | Test Frequency - Once
label | QA Record - MDS & Approval
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Tactile Cement Blinding
label | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction, FP009 Pram Crossing, 3235599-SP03-CA-1001 - Rev 1, Note 12
label | Construction Activity Description, Test Type and Acceptance Criteria - Minimum 50 Mpa cement to be used according to supplier installations.
label | Test Frequency - Once
label | QA Record - MDS & Approval
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Joint Filler
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1025 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - Sika BlackSeal-1 Bitumionous joint filler or alternativly approved material.
label | Test Frequency - Once
label | QA Record - MDS & Approval
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Moddex Handrail
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1024 - Rev 1, 3235599-SP03-CA-1025 - Rev 1, Note 1.11
label | Construction Activity Description, Test Type and Acceptance Criteria - Moddex AR10 or Similar approved handrail.
label | Test Frequency - Once
label | QA Record - PS1 & Approval
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | 3 - CONSTRUCTION ACTIVITIES
checkpoint | 3.1 - Staircase set out and excavation to subgrade
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1024 - Rev 1, 746-22-052-PS Page 9 Table 1
label | Construction Activity Description, Test Type and Acceptance Criteria - Excavated as per IFC long section.
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Installation of benching
label | Standard, Drawing or Specification Reference - As Per CAN 033
label | Construction Activity Description, Test Type and Acceptance Criteria - Installation of benching for backfill of GAP 65 as per CAN 033
label | Test Frequency - Once
label | QA Record - Photos
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Subgrade Testing (Scala)
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1025 - Rev 1, Note 2.3a, 746-22-052-PS Page 9 Table 1
label | Construction Activity Description, Test Type and Acceptance Criteria - If clay based material is encountered - ensure subgrade has a minimum CBR of 3
label | ○ Test to a depth to 1m, not less than 3 blows per 150mm for CBR 3.5% and 3 blows per 200mm for CBR 2%.
label | Test Frequency - 1 per unit
label | QA Record - Scala Test Results, CBR of 3
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Undercut (If required)
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1025 - Rev 1, Note 2.3c, 746-22-052-PS Page 10 Table 2, NZS 4407:2015 4.1.2
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to subgrade undercutting, the Engineer shall confirm the extent and depth of subgrade undercut.
label | ○ Replace with compacted AP/GAP 65, compact to a minimum 95% MDD.
label | ○ Minimum two NDM tests per footing location.
label | Test Frequency - As required
label | QA Record - NDM Results
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Precast Units Pre-Pour
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1024 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - Supplier to fabricate precast units as per the approved shop drawings.
label | ○ Pre-Pour inspection to be completed by DNZ and BECA Representative.
label | Test Frequency - Every Unit
label | QA Record - Supplier QA Report, Concrete Test Results, Mill Certificates
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Precast Units Post-Pour
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1024 - Rev 1
label | Construction Activity Description, Test Type and Acceptance Criteria - Before site delivery, a post-pour inspection must be completed by the DNZ Engineer or Precast Supplier to check for any defects and to confirm that the exposed aggregate finish meets the design intent.
label | Test Frequency - Every Unit
label | QA Record - Supplier QA Report, Photos
label | DNZ Engineer - I
checkpoint | 3.7 - Insitu Stitch Works
label | Standard, Drawing or Specification Reference - 24-178_FC_201124, 3235599-SP03-CA-1031
label | Construction Activity Description, Test Type and Acceptance Criteria - Required at the top and the bottom of stairs.
label | ○ As per RFI 012 - Staircase Detail.
label | ○ Starter bars will project into the top landing only. Starter bars from the precast section shall be lapped with DH12 bars which extend (and terminate with cover) to the end of the insitu portion of the stairs landing.
label | ○ Cover of reinforcement will be checked with minimum 75mm cover at the base of reinforcement with 50mm cover on the side.
label | ○ Concrete will also be poured as per AT finish with exposed aggregate finish and 4kg/m³ of black oxide present.
label | ○ Precast to be shrink wrapped to allow 7 Days curing time.
label | Test Frequency - Every Stitch
label | QA Record - Concrete Dockets, Pre-pour checklist, Photos
label | DNZ Engineer - I
checkpoint | 3.8 - Place Tactilies
label | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction, FP009 Pram Crossing, 3235599-SP03-CA-1001 - Rev 1, Note 11
label | Construction Activity Description, Test Type and Acceptance Criteria - Note that per CAN 2, the middle landing of staircases will not have tactiles. Only the pre-cast units that will be installed on top and bottom landing.
label | ○ The horizontal tolerence should be between 3mm and 5mm. Vertical tolerance -10mm max.
label | ○ Orientation and set out shall be approved by the Engineer and or ATOC Representative prior to concrete placement.
label | ○ A one coat sealer with UV stabiliser is to be applied for maintenance and durability reasons
label | Test Frequency - Per installation
label | QA Record - Delivery Dockets, Photos
label | DNZ Engineer - H
label | Engineer's Rep - I
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
section | 4 - FINAL RECORDS
checkpoint | 4.1 - Construction Record Compilation
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Test Frequency - Once
label | QA Record - QA Records
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey Records
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Redline Drawings
label | Standard, Drawing or Specification Reference - IFC Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Test Frequency - Once
label | QA Record - IFC Mark-Up
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Defect, Snag and Punch List
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Test Frequency - If required
label | QA Record - Snag Register
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
textbox | NCR Reference
label | Test Frequency - When Required
label | QA Record - NCR Forms on InEight
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Quality Engineer - Nas Matar
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed By: Design Engineer - Daniel Cvitanich
label | Reviewed By: AT Project Manager - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Designers Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-007 Pier 3 & Pier 4 - Column and Headstock Construction | itp |  |  |  |  | DN1212-ITP-007 Pier 3 & Pier 4 - Column and Headstock Construction Rev2
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - Method Statement Development & Safety Analysis
label | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to Construction: Document Review
label | ○ Method Statement & JSEA
label | ○ Completed & signed by relevant authority
label | Test Frequency - Once
label | QA Record - Work pack (MS,JSEA,ITP)
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - IFC Drawings and Specification
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
label | ○ Works done in accordance with KiwiRail specification
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
checkpoint | 1.3 - Model
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - Model reviewed and confirmed with correct location; depth, height and orientation for column and headstock
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
checkpoint | 1.4 - Permit to Dig
label | Standard, Drawing or Specification Reference - DG-ZH-ST004 Ground Disturbance
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit issued each week
textbox | QA Record - FlowForm Permit Register/Permit Number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Lifting Permit
label | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Loads
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Prior to Construction when required
textbox | QA Record - FlowForm Permit Register/Permit Number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Working at Heights Permit
label | Standard, Drawing or Specification Reference - DG-ZH-ST042 Working at Height
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit issued each week
textbox | QA Record - FlowForm Permit Register/Permit Number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Permit to Load - Scaffolding
label | Standard, Drawing or Specification Reference - DG-DM-PR036 Temporary Works Procedure DG-DM-FM066
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit Issued prior to construction
label | QA Record - Temp Works Certification ITP
textbox | Permit to Load - PtL
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Concrete Mix Design
label | Standard, Drawing or Specification Reference - NZS 3104, SP-NIMT-ST-AD-00001, Section 2.3.10
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval.
label | ○ 50MPa @ 28 Day Compressive Strength.
label | Test Frequency - Once
textbox | QA Record - Mix Certification InEight Response
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Reinforcing Cages
label | Standard, Drawing or Specification Reference - Reinforcing Cage Drawings -
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Column Reinforcing IFC detail drawings.
label | ○ Shop Drawings shall be provided to the Engineer for review and approval.
label | ○ Note any changes undertaken to reinforcing to be captured as per item 4.2
label | Test Frequency - Every Reinforcement Cage
label | QA Record - Mill Test Certificates, Delivery Dockets
textbox | In Eight Response
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Formwork
label | Standard, Drawing or Specification Reference - Material Data Sheet, Temporary works drawings Piers 3 and 4.
label | Construction Activity Description, Test Type and Acceptance Criteria - Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules
label | ○ Rigid hollow-section steel frame
label | ○ High-grade hot dip galvinising for durability & long life
label | ○ Gang forms and lifting applications available
label | ○ Full range of safety features
label | ○ High Quality plywood
label | ○ 60kN/m2 permissible fresh concrete pressure
label | ○ To be captured on temp works drawings.
label | ○ Inclusive of structural shore loading for super structure
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - I
label | Designer Rep - R
checkpoint | 2.4 - Formwork Curing Agent
label | Standard, Drawing or Specification Reference - Material Data Sheet
label | Construction Activity Description, Test Type and Acceptance Criteria - Chemical curing agent.
label | ○ Concrete to be retained in shutter for at least 3 days, must obtain 30 Mpa prior to striking. Curing agent to be applied to the top to of concrete pour to act as a sealant.
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - R
label | Designer Rep - R
checkpoint | 2.5 - Reid Bars
label | Standard, Drawing or Specification Reference - Material Data Sheet, 3235599-SP03-ST-3002
label | Construction Activity Description, Test Type and Acceptance Criteria - RB25FNS Reidbar Steel Flange nut, as per noted 8 & 9 on drawing 3235599-SP03-ST-3002. Proposed epoxy will be per manufacturers recommendations to use C8 extreme epoxy. Superstructural couplers will be covered under PFS installation methodology and ITP. This is only for column / headstock construction.
label | Test Frequency - Once
textbox | QA Record - MDS, Delivery Dockets, mill certs
label | DNZ Engineer - R
label | Designer Rep - R
section | 3 - CONSTRUCTION ACTIVITIES
checkpoint | 3.1 - Column Set-Out
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3100, 3235599-SP03-ST-3150, 3235599-SP03-ST-3202
label | Construction Activity Description, Test Type and Acceptance Criteria - Before commencing formwork installation, survey set out column position based on drawings with RL supplied. Set out to include; Column centre, height and offset. Tollerances for insitu concrete pour taken from NZS 3109 table 5.2
label | Test Frequency - Each Column
label | QA Record - As-Built
label | DNZ Engineer - W
checkpoint | 3.2 - Formwork Installation
label | Standard, Drawing or Specification Reference - Material Data Sheet, Temporary works drawings Piers 3 and 4.
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Temporary works drawings for Piers 3 & 4. Inclusive of shoreloading requirements for the support of the bridge superstructure around Piers 3 and Piers 4.
label | Test Frequency - Each Structure
label | QA Record - Photos plus signed off Temporary works inspection of shuttering and formwork.
label | DNZ Engineer - W
checkpoint | 3.3 - Steel Cage Installation
label | Standard, Drawing or Specification Reference - As per detail Sheets for Pier 3 and Pier 4, 3235599-SP03-ST-3210
label | Construction Activity Description, Test Type and Acceptance Criteria - Cage installation will checked prior to placement to ensure that cage inspection requirements identified by BECA on 09/12/24 have been addressed and closed out prior to placement. Checks to be undertaken to confirm that lap lenths have been achieved during placement and survey to be undertaken to confirm posistion.
label | Test Frequency - Each Structure
label | QA Record - Photos
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Concrete Pre-Pour Inspection
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
label | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing cage as per IFC and shop drawings.
label | ○ Correct number of bars and grade.
label | ○ Correct steel lapping.
label | ○ Earthing and Earth terminal tested and inspected.
label | ○ Formwork installed as per the Temporary works drawings.
label | ○ Minimum 40mm cover achieved.
label | ○ Test specimens to be supplied by plant for every 75m³ for each shift of conncrete ordered.
label | Test Frequency - Each Structure
label | QA Record - Survey Check, Structural Engineer Inspection, MSQA SVR, Pre-Pour Checklist, Photos
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Concrete Pour
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
label | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete: 50MPa - Self Compacting Concrete - WS5010FS
label | ○ Cylinder test taken at supply Yard only.
label | ○ Spread Test to be completed on site prior to concrete pour.
label | ○ Target Spread Test - 680mm +/- 60mm
label | Test Frequency - Each Pour
label | QA Record - Delivery Dockets, Compressive Test Results, Photos
label | DNZ Engineer - H
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Stuctural Concrete Finish
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003, NZS 3114, NZS 3109
label | Construction Activity Description, Test Type and Acceptance Criteria - Non Visible Surface Finish - F1
label | ○ Visible Surface Finish - F5
label | Test Frequency - Each Structure
label | QA Record - Visual Inspection, Photos
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Concrete Curing
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3200
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete to be cured for a minimum of 3 days as per drawing st-3200, curing methodology will be formwork curing. Cylinder to be taken at 3 days to verify strength of 30 Mpa has been achieved prior to stripping of formwork.
label | Test Frequency - Each Structure
label | QA Record - Concrete strength results, concrete pour checksheet notifying date of formwork striking.
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Post Pour Inspection
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003, NZS 3114
label | Construction Activity Description, Test Type and Acceptance Criteria - Joint inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/ check dimeniosn of structure have acieved stipulated tollarences stated in drawing suite and NZS 3109 Must achieve F5 finish for surface.
label | Test Frequency - Each Headstock
label | QA Record - Visual Inspection, Photos
label | DNZ Engineer - H
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
section | 4 - FINAL RECORDS
checkpoint | 4.1 - As-Built
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Redline Mark-Up
label | Standard, Drawing or Specification Reference - IFC Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings mark-Up on ACC sheets dated and signed.
label | Test Frequency - Once
label | QA Record - IFC Drawings Mark-Up on ACC
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
textbox | NCR Reference
label | Test Frequency - Each NCR
label | QA Record - NCR forms on InEight
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Project Engineer - Grant Wallace
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed by: Quality Manager - Cordelia Girdler-Brown
label | Reviewed By: Design Engineer - Daniel Cvitanich
label | Reviewed By: AT Project Manager - Nel Werner
label | Reviewed By: AT Engineer to Contract - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Designers Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-008 Pier 1 & Pier 2 Headstock construction (Replacement) | itp |  |  |  |  | DN1212-ITP-008 Pier 1 & Pier 2 Headstock construction (Replacement) Rev2
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - Method Statement Development & Safety Analysis
label | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to Construction: Document Review
label | ○ Method Statement & JSEA
label | ○ Completed & signed by relevant authority
label | Test Frequency - Once
label | QA Record - Work pack (MS,JSEA,ITP)
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - IFC Drawings and Specification
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
label | ○ Works done in accordance with KiwiRail specification
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
checkpoint | 1.3 - Model
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - Model reviewed and confirmed with correct location; depth, height and orientation for column, headstock and stiarcase
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
checkpoint | 1.4 - Lifting Permit
label | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Loads
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Prior to Construction when required
textbox | QA Record - FlowForm Permit Register/Permit Number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Working at Heights Permit
label | Standard, Drawing or Specification Reference - DG-ZH-ST042 Working at Height
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit issued each week
textbox | QA Record - FlowForm Permit Register/Permit Number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Permit to Load - Scaffolding
label | Standard, Drawing or Specification Reference - DG-DM-PR036 Temporary Works Procedure DG-DM-FM066
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit Issued prior to construction
label | QA Record - Temp Works Certification ITP
textbox | Permit to Load - PtL
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Concrete Mix Design
label | Standard, Drawing or Specification Reference - NZS 3104, App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval.
label | ○ 50MPa @ 28 Day Compressive Strength.
label | Test Frequency - Once
textbox | QA Record - Mix Certification InEight Response
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Reinforcing Cages
label | Standard, Drawing or Specification Reference - Reinforcing Cage Drawings -
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Column Reinforcing IFC detail drawings.
label | ○ Shop Drawings shall be provided to the Engineer for review and approval.
label | ○ Note any changes undertaken to reinforcing to be captured as per item 4.2
label | Test Frequency - Every Reinforcment Cage
label | QA Record - Mill Test Certificates, Delivery Dockets
textbox | In Eight Response
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Formwork
label | Standard, Drawing or Specification Reference - Material Data Sheet, Temporary works drawings Piers 1 and 2.
label | Construction Activity Description, Test Type and Acceptance Criteria - Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules
label | ○ Rigid hollow-section steel frame
label | ○ High-grade hot dip galvinising for durability & long life
label | ○ Gang forms and lifting applications available
label | ○ Full range of safety features
label | ○ High Quality plywood
label | ○ 60kN/m2 permissible fresh concrete pressure
label | ○ To be captured on temp works drawings.
label | ○ Inclusive of structural shore loading for super structure
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - R
label | Designer Rep - R
checkpoint | 2.4 - Formwork Curing Agent
label | Standard, Drawing or Specification Reference - Material Data Sheet
label | Construction Activity Description, Test Type and Acceptance Criteria - Chemical curing agent.
label | ○ Concrete to be retained in shutter for at least 3 days, must obtain 30 Mpa prior to striking. Curing agent to be applied to the top to of concrete pour to act as a sealant. Not to be applied to top of headtock as type B constrcution Joint is required.)
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - R
label | Designer Rep - R
checkpoint | 2.5 - Reid Bars Products
label | Standard, Drawing or Specification Reference - Material Data Sheet, 3235599-SP03-ST-3002, CAN 010
label | Construction Activity Description, Test Type and Acceptance Criteria - RB25FNS Reidbar Steel Flange nut & RB25 Couplers as per noted 8 & 9 on drawing 3235599-SP03-ST-3002. Proposed epoxy will be per manufacturers recommendations to use C8 extreme epoxy. Superstructural couplers will be covered under PFS installation methodology and ITP. This is only for column / headstock construction.
label | Test Frequency - Once
textbox | QA Record - MDS, Delivery Dockets, mill certs
label | DNZ Engineer - R
label | Designer Rep - R
section | 3 - CONSTRUCTION ACTIVITIES
checkpoint | 3.1 - Setout
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3100
label | ○ 3235599-SP03-ST-3150
label | ○ 3235599-SP03-ST-3202
label | Construction Activity Description, Test Type and Acceptance Criteria - Before commencing formwork installation, survey set out column position based on drawings with RL supplied. Set out to include; Column centre, height and offset. Tollerances for insitu concrete pour taken from NZS 3109 table 5.2
label | Test Frequency - Each Headstock
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Formwork Installation
label | Standard, Drawing or Specification Reference - Material Data Sheet, Temporary works drawings Piers 1 and 2.
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Temporary works drawings for Piers 1 & 2. Inclusive of shoreloading requirements for the support of the bridge superstructure around Piers 1 and Piers 2.
label | Test Frequency - Each Headstock
label | QA Record - Photos plus signed off Temporary works inspection of shuttering and formwork.
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Steel Cage Installation
label | Standard, Drawing or Specification Reference - As per detail Sheets for Pier 1 and Pier 2, 3235599-SP03-ST-3210
label | Construction Activity Description, Test Type and Acceptance Criteria - Cage installation will checked prior to placement to ensure that cage inspection requirements identified by BECA on 09/12/24 have been addressed and closed out prior to placement. Checks to be undertaken to confirm that lap lenths have been achieved during placement and survey to be undertaken to confirm posistion.
label | Test Frequency - Each Headstock
label | QA Record - Photos
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Reidbar Product Installation
label | Standard, Drawing or Specification Reference - CAN 010
label | Construction Activity Description, Test Type and Acceptance Criteria - As per CAN 010 regarding the installation of pier imnterface couplers as per option 1
label | ○ Product to be installed as per manufacturers instructions with C8 extreme epoxy placed internally within coupler
label | Test Frequency - Each Headstock
label | QA Record - Photos of Epoxy and coupler installation
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Concrete Pre-Pour Inspection
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
label | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing cage as per IFC and shop drawings.
label | ○ Correct number of bars and grade.
label | ○ Correct steel lapping.
label | ○ Earthing and Earth terminal tested and inspected.
label | ○ Formwork installed as per the Temporary works drawings.
label | ○ Minimum 40mm cover achieved.
label | ○ Test specimens to be supplied by plant for every 75m³ for each shift of conncrete ordered.
label | Test Frequency - Each Headstock
label | QA Record - Survey Check, Structural Engineer Inspection, MSQA SVR, Pre-Pour Checklist, Photos
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Concrete Pour
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
label | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete: 50MPa - Self Compacting Concrete - WS5010FS
label | ○ Cylinder test taken at supply Yard only.
label | ○ Spread Test to be completed on site prior to concrete pour.
label | ○ Target Spread Test - 680mm +/- 60mm
label | Test Frequency - Each Headstock
label | QA Record - Delivery Dockets, Compressive Test Results, Photos
label | DNZ Engineer - H
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Surface Finish/Construction Joint
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3200, NZS 3114
label | Construction Activity Description, Test Type and Acceptance Criteria - F1 Surface Finish - Concealed Formed faces
label | ○ F5 Surface Finish - Exposed and Visible Faces
label | ○ Type B Construction Joint to be installed on top of headstock.
label | ○ Insitu Concrete Stich Pour on Pier 1 - surface to have U2 broomed finish for slip resitstance in both rain and dry as per NZBC D1 requirements.
label | Test Frequency - Each Headstock
label | QA Record - Visual Inspection, Photos
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Concrete Curing
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3200
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete to be cured for a minimum of 3 days as per drawing st-3200, curing methodology will be formwork curing. Cylinder to be taken at 3 days to verify strength of 30 Mpa has been achieved prior to stripping of formwork.
label | Test Frequency - Each Headstock
label | QA Record - Concrete strength results, concrete pour checksheet notifying date of formwork striking.
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Post Pour Inspection
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003, NZS 3114
label | Construction Activity Description, Test Type and Acceptance Criteria - Joint inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/ check dimeniosn of structure have acieved stipulated tollarences stated in drawing suite and NZS 3109
label | Test Frequency - Each Headstock
label | QA Record - Visual Inspection, Photos
label | DNZ Engineer - H
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
section | 4 - FINAL RECORDS
checkpoint | 4.1 - As-Built
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Redline Mark-Up
label | Standard, Drawing or Specification Reference - IFC Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings mark-Up on ACC sheets dated and signed.
label | Test Frequency - Once
label | QA Record - IFC Drawings Mark-Up on ACC
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
textbox | NCR Reference
label | Test Frequency - Each NCR
label | QA Record - NCR forms on InEight
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Project Engineer - Grant Wallace
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed by: Quality Manager - Cordelia Girdler-Brown
label | Reviewed By: Design Engineer - Daniel Cvitanich
label | Reviewed By: AT Project Manager - Werner Nel
label | Reviewed By: AT Engineer to Contract - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Designers Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-009 Bridge Abutment | itp |  |  |  |  | DN1212-ITP-009 Bridge Abutment Rev3
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - Method Statement Development & Safety Analysis
label | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to Construction: Document Review
label | ○ Method Statement & JSEA
label | ○ Completed & signed by relevant authority
label | Test Frequency - Once
label | QA Record - Work pack (MS,JSEA,ITP)
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - IFC Drawings and Specification
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
label | ○ Works done in accordance with KiwiRail specification
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
checkpoint | 1.3 - Model
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - Model reviewed and confirmed with correct location; depth, height and orientation for column, headstock and stiarcase
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
checkpoint | 1.4 - Permit to Dig
label | Standard, Drawing or Specification Reference - DG-ZH-ST004 Ground Disturbance
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit issued each week
textbox | QA Record - FlowForm Permit Register/Permit Number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Lifting Permit
label | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Loads
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Prior to Construction when required
textbox | QA Record - FlowForm Permit Register/Permit Number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Concrete Mix Design
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 2.1
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval.
label | ○ 40MPa @ 28 Day Compressive Strength.
label | Test Frequency - Once
label | QA Record - Mix Certification, Plant Certification
textbox | InEight Approval
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Reinforcing Cage
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note: 2.3, 3235599-SP03-ST-3002, AS/NZS 4671
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Abutment Reinforcing IFC detail drawing.
label | ○ Shop Drawings shall be provided to the Engineer for review and approval.
label | ○ Grade 500E MA.
label | Test Frequency - Once
label | QA Record - Mill Test Certificates, Delivery Dockets
textbox | Shop Drawing Approval
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Formwork
label | Standard, Drawing or Specification Reference - MDS, Temporary works drawings Abutment A
label | Construction Activity Description, Test Type and Acceptance Criteria - Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules
label | ○ Full range of safety features
label | ○ High Quality plywood to provide
label | ○ F5 finish.
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - I
label | Designer Rep - R
checkpoint | 2.4 - Formwork Curing Agent
label | Standard, Drawing or Specification Reference - MDS
label | Construction Activity Description, Test Type and Acceptance Criteria - Chemical curing agent.
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - R
label | Designer Rep - R
checkpoint | 2.5 - RCC65
label | Standard, Drawing or Specification Reference - MDS
label | Construction Activity Description, Test Type and Acceptance Criteria - Recycled crushed concrete 65.
label | Test Frequency - Once
textbox | QA Record - Test Reports InEight Approval
label | DNZ Engineer - R
label | Designer Rep - R
checkpoint | 2.6 - Threaded M20 Bolts
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 1.5
label | Construction Activity Description, Test Type and Acceptance Criteria - Grade 316 (A4) SS M20 uplift restraint hold down bolts, to have UTS of 700MPa.
label | Test Frequency - Once
label | QA Record - Mill Certificates, Delivery Dockets
label | DNZ Engineer - I
label | Designer Rep - R
checkpoint | 2.7 - Geotextile (Bidim)
label | Standard, Drawing or Specification Reference - MDS
label | Construction Activity Description, Test Type and Acceptance Criteria - Geotextile A29 or similar approved material.
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - R
label | Designer Rep - R
checkpoint | 2.8 - Sika Rugasol C
label | Standard, Drawing or Specification Reference - NZS 3104, 3235599-SP03-ST-3002, Section 2.1
label | Construction Activity Description, Test Type and Acceptance Criteria - Sika Rugasol C to be used for forming construction joint.
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - R
label | Designer Rep - R
checkpoint | 2.9 - Bearing
label | Standard, Drawing or Specification Reference - AS5100.4 NZTA Bridge Manual, 3235599-SP03-ST-3252: Section 2
label | Construction Activity Description, Test Type and Acceptance Criteria - All details and dimensions to be confirmed upon final bearing selection, including coordination of hold down bolts with the bearing supplier. Bearing shall be replaceable, bearing shall have temporary transit plates that hold the bearing in the preset position ready for installation. Bearings shall be level in both directions after making allowance for girder camber if any.
label | Test Frequency - Once
textbox | QA Record - Bearing Certification InEight Approval
label | DNZ Engineer - R
label | Engineer's Rep - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
section | 3 - CONSTRUCTION ACTIVITIES
checkpoint | 3.1 - Survey Setout
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3100
label | ○ 3235599-SP03-ST-3150
label | ○ 3235599-SP03-ST-3202
label | Construction Activity Description, Test Type and Acceptance Criteria - Survey set out Abutment position based on model. Set out to include; Centre of abutment, height and offsets. Tollerances for insitu concrete pour taken from NZS 3109 table 5.2
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - W
checkpoint | 3.2 - Excavation
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250
label | Construction Activity Description, Test Type and Acceptance Criteria - Excavtion to be 1000mm below existing platform level.
label | ○ Insitu subgrade material at the base of undercut shall be inspected by the Engineer to confirm design assuptions prior to backfilling.
label | Test Frequency - Once
label | QA Record - Photos
label | DNZ Engineer - I
checkpoint | 3.3 - Subgrade Testing
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 3.2
label | Construction Activity Description, Test Type and Acceptance Criteria - Minimum subgrade shear strength of 40kPa.
label | Test Frequency - Once
label | QA Record - Shear Vane Test Results, Photos
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Subgrade Undercut (If required)
label | Standard, Drawing or Specification Reference - 746-24-847-AC Tech Spec Section C0302.4.2, 3235599-SP03-ST-3250: Note 3.2
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to subgrade undercutting, the Engineer shall confirm the extent of subgrade undercut and fill requirements.
label | ○ Undercut area to be wrampped in A29 and backfilled and compacted in layers of 200mm RCC65.
label | Test Frequency - Once
label | QA Record - As-Built, Photo
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Backfill & Compaction
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250, 746-24-847-AC Tech Spec Section C0302.4.3,4&5
label | Construction Activity Description, Test Type and Acceptance Criteria - Subgrade to be covered with A29 or similar approved Geotextile.
label | ○ Backfill to be in maximum of 200mm layers.
label | ○ Each lift to be tested to 95% MDD.
label | Test Frequency - Once
label | QA Record - NDM Test Results, Photos
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Formwork Installation
label | Standard, Drawing or Specification Reference - MDS
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Temporary works drawings for Abutment A and shop drawings.
label | Test Frequency - Once
label | QA Record - Pre-Pour Checksheet, Photos
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Reinforcing Cage Installation
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250
label | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per IFC detail drawing.
label | Test Frequency - Once
label | QA Record - Pre-Pour Checksheet, Photos
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Girder Installation on Temporary shore loading
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250
label | Construction Activity Description, Test Type and Acceptance Criteria - Shore loading sign off by the Temporary Works Engineer.
label | ○ Surveyor as-built for girder installation.
label | Test Frequency - Per Girder
label | QA Record - As-Built, PT Load Certificate
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - M20 Threaded Rods Installation
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 1.5
label | Construction Activity Description, Test Type and Acceptance Criteria - M20 Grade 316 threaded rod with SS nut, lock nut and nylon washer to be installed in the reinforcing cage, and to have 250mm minimum embedment into abutment.
label | Test Frequency - Once
label | QA Record - Pre-Pour Checksheet, Photos
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Concrete Pre-Pour Inspection
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250
label | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing cage as per IFC and shop drawings.
label | ○ Correct number of bars and grade.
label | ○ Correct steel lapping.
label | ○ Minimum cover to be 40mm or 75mm if casted directly on exposed earth.
label | Test Frequency - Once
label | QA Record - Survey Check, Structural Engineer Inspection, MSQA SVR, Pre-Pour Checksheet, Photos
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Concrete Pour
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 2.1
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete: 40MPa
label | ○ 28 Days Concrete Compressive Strength.
label | Test Frequency - Each Pour
label | QA Record - Delivery Dockets, Compressive Test Results, Photos
label | DNZ Engineer - H
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Abutment Surface Finish
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 2.4
label | Construction Activity Description, Test Type and Acceptance Criteria - All surfaces subjected to foot traffic to have F5 finish (exposed aggregate finish).
label | Test Frequency - Every Section
label | QA Record - Photos
label | DNZ Engineer - I
label | Designer Rep - I
section | 4 - FINAL RECORDS
checkpoint | 4.1 - As-Built
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Redline Mark-Up
label | Standard, Drawing or Specification Reference - IFC Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings mark-Up on ACC sheets dated and signed.
label | Test Frequency - Once
label | QA Record - IFC Drawings Mark-Up on ACC
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
textbox | NCR Reference
label | Test Frequency - Each NCR
label | QA Record - NCR forms on InEight
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Project Engineer - Moses Kaufanga
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed by: Quality Mgr./Eng. - Nas Matar
label | Reviewed By: Design Engineer - Daniel Cvitanich
label | Reviewed By: AT Project Manager - Werner Nel
label | Reviewed By: AT Engineer to Contract - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Designers Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-012 Pier 5 - Column and Headstock Construction | itp |  |  |  |  | DN1212-ITP-012 Pier 5 - Column and Headstock Construction Rev1
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - Method Statement Development & Safety Analysis
label | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to Construction: Document Review
label | ○ Method Statement & JSEA
label | ○ Completed & signed by relevant authority
label | Test Frequency - Once
label | QA Record - Work pack (MS,JSEA,ITP)
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - IFC Drawings and Specification
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
label | ○ Works done in accordance with KiwiRail specification
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
checkpoint | 1.3 - Permit to Dig
label | Standard, Drawing or Specification Reference - DG-ZH-ST004 Ground Disturbance
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit issued each week
textbox | QA Record - FlowForm Permit Register/Permit Number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Lifting Permit
label | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Loads
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Prior to Construction when required
textbox | QA Record - FlowForm Permit Register/Permit Number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Working at Heights Permit
label | Standard, Drawing or Specification Reference - DG-ZH-ST042 Working at Height
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit issued each week
textbox | QA Record - FlowForm Permit Register/Permit Number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Permit to Load - Scaffolding
label | Standard, Drawing or Specification Reference - DG-DM-PR036 Temporary Works Procedure DG-DM-FM066
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit Issued prior to construction
label | QA Record - Temp Works Certification ITP
textbox | Permit to Load - PtL
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Concrete Mix Design
label | Standard, Drawing or Specification Reference - NZS 3104, SP-NIMT-ST-AD-00001, Section 2.3.10
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval.
label | ○ 40MPa @ 28 Day Compressive Strength.
label | Test Frequency - Once
textbox | QA Record - Mix Certification InEight Response
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Reinforcing Cages
label | Standard, Drawing or Specification Reference - Reinforcing Cage Drawings - Pier 5 datail sheet
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Column Reinforcing IFC detail drawings.
label | ○ Shop Drawings shall be provided to the Engineer for review and approval.
label | ○ Note any changes undertaken to reinforcing to be captured as per item 4.2
label | Test Frequency - Every Reinforcement Cage
label | QA Record - Mill Test Certificates, Delivery Dockets
textbox | In Eight Response
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Formwork
label | Standard, Drawing or Specification Reference - Material Data Sheet
label | ○ Temporaray works drawings Piers 3 and 4.
label | Construction Activity Description, Test Type and Acceptance Criteria - Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules
label | ○ Rigid hollow-section steel frame
label | ○ High-grade hot dip galvinising for durability & long life
label | ○ Gang forms and lifting applications available
label | ○ Full range of safety features
label | ○ High Quality plywood
label | ○ 60kN/m2 permissible fresh concrete pressure
label | ○ To be captured on temp works drawings.
label | ○ Inclusive of structural shore loading for super structure
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - I
label | Designer Rep - R
checkpoint | 2.4 - Formwork Curing Agent
label | Standard, Drawing or Specification Reference - Material Data Sheet
label | Construction Activity Description, Test Type and Acceptance Criteria - Chemical curing agent.
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - R
label | Designer Rep - R
checkpoint | 2.6 - Reid Bars Products
label | Standard, Drawing or Specification Reference - Material Data Sheet, 3235599-SP03-ST-3002
label | Construction Activity Description, Test Type and Acceptance Criteria - RB 25 Couplers & RB25FNS Reidbar Steel Flange nut, as per noted 8 & 9 on drawing 3235599-SP03-ST-3002. Proposed epoxy will be per manufacturers recommendations to use C8 extreme epoxy. Superstructural couplers will be covered under PFS installation methodology and ITP. This is only for column / headstock construction.
label | Test Frequency - Once
textbox | QA Record - MDS, Delivery Dockets, mill certs
label | DNZ Engineer - R
label | Designer Rep - R
section | 3 - CONSTRUCTION ACTIVITIES
checkpoint | 3.1 - Column Set-Out
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3100
label | ○ 3235599-SP03-ST-3150
label | ○ 3235599-SP03-ST-3202
label | Construction Activity Description, Test Type and Acceptance Criteria - Before commencing formwork installation, survey set out column position based on drawings with RL supplied. Set out to include; Column centre, height and offset. Tollerances for insitu concrete pour taken from NZS 3109 table 5.2
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - W
checkpoint | 3.2 - Formwork Installation
label | Standard, Drawing or Specification Reference - Material Data Sheet, Temporaray works drawings Pier 5
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Temporaray works drawings for Piers 5. Inclusive of shoreloading requirements for the support of the bridge superstructure around Pier 5.
label | Test Frequency - Once
label | QA Record - Photos plus signed off temporaray works inspection of shuttering and formwork.
label | DNZ Engineer - W
checkpoint | 3.3 - Steel Cage Installation
label | Standard, Drawing or Specification Reference - As per detail Sheets for Pier 5, 3235599-SP03-ST-3210
label | Construction Activity Description, Test Type and Acceptance Criteria - Cage installation will be checked prior to placement to ensure that cage inspection requirements identified by BECA and DNZ will install cage and secure with RB 25 couplers that will be installed between the pier and pile starter bars.
label | ○ Couplers will be installed and epoxied in place using manufac turer recommended C8 extreme epoxy and photos of coupler will be supplied a spart of installation QA. Surveyors will also survey cage to ensure verticality and correct height of steel has been achieved prior to epoxying.
label | Test Frequency - Once
label | QA Record - Photos,
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Concrete Pre-Pour Inspection
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
label | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing cage as per IFC and shop drawings.
label | ○ Correct number of bars and grade.
label | ○ Correct steel lapping.
label | ○ Earthing and Earth terminal tested and inspected.
label | ○ Formwork installed as per the temporaray works drawings.
label | ○ Minimum 40mm cover achieved.
label | ○ Test specimens to be supplied by plant for every 75m³ for each shift of conncrete ordered.
label | Test Frequency - Once
label | QA Record - Survey Check, Structural Engineer Inspection, MSQA SVR, Pre-Pour Checklist, Photos
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Concrete Pour
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
label | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete: 40MPa - Self Compacting Concrete - WS4010FS
label | ○ Cylinder test taken at supply Yard only.
label | ○ Spread Test to be completed on site prior to concrete pour.
label | ○ Target Spread Test - 680mm +/- 60mm
label | Test Frequency - Once
label | QA Record - Delivery Dockets, Compressive Test Results, Photos
label | DNZ Engineer - H
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Structural Surface Finish
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003, NZS 3114, NZS 3109
label | Construction Activity Description, Test Type and Acceptance Criteria - F1 Surface Finish - Concealed Formed faces
label | ○ F5 Surface Finish - Exposed and Visible Faces
label | Test Frequency - Each joint and surface.
label | QA Record - Visual Inspection, Photos, cylinders for blinding
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Concrete Curing
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3200
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete to be cured for a minimum of 3 days as per drawing st-3200, curing methodology will be formwork curing. Cylinder to be taken at 3 days to verify strength of 30 Mpa has been achieved prior to stripping of formwork if required. Intention is to leave formwork on to 7 days max if possible.
label | Test Frequency - Once
label | QA Record - Concrete strength results, concrete pour checksheet notifying date of formwork striking.
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Post Pour Inspection
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003, NZS 3114
label | Construction Activity Description, Test Type and Acceptance Criteria - Joint inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/ check dimeniosn of structure have acieved stipulated tollarences stated in drawing suite and NZS 3109
label | Test Frequency - Once
label | QA Record - Visual Inspection, Photos
label | DNZ Engineer - H
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
section | 4 - FINAL RECORDS
checkpoint | 4.1 - As-Built
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Redline Mark-Up
label | Standard, Drawing or Specification Reference - IFC Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings mark-Up on ACC sheets dated and signed.
label | Test Frequency - Once
label | QA Record - IFC Drawings Mark-Up on ACC
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
textbox | NCR Reference
label | Test Frequency - Each NCR
label | QA Record - NCR forms on InEight
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Project Engineer - Grant Wallace
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed by: Quality Manager - Cordelia Girdler-Brown
label | Reviewed By: Design Engineer - Daniel Cvitanich
label | Reviewed By: AT Project Manager - Werner Nel
label | Reviewed By: AT Engineer to Contract - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Designers Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-013 Pre Cast Cantilever Deck Fabrication | itp |  |  |  |  | DN1212-ITP-013 Pre Cast Cantilever Deck Fabrication Rev1
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - IFC Drawings and Specification
label | Standard, Drawing or Specification Reference - IFC Drawings, Wilco Shop Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per the instruction.
label | ○ Work is done in accordance with IFC design and specification.
label | Test Frequency - Once
textbox | QA Record - Reviewed Shop Drawings InEight Reference
label | DNZ Engineer - R
label | Wilco PM - R
label | Designer Rep - R
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Concrete Mix Design
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3001 - PROPOSED ACCESS RAMP- GENERAL NOTES
label | ○ 3235599-SP03-ST-3002 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET1 OF 2)
label | ○ 3235599-SP03-ST-3003 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET2 OF 2)
label | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval.
label | ○ 50MPa @ 28 Day Compressive Strength.
label | ○ Maximum Aggregate Size 20mm.
label | ○ Maximum Water/Cement Ratio 0.43 (drawing/ notes state 40 Mpa but concrete increased to 50 Mpa mix to reach target strength quicker for demoulding).
label | Test Frequency - Once
label | QA Record - Mix Certificate, Plant Certification
textbox | InEight Reference Approval
label | DNZ Engineer - R
label | Wilco PM - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Reinforcement
label | Standard, Drawing or Specification Reference - IFC Reinforcement Detail Sheets
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Cantilever Reinforcement shop drawing detail.
label | ○ Shop Drawings shall be provided to the Engineer for review.
label | ○ Grade 500.
label | Test Frequency - Once
label | QA Record - Mill Test Certificates, Delivery Dockets, Wilco Shop Drawings
textbox | InEight Reference
label | DNZ Engineer - R
label | Wilco PM - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Lifting And Handling
label | Standard, Drawing or Specification Reference - REIDS Lifting Manual
label | Construction Activity Description, Test Type and Acceptance Criteria - Lifting Design added to the shop drawings.
label | Test Frequency - Once
label | QA Record - Lift Design Approval
label | DNZ Engineer - R
label | Wilco PM - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Curing Method
label | Standard, Drawing or Specification Reference - C0602.7, NZS 3109:1997 Section 7
label | Construction Activity Description, Test Type and Acceptance Criteria - Curing method shall be by wrapping of the precast concrete with shrink wrapping for a minimum of 7 days.
label | Test Frequency - Once
label | QA Record - Photos
textbox | InEight Reference
label | DNZ Engineer - H
label | Wilco PM - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Cast in Plate
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
label | Construction Activity Description, Test Type and Acceptance Criteria - Stainless Steel:
label | 1) M10 SS Grade 316 Bolts with Nylon Washers
label | 2) M10 SS Grade 316 TCM threaded inserts
label | Hot Dipped Galvanised:
label | 1) 450 x 10mm thick HDG 600 plate with approved surface treatment. Colour matched to concrete.
label | Test Frequency - Once
label | QA Record - Material Certificate & Photos
label | DNZ Engineer - R
label | Wilco PM - R
section | 3 - PRE-CAST FABRICATION ACTIVITIES
checkpoint | 3.1 - Mould assembly / set-up
label | Standard, Drawing or Specification Reference - Approved Shop Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - Mould shall be set-up as per IFC Shop Drawings.
label | Test Frequency - Once
label | QA Record - Wilco QA Report
label | DNZ Engineer - W
label | Wilco PM - I
label | Designer Rep - W
checkpoint | 3.2 - Reo Assembly & Placement
label | Standard, Drawing or Specification Reference - Approved Shop Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcement cage assembled & installed as per IFC Shop Drawings.
label | ○ Threaded rods shall be wrapped with 2 layers of Denso tape at the interface.
label | ○ Stainless steel 50EA6 Studs to have 100mm embedment and to be flush with the surface of headstock.
label | Test Frequency - Once
label | QA Record - Wilco QA Report
label | DNZ Engineer - W
label | Wilco PM - I
label | Designer Rep - W
checkpoint | 3.3 - Corners and edges
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200
label | ○ 3235599-SP03-ST-3001
label | ○ 3235599-SP03-ST-3002
label | ○ 3235599-SP03-ST-3003
label | Construction Activity Description, Test Type and Acceptance Criteria - All external corners and edges to concrete surfaces shall have a 20x20mm CHAMFER unless shown otherwise on the drawings.
label | Test Frequency - Once
label | QA Record - Wilco QA Report
label | DNZ Engineer - W
label | Wilco PM - I
label | Designer Rep - I
checkpoint | 3.4 - Dimensional Tolerances
label | Standard, Drawing or Specification Reference - NZS 3109: 1997, Table 5.1
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Table 5.1 – Tolerance for precast components NZS 3109: 1997.
label | Test Frequency - Once
label | QA Record - Wilco QA Report
label | DNZ Engineer - W
label | Wilco PM - I
label | Designer Rep - W
checkpoint | 3.5 - Cast-in Installation & Inspection
label | Standard, Drawing or Specification Reference - Approved Shop Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - Set-up as per IFC Shop Drawings.
label | Test Frequency - Once
label | QA Record - Wilco QA Report
label | DNZ Engineer - W
label | Wilco PM - I
label | Designer Rep - W
checkpoint | 3.6 - Approval to cast (Pre-Pour)
label | Standard, Drawing or Specification Reference - Approved Shop Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - DNZ/Beca to be notified of the cast date for a Pre-pour inspection.
label | ○ PS3 to be supplied by Wilson.
label | Test Frequency - Once
label | QA Record - Wilco QA Report, DNZ/Beca Pre-Pour Inspection, Photos
label | DNZ Engineer - I
label | Wilco PM - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Concrete Testing
label | Standard, Drawing or Specification Reference - NZS3104:2021
label | Construction Activity Description, Test Type and Acceptance Criteria - 3 x Cylinders for 28 Days Compressive Strength Testing.
label | Test Frequency - Once
label | QA Record - One set of samples, 28 Days Concrete Compressive Results
label | DNZ Engineer - R
label | Wilco PM - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Concrete Placement and Finish
label | Standard, Drawing or Specification Reference - NZS 3114:1987
label | Construction Activity Description, Test Type and Acceptance Criteria - 50Mpa Concrete.
label | ○ Finish as per Shop Drawings.
label | ○ U3/F5 finish class.
label | ○ Tolerance on Cover: -0, +5mm
label | Test Frequency - Once
label | QA Record - Wilco QA Report, Concrete Dockets
label | DNZ Engineer - W
label | Wilco PM - I
label | Designer Rep - W
checkpoint | 3.9 - Demoulding
label | Standard, Drawing or Specification Reference - Reid Lifting Manual, Reid Lift Plan
label | Construction Activity Description, Test Type and Acceptance Criteria - Minimum demoulding strength achieved.
label | ○ Lift plan shall be followed.
label | Test Frequency - Once
label | QA Record - Lift Plan, Compressive strength Test Results, Reid lifting manual, Reid Lift Plan
label | DNZ Engineer - R
label | Wilco PM - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Post Pour Inspection
label | Standard, Drawing or Specification Reference - Approved Shop Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - Cantilever to be inspected to ensure are free of defects prior to site delivery.
label | ○ Confirmation that F5 finish has been acieved for the pre cast unit and the U5 broom finish has been applied to the top deck as per shop drawings.
label | Test Frequency - Once
label | QA Record - Wilco QA Report
label | DNZ Engineer - I
label | Wilco PM - I
label | Designer Rep - I
checkpoint | 3.11 - Unit Marking
label | Standard, Drawing or Specification Reference - Approved Shop Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - Product marked with the correct information. (Date of cast, Unit ID, Weight)
label | Test Frequency - Once
label | QA Record - ID Label
label | DNZ Engineer - R
label | Wilco PM - I
label | Designer Rep - R
checkpoint | 3.12 - Curing
label | Standard, Drawing or Specification Reference - NZS 3101.1&2:2006
label | Construction Activity Description, Test Type and Acceptance Criteria - Standard 7 days curing with concrete unit remaining shrink wrapped to provide membrane for curing.
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
label | Wilco PM - I
label | Designer Rep - R
section | 4 - FINAL RECORDS
checkpoint | 4.1 - Compiled QA
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Quality Assurance documents are compiled as per the ITP acceptance criteria.
label | Test Frequency - Once
label | QA Record - Wilco QA Report
label | DNZ Engineer - R
label | Wilco PM - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Producer Statement (PS3)
label | Standard, Drawing or Specification Reference - NZS 3916:2013 Schedule 6
label | Construction Activity Description, Test Type and Acceptance Criteria - Completed and signed PS3 by Wilco Confirming Compliance with the IFC drawings and specification for the fabrication of Cantilever Deck.
label | Test Frequency - Once
label | QA Record - Signed PS3
label | DNZ Engineer - R
label | Wilco PM - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
textbox | NCR Reference
label | Test Frequency - Each NCR
label | QA Record - NCR forms on InEight
label | DNZ Engineer - H
label | Wilco PM - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Project Engineer - Grant Wallace
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed by: Quality Eng./Mgr. - Nas Matar
label | Reviewed By: Design Engineer - Daniel Cvitanich
label | Reviewed By: AT Project Manager - Werner Nel
label | Reviewed By: AT Engineer to Contract - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Designers Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-014 Pier 1 Cantilever Deck Install & Stitch | itp |  |  |  |  | DN1212-ITP-014 Pier 1 Cantilever Deck Install & Stitch Rev1
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - IFC Drawings and Specification
label | Standard, Drawing or Specification Reference - IFC Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - Work is done in accordance with IFC design and specification.
label | Test Frequency - Once
label | QA Record - DN1212-ITP-013
label | DNZ Engineer - R
label | Engineers Rep - R
label | Designer Rep - R
checkpoint | 1.2 - Method Statement Development & Safety Analysis
label | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
label | Test Frequency - Once
label | QA Record - Method Statement & JSEA Completed & signed by relevant authority
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Model
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - Model reviewed and confirmed with correct location; depth, height and orientation
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Concrete Mix Design (Stitch)
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3001 - PROPOSED ACCESS RAMP- GENERAL NOTES 3235599-SP03-ST-3002 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET1 OF 2) 3235599-SP03-ST-3003 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET2 OF 2) App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval. 50MPa @ 28 Day Compressive Strength. Maximum Water/Cement Ratio 0.43 (drawing/ notes state 40 Mpa but concrete increased to 50 Mpa mix to reach target strength quicker). Samples to be taken at 1, 2,3, 7 and 28 day strengths.
label | Test Frequency - Once
label | QA Record - Mix Certificate Plant Certification InEight Reference Approval ..................
label | DNZ Engineer - R
label | Engineers Rep - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Reinforcement (corbel steel and Stitch pour Steel)
label | Standard, Drawing or Specification Reference - IFC Reinforcement Detail Sheets
label | Construction Activity Description, Test Type and Acceptance Criteria - As per NTC 058 Installation of DH12 bars on precast edges to create corbels.. Grade 500. Also includes the structural steel required for the stitch pour.
label | Test Frequency - Once
label | QA Record - Mill Test Certificates Delivery Dockets InEight Reference ...................
label | DNZ Engineer - R
label | Engineers Rep - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Formwork
label | Standard, Drawing or Specification Reference - Material Data Sheet Temporary works drawings Piers 1 and 2.
label | Construction Activity Description, Test Type and Acceptance Criteria - Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules Rigid hollow-section steel frame High-grade hot dip galvanising for durability & long life Gang forms and lifting applications available Full range of safety features High Quality plywood 60kN/m2 permissible fresh concrete pressure To be captured on temp works drawings. Inclusive of structural shore loading for super structure
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Formwork Curing Agent
label | Standard, Drawing or Specification Reference - Material Data Sheet
label | Construction Activity Description, Test Type and Acceptance Criteria - Chemical curing agent.
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - R
label | Engineers Rep - R
label | Designer Rep - R
checkpoint | 2.5 - Installation - Lift Plan
label | Standard, Drawing or Specification Reference - DNZ Lift Plan for GMK 300 L
label | Construction Activity Description, Test Type and Acceptance Criteria - Lifting plan for the installation of the pre cast cantilever deck.
label | Test Frequency - Once
label | QA Record - Lift Design Approval
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Epoxy for corbel Installation
label | Standard, Drawing or Specification Reference - As per NTC 058
label | Construction Activity Description, Test Type and Acceptance Criteria - R12 bars to be installed and epoxied into place using C8 epoxy. Requires designer approval.
label | Test Frequency - Once
label | QA Record - MDS In Eight Reference ….........
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Concrete Bags
label | Standard, Drawing or Specification Reference - MDS
label | Construction Activity Description, Test Type and Acceptance Criteria - 40Mpa Concrete Dricon High Strength Handicrete or similar approved product.
label | Test Frequency - Once
label | QA Record - MDS
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Column and Headstock ITP Sign Off
label | Standard, Drawing or Specification Reference - Signed ITP
label | Construction Activity Description, Test Type and Acceptance Criteria - Sign off of Column and headstock construction
label | Test Frequency - Once
label | QA Record - Signed ITP
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Structural Steel Deck Installation ITP Sign Off
label | Standard, Drawing or Specification Reference - Signed ITP
label | Construction Activity Description, Test Type and Acceptance Criteria - Required before pouring of concrete stitch pour.
label | Test Frequency - Once
label | QA Record - Signed ITP
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | 3 - CONSTRUCTION ACTIVITIES
checkpoint | 3.1 - Setout
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3100 3235599-SP03-ST-3150 3235599-SP03-ST-3202
label | Construction Activity Description, Test Type and Acceptance Criteria - Before commencing formwork installation, survey set out top of cantilever position based on drawings with RL supplied. Tolerances for insitu concrete pour taken from NZS 3109 table 5.2. Required to check and confirm that the position of the slab has the correct clearance from the bridge structure of 160mm and that the Macalloy bars are installed per the correct place.
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Type B Construction Joint Corbels
label | Standard, Drawing or Specification Reference - As per CAN 69
label | Construction Activity Description, Test Type and Acceptance Criteria - As per CAN 069 Type B construction joint to be formed on the vertical faces of the corbels to ensure connection when concrete poured.
label | Test Frequency - Each Corbel
label | QA Record - Photos
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Formwork Installation
label | Standard, Drawing or Specification Reference - Material Data Sheet Temporary works drawings Piers 1 and 2.
label | Construction Activity Description, Test Type and Acceptance Criteria - As per Temporary works drawings for Piers Stitch Pour.
label | Test Frequency - Once
label | QA Record - Photos plus signed off temporary works inspection of shuttering and formwork.
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Steel Installation for Corbel
label | Standard, Drawing or Specification Reference - As per NTC 058
label | Construction Activity Description, Test Type and Acceptance Criteria - R12 U bars to be installed within concrete corbel as per NTC 058. 40mm cover to be obtained surrounding steel. All bars must be epoxied into place with visual evidence to support that approved epoxy has been installed. Epoxy to be installed as per manufacturers installation instructions. Refer to CAN 069
label | Test Frequency - Once
label | QA Record - Photos
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Concrete Corbel Pre-Pour Inspection
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing installed as per NTC 058. Correct number of bars and grade. Correct steel lapping. Minimum 40mm cover achieved. 40Mpa Bagged Concrete to achieve 28 Days Compressive Strength. Mixing as per manufactures guidelines. Refer to CAN 069
label | Test Frequency - Once
label | QA Record - Survey Check Structural Engineer Inspection MSQA SVR Pre-Pour Checklist Photos
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Corbel Concrete Pour
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Minimum 40mm cover achieved. 40Mpa Bagged Concrete to achieve 28 Days Compressive Strength. Mixing as per manufactures guidelines.
label | Test Frequency - Once
label | QA Record - Survey Check Pre-Pour Checklist Photos
label | DNZ Engineer - H
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Concrete Stitch Pre-Pour
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing installed as per IFC drawings. Minimum cover 50mm.
label | Test Frequency - Once
label | QA Record - Survey Check Structural Engineer Inspection MSQA SVR Pre-Pour Checklist Photos
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Concrete Stitch Pour
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete: 50MPa - Self Compacting Concrete Cylinder test taken at supply Yard only. Spread Test to be completed on site prior to concrete pour. Target Spread Test - 680mm +/- 60mm
label | Test Frequency - Once
label | QA Record - Delivery Dockets Compressive Test Results Photos
label | DNZ Engineer - H
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Surface Finish/Construction Joint
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003 NZS 3114
label | Construction Activity Description, Test Type and Acceptance Criteria - F1 Surface Finish - Concealed Formed faces F5 Surface Finish - Exposed and Visible Faces Type B Construction Joint to be used between insitu and pre-cast deck placement, as well as headstock placement on existing column. Insitu Concrete Stich Pour on Pier 1 - surface to have U2 broomed finish for slip resistance in both rain and dry as per NZBC D1 requirements.
label | Test Frequency - Once
label | QA Record - Visual Inspection Photos
label | DNZ Engineer - H
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Concrete Curing
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3200
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete to be cured for a minimum of 3 days as per drawing ST-3200, curing methodology will be formwork curing. Cylinder to be taken at 3 days to verify strength of 30 Mpa has been achieved prior to stripping of formwork.
label | Test Frequency - Once
label | QA Record - Concrete strength results, concrete pour checksheet notifying date of formwork striking.
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Post Pour Inspection
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003 NZS 3114
label | Construction Activity Description, Test Type and Acceptance Criteria - Joint inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/ check dimension of structure have achieved stipulated tolerances stated in drawing suite and NZS 3109
label | Test Frequency - Once
label | QA Record - Visual Inspection Photos
label | DNZ Engineer - H
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
section | 4 - FINAL RECORDS
checkpoint | 4.1 - As-Built
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Redline Mark-Up
label | Standard, Drawing or Specification Reference - IFC Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings marked up and signed.
label | Test Frequency - Once
label | QA Record - IFC Drawings Mark-Up
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report. NCR Reference …..................
label | Test Frequency - Each NCR
label | QA Record - NCR forms on InEight
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Project Engineer - Grant Wallace
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed by: Quality Eng./Mgr. - Nas Matar
label | Reviewed By: Design Engineer - Daniel Cvitanich
label | Reviewed By: AT Project Manager - Werner Nel
label | Reviewed By: AT Engineer to Contract - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Designers Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-015 Bearing Pad Grouting | itp |  |  |  |  | DN1212-ITP-015 Bearing Pad Grouting Rev1
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - Method Statement Development & Safety Analysis
label | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
label | Test Frequency - Once
label | QA Record - Method Statement & JSEA Completed & signed by relevant authority
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Confirmation of superstructure position.
label | Standard, Drawing or Specification Reference - Signed ITP
label | Construction Activity Description, Test Type and Acceptance Criteria - Signed ITP required for the position of the superstructure before grouting.
label | Test Frequency - Once
label | QA Record - Signed ITP
label | DNZ Engineer - I
label | Engineers Rep - W
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Non Shrink Grout Approval
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
label | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ 3235599-SP03-ST-3250 - PROPOSED ACCESS RAMP- ABUTMENT DETAILS- SHEET1
label | ○ 3235599-SP03-ST-3252 - PROPOSED ACCESS RAMP- ABUTMENT BEARING
label | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | ○ Spec - C0602.10.04
label | Construction Activity Description, Test Type and Acceptance Criteria - Non shrink grout - sika 212 HP to be submitted to designer for review and approval as it obtains 85 Mpa after 28 Days > 50 Mpa as per 3252 - Note 1.4
label | Test Frequency - Once
textbox | QA Record - MDS, In Eight Ref
label | DNZ Engineer - R
label | Engineers Rep - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Glass Plate Trial
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3252 - PROPOSED ACCESS RAMP- ABUTMENT BEARING - Note
label | Construction Activity Description, Test Type and Acceptance Criteria - As per 3235599-SP03-ST-3252 - PROPOSED ACCESS RAMP- ABUTMENT BEARING - Note 1.4. Glass Plate trial to be undertaken to replicate bearing pad footprint of 230mm x 230mm x 20mm. Area is to be poured prior to installation of bearing grout to confirm voiding is less than 10% of area. Undertaken with MSQA observations
label | ○ Methodology to be submitted prior to commencement..
label | Test Frequency - Once
label | QA Record - Site Observation Report, Written acceptance of material following trial.
label | DNZ Engineer - I
label | Engineers Rep - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Curing Method
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - According to MDS sheet for Sika 212 HP, See below, grout to be sealed with timber shutter, left to cure within small shutter and then treated with Sika Anti Sol as per data sheet attached..
label | Curing Treatment
label | ○ Formwork should be left in place for at least 5 days if possible, to prevent moisture evaporation and provide restraint to early age hardened expansion. Once formwork is removed a suitable curing membrane such as Sika Antisol should be applied to any exposed faces. Refer to separate data sheet for further information.
label | Test Frequency - Once
label | QA Record - MDS, Photos
label | DNZ Engineer - R
label | Engineers Rep - R
label | Designer Rep - R
section | 3 - CONSTRUCTION ACTIVITIES
checkpoint | 3.1 - Construction Joint
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3252 - PROPOSED ACCESS RAMP- ABUTMENT BEARING
label | Construction Activity Description, Test Type and Acceptance Criteria - Formation of construction joint required on top of pier / abutment to the construction joint must be visible.
label | Test Frequency - Once
label | QA Record - Photos
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Grouting Pre-Pour Inspection
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
label | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
label | Construction Activity Description, Test Type and Acceptance Criteria - No reinforcing requirements.
label | ○ Check to ensure that the surface is prepped, underside of bearing pad is in correct location prior to pouring. Nominal 20mm will be poured.
label | Test Frequency - Each Structure
label | QA Record - MSQA SVR, Pre-Pour Checklist, Photos
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Grouting Pour
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3252 - PROPOSED ACCESS RAMP- ABUTMENT BEARING, NS 3109, AS1012, Spec - C0602.10.04
label | Construction Activity Description, Test Type and Acceptance Criteria - Concrete to be poured as per manufacturers recommendations where 3.7 litres per bag.
label | ○ Samples to be taken from each batch using steel moulds where 1, 2, 3, 5, 14 and 28 day tests are to be taken to ensure that grout has reached necessary strength
label | Mixing
label | ○ Place about 70-80 % of the premeasured clean water (depending on consistency required - refer to "Mix Ratio") into a clean container and gradually add the whole bag of SikaGrout-212 HP into it while continuously mixing. Add the remaining water until the desired consistency is obtained. Mix for 3-5 minutes with a low speed drill (500 rpm max.). Allow to stand so any entrapped air can escape. Do not add more water to increase flow of the grout if a mix has stiffended due to time delays. If the ground is unworkable discard.
label | Test Frequency - Once
label | QA Record - Photos, Test Report for Compressive Strength
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Post Pour Inspection
label | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003, NZS 3114
label | Construction Activity Description, Test Type and Acceptance Criteria - Joint inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/ check dimension of structure have achieved stipulated tolerances stated in drawing suite and NZS 3109
label | Test Frequency - Once
label | QA Record - Visual Inspection, Photos
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
section | 4 - FINAL RECORDS
checkpoint | 4.1 - As-Built
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
textbox | NCR Reference
label | Test Frequency - Each NCR
label | QA Record - NCR forms on InEight
label | DNZ Engineer - H
label | Engineers Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Project Engineer - Grant Wallace
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed by: Quality Eng./Mgr. - Nas Matar
label | Reviewed By: Design Engineer - Daniel Cvitanich
label | Reviewed By: AT Project Manager - Werner Nel
label | Reviewed By: AT Engineer to Contract - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Designers Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature