## ITP Summery
Job | 2025-02 - NPWS Bridge Components -MIFSUD | values | Check list | options
checklist-sectioned | Precast Components ITP
section | Documentations
checkpoint | Special Instructions |  |  | attachments/photos/Sign
checkpoint | approved Shop Drawings |  |  | attachments/photos/Sign
tick Box | 3.9m Wide Deck Type A Panels
tick Box | 3.9m Wide Deck Type B Panels
tick Box | Abutment AA
tick Box | 582mm Upper Wall to suit Abutment AA
tick Box | Abutment BB
tick Box | 776mm Upper Wall to suit Abutment BB
checkpoint | Other |  |  | attachments/photos/Sign
section | Job Approval Documents/Construction Documents
checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction" |  | Pass/Fail/NA | attachments/photos
All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint | Formwork |  |  | attachments/photos/Sign
checkpoint | Reinforcement(Reo) |  |  | attachments/photos/Sign
checkpoint | Embedded Items and their placement |  |  | attachments/photos/Sign
checkpoint | Lift Procedure
checkpoint | Concreting (mix design |  |  | attachments/photos/Sign
section | Test on Concrete (requests and approvals)
checkpoint | Request From Client |  |  | attachments/photos/Sign
checkpoint | Test schedule and Test Results |  |  | attachments/photos/Sign
Repeating items
This is a General Section
No repeating Items

## Deck Panel Type A
Checkers Checklist - Type A - Bridge Plank
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type A (300F1450F400F1450F300) |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | 300F1450F
dropdown |  | 250F1450F
checkpoint | Overall Measurements of construction Element |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double check ferrules are firmly positioned & Fixed with M12 on shutter |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel Thickness check,allignment check -150mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel length check, alignment check -3900mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Diagonal length check, alignment check (4025 mm or close to this) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Type A - Bridge Plank
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Eye Anchor - 2.5T - 04 |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Ferrules - M20 x 96mm - 10 |  | Pass/Fail/NA | attachments/photos/Comments | Repeating items | DP-A1
checkpoint | ID Plate |  | Pass/Fail/NA | attachments/photos/Comments |  | DP-A2
text box | [5 empty] | DP-A3
section | Pre-Pour Check Approvals |  |  |  |  | DP-A4
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments |  | DP-A5
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photos/Comments |  | DP-A6
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photos/Comments |  | DP-A7
checkpoint | Double Check the Ferrule placement -Type A |  | Pass/Fail/NA | attachments/photos/Comments |  | DP-A8
checkpoint | Reinforcement Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photos/Comments |  | DP-A9
checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check |  | Pass/Fail/NA | attachments/photos/Comments |  | DP-A10
tick box | Embedded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
tick box | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
checkpoint | Concrete cover Check - minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mixdesign ,variations%, adjustments%, mix time |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER |  | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged |  | Pass/Fail/NA | attachments/photos/Comments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments

## Deck Panel Type B
Checkers Checklist - Type B - Bridge Plank
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Double Check the Ferrule placment -Type A (250F1450F500F1450F250) |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 300F1450F
dropdown |  | 250F1450F
checkpoint | Overall Measurements of construction Eliment |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Double check ferrules are firmly positioned & Fixed with M12 on shutter |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Panel Thickness check,allignment check -150mm |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Panel length check, allignment check -3900mm |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Diaganal length check, allignment check (4025 mm or close to this) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcement (Reo) placed, cleaned, tightned |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photoes/Coments
Installers Checklist - Type B - Bridge Plank
section | Job Aproval Documents/Constrction Documents
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Eye Anchor - 2.5T - 04 |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Ferrules - M20 x 96mm - 10 |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | ID Plate |  | Pass/Fail/NA | attachments/photoes/Coments | Repeating items | DP-B1
text box | [5 empty] | DP-B2
section | Pre-Pour Check Approvals |  |  |  |  | DP-B3
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments |  | DP-B4
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photoes/Coments |  | DP-B5
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photoes/Coments |  | DP-B6
checkpoint | Double Check the Ferrule placment -Type B |  | Pass/Fail/NA | attachments/photoes/Coments |  | DP-B7
checkpoint | Reinforcment Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photoes/Coments |  | DP-B8
checkpoint | Lifters, Ferrules Fixed Firm & alligned -Check |  | Pass/Fail/NA | attachments/photoes/Coments |  | DP-B9
tick box | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos |  |  |  |  | DP-B10
tick box | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal |  |  |  |  | DP-B11
checkpoint | Concrete cover Check - minimum 30mm |  | Pass/Fail/NA | attachments/photoes/Coments |  | DP-B12
section | Quality Assuarance |  |  |  |  | DP-B13
checkpoint | QA - Final Check of ALL measurerments |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER |  | Pass/Fail/NA | attachments/photos/Comments
section | Other Arangments
checkpoint | Concrete surface Finish Requirment arranged |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments

## Abutment Base AA
Checkers Checklist - Abutment Base -AA
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type AA (550F400F1050F400F1050F400F550) |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | 550F400F1050
dropdown |  | 500F500F950
checkpoint | Overall Measurements of construction Element |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) - 06Nos |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) - 07Nos |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mmDia ,300mm - 06 Nos as per the Dwg: S06 |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double check ferrules are firmly positioned & Fixed with M12 bars on shutter |  | Pass/Fail/NA | attachments/photos/Comments
Concrete cover check minimum 30mm
Panel length check, alignment check -4400x800mm
checkpoint | Diagonal length check, alignment check (4472 mm or close to this) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Abutment Base - AA
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Eye Anchor - 2.5T(170mm) - 04 |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Ferrules - M24 x 96mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate |  | Pass/Fail/NA | attachments/photos/Comments | Repeating items | Ab-AA1
text box | [5 empty] | Ab-AA2
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type AA |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) - 06Nos |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Ferrules for Dowels - Position,Size -M24 (96mm) - 07Nos |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover Check - minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER |  | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged |  | Pass/Fail/NA | attachments/photos/Comments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments

## Abutment Base BB
Checkers Checklist - Abutment Base -BB
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type BB (500F500F950F500F950F500F500) |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | 550F400F1050
dropdown |  | 500F500F950
checkpoint | Overall Measurements of construction Element |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) - 06Nos |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) - 07Nos |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mmDia ,300mm - 06 Nos as per the Dwg: S06 |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double check ferrules are firmly positioned & Fixed with M12 bars on shutter |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel length check, alignment check -4400x800mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Diagonal length check, alignment check (4472 mm or close to this) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Abutment Base - BB
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Eye Anchor - 2.5T(170mm) - 04 |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Ferrules - M24 x 96mm |  | Pass/Fail/NA | attachments/photos/Comments | Repeating items | Ab-BB1
checkpoint | ID Plate |  | Pass/Fail/NA | attachments/photos/Comments |  | Ab-BB2
text box
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type BB |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) - 06Nos |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) - 07Nos |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover Check - minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER |  | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged |  | Pass/Fail/NA | attachments/photos/Comments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments

## Upper Wall AA
Checkers Checklist - Upper Wall -AA
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type AA Wall Height - 582mm |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | 582mm
dropdown |  | 776mm
checkpoint | Overall Measurements of construction Element |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double check ferrules are firmly positioned & Fixed with M12 bars on shutter |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel Thickness check,allignment check -150mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel length check, alignment check -4400x800mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Diagonal length check, alignment check (4472 mm or close to this) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Upper Wall - AA
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Eye Anchor - 2.5T(170mm) - 04 |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate |  | Pass/Fail/NA | attachments/photos/Comments | Repeating items | UW-AA1
text box | [5 empty] | UW-AA2
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type AA |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover Check - minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER |  | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged |  | Pass/Fail/NA | attachments/photos/Comments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments

## Upper Wall BB
Checkers Checklist - Upper Wall -BB
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type BB Wall Height - 776mm |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | 582mm
dropdown |  | 776mm
checkpoint | Overall Measurements of construction Element |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double check ferrules are firmly positioned & Fixed with M12 bars on shutter |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel Thickness check,allignment check -150mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel length check, alignment check -4400x800mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Diagonal length check, alignment check (4472 mm or close to this) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Upper Wall - BB
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Eye Anchor - 2.5T(170mm) - 04 |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate |  | Pass/Fail/NA | attachments/photos/Comments | Repeating items | UW- BB1
text box | [5 empty] | UW- BB2
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type BB |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
tick box | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover Check - minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER |  | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged |  | Pass/Fail/NA | attachments/photos/Comments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments

## Sheet5 (hidden)
Repeating items | FFBP-A1 | FFBP-B1
| FFBP-A2 | FFBP-B2
| FFBP-A3 | FFBP-B3
| FFBP-A4 | FFBP-B4
| FFBP-A5 | FFBP-B5
| FFBP-A6 | FFBP-B6
| FFBP-A7 | FFBP-B7
| FFBP-A8 | FFBP-B8
| FFBP-A9 | FFBP-B9
| FFBP-A10 | FFBP-B10
| FFBP-A11 | FFBP-B11
| FFBP-A12 | FFBP-B12
| FFBP-A13 | FFBP-B13
| FFBP-A14 | FFBP-B14
| FFBP-A15 | FFBP-B15
| FFBP-A16 | FFBP-B16
FFBP-B17
FFBP-B18
FFBP-B19
FFBP-B20
FFBP-B21
FFBP-B22
FFBP-B23
FFBP-B24
FFBP-B25
FFBP-B26
FFBP-B27
FFBP-B28
FFBP-B29
FFBP-B30
FFBP-B31
FFBP-B32