## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-015 - Construction of Concrete Paving | itp |  |  |  |  | ITP-015 - Construction of Concrete Paving
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY - Prior to commencing any activity
label | ACCEPTANCE CRITERIA - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS - Drawings and drawing registers
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - ITP Signed
label | HP*
label | RESPONSIBILITY - Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY - Prior to commencing any activity
label | ACCEPTANCE CRITERIA - All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS - QMP, TMP, JSEA, SWMS, WP
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - ITP Signed
label | HP*
label | RESPONSIBILITY - Project Engineer/ Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY - Prior to start
label | ACCEPTANCE CRITERIA - Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | REFERENCE DOCUMENTS - 703.17
label | INSPECTION / TEST METHOD - Verify
label | RECORD OF CONFORMITY - ITP Signed
label | HP
label | RESPONSIBILITY - Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Temporary Drainage Provisions
label | FREQUENCY - If Required
label | ACCEPTANCE CRITERIA - If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
label | REFERENCE DOCUMENTS - Cl 703.18
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - ITP Signed
label | WP
label | RESPONSIBILITY - Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Bedding
label | FREQUENCY - Each lot
label | ACCEPTANCE CRITERIA - All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
label | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
label | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | REFERENCE DOCUMENTS - Cl 703.21
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - ITP Signed
label | WP
label | RESPONSIBILITY - Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.4 - Pre-concrete check
label | FREQUENCY - Each lot
label | ACCEPTANCE CRITERIA - Bedding shall be moist but shall have no free water on the surface.
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
label | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
label | REFERENCE DOCUMENTS - Cl 703.08
label | INSPECTION / TEST METHOD - Verify
label | RECORD OF CONFORMITY - ITP Signed
textbox | Ambient Temperature |  |  | °C
textbox | Concrete Temperature |  |  | °C
label | HP*/ WP
label | RESPONSIBILITY - Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.5 - Reinforcement
label | FREQUENCY - Each Lot
label | ACCEPTANCE CRITERIA - Steel reinforcement shall comply with the requirements of AS/NZS 4671, Minimum cover of 50mm
label | REFERENCE DOCUMENTS - AS/NZS 4671
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - ITP Signed
label | IP
label | RESPONSIBILITY - Project Engineer
date | Date Completed:
checkpoint | 2.6 - Concrete Placement
label | FREQUENCY - Each lot
label | ACCEPTANCE CRITERIA - Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
label | REFERENCE DOCUMENTS - VicRoads Spec Cl 703.23
label | INSPECTION / TEST METHOD - Site Inspection
label | RECORD OF CONFORMITY - ITP Signed
label | IP
label | RESPONSIBILITY - Project Engineer
date | Date Completed:
checkpoint | 2.7 - Finish Surfaces
label | FREQUENCY - Each Lot
label | ACCEPTANCE CRITERIA - Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
label | ○ Concrete to have a neat appearance and uniform colour
label | REFERENCE DOCUMENTS - 703.25
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - ITP Signed
label | IP
label | RESPONSIBILITY - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.8 - Joints
label | FREQUENCY - Each joint
label | ACCEPTANCE CRITERIA - Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
label | REFERENCE DOCUMENTS - 703.26
label | INSPECTION / TEST METHOD - Verify
label | RECORD OF CONFORMITY - ITP Signed
label | IP
label | RESPONSIBILITY - Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.9 - Backfilling
label | FREQUENCY - Each Lot
label | ACCEPTANCE CRITERIA - Not earlier than 3 days after casting.
label | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
label | ○ Layers shall not exceed 150mm compacted depth
label | REFERENCE DOCUMENTS - 703.29
label | INSPECTION / TEST METHOD - Verify
label | RECORD OF CONFORMITY - ITP Signed
label | IP
label | RESPONSIBILITY - Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-032 - Construction of Kerb & Channel | itp |  |  |  |  | ITP-032 - Construction of Kerb & Channel
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY - Prior to commencing any activity
label | ACCEPTANCE CRITERIA - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS - Drawings and drawing registers
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - ITP Signed
label | HP*
label | RESPONSIBILITY - Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY - Prior to commencing any activity
label | ACCEPTANCE CRITERIA - All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS - QMP, TMP, JSEA, SWMS, WP
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - ITP Signed
label | HP*
label | RESPONSIBILITY - Project Engineer/ Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY - Prior to start
label | ACCEPTANCE CRITERIA - Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | REFERENCE DOCUMENTS - 703.17
label | INSPECTION / TEST METHOD - Verify
label | RECORD OF CONFORMITY - ITP Signed
label | HP
label | RESPONSIBILITY - Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Temporary Drainage Provisions
label | FREQUENCY - If Required
label | ACCEPTANCE CRITERIA - If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
label | REFERENCE DOCUMENTS - Cl 703.18
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - ITP Signed
label | WP
label | RESPONSIBILITY - Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Bedding
label | FREQUENCY - Each lot
label | ACCEPTANCE CRITERIA - All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
label | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
label | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | REFERENCE DOCUMENTS - Cl 703.21
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - ITP Signed
label | WP
label | RESPONSIBILITY - Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.4 - Pre-concrete check
label | FREQUENCY - Each lot
label | ACCEPTANCE CRITERIA - Bedding shall be moist but shall have no free water on the surface.
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
label | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
label | REFERENCE DOCUMENTS - Cl 703.08
label | INSPECTION / TEST METHOD - Verify
label | RECORD OF CONFORMITY - ITP Signed
textbox | Ambient Temperature |  |  | °C
textbox | Concrete Temperature |  |  | °C
label | HP
label | RESPONSIBILITY - Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Concrete Placement
label | FREQUENCY - Each lot
label | ACCEPTANCE CRITERIA - Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
label | REFERENCE DOCUMENTS - VicRoads Spec Cl 703.23
label | INSPECTION / TEST METHOD - Site Inspection
label | RECORD OF CONFORMITY - ITP Signed
label | IP
label | RESPONSIBILITY - Project Engineer
date | Date Completed:
checkpoint | 2.6 - Finish Surfaces
label | FREQUENCY - Each Lot
label | ACCEPTANCE CRITERIA - Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
label | ○ Concrete to have a neat appearance and uniform colour
label | REFERENCE DOCUMENTS - 703.25
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - ITP Signed
label | IP
label | RESPONSIBILITY - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.7 - Joints
label | FREQUENCY - Each joint
label | ACCEPTANCE CRITERIA - Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
label | REFERENCE DOCUMENTS - 703.26
label | INSPECTION / TEST METHOD - Verify
label | RECORD OF CONFORMITY - ITP Signed
label | IP
label | RESPONSIBILITY - Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.8 - Backfilling
label | FREQUENCY - Each Lot
label | ACCEPTANCE CRITERIA - Not earlier than 3 days after casting.
label | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
label | ○ Layers shall not exceed 150mm compacted depth
label | REFERENCE DOCUMENTS - 703.29
label | INSPECTION / TEST METHOD - Verify
label | RECORD OF CONFORMITY - ITP Signed
label | IP
label | RESPONSIBILITY - Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP