## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - Watermain | itp |  |  |  | Yes | ITP - Watermain | 0255ba0f-b61c-4e87-965e-b9c8d877c229
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 400.1 - Survey Set Out
label | 7892bc5f-37de-5136-a47b-7e7ca4279356 |  | note | Detail of Activity - GPS Setout of the watermain as per the construction drawings.
label | 9487458a-e401-5341-8977-e88aaa4d2d7e |  | note | Action - W
label | 3764699f-8ef4-5576-b31b-f018055d9e6f |  | note | Minimum Test Frequency - All lengths of watermain and connections
label | 30057d85-5fcf-5eb4-b706-b17944d24ec3 |  | note | Inspection / Test method - Visual Inspection
label | 089d64bb-0537-5346-b2e5-15f3646f4079 |  | note | Acceptance Criteria - N/A
label | bb22d449-235d-5e68-bd16-eae066d8ce44 |  | note | Record documents - Contractor's site diary and/or photos
label | 4f0b9d1c-7689-5e0e-bffd-90e22e901674 |  | note | Comments - Setout location prior to commencing works.
checkpoint-status |  |  | checkpoint | 400.2 - Materials Approvals
label | 419eeec1-375a-5530-99fd-b9df0244e6f7 |  | note | Detail of Activity - Line Materials/Fittings
label | 2211042e-6f00-5bc0-9924-d81076512817 |  | note | Action - M
label | 0d87a3cc-7cfa-5cec-b6ca-a2882e3f6687 |  | note | Minimum Test Frequency - All materials/fittings
label | c2a9eef7-e738-57dc-93a9-bc9c2c6cf4f1 |  | note | Inspection / Test method - Review
label | ed226c26-f42c-5f95-ab07-d41d25a61efb |  | note | Acceptance Criteria - All fittings and materials per RLC's Approved Fittings and Materials List. Any not listed are to be submitted and approved by RDC and the Engineer.
label | 6dcd6ea0-9b1e-5bfe-b733-5d949f1f301a |  | note | Record documents - Contractor's site diary/QC sheets
label | 845f1a64-71e7-5017-8a71-4745bc909d3d |  | note | In Eight record
checkpoint-status |  |  | checkpoint | 400.3 - Materials Approvals
label | 7987c5bc-be13-5e88-b243-ea83ed342a9a |  | note | Detail of Activity - Bedding/Backfill
label | 7326e914-b64d-5b6e-8414-754088976d36 |  | note | Action - H
label | 5884b5aa-bf92-5719-b157-95f46c04020e |  | note | Minimum Test Frequency - Once per imported backfill material type.
label | 99b40fd2-aeb5-5694-9f5c-82f6bf561b18 |  | note | Inspection / Test method - Material Testing Data
label | 2ee3b374-938c-59d0-bb26-6e06316c9a35 |  | note | Acceptance Criteria - Engineer's acceptance
label | bd00ed0c-df13-513b-953c-40fa0ab00a9e |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.4 - Asbestos Management Plan
label | 78078f45-2f62-55b5-b17e-83160e40831f |  | note | Detail of Activity - Submit Asbestos/Contaminated Material Management Plan
label | cc5f64c3-ee23-5776-8d83-13019746409b |  | note | Action - H
label | af8d2aa9-4aa8-56ce-a9ea-0042b56871e7 |  | note | Minimum Test Frequency - Once for Project
label | 1d59b071-9fd9-5a47-82c8-58b1e58cec62 |  | note | Inspection / Test method - Plan Submission
label | 88ef26d0-ebe6-5535-92c0-435d6aa3c20c |  | note | Acceptance Criteria - Engineer approval.
label | 487011c8-16a0-5df0-b26f-229bddd47904 |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.5 - Personnel - Registered Drain Layer Records
label | 7cec8ae9-2f97-5b86-ab1c-87e74817fa65 |  | note | Detail of Activity - All pipe layers to be registered drain layers
label | 037a5525-b5f7-574c-914e-c8d01ccfae79 |  | note | Action - H
label | 7bf3f428-b0e6-5921-8169-fbdb30c9c99d |  | note | Minimum Test Frequency - Once for all personnel on project
label | 9ccef0f5-fad9-5ca6-bf83-9cdf31079ac6 |  | note | Inspection / Test method - Training Record Verification
label | 0eec11e8-2fd2-51b8-a82a-699db3705fcd |  | note | Acceptance Criteria - Competencies forwarded to the Engineer.
label | d0ee8b72-7346-5a61-a412-c0a71872b2ae |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Construction and Finishing
checkpoint-status |  |  | checkpoint | 400.6 - Open Cut/Trenched Excavation
label | 25bbc0c5-7bcc-5a72-bd00-d2f5bd07e1fe |  | note | Detail of Activity - Confirm trench excavation is to the correct dimensions
label | 5bb57ca9-b236-580e-be5e-8ff9b3ef0ea5 |  | note | Action - W
label | 7be8b99b-8a6e-58de-9207-74cac0b1a81d |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 996f0e01-d26e-5d8d-b785-fb1dd77c8531 |  | note | Inspection / Test method - Visual Inspection with tape measure.
label | 28271551-997d-58c4-9563-45871653c163 |  | note | Acceptance Criteria - Depths/widths in accordance with design.
label | 64002e5e-37c9-5a02-9f14-b94e215a33fa |  | note | Record documents - Contractor's site diary and/or photos
checkpoint-status |  |  | checkpoint | 400.7 - Open Cut/Trenched Excavation
label | cbe5b8e1-497d-51c7-9993-31c7e4c9213d |  | note | Detail of Activity - Check quality of trench subgrade/foundation
label | b82ee02d-688c-5e4d-81b5-8bd5234fa30a |  | note | Action - W
label | 6f9c10c0-5dc5-5d39-a14f-7566a1470d21 |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 17e6ea87-d62b-59ca-9caf-5165690b7d49 |  | note | Inspection / Test method - Visual inspection / Scala Test
label | 784937d6-0fc7-5caf-b48b-d318e3e0054e |  | note | Acceptance Criteria - Firm and unyielding. Scala result of 2 blows per 100mm at 300mm depth.
label | 498fa7f9-93ae-530b-a9b9-061d834661b2 |  | note | If Scala doesn't pass undercut 200mm and replace with geotextile and GAP65.
label | 85d9b2dd-937c-5465-87cb-31759467dd42 |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.8 - Installation of Pipes
label | bf406b81-6a2e-552a-bc29-c605831aefab |  | note | Detail of Activity - Confirm minimum pipe cover - in carriageway
label | bcd13416-bb53-5b40-87b0-4134a1766888 |  | note | Action - W
label | 940d706b-8c93-58cf-83f5-ee7b001df257 |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 7982d7fc-36ec-5d8b-8448-3de36fc41c2c |  | note | Inspection / Test method - Visual Inspection
label | 99d1b3ae-53b8-54b5-9bd0-7259525e97c2 |  | note | Acceptance Criteria - Min 1m cover to top of pipe in carriageways.
label | 22c60346-0597-5645-8e7d-ba8f46215283 |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.9 - Installation of Pipes
label | 2a9e5924-fa83-5b57-9e35-5ad19db3c6a6 |  | note | Detail of Activity - Confirm minimum pipe cover - in berm
label | 580c466d-ba48-5648-a32b-7804fefc547d |  | note | Action - W
label | a875c189-d170-58c6-af81-ec7a1faac36f |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 26a5590b-cd7a-5a96-b5a4-9d17183d9918 |  | note | Inspection / Test method - Visual Inspection
label | 7214bf9f-d287-5500-8713-b9a407db9ddf |  | note | Acceptance Criteria - Min 0.75m cover to top of pipe in nontrafficed areas.
label | 3c0e2fd9-6e5b-5e1d-9692-2ee2967ebddd |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.10 - Installation of Pipes
label | ccdc13ce-57b2-5332-a945-949d480c317a |  | note | Detail of Activity - Verify pipe levels are within tolerances
label | e4d8b3b2-f51d-58c2-9476-9da59d8dde35 |  | note | Action - M
label | 6c7e5cf5-e68f-5be7-a96c-777e51ad9975 |  | note | Minimum Test Frequency - Every 50 lineal meters.
label | 6f5d2726-3566-5f6f-ae2b-41f93468498d |  | note | Inspection / Test method - Visual Inspection
label | 5da775b4-65b3-58f8-9c95-0d8c48cec7e0 |  | note | Acceptance Criteria - + / - 100mm from DL
label | 50a1559d-4baf-5043-bddd-05c0b9a9815d |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.11 - Installation of Pipes
label | c5aee3da-9a9b-55df-aade-8d17504021b3 |  | note | Detail of Activity - Install warning tape
label | b910c4d4-06c7-5474-a4b6-aab0686851aa |  | note | Action - M
label | 2310a16e-9f99-5864-a400-90e256b1295c |  | note | Minimum Test Frequency - Continuous along pipe.
label | 78bb7dac-0d8c-5c48-87c8-74b749987e2b |  | note | Inspection / Test method - Visual Inspection
label | 4d32002d-4212-5ece-b704-57215470de6e |  | note | Acceptance Criteria - Warning tape at 300mm above pipe.
label | f4fea4e9-8a41-567a-bc66-94646c628996 |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.12 - Pipe Connections
label | 0830783e-eec8-56bf-a0cd-3244493f0797 |  | note | Detail of Activity - Record connection configurations
label | 511785e2-c307-52c4-a0ee-d6d5d8fd22f3 |  | note | Action - W
label | 742005b7-132b-53da-a730-4bc970aff8ce |  | note | Minimum Test Frequency - Every connection.
label | 85bf2629-f121-5408-abfd-0b59e9683441 |  | note | Inspection / Test method - Visual Inspection
label | ad911992-84e1-5b0a-8db2-03c5aca4670a |  | note | Acceptance Criteria - Photo and sketch of connection.
label | b112aa1d-a898-51dc-be86-66c12177468f |  | note | All buried bolted connections wrapped appropriately (i.e. denso)
label | 81549139-b183-55c0-9455-fa5032973448 |  | note | Record documents - Watermain Pipeline QC Sheet / Contractors Site Diary
checkpoint-status |  |  | checkpoint | 400.13 - Thrust / Anchor Blocks
label | 449bf1cb-7ccd-5e0e-893a-271d2246fff2 |  | note | Detail of Activity - Test thrust block subgrade
label | 363bf5e8-d2d2-56db-a2d1-e685f32a0fcf |  | note | Action - H
label | 53147438-62ba-50bc-8535-9aa2b4a74aa5 |  | note | Minimum Test Frequency - All thrust block locations.
label | f2c3a63b-a837-59f2-b8f7-f42cf6c46331 |  | note | Inspection / Test method - Scala Test
label | 8f41f832-d0cc-5ea3-9cd2-07582c14e8b4 |  | note | Acceptance Criteria - Scala result of 2 blows per 100mm at 300mm depth.
label | 47fa7d47-f785-5234-8a5d-f0cc998d19de |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.14 - Thrust / Anchor Blocks
label | c7a753cf-8bd9-5f63-ae62-f50fda3f948b |  | note | Detail of Activity - Confirm thrust block size
label | cd2d657b-5792-5705-a4f5-2ed559ae019f |  | note | Action - H
label | 4ecb3e43-e45b-56d7-a32c-39e98a484943 |  | note | Minimum Test Frequency - All thrust blocks
label | cef9cfbe-def2-5484-8f1f-cf9b2bb984c4 |  | note | Inspection / Test method - Engineer's Confirmation
label | 103f2dea-1ac4-504a-b100-38b81f155b54 |  | note | Acceptance Criteria - Engineer's confirmation of design size or advise otherwise.
label | 3968b90d-91d2-58dd-a4ad-e4cea9118629 |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.15 - Thrust / Anchor Blocks
label | ae561f57-9a8e-5dff-ab5a-3bbffbdb3859 |  | note | Detail of Activity - Wrap PE pipe/pipe fittings through anchor block
label | 13974826-b6b4-5224-b595-da3fe2d1d805 |  | note | Action - W
label | 96f12947-78ac-54f8-81a7-0ebd739f426c |  | note | Minimum Test Frequency - All pipes through thrust block concrete
label | 0f79aa3f-3b96-5e65-962d-205bcfbe7701 |  | note | Inspection / Test method - Visual Inspection
label | e85ada9e-380e-5182-9c8b-0a570e276091 |  | note | Acceptance Criteria - Wrapped in 2 layers, extending 50mm beyond edge.
label | 7d73b76c-dcb5-54e1-9c92-ee5f00af896b |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.16 - Thrust / Anchor Blocks
label | 8a799167-58b9-58df-b8f2-43474806a448 |  | note | Detail of Activity - Thrust block construction
label | c72d7bf7-99b7-5322-ad94-559ca018ff9d |  | note | Action - W
label | d3be45eb-3b60-5b90-9f5a-ff40d7dadf42 |  | note | Minimum Test Frequency - All thrust blocks
label | 23f65904-d71d-500e-9dc0-395f5e9de99f |  | note | Inspection / Test method - Visual Inspection
label | 9ec50ee0-b153-5ed8-9ce9-16d6fd6b502a |  | note | Acceptance Criteria - 17.5MPa concrete with 7 days cure time (no loading).
label | 4a55dc35-8370-54bd-be12-f84b650a3c5b |  | note | Record documents - Watermain Pipeline QC Sheet
checkpoint-status |  |  | checkpoint | 400.17 - Thrust / Anchor Blocks
label | eb941c75-05ba-5192-bd72-88321502873d |  | note | Detail of Activity - Engineer's Inspection
label | 90bb0e8e-6d49-5d3c-8290-2776aa79ef25 |  | note | Action - H
label | 31a2b343-2ecc-5859-8727-1c4c0b7b4a4d |  | note | Minimum Test Frequency - All thrust blocks
label | 722a0650-f643-5f5f-94fc-9e67e8ec7b8d |  | note | Inspection / Test method - Engineer's Confirmation
label | 88be94c2-cbea-506b-9495-9bbe38d567c1 |  | note | Acceptance Criteria - Engineer's acceptance
label | 90cdc951-18e1-51d0-bf37-cc44c7bbfefe |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.18 - Valves
label | 4dab3fa9-8841-57d0-9c49-6733369e8ea7 |  | note | Detail of Activity - Check valve levels are within tolerances
label | 1f1943b2-3fde-50c8-aef2-99a51b2ce025 |  | note | Action - H
label | 3e11ce63-bfd6-53a7-aae1-8732e21b700d |  | note | Minimum Test Frequency - All valves
label | 0adedd8d-56ff-5c33-8e09-a1ecfdaa5c82 |  | note | Inspection / Test method - Visual Inspection
label | 7f211685-f05f-5060-97a0-3d01122e9707 |  | note | Acceptance Criteria - Grass Berm: +5mm / -5mm
label | 7a10a653-2b60-54ea-8ce6-79010b982eab |  | note | Footpath or seal: +10mm / -0mm
label | 3ec8d63e-a398-5d51-ae71-747e90e4963b |  | note | Heavy Trafficked Areas: +10mm / -0mm
label | 0625174f-de2e-58cc-9da5-9e297d17c8b4 |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.19 - Backfill in Berm
label | 2a0a8c44-0828-5b5c-b074-5e93f12111bb |  | note | Detail of Activity - Layer Thickness for compaction
label | d7acd4cc-624a-5785-9659-64bde2de6b0d |  | note | Action - M
label | cd37bbe9-dc88-5dfa-b70d-f3face9a6560 |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 6b6debb6-12d6-5452-b33b-88b1bfad4e73 |  | note | Inspection / Test method - Visual Inspection with tape measure & photo.
label | 37819956-e373-5ac0-8482-c75c8c4f6905 |  | note | Acceptance Criteria - Layers ≤ 150mm thick
label | 6cd5c2b9-b1ec-537e-bbd3-b07bd495c6eb |  | note | Record documents - Contractor's site diary and/or photos
checkpoint-status |  |  | checkpoint | 400.20 - Backfill in Berm
label | 2d8a1612-6283-504c-a4a4-0c2b19862317 |  | note | Detail of Activity - Berm Compaction - as-dug material
label | 874b001f-4a86-5292-bdd1-c518b4943142 |  | note | Action - H
label | e4e82b46-35fa-56f3-b459-dcda992537cc |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 2dc3b0c2-9358-59e8-a17c-1087815d6bce |  | note | Inspection / Test method - Scala Test
label | 20583398-e1e8-5a51-94ce-42f51ce73637 |  | note | Acceptance Criteria - Scala result of 4 blows per 100mm at 300mm depth.
label | 520afbdc-0570-50af-81ef-222971a2e1e0 |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.21 - Backfill in Berm
label | 2c8c7e82-0c25-5601-a142-1eaa58791f15 |  | note | Detail of Activity - Berm Compaction - imported GAP40 hardfill material (as-dug unsuitable)
label | a0acb571-d395-5068-860c-93c58d1314d0 |  | note | Action - H
label | 0b74c38c-dbb4-5773-9ddf-331ef5f3fb8f |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | e49213d8-2cb6-5aad-b3de-07214cd691f0 |  | note | Inspection / Test method - Clegg Test
label | ca733c9e-0e05-5fa9-8a11-0c1669546f67 |  | note | Acceptance Criteria - CIV ≥ 15 at top of trench
label | f1e8f37e-954a-5bf3-88a1-60a5c197a54e |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.22 - Backfill in Road
label | 13a45997-ce3d-57fe-8341-76d259bf1793 |  | note | Detail of Activity - Subgrade: Carriageway Compaction - as-dug if suitable or GAP40 hardfill to subbase level (500mm below FL)
label | 556eaa58-b357-59f9-8b2e-fda834b995d7 |  | note | Action - H
label | e3fb25cb-36f7-5013-8f72-f69dd2346fc7 |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 55268838-2b2c-5afb-af8e-9676da0e27e9 |  | note | Inspection / Test method - Scala Test/Clegg test
label | 869974b4-15ce-56d9-ac68-47e21158be26 |  | note | Acceptance Criteria - Scala to 500mm. Target = 3 blows per 100mm.
label | f79fc93d-b103-5511-952b-45cd7de3d4c8 |  | note | CIV ≥ 12
label | d6fcdddc-a2f0-56d2-8621-5ce242c47f16 |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.23 - Backfill in Road
label | dd49a5d5-e029-569b-a175-e1f2c604c2ac |  | note | Detail of Activity - Subbase: Carriageway Compaction - GAP 65 subbase (to 80mm below FL)
label | edd28012-3606-5ab5-b470-74c766f1e45e |  | note | Action - H
label | 5133031e-bbf9-543d-8033-2590c01d7d02 |  | note | Minimum Test Frequency - Every 20 lineal meters.
label | 40ba3886-51fe-567b-933d-2ae7e1acc79c |  | note | Inspection / Test method - Clegg Test
label | b6522157-2d52-58a1-a21a-9b6e439689c0 |  | note | Acceptance Criteria - In road (granular) clegg every 300mm lift (i.e. 2 lifts). CIV ≥ 20.
label | d184d4ee-4b25-5de9-8c9b-afd30e007fc6 |  | note | Record documents - Watermain Pipeline QC Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.24 - Trench Surface
label | 6d0fcab5-0b5b-5764-bcb2-5373817f8345 |  | note | Detail of Activity - Visual Inspection
label | bfb1be8a-3894-5af0-9f41-e88797d51c3f |  | note | Action - M
label | bf357ce6-8310-59e9-a8e3-ec6e502352c8 |  | note | Minimum Test Frequency - All filled trench surfaces
label | 97400de8-7b89-5ed1-9643-19c4b361e3cf |  | note | Inspection / Test method - Visual Inspection
label | f1453ac6-8d0a-5500-a60d-ab4420d67587 |  | note | Acceptance Criteria - Left appropriate for temporary or permanent use (as applicable). I.E. temporary sealed, left flush or ramped with surrounding area and maintained.
label | b9fd1536-06ac-58fa-a27f-12188da1725a |  | note | Record documents - Contractor's site diary and/or photos
checkpoint-status |  |  | checkpoint | 400.25 - Pipe Testing
label | f8293820-713e-52ea-8ae6-a9495992ad91 |  | note | Detail of Activity - Sterilization
label | e5e2cdb0-0739-5edf-a298-c23cd2038e7a |  | note | Action - H
label | 4ed5030f-ce61-5317-81f2-751000eb33bc |  | note | Minimum Test Frequency - All pipelines
label | 8a76a347-845c-5faf-a4ea-8c0fce2bbc85 |  | note | Inspection / Test method - Residual Chlorine Test
label | b1632b95-1f20-5a80-9630-303def8eed55 |  | note | Acceptance Criteria - Test passed
label | 813b729c-9943-5bb7-9c12-b2fac3d88a97 |  | note | Record documents - Watermain Pipeline QC Sheet / Results Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.26 - Pipe Testing
label | 259f33d7-ad13-5b53-acf1-3997f0ed6401 |  | note | Detail of Activity - Pressure Testing
label | 9e3d7c10-a012-55fb-93d7-9dbd37ac10cb |  | note | Action - H
label | 13ed5302-2e07-50ec-aed4-bde29129ff23 |  | note | Minimum Test Frequency - All pipelines
label | 874ac193-7223-5ac4-ab30-c3214f47d3ea |  | note | Inspection / Test method - Pressure Testing
label | 396bb61e-6bdd-55e1-961f-aa44314241b5 |  | note | Acceptance Criteria - Test passed
label | 28a93ef4-aaa1-5bea-b845-fa660c6a2c3c |  | note | Record documents - Watermain Pipeline QC Sheet / Results Sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | 400.27 - Collate above documentation
label | 000f670a-1d3e-56db-9d26-5c1c1d8eb229 |  | note | Detail of Activity - Document review
label | 2f9065b2-b701-5cc7-88bb-fd6184388200 |  | note | Action - H
label | 591faf52-94ba-5e15-828b-c055335a7880 |  | note | Minimum Test Frequency - Each ITP
label | d16e5c0d-f595-5f1f-9e9d-37a8df2fddc3 |  | note | Inspection / Test method - Review
label | 43774ac7-117e-5345-8dd7-791beb510b91 |  | note | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | e2c1f006-c956-5786-bf39-a192614bb855 |  | note | Record documents - Review
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.28 - As-built drawings
label | 8bc22391-8cb1-5041-8b22-89775ae9d8df |  | note | Detail of Activity - Survey
label | 1f50cfdb-d833-5136-b4c0-c3f2cd0230e7 |  | note | Action - H
label | c7fb2d5a-3559-5e8b-aaf1-b19622370587 |  | note | Minimum Test Frequency - At completion of construction
label | 3fa54fac-a344-5ce7-8fff-abfeadb6afb5 |  | note | Inspection / Test method - Asbuilts to be submitted at the completion of construction, information to be captured
label | fcd54269-9a5c-5b8c-91d2-915145a6c25c |  | note | Acceptance Criteria - Asbuilts reviewed and submitted
label | 804e6aa0-5997-575e-b996-dc8a82fdeaec |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 400.29 - Acceptance Certificate
label | 6cb172ed-9e5b-5666-971a-d71cda24d897 |  | note | Detail of Activity - Acceptance certificate jointly signed by contractor and respective service owners.
label | a62ed8c2-26e3-512b-a7f1-42c96a3c7ddc |  | note | Action - H
label | 7cd9211a-3c18-5217-9531-c0908385b1b7 |  | note | Minimum Test Frequency - At completion of work or stage
label | 0f0bd67c-bd6c-5301-bf32-8a8d1c294866 |  | note | Inspection / Test method - Certificate
label | 01326cc1-6b0f-5c6a-9cbd-c4c430ca9e1b |  | note | Acceptance Criteria - Submission of jointly signed certificate.
label | 02b8ce7b-da7a-5a1d-8b2e-e1d140ceb8ce |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | bcf6969b-6e25-5928-be8e-fbf11e3ecdae |  | textbox | Contractor's Rep Name:
text | 0038f27a-c77d-57c0-8485-edbf5a1bb226 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Traffic Signals | itp |  |  |  | Yes | ITP - Traffic Signals | 07795f08-0b93-4954-81f0-16c8e0a0e5c8
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 900.1 - Method Statement Development / Job Safety & Environmental Analysis
label | 105adb0f-1c29-5920-b613-a31caeff3580 |  | note | Detail of Activity - Prepare shared services trench construction methodology and Job Safety & Environmental Analysis suitable for site (eg access, working areas, proximity to slopes, traffic and other site hazards, construction stages proposed)
label | 94715ac7-45c8-58da-94d4-e79b547a47db |  | note | H
label | 314d319c-a92a-5bf8-aa93-eb091d88943a |  | note | Minimum Test Frequency - NA
label | ed97f43b-1ab7-508f-93f5-996b43c26780 |  | note | Inspection / Test method - NA
label | 48e2266e-4018-50db-bd00-ef259ddb72ee |  | note | Acceptance Criteria - Method Statement and JSEA Completed and signed by relevant authority.
label | 2e554bf3-e29d-5af2-9861-cb3f958e8ddf |  | note | Record documents - MS & JSEA
label | 65469b65-1585-5d90-9240-84113515cdd1 |  | note | Responsibility - Contractor
label | d053055b-723e-5625-849e-077515eaf40c |  | note | Comments - Method Statement and Job Safety & Environmental Analysis to be provided to Engineer for review prior to commencing excavation on site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.2 - Drawings and Specifications
label | 2f1c2202-c737-58d0-b2aa-f34c2938afd7 |  | note | Detail of Activity - Check drawings are for construction and latest revision. Check Specification is for construction and latest revision
label | 16994a3f-9dcb-5eca-8e30-5209cacf75e0 |  | note | H
label | fce5f9ae-2183-5bed-ba2e-cdf6e9edbac6 |  | note | Minimum Test Frequency - NA
label | ab31859d-f495-5e45-9cb6-01eb64116137 |  | note | Inspection / Test method - NA
label | 9485376b-7cab-5610-a568-8d4900dd8ace |  | note | Acceptance Criteria - Drawings and Specification are the latest revision.
label | 9f75aa88-4a51-51c7-b27f-859c1e8278d0 |  | note | Record documents - IFC Drawings and Specification
label | 77cfac0f-b320-514f-ae86-e517bce1f9b3 |  | note | Responsibility - Contractor
label | 9e0850a6-e05d-5ee5-b046-f5d73d2574cc |  | note | Comments - Up to date drawings and specification to be reviewed before construction.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.3 - Power Connection
label | bb10f087-ea4e-5552-aa38-0344e97bcd8e |  | note | Detail of Activity - Ensure power supply is organised and connection is in place
label | a78e39ad-c499-56fb-b9cd-6e5214d429bb |  | note | H
label | a79c8267-ad2a-5511-b78b-08d8efb6dc4f |  | note | Minimum Test Frequency - once per set of traffic lights
label | a01e4d9a-b6b6-5e1d-975d-76d1941f9e03 |  | note | Inspection / Test method - NA
label | 81b9064a-2160-51e8-b96a-7955bcd1ff8b |  | note | Acceptance Criteria - Complete NC1 form and ensure ducting for power is in place.
label | b8a7b4aa-4c56-5c7b-8017-93c233e46d84 |  | note | Record documents - NC1 Form
label | 9fe26c6d-a28d-5dc6-8632-ae7d61e00f48 |  | note | Responsibility - WSP / Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.4 - Comms Connection
label | f585f3d7-33d4-5dfe-99d3-0439d902db8e |  | note | Detail of Activity - Ensure comms connection is organised and ducting is in place
label | 123cb97a-689b-5800-955a-364c48ead526 |  | note | H
label | 9b529345-6fd2-5066-848f-3a05c7572f9f |  | note | Minimum Test Frequency - once per set of traffic lights
label | d780acfc-2252-5a9a-9085-0acea37435cb |  | note | Inspection / Test method - NA
label | a2cbfb9f-c6d1-5a95-a5e8-00034f9c96b5 |  | note | Acceptance Criteria - Liase with service provider and organise connection (UCG) Universal communications group.
label | d0803876-fbcf-555c-8390-c5c12a6cb943 |  | note | Responsibility - Contractor
label | 23bc0734-26e1-501a-b5ff-5ef856e0f21a |  | note | Comments - Order connection from Chorus
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.5 - Survey Set Out
label | faf840a2-7db5-5ac5-aa99-e17c6dd3e67a |  | note | Detail of Activity - GPS Setout of the shared services trench location as per the construction drawings.
label | a54ae7c7-c4a8-52f8-b2a8-9b99b50defb2 |  | note | W
label | bb806397-6bce-511b-ab71-dae3760ddb40 |  | note | Minimum Test Frequency - All shared trenches.
label | cf26677e-c881-5960-9f64-0262d1b60253 |  | note | Inspection / Test method - Visual Inspection
label | 00597f42-48cc-5b01-8884-2621a0fe57a0 |  | note | Acceptance Criteria - N/A
label | 60b00f0a-9d8b-533f-a0fc-908fd9edb244 |  | note | Record documents - Contractor's site diary and/or photos
label | ffc7b735-7454-5185-9edb-be4cb486b79a |  | note | Responsibility - Contractor
label | 9747205a-ef17-5c95-8b4f-6245c7e5a853 |  | note | Comments - Setout location prior to commencing works.
checkpoint-status |  |  | checkpoint | 900.6 - Sediment Controls are in place for the particular section
label | ddd96093-ee36-5bbf-9f8f-cca049ba12af |  | note | Detail of Activity - Check ESCP and ensure any controls needed are in place before excavation.
label | 901db767-ddd8-5be0-9c61-4168c27adc57 |  | note | M
label | 46ded844-74aa-5df7-a5d2-e96c1a3458f2 |  | note | Minimum Test Frequency - once per section
label | da8f3b3e-b04e-5115-843c-3939e12917b4 |  | note | Inspection / Test method - Visual Inspection
label | cb663310-36fd-597c-a07c-35e6609aa885 |  | note | Acceptance Criteria - Erosion and Sediment controls are in place prior to starting works.
label | 8ecfd64d-216f-5e60-b9a4-77bb7f9470e0 |  | note | Record documents - Contractor's site diary and/or photos
label | 33c08e3a-ac3d-5239-91b2-f2ee09ce13d8 |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | Construction and Finshing
checkpoint-status |  |  | checkpoint | 900.7 - Element Locations / Positioning / Types
label | 5d301014-9e15-5529-bdb4-ee665ccce6e4 |  | note | Detail of Activity - Walk over with TTOC, WSP, TSL & Downer representatives to agree positions of intersection elements
label | 6660a64a-483e-56df-9f7e-5ff006b86999 |  | note | H
label | 56d226c3-fc73-5b4b-8b38-94f62d7b0edc |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | 0cb067a3-5f17-5354-89b6-9d0c09c850f5 |  | note | Inspection / Test method - Visual Inspection
label | 46264ac8-ad19-5937-9302-567021b8fa94 |  | note | Acceptance Criteria - TTOC, WSP, TSL acceptance.
label | 830d852d-b4c2-5d15-b2c7-fe5accdca13d |  | note | Record documents - Written confirmation
label | 4400c05c-90fd-50c7-8f6b-0b690d9addd4 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.8 - CIS Production
label | 572712d7-783e-55a4-a644-d16a8f4f2b6f |  | note | Detail of Activity - Draft CIS to be produced, independently reviewed and approved.
label | 3b27ce38-8e52-5e16-b530-1e881e9cf4eb |  | note | H
label | bc4aca45-9c22-59a4-bfca-3148a61db2ff |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | d7407b3c-12d3-50b6-b4f0-99963f765542 |  | note | Inspection / Test method - Document Review
label | 92fe801b-de2f-5807-895e-604cca4e0b76 |  | note | Acceptance Criteria - Review completed and development approved.
label | c671aea4-4709-5a73-8110-bfbc4d24dc63 |  | note | Record documents - InEight Documents
label | c8756b0e-1821-5271-ba48-2860d8ea4f7a |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.9 - Software Testing
label | bf0f66aa-b468-578a-897e-579b7b0cd719 |  | note | Detail of Activity - Software to be independently tested using traffic signal emulator software (SFT Testing)
label | 4d0c2719-ee84-56f2-9731-172c1efb8a4a |  | note | H
label | f62137d2-3116-5068-8b9d-797eeef592c0 |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | ad270cd4-67b4-585c-b696-602d3d8f2d27 |  | note | Inspection / Test method - Document Review
label | 7a2883d1-c14e-5f0d-be3c-26afb66cabcc |  | note | Acceptance Criteria - Approval for release received.
label | 4ec71430-4c11-5f98-9755-01745fa16a39 |  | note | Record documents - SFT Test Result Summary Sheet
label | e60fba1c-b905-5b04-b1c1-608889513b08 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.10 - Software Testing
label | 0ef7b159-66d7-588d-80c8-eebcd661a4ea |  | note | Detail of Activity - SFT files provided to create PROM, bench testing to be completed by TSL
label | 06859e5f-e5d9-5ce6-b540-956e378d3273 |  | note | H
label | ba5cdfb1-e1a7-504b-8f2e-2b96bd7ebf2a |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | db4455da-756f-5681-9dab-2455063af60e |  | note | Inspection / Test method - Document Review
label | c13f3485-c56e-5da2-b292-03d9e8c97211 |  | note | Acceptance Criteria - Pass result for bench test on "Appendix H - Controller Bench Testing Form".
label | 80eb7553-3c44-561d-b8df-a5226b7488b3 |  | note | Record documents - Appendix H NZTA P43
label | 1327b2f4-0615-5265-b64a-fc8a630f04d3 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.11 - Pole - Installation
label | 57cfac5e-44c4-5818-8b8c-6d58a6263457 |  | note | Detail of Activity - Ensure poles are plumbed vertical
label | e6850dc1-fe67-558f-84d3-097503e03ca0 |  | note | W
label | 4c18a130-6a24-50be-b930-f2c8383244cd |  | note | Minimum Test Frequency - Each pole
label | c37b833a-42c2-50e9-bdaa-409857d95d73 |  | note | Inspection / Test method - Location/Position Acceptance
label | 0c885a7b-8a93-50b3-97bf-6b7441aa0905 |  | note | Acceptance Criteria - Plumbed vertical
label | a56bbe7c-eb24-5100-9e0e-af21f49ef7e2 |  | note | • Tolerance: +/- 10mm per 5.0m length
label | 607a6578-b696-5cbc-a502-14d6ea350c59 |  | note | Record documents - QC Sheets
label | c646c59c-8578-51f6-b4e2-f0564d6de76b |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.12 - Pole - Identification / Finishing
label | fb9020ef-f800-5293-8d5c-fecb6d4e5cbd |  | note | Detail of Activity - Pole Number Verification
label | 80f3a163-8c39-5764-b86b-a0d734ae6336 |  | note | W
label | 429f24ca-a303-523d-8faf-fb6f71d5866a |  | note | Minimum Test Frequency - Each pole
label | b55e9df7-c0d1-52db-862e-17e28e6a38d1 |  | note | Inspection / Test method - Visual Inspection
label | 61d03303-db1a-5941-ac6a-8166993fc89b |  | note | Acceptance Criteria - Ensure poles are numbered correctly and match the CIS sheets (pole numbers match program and diagram numbers).
label | e4512c65-a2e6-56b3-b5d8-b371a2c683f6 |  | note | Record documents - QC Sheets
label | ba410db0-1771-52a6-a13c-4178d5887fc5 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.13 - Pole - Footings
label | 813f8acd-081b-5756-b875-8db363ace475 |  | note | Detail of Activity - Footing Type
label | 73b63e40-d802-55f7-9ab1-1677e9c664f3 |  | note | W
label | f1a0af8d-da24-51b3-9998-2ac54f51327f |  | note | Minimum Test Frequency - Each pole
label | 1b1f90d1-a246-5c41-b0d3-a8cac14e9b0a |  | note | Inspection / Test method - Visual Inspection
label | ab340585-deac-532e-acd2-30351eb51325 |  | note | Acceptance Criteria - TSL engineer confirmation that poles are founded securely and have adequatley sized footings for the site conditions.
label | 28356d70-135a-522d-925a-a23834c0dc3e |  | note | Record documents - QC Sheets
label | 46416c62-9a39-5be4-8f0b-51fe12ed7651 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.14 - Pole - Footings
label | 442d06f3-dd69-52ab-9a19-5ca878cefe59 |  | note | Detail of Activity - Soil Bearing Strength
label | 6ac36f0c-4cf0-5afc-8060-2d3bc87f0443 |  | note | H
label | b3d2f349-4b9d-5dcc-b077-42e66f70c130 |  | note | Minimum Test Frequency - One per pole cluster area (i.e. north-eastern corner, median etc.)
label | 24fd07c3-bd16-5226-bf71-2abaf8a23295 |  | note | Inspection / Test method - Scala Penetrometer
label | e00ef5a6-4b21-50e4-a00d-3f06eaebff36 |  | note | Acceptance Criteria - Average 3 blows / 100mm over 500mm or per comments
label | 0ef31632-696e-539b-a74b-52e9588feb03 |  | note | Record documents - Scala Testing
label | 508b5a4d-53a4-5bf8-9832-1948b923bc4d |  | note | Responsibility - Contractor
label | bc9997f6-248e-5351-96a5-c00b316859af |  | note | Comments - Scala results to meet or exceed per below:
label | f6570498-c6d6-5c5a-8ce1-d4f14609272c |  | note | 0mm - 100mm - ≥ 3 blows per 100mm, 100mm - 200mm - ≥ 2 blows per 100mm, 200mm - 300mm - ≥ 2 blows per 100mm, 300mm - 400mm - ≥ 1 blow per 100mm, 400mm - 500mm - ≥ 1 blow per 100mm
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.15 - Pole - Footings
label | d7725886-a521-56ad-931b-95d2f3373b08 |  | note | Detail of Activity - Concrete Foundation Dimensions
label | 35b377e1-c9ec-583f-bd2e-a1c2eb797d60 |  | note | W
label | 3cef9e6a-4d7d-5f6b-b56e-62dfd9140844 |  | note | Minimum Test Frequency - Each footing not within concrete or asphalt.
label | 1d59b4e7-2431-5e5f-9888-f54a75ca040d |  | note | Inspection / Test method - Visual Inspection
label | 1ef3fb62-5e4c-5f66-93de-a62adcc3b1f8 |  | note | Acceptance Criteria - Where a pole is not surrounded by concrete, the pole must have 500mm2 of concrete surrounding it with a depth of 150mm (20MPa as below).
label | ed067392-815e-5896-88e4-b266fa993a62 |  | note | Record documents - QC Sheets
label | 7e697dac-05f0-5816-8a59-29551d1b57d9 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.16 - Pole - Footings
label | 91aed092-7863-5f30-bcba-ca84856041d0 |  | note | Detail of Activity - Footing Concrete Strength
label | 87940460-5553-5346-9a8c-755f45500a09 |  | note | M
label | 6a6042c4-ac78-5b60-ac96-2063955d6d2d |  | note | Minimum Test Frequency - Each footing requiring concrete
label | aa61b13b-50f4-55ab-8b7c-d3ada3579bfa |  | note | Inspection / Test method - Visual Inspection/Concrete Dockets
label | 8db32eb1-e667-53a7-b3a0-f8e11ee780b3 |  | note | Acceptance Criteria - Confirmation footing concrete strength (where required - i.e. delivery dockets) is min 20MPa at 28days, or as specified in foudation design.
label | ed9e3013-58ca-5943-8345-fb302b5158d3 |  | note | Record documents - QC Sheets/concrete dockets
label | a6d94807-7a6b-5ecd-9cc5-fd8beed7ed41 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.17 - Cabling
label | f7a81a81-0677-5807-976f-08f469376b0f |  | note | Detail of Activity - Continuous Lengths
label | ef06cfc8-9f27-54cc-947f-e295f89d120e |  | note | M
label | 42a20b9e-6931-50db-93bf-1f1f0ab9a6e4 |  | note | Minimum Test Frequency - All lengths
label | e63f1e75-f4ce-5f6f-b278-cbae0e455a78 |  | note | Inspection / Test method - Visual Inspection
label | 1e6c5e9d-0878-5ac9-8e1d-ed59018ed5be |  | note | Acceptance Criteria - Cabling to be continuous lengths from controller to the pole, and from pole to pole (i.e. no joints between poles).
label | 55bb2de9-7b92-56be-a881-dc05a1e016eb |  | note | Record documents - QC Sheets
label | bd64db07-d2a8-52cd-857e-2bc95291851a |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.18 - Cabling
label | f7ec46c8-b503-579d-b5de-05caab527290 |  | note | Detail of Activity - Looper Feeder Cable Slack
label | c6514376-488a-5aec-bb0a-0c4478556edc |  | note | M
label | e4cb704e-cd19-572d-969c-e89f9f724ae5 |  | note | Minimum Test Frequency - All lengths
label | 817e8e6d-73c4-5c06-8613-12d56e57b98c |  | note | Inspection / Test method - Visual Inspection
label | 786fa568-2782-5cf9-ac51-e8160ae71de6 |  | note | Acceptance Criteria - Following cable slacks to be provided:
label | b24d7035-c982-5bbd-afd5-f6b7d6b5de3f |  | note | – 1.8m (minimum) at controller base
label | 4ab2c433-eee1-5940-8e72-794a85fe368c |  | note | – 0.5m (minimum) inside KSJB
label | ca816e3d-9216-5ae9-be3a-dc4a943a961a |  | note | Record documents - QC Sheets
label | ec5e6ef0-a04d-5338-bb3b-7950130634b3 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 900.19 - Cable Termination Chart
label | d6ce7219-dd81-5d87-8eed-dd51a5cf3ea4 |  | note | Detail of Activity - Provide cable termination chart in controller cabinet.
label | 4914d6bb-9819-5ba5-a7db-543be1112230 |  | note | H
label | bdd11eb1-39b1-5f3e-8854-1cf9eb6b5655 |  | note | Minimum Test Frequency - Each controller cabinet
label | cea169db-3d5a-5a5f-8ef5-beeb0659cddb |  | note | Inspection / Test method - Inspection
label | ee72b100-2202-5f99-9427-a1e7684d1c37 |  | note | Acceptance Criteria - Cable termination chart provided.
label | 10ccc2dd-31dc-5fcb-9810-c086745289ac |  | note | Record documents - QC Sheets
label | 0adde78e-dda2-5006-9ed2-3d89444994fd |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.20 - Earth / Earth Loop Impedance Testing
label | 86e6c8bc-bf8f-5e96-96ee-74cfdc05a0ef |  | note | Detail of Activity - Complete earth loop impedance testing per 3.15.2 of NZTA P43.
label | 2912ebed-ec65-57ee-8c34-7acd7efb5d28 |  | note | H
label | 11195267-e82f-5d38-99a3-855f3ece3d49 |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection as specified in 3.15.2 of NZTA P43
label | 15ea2858-d5f1-5c2b-9065-fbafa988d2fe |  | note | Inspection / Test method - Inspection
label | 270f5d2f-7f32-55a1-8be8-eeae8b05202b |  | note | Acceptance Criteria - Submit results in a report.
label | fb4d9d11-80a7-58d9-9ada-2cee2015b2f4 |  | note | Record documents - QC Sheets
label | fbdc1180-6a8d-5ea6-adac-4e40187fbb9f |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.21 - Loop Testing
label | 788fb157-b8fb-53c7-8a47-dd2a763ee4f5 |  | note | Detail of Activity - 500V test from the isolated conductors down to earth.
label | cebd87a3-04b2-5e73-b7f6-7f286a290aeb |  | note | H
label | f36760fd-4604-57ed-a073-12975de3bfcb |  | note | Minimum Test Frequency - All loops
label | e93a179a-79f6-5465-a576-e3bb28295a36 |  | note | Inspection / Test method - Electrical Testing
label | e81534aa-210e-5e05-9fb7-515fcbf7a88d |  | note | Acceptance Criteria - Result ≥ 10 megaohms.
label | 90b90f46-4549-5ff0-b9c0-706183479633 |  | note | • Q ≥ 15 when measured in the kerbside junction box (KJB).
label | 41f17f3b-c48a-5ff0-a8f9-76baa8427442 |  | note | • Submit results signed by technician who conducted the testing and in a report.
label | 9350339a-fc4e-519a-88b6-f0da0d14da6d |  | note | Record documents - QC Sheets
label | 4e86d1d4-3c31-50a1-b84d-f772176d3ba3 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.22 - Loop Feeder Cable Testing
label | 828f6b66-409e-51cc-97f0-8f60c77de52a |  | note | Detail of Activity - 500V test from isolated conductors down to earth.
label | abcc2cb5-298a-5de0-8c78-f7d139e140b8 |  | note | H
label | f668757c-1a5d-57f2-9820-93011dc2dfe8 |  | note | Minimum Test Frequency - All feeder cables
label | f703d431-a83c-58bd-a849-bf28040b2450 |  | note | Inspection / Test method - Electrical Testing
label | b7419fa8-4fb7-5079-8f87-4ba3c16b0b4f |  | note | Acceptance Criteria - Result ≥ 10 megaohms.
label | c5acf66d-550b-5881-b886-ad15523900af |  | note | • Resistance of feeder cable ≤ 10 megaohms when measured at the controller. Submit results signed by technician who conducted the testing and in a report.
label | 8cdb0b3c-81ac-5383-86f3-f96300b173c3 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.23 - Log Book
label | 521d941c-9da2-5dec-8bac-fc8a2f6145b7 |  | note | Detail of Activity - Log book detailing any attendance at site, reason for attending and brief description of work carried out.
label | 8aa9ba60-931a-5ef5-aac6-cf5e3b642a42 |  | note | H
label | f028a4ad-46d0-5553-b667-cedfd65b9d81 |  | note | Minimum Test Frequency - Once per controller box
label | 9fa7a20b-cfce-57d2-a37a-0debf80a9bb3 |  | note | Inspection / Test method - Visual Inspection
label | 93762220-ea42-59ed-b367-0cd69f23b9a2 |  | note | Acceptance Criteria - Log book provided/completed as required.
label | b28c7222-1904-5ec3-ac27-ed39d3b26456 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.24 - Site Acceptance Testing
label | 04f189fe-a43e-5a02-bdb9-a80de142eefa |  | note | Detail of Activity - Completion and sign off of TTOC-07 Site Acceptance Test (SAT) documentation.
label | f4f616d9-4a0c-5c41-aab6-129193cc65f3 |  | note | H
label | 5c9b57e5-c7c3-5bb3-8008-eeedaac2825a |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | 41d2af85-927a-542d-84b9-2debdf531f91 |  | note | Inspection / Test method - Inspection / Audit
label | 75f2479d-feba-5071-98cf-b31f150ee7aa |  | note | Acceptance Criteria - All requirements satisfied and TTOC Traffic Signals Engineer signed acceptance of SAT document.
label | d8e0b99f-3335-50a2-a757-363ce1272608 |  | note | Record documents - TTOC-07 SAT
label | 7e31aaf9-f656-5896-8c98-6a7d0cb51bf9 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.25 - Electrical certificate of compliance and record of inspection
label | bb1f7fd5-b833-5791-ae9f-2951cf7cbfa9 |  | note | Detail of Activity - Complete COC and ROI.
label | a7815f59-b632-592c-b73b-57819934d99c |  | note | H
label | 74f20b7d-e97f-5885-83d3-ed30909823e0 |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | 161d0154-5e59-50c5-b327-b888fe2c5a91 |  | note | Inspection / Test method - Inspection / Audit
label | c14fc511-6ba1-58b0-a591-c4d0ba227fcf |  | note | Acceptance Criteria - Submit COC and ROI.
label | 40bd3889-f314-53a7-8788-a08ef5fe9476 |  | note | Record documents - COC & ROI
label | 33cf7acd-2674-58ed-b3aa-cdd6000249c3 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.26 - Commissioning
label | 2b6a9268-6b88-5164-a0f8-a91c460f7288 |  | note | Detail of Activity - Submit completed and signed Appendix H forms 5 working days prior to commissioning.
label | 41d43728-468d-5801-8e8f-04d7d6ef83a0 |  | note | H
label | cb9e3609-af38-5f9f-9cce-293047c45bd7 |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | 3ec4ed0d-32e5-5d55-88fa-5e1ed11e420c |  | note | Inspection / Test method - Document Submission
label | 0d49582d-d876-574c-bcd9-5cd901293e63 |  | note | Acceptance Criteria - Submit Appendix H forms to TTOC.
label | 9e4a2437-aba7-53c8-9e30-728ba1a40a26 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.27 - Commissioning
label | 8e8a7240-af94-52cb-af6f-3ceabddd5bbc |  | note | Detail of Activity - Notify TTOC with 48hrs notice before commissioning lights.
label | 40885ef8-2101-5789-904b-b17cf6671719 |  | note | H
label | 0d18345c-57a3-58e4-a5d7-600cb63971a5 |  | note | Minimum Test Frequency - Once per set of traffic lights/intersection
label | 2fda3dc9-6c7d-5f83-bc95-917e844f1a7a |  | note | Inspection / Test method - Inspection
label | e8b043ef-d442-51d9-8a8d-92536d17249a |  | note | Acceptance Criteria - TTOC Acceptance.
label | 3fc74bbc-6b2a-5fc7-9dde-1dfe8ad936b8 |  | note | Record documents - Written confirmation
label | 48fb6c97-425c-598e-a916-0f6809b14a0e |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | 900.28 - Collate above documentation
label | 55f20c0e-9684-56cd-abc4-c0d161c4671b |  | note | Detail of Activity - Document review
label | 1be4b1e3-1748-59a9-a0e1-703228ffe97f |  | note | H
label | 3d58b9db-9595-517e-a77e-7507e33870f4 |  | note | Minimum Test Frequency - Each ITP
label | 81c4fe26-c11d-5a5a-b833-e7a8151a92e7 |  | note | Inspection / Test method - Review
label | 88d97789-4bf0-5286-b7f9-17f50c82b856 |  | note | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | 7165cd74-84f4-5c52-b359-01a431888527 |  | note | Record documents - Review
label | f0b8ebc3-b281-527a-9433-7eabe1db03f5 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.29 - Controller cabinet documents
label | 2cb622fd-460f-53dd-a608-49a6a3cc4071 |  | note | Detail of Activity - Controller Cabinet Information
label | ab25afb2-bf7c-5642-a4f8-aef4ad95fcf4 |  | note | H
label | 1eda2f01-3a97-5bfa-bd26-3a48196c67cc |  | note | Minimum Test Frequency - At time of commissioning
label | 5524a14e-cc72-553d-92f5-1d02821b6791 |  | note | Inspection / Test method - Review
label | cca5fb79-ad74-531f-b63e-c3d4e177ec78 |  | note | Acceptance Criteria - Laminated copies of below placed in document pocket inside controller cabinet, within two weeks of commissioning:
label | c5ed4026-faaa-5031-ba94-3f42ffa7cf6e |  | note | – As-built plans
label | 14287aa3-de21-57f5-88f6-28995ff3d8b8 |  | note | – Completed cable termination chart
label | 77da0412-589f-549b-82ca-c9bfe6f896d7 |  | note | – Controller Information Sheet (CIS)
label | 9f88de8a-a5ff-5e16-b204-ce52e53f34c0 |  | note | – Log-book
label | b900b676-e34a-5f93-9ed2-e645833f7b3f |  | note | Record documents - Review
label | a9a79c56-0212-537e-a2d5-2f431c4139e8 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.30 - As-built drawings
label | c83c3901-e447-563c-9303-ae9c10221895 |  | note | Detail of Activity - Survey
label | ba72b262-629a-5ea9-b4b6-01243d4b39b5 |  | note | H
label | 76fb8e38-3dc4-576f-b64f-e120560f2fa0 |  | note | Minimum Test Frequency - At completion of construction
label | d767eca4-be94-5f0b-b6a9-ae2be1e1bbf7 |  | note | Inspection / Test method - Asbuilts to be submitted at the completion of construction, information to be captured regularly.
label | f24dfecf-e558-521f-9276-39e64476e4fd |  | note | Acceptance Criteria - Asbuilts reviewed and submitted showing final location of all poles, access chambers, KJB, loops, lantern displays and cabinets. Completion and sign off of TTOC-08 Site Asset Collection Sheet/Appendix K of NZTA P43 documentation.
label | 2c3d0851-c501-5d2b-9fbc-213f7e07c266 |  | note | Record documents - In Eight record
label | 966e497e-5536-5f43-be05-b1099f7db27a |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - Contractor
label | 4c1a6dc2-03c1-5613-bbf0-16ec52cf1d8d |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 6c8379b2-46c7-5162-8c3b-44e00c71fcc9 |  | textbox | Contractor's Rep Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Client Final Inspection - BBO Engineer
label | 8e034b10-848c-5ded-bedc-3745e81e4425 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 28d9cac6-c115-569e-8057-4acda09e0c02 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Side Road Pavement | itp |  |  |  | Yes | ITP - Side Road Pavement | 2cfba3d9-449a-4da6-ba6a-eed0c5b69af5
checkpoint-group |  |  | section | Pre-construction / Preliminary Compliance Requirements
checkpoint-status |  |  | checkpoint | 600.1 - Method Statement Development / Job Safety Analysis / Enviro Site Specific Plans
label | f37a1f03-66ac-540b-9767-3ed18ee4a578 |  | note | H
label | cf418726-7ce0-5d1e-b17f-3630c8538106 |  | note | Minimum Test Frequency - Prior to Construction
label | fdf327e3-a2e6-5097-9c24-69602d86146b |  | note | Acceptance Criteria - Method Statement and JSEA Completed and signed by relevant authority
label | 2b3731cd-2c8f-57a2-a59a-c78914fb29b9 |  | note | Responsibility - Downer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.2 - Drawings and Specification
label | e784e90f-cfe0-5fa0-b9f7-b8c92d1d2485 |  | note | H
label | 5c86c434-6c48-5e47-9839-8acb1673c186 |  | note | Minimum Test Frequency - Prior to Construction
label | 1dab21ac-fd76-54de-b0a8-687546d1912f |  | note | Acceptance Criteria - DWG’s and Specifications are of For Construction and latest revision. Reviewed and approved by Designer and Client.
label | 7d341d69-a767-51dc-8633-f4a195052169 |  | note | Responsibility - Downer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.3 - Set out
label | b4a2d1bf-5dcd-5c91-a46a-82d724602d6d |  | note | H
label | de11f0da-6c9a-5ffb-b671-1b1319b2cd41 |  | note | Minimum Test Frequency - Prior to Construction
label | db82ab98-bb9b-5cec-acfd-f30de6e96e33 |  | note | Acceptance Criteria - Set out as per latest Design Model / For Construction Drawings.
label | a03439cb-25ab-5785-b0fb-c02bf26b9960 |  | note | Responsibility - Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.4 - Material Approvals
label | 1321141e-a0a8-5128-a7bf-b6c08577c7e2 |  | note | Detail of Activity - Submit testing data for the following materials: AP65
label | c1bdd53a-a587-5431-bc24-83a29d8b75d5 |  | note | H
label | 236ba9de-8ec9-5b01-936f-82962e929177 |  | note | Minimum Test Frequency - Prior to Construction
label | dd1ecdeb-671f-51a4-9446-819492e12d9b |  | note | Inspection / Test method - Quarry Testing Data
label | c6ee1f3e-6658-5d68-a986-6a2789cdfc9a |  | note | Acceptance Criteria - Material approvals to be sent to the Engineer. Refer Project Specs and Drawings;
label | 399c8db8-21e7-5b78-91eb-474025a9680b |  | note | • AP65:
label | 389d7f3d-dabd-5c26-a02a-ca23ab428199 |  | note | o Crushing Resistance < 100kN
label | bc98f046-82a0-5d93-a013-aa973a1baf35 |  | note | o Weathering Quality Index of A,AB, AC, BA, BB or CA o Sand Equivalent ≥ 25 if > 4% passing 75um sieve
label | 36194fb4-5472-500e-b3d8-175aa28ab2d0 |  | note | o CBR minimum 40 using heavy compaction
label | 3a6e6a08-99b1-574a-980d-5519636e4704 |  | note | o Grading
label | e494feef-018e-51e6-aaca-b61181d6ae61 |  | note | Responsibility - Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.5 - Material Approvals
label | 0b20d7c2-8ce6-56d0-bb8d-9394029458a2 |  | note | Detail of Activity - Submit testing data for the following materials: AP40
label | c50d8f00-dcb0-5d26-b470-8b5c841631d8 |  | note | H
label | 7accb6a1-3721-5ee0-850c-797e5757a741 |  | note | Minimum Test Frequency - Prior to Construction
label | 7f34890b-7af4-5215-8c6f-8676ce30910c |  | note | Inspection / Test method - Quarry Testing Data
label | cd48e964-e221-5a8e-9fc5-e2c9b2706224 |  | note | Acceptance Criteria - Material approvals to be sent to the Engineer. Refer Project Specs and Drawings;
label | 73f61c49-9bd7-5198-9332-d8573299a3c9 |  | note | • AP40:
label | f757e0ce-00c4-5b9d-9c61-fa36da1a9496 |  | note | o Crushing Resistance <10% fines passing 2.36mm under 130 KN load o Weathering Quality Index of AA,AB, AC, BA, BB or CA
label | edb7d163-aec6-5683-9980-66e0869e2ef4 |  | note | o Sand Equivalent ≥ 40 o Soaked CBR ≥ 80%
label | 2b0db6e5-7a96-57e0-9c5f-2b262a6638c1 |  | note | o Solid Density > report value only
label | 32525862-a3b6-5f2f-8dba-f2bc72ddfa5f |  | note | o Determination of MDD & OWC > report value only
label | 1fcfcf3d-9d32-5715-a5f0-377854223cfd |  | note | o Broken Face Content: each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces
label | 7ae0b712-0c5a-5c4c-bc24-e4236b124235 |  | note | o Particle size distribution / Grading
label | 35aea5c8-5101-55dc-a4a7-9594c20c292b |  | note | • 100% passing 37.5mm
label | 79a484e5-f012-5289-80f0-9b02bc9df895 |  | note | • 66 - 81% passing 19mm
label | e6bf46a8-194d-595a-b0ab-8eb96d72dd40 |  | note | • 43 - 57 passing 9.5mm
label | 915bf45e-1bf4-56d8-b2f5-372a0a08f328 |  | note | • 28 - 43 passing 4.75mm
label | fcdd74f1-a0bf-5e95-8bc4-80dc9b132e4a |  | note | • 19 - 33 passing 2.36mm
label | c126ae75-a5d8-5867-848a-f8dfe7b26f0b |  | note | • 12 - 25 passing 1.18mm
label | a433e419-355a-568c-b982-3a54402ce6f3 |  | note | • 7 - 19 passing 600µm
label | 8c4c89a9-33e6-5f99-8823-969c104692f8 |  | note | • 3 - 14 Passing 300µm
label | c2a6fd3d-2fca-5424-8400-45adad5ba8b8 |  | note | • 0 - 10 passing 150µm
label | beb06025-bb99-54ff-9c6c-3c9d6baa13e3 |  | note | • 0 - 7 passing 75µm
label | d248831a-1731-53a8-81d8-f7b8364e5a19 |  | note | o Plasticity Index: Basecourse passing the 425μm
label | 160a1c15-fa53-55b0-a91d-44be1b9a2791 |  | note | o Sieve shall not be greater than 5 when the aggregate is tested according to NZS 4407 : 1991, Test 3.4 Plasticity Index Test.
label | 5dc0982d-70f7-55d5-b208-868bddc80ba4 |  | note | o Clay Index: Basecourse passing the 75μm sieve
label | 96195bc6-60dc-58a3-affa-295858be8361 |  | note | Responsibility - Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.6 - Identification of Underground Services
label | b09be4ea-e15c-5887-bb87-9e7ac42c7743 |  | note | H
label | b84a9f77-0b66-56db-b717-34e82c13b60e |  | note | Minimum Test Frequency - Prior To Construction
label | 2c73daf8-9346-56d4-a591-facfdff363db |  | note | Acceptance Criteria - Ensure underground services are positively identified and asbuilt. Where this interferes with design permanent works, Service provider and Designer to be notified immediately.
label | a7fcce56-c1ab-5c1f-8407-50e9524ea764 |  | note | Record Document - InEight Records
label | 292eb8ef-7bb5-5031-83ee-d08e30b81c82 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Subgrade Construction
checkpoint-status |  |  | checkpoint | 600.7 - Subgrade Inspection
label | d9f341d9-d599-5b3c-96c6-72e5528370e2 |  | note | Detail of Activity - Subgrade Levels
label | 3827de46-c91b-50d9-94df-85eae97d26e3 |  | note | M
label | d5c0e8a4-b364-52ae-9503-b6f250a99bfe |  | note | Minimum Test Frequency - 20m centres
label | 317a530e-a5c5-56b0-8dd0-7e36b78a079a |  | note | Inspection / Test method - Visual Inspection
label | f09f0ca9-0cd4-5c86-9363-2a04d22315f7 |  | note | Acceptance Criteria - Cut subgrade to 355mm below finished level. String line tolerance to be within +0mm/-30mm (i.e. 0mm high, 30mm deep)
label | e5fbc269-49ce-5e85-83b5-2bd042bec794 |  | note | Record Document - QC Sheets
label | e80272ab-e4f3-54ee-8e65-7527a7c36d9a |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.8 - Subgrade Inspection
label | e242246f-3080-5cfa-babf-0679f4841a38 |  | note | Detail of Activity - Bearing Strength
label | 7883f27b-f2d3-5070-bb79-5fb622af844d |  | note | H
label | f769337c-13cf-58b8-8fbf-fe420225167c |  | note | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2.1 per 20lm
label | b29d029e-a39d-52a3-8a69-0bcb0eeffcba |  | note | Inspection / Test method - Scala Panatrometer
label | 8dc665b4-d208-5292-811b-b1710adfbd8a |  | note | Acceptance Criteria - Scala (bearing Strength on insitu subgrade) to depth 500mm, with the following requirement to be achieved;≥
label | a15c2d86-4246-5d01-bcea-e3a8fa8b74f0 |  | note | • 5 blows per 100mm - No undercut 4 blows per 100mm - 100mm
label | 6ec31768-3159-5fe4-93f7-704b0295274f |  | note | • 3 blows per 100mm - 175mm 2 blows per 100mm - 275mm
label | 9fea2af5-4a37-5200-a7c7-0b6f8105657a |  | note | • <1 blow per 100mm - 500mm undercut
label | 58e11b6e-630a-572f-908a-b83b14669353 |  | note | Record Document - QC Sheets (Scala Sheet)
label | 4555545f-95ed-501b-a3d3-be2590315cb1 |  | note | Responsibility - Contractor
label | 3ee03db8-2036-51e2-9e47-ea7da9ba9ede |  | note | Comments - Scala results to meet or exceed per below:
label | 2a7a217e-9cbd-5ded-8e04-564e10134425 |  | note | • 0mm - 100mm - ≥ 3 blows per 100mm
label | 376e2dac-64c0-592e-b253-c9a37fbbca26 |  | note | • 100mm - 200mm - ≥ 2 blows per 100mm
label | d6f4f58d-6317-5dfc-9c66-f4416e4910c3 |  | note | • 200mm - 300mm - ≥ 2 blows per 100mm
label | 20548185-02ca-5633-8025-4869d23e9b93 |  | note | • 300mm - 400mm - ≥ 1 blow per 100mm
label | dbc73995-8c1b-5ecd-abc1-1f44f4b55415 |  | note | • 400mm - 500mm - ≥ 1 blow per 100mm
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.9 - Subgrade Inspection
label | ceb42937-68a5-5b41-b3b4-4519191cea7d |  | note | Detail of Activity - Proof Roll
label | 0820055d-92ca-58c0-9eae-c2bed2c2a738 |  | note | H
label | b8b4d29e-f713-5650-b6f3-00e8d7c591a8 |  | note | Minimum Test Frequency - One per lot
label | 28c7af32-3498-5f89-837b-4f0babe76b8e |  | note | Inspection / Test method - Visual Inspection
label | e0d92c3f-a31f-526f-8ed1-d68cadaddaae |  | note | Acceptance Criteria - Proof roll – Check for uniformity, soft areas to be undercut 200mm and backfilled with recycled pavement, AP40 Hardfill or AP65.
label | 5723e1c4-93fb-5bee-b936-18f1e3ad9d43 |  | note | Record Document - (Scala Sheet)
label | 3979ba9a-0aa9-5c60-b066-0424c97dada2 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Subbase Construction
checkpoint-status |  |  | checkpoint | 600.10 - Finished Level
label | ad636a5e-2c09-597d-82d7-3d68e95b6544 |  | note | Detail of Activity - String line or equivalent
label | beea3319-4a48-502d-8a6a-4bb76f421805 |  | note | H
label | 56e96884-d81f-5114-9065-2b2cb5e5f9ea |  | note | Minimum Test Frequency - 20m centres each side
label | 1374bc2e-2cf7-5dd9-b448-bf01f551b872 |  | note | Inspection / Test method - Stringline, tape measure
label | a339ffa2-3a5b-5625-b55c-c9cfa7b4bf31 |  | note | Acceptance Criteria - Layer Finished Level – String Line, each lane, Tolerance: +5mm/-25mm
label | d7ba771b-9cdb-58e3-b000-3362cef6784c |  | note | Record Document - QC Sheets
label | a1ce01ea-6612-5396-a7f2-d3ab17836fb4 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.11 - Compaction
label | 4b1fbc56-0270-5649-b0d9-ee5606cf2d74 |  | note | Detail of Activity - Basecourse Compaction
label | e64a0782-c495-53a5-98b6-ac7c9a0a6999 |  | note | M
label | ef1ce927-2d51-5905-b81e-3d9066c0691b |  | note | Minimum Test Frequency - Direct Transmission NDM (1 per 200m2)
label | eb1b3920-a5e7-545e-8568-4abfba4c4856 |  | note | Inspection / Test method - NDM
label | 5450c6da-f84d-5c3d-9eb6-a212f589f07d |  | note | Acceptance Criteria - Mean ≥ 95% MDD, Min ≥92%
label | 55bc02ab-8cea-5180-a547-4123c82b112e |  | note | Record Document - QC Sheets
label | 499af8b1-1699-5167-8488-021dcf4f2391 |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | Basecourse Construction
checkpoint-status |  |  | checkpoint | 600.12 - Finished Level
label | 18bda73d-ddc3-5b7b-b519-72753ebcf899 |  | note | Detail of Activity - String line or equivalent
label | d2553e53-602c-58d0-9819-cd75604d562b |  | note | H
label | 299c11b8-2b8f-5d74-982b-61713736dec7 |  | note | Minimum Test Frequency - 20m centres each side
label | 740e5467-730a-5df0-8050-ebc633f43654 |  | note | Inspection / Test method - Stringline, tape measure
label | 9d394a49-f423-570f-ac0e-3b97b790d198 |  | note | Acceptance Criteria - Layer Finished Level – String Line, each lane, Tolerance: +15mm/-5mm
label | 08085050-ace5-56ff-9e04-361aca1d5bec |  | note | Record Document - QC Sheets
label | 66fa5f35-337d-5946-aa9e-d8024fa8c383 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.13 - Compaction
label | 4c7e9486-8152-5f2a-a91d-7b57c2d3314b |  | note | Detail of Activity - Basecourse Compaction
label | b005e855-dc7e-5ae6-b1b3-069e084cfe52 |  | note | M
label | 75b7b9c3-c723-504c-976f-0f266e7fda18 |  | note | Minimum Test Frequency - Direct Transmission NDM (1 per 200m2)
label | a35da207-6fbe-5679-97b4-877a9735389e |  | note | Inspection / Test method - NDM
label | 06a697bd-a9db-5f78-b73f-a52b1ed67fa0 |  | note | Acceptance Criteria - Mean ≥ 98% MDD, Min ≥95%
label | d6d2ed87-30f3-5117-ad19-d93811d8ca08 |  | note | Record Document - QC Sheets
label | f6f0e21b-cc70-59ab-9d74-f6f908ad1fd1 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.14 - Degree of Saturation
label | 2614cb9b-1615-57b4-856d-949d4063a6e7 |  | note | Detail of Activity - Basecourse Compaction
label | f980bd4b-066b-5644-aa26-87b7e995aa28 |  | note | M
label | f7ac7652-b571-5a04-aeb5-70d750918ba3 |  | note | Minimum Test Frequency - Direct Transmission NDM (1 per 200m2)
label | 4c507957-ac3d-5ac8-90a6-d7ca2973fa52 |  | note | Inspection / Test method - NDM
label | 5d9b39ed-543a-5a84-8766-66b9c57614e2 |  | note | Acceptance Criteria - < 60% (or 80% on consultation with the pavement designer)
label | 82d746e4-d63f-55ac-a918-be4abcedfd7a |  | note | Record Document - QC Sheets
label | e4fcb6fa-d8ea-559e-9ccc-b7ed221ff63d |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | 600.15 - Collate above documentation
label | 6ebe2651-65ed-5243-986a-8a7a6cce1056 |  | note | Detail of Activity - Document review
label | aa1e1c8a-7e63-5701-8e70-871c96ca18d2 |  | note | H
label | 01d3fb8d-2946-55d8-a9d8-255f03638fac |  | note | Minimum Test Frequency - Each ITP
label | dda21c54-bc3f-5862-866d-0edc592ceb49 |  | note | Inspection / Test method - Review
label | 47119406-a62e-549f-a9bf-4fce1c491311 |  | note | Record Document - N/A
label | b2339bf2-0342-55ec-80a8-1b5f3853d8c7 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.16 - As-built drawings
label | c6a7f79d-63fd-5bae-8113-526a4d0e7e85 |  | note | Detail of Activity - Survey
label | a89ddbd2-7783-52c4-a7cc-46394f04ade9 |  | note | H
label | 61aea587-62f0-5d4f-a76c-e3528096a506 |  | note | Minimum Test Frequency - At completion of construction
label | 261049e5-a6c0-591e-9197-0c6ac9499572 |  | note | Inspection / Test method - Asbuilts to be submitted at the completion of construction
label | dffdba05-759a-5ae2-b200-894d2b0fe546 |  | note | Acceptance Criteria - A s-built to be submitted at the completion of construction
label | cd838f35-344d-50fb-947d-027b48a01acf |  | note | • Information to be captured:
label | e627eed3-9a56-5f4c-a42c-ea82770181a0 |  | note | • Maintain Redline drawings through works.
label | 93959020-8165-5dac-ba08-6ccdf984afbf |  | note | Record Document - N/A
label | ddaeb823-c04e-514f-8d67-f10c0fd843f8 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.17 - RAMM Data
label | b5a2c98c-3d9e-5ead-9028-7df04ca36d54 |  | note | H
label | 8f7a85b5-a29d-5eec-b431-171663d4a7c8 |  | note | Inspection / Test method - Info to be submitted by the completion of project construction
label | 0e4744f8-fb56-555f-aee5-9f0b238b661a |  | note | Acceptance Criteria - Information to be captured:
label | a5d55b7a-b48d-5980-8023-b81d30139987 |  | note | Record Document - N/A
label | 76b1e0d7-42e4-550e-afa4-d7696b1f0ba6 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - Contractor
label | 72cca121-7a32-5f1c-8067-7b8c596493ec |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 070f6b4c-3c10-5ef1-8da7-73a32eeddaf2 |  | textbox | Contractor's Rep Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Client Final Inspection - BBO Engineer
label | 0c48cc09-a675-54a2-a9db-86428df66a57 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 4866bd12-ada6-5e5d-8b8a-d4c5770d9008 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Retaining Wall |  |  |  |  | Yes | ITP - Retaining Wall | b674d29f-959a-4c84-be0e-c444ce5ffcc0
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | .1 - Survey Set Out
label | ad732764-75c8-59c9-ba18-2d799d6c7a1a |  | note | Detail of Activity - GPS Setout of the Retaining wall as per the construction drawings.
label | 967aa605-8a80-5c6c-8c87-765caa5505b1 |  | note | W
label | 1e0de175-7e83-5058-b91e-5061f3cf6044 |  | note | Minimum Test Frequency - Length of the retaining wall
label | 5036012b-51e4-5029-9997-3cd6321499cf |  | note | Inspection / Test method - Visual Inspection
label | 063d6288-d86e-58f8-a6b0-0475b0712ff1 |  | note | Acceptance Criteria - N/A
label | 10aef099-004e-5225-b812-a588aef47949 |  | note | Record documents - Contractor's site diary and/or photos
label | a23aafc0-9e64-5aff-a318-91f44017b6e0 |  | note | Responsibility - Contractor
label | 3133468e-b62e-56d2-a3d5-fa0b8c30a203 |  | note | Comments - Setout location prior to commencing works.
checkpoint-status |  |  | checkpoint | .2 - Materials Approvals
label | acab6a58-62ef-54a3-9591-d584427ad2bc |  | note | Detail of Activity - Submit testing data fir the following materials:
label | d944ef5e-461a-5d30-bd96-017df0410c9a |  | note | – AP65
label | dccd6762-9278-5d37-afbc-35aa0f2cfe83 |  | note | – GAP 40
label | 3e72681f-f08d-5140-9590-e229c15d1bb1 |  | note | – GAP 20
label | e25349a8-6e2e-5fd8-9a81-5e7119eda07e |  | note | – Hardfill
label | 4bd761d4-8299-5ad1-9243-9c2eeb5b309d |  | note | H
label | af7412c9-9335-5b36-8f88-039c4ee72be2 |  | note | Minimum Test Frequency - Once for each material
label | 3b7b4ded-0891-554c-8964-118625a64220 |  | note | Inspection / Test method - Quarry Testing Data
label | c320fdee-c351-5ade-ac3d-29b44ebf6b95 |  | note | Acceptance Criteria - Engineer's Acceptance
label | 50959863-9ec5-5efd-a820-e810b2ef1c93 |  | note | Record documents - InEight Records
label | 2d8a6e5e-c531-5ca3-bbd7-0ad5d0054941 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction and Finshing
checkpoint-status |  |  | checkpoint | .3 - Bases, Footings and/or Toes
label | 0d92c3e7-0259-550e-a063-87a4b0d58fc1 |  | note | Detail of Activity - Subgrade Cut / Base Thickness
label | ed60c655-e00a-5f70-8002-00ee01ebfdd3 |  | note | M
label | 73e6711b-d942-5644-b6c1-3852e6eccb94 |  | note | Minimum Test Frequency - Every 5m section
label | 5e9a1902-ad84-5f76-be66-7dd49ad55abb |  | note | Inspection / Test method - Visual Inspection
label | 599bc99d-decc-5cb8-903a-4c980ddab854 |  | note | Acceptance Criteria - As per drawing
label | 393b0c33-301f-5a4a-8256-1a7db9bc0fbb |  | note | Record documents - QC Sheets
label | bd532e46-50ac-53f8-b2f4-44926f0f9cb3 |  | note | Responsibility - Contractor
label | 4976c1e2-3d1a-5063-bf53-50b7808b315b |  | note | Comments - THE SAFETY OF ALL TEMPORARY OPEN CUTS SHALL BE THE RESPONSIBILITY OF THE CONTRACTOR. THE CONTRACTOR SHALL PROVIDE ANY AND ALL SLOPE PROTECTION NECESSARY TO PREVENT ANY GROUND MOVEMENT.
checkpoint-status |  |  | checkpoint | .4 - Bases, Footings and/or Toes
label | 44e09303-9fbe-5f19-a7c1-4be8bca27a2a |  | note | Detail of Activity - Subgrade Testing
label | 6f6466fd-4d76-5ff6-a33f-8a61d6214430 |  | note | H
label | e58ccaa8-03ce-5834-9ec5-8130b06bb6d1 |  | note | Minimum Test Frequency - Every 20m
label | 6a67f84a-2486-5dd9-9cbc-6aa6ae243efa |  | note | Inspection / Test method - Scalar Penetrometer
label | 0a4d966f-e77d-5cb4-ad69-0b7929a7a525 |  | note | Acceptance Criteria - ≥ 3 blows per 100mm. 500mm depth.
label | 6bec47eb-b7c0-593c-83c3-97f6f2eee2ca |  | note | Record documents - QC Sheets
label | 6d4e888f-e631-5b34-b084-a64e9463e1b6 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .5 - Bases, Footings and/or Toes
label | e23f6817-5ca5-58d9-b4e0-c83fc167c873 |  | note | Detail of Activity - Reinforcing
label | 4fb04d3e-fc89-56b3-8a65-6af36a9ce906 |  | note | M
label | 9132f6a7-7933-5e1c-8e4f-dc8db7e16523 |  | note | Minimum Test Frequency - Every 6m panels
label | 6c1104d0-e791-58e8-9e57-b27e7c8fa622 |  | note | Inspection / Test method - Visual Inspection
label | 66e6dcd7-e255-589b-95b8-d8fc1bcc941f |  | note | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL.
label | 11c5a9ae-6b91-5e86-b006-3ce4739663ca |  | note | • MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | 945600ad-377d-5206-b31a-5494a212cb25 |  | note | Record documents - QC Sheets
label | c9907e4e-2073-5529-82b1-5d647080f657 |  | note | Responsibility - Contractor/Engineer
checkpoint-status |  |  | checkpoint | .5 - Bases, Footings and/or Toes (2)
label | 248e40f6-3a8e-5d0a-a468-1e9b27591b30 |  | note | Detail of Activity - WSP INSPECTION
label | bdd85db4-0de4-59b4-9baa-3eae517ab9e4 |  | note | H
label | 961ad5db-d3c1-5065-8ca6-7fd5bb96fff2 |  | note | Minimum Test Frequency - Every 6m panels
label | 7abcbb09-0af6-5ccd-ab6e-26f2e6c4dc78 |  | note | Inspection / Test method - Visual Inspection
label | 860b0906-e1da-52b3-ac71-754b93c4661d |  | note | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL.
label | a90b6124-00bc-5fd7-8151-5a1db9c813f0 |  | note | • MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | 4366f5d1-a912-5d22-9c6b-450b399fe7cb |  | note | Record documents - QC Sheets
label | a386d624-d994-5e4d-bcfd-e827da8eca4c |  | note | Responsibility - Contractor/Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .6 - Bases, Footings and/or Toes
label | 555214e4-15ed-56db-a271-adc7ccae12ff |  | note | Detail of Activity - Formwork
label | 4e499663-e7e4-5101-bf39-0255fe37d095 |  | note | Minimum Test Frequency - Every 6m
label | 68b36227-bf81-505a-bb9c-ffdd4ac071ff |  | note | Inspection / Test method - Visual Inspection
label | 9258313d-66d8-5203-a407-db029ca7c073 |  | note | Acceptance Criteria - As per drawing
label | b60a0023-a6f6-5f3f-a14e-214c09be2e9f |  | note | Record documents - QC Sheets
label | f954b3a6-f369-573e-8abe-42f9c9505777 |  | note | Responsibility - Contractor
label | 3a07bf6f-8c77-50e5-bd8b-81296f0ca020 |  | note | Comments - FORMWORK SUPPLIED BY DOKA
checkpoint-status |  |  | checkpoint | .6 - Bases, Footings and/or Toes (2)
label | a93ee675-9f79-53e4-a3f8-8a94448d20b1 |  | note | Detail of Activity - Concrete
label | 4c654b2f-f7a3-56e3-89f0-8c742f5339a0 |  | note | H
label | bfb14c78-64c3-504b-8672-5c9d1c13691d |  | note | Minimum Test Frequency - All concrete orders
label | a18fe902-c77f-5d50-8192-a06f2a54383e |  | note | Inspection / Test method - Concrete Dockets
label | e45fe36c-7478-511d-b429-471130a1460f |  | note | Acceptance Criteria - Concrete strength 25MPa at 28 days
label | e5d71eb4-7189-5a23-ad7a-7c2207439ad6 |  | note | Record documents - Concrete Dockets
label | b1944f55-ca54-5128-a50d-4baa5a573caa |  | note | Responsibility - Contractor
label | 226a14f9-1786-573d-93f4-ac6d0b207b4d |  | note | Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE.
label | c1a62ba8-a6cf-54b4-8062-44e4921e3ae4 |  | note | • ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
label | b94313bb-4a8b-5171-a36a-850f374ddb4b |  | note | • THE CONTRACTOR SHALL PROVIDE THE CONCRETE MIX DESIGN FOR THE APPROVAL OF THE ENGINEER PRIOR TO THE COMMENCEMENT OF ANY CONCRETE WORKS
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .7 - Bases, Footings and/or Toes
label | 0d36684b-48bd-5006-b7b8-594a2ff8bdf9 |  | note | Detail of Activity - Dowels (greased and plain ended)
label | d66d11a6-2760-5e0e-b7f8-48127557316c |  | note | H
label | 423db358-6aea-576f-9b74-a540e3a0f523 |  | note | Minimum Test Frequency - Every 300mm centers
label | 55bfa214-b67c-516d-8e75-4a844f9e82b5 |  | note | Inspection / Test method - Visual Inspection
label | a3493e97-0de4-5059-aec8-534351bd4864 |  | note | Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS
label | 0e8254ba-5bbf-51f8-b726-436f0c7ce79e |  | note | Record documents - QC Sheets
label | 3ff3b18a-3c81-5bde-a7f5-aac63504d595 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .9 - Walls
label | 78de2d51-2ad0-58bf-97a8-bc02ea946dba |  | note | Detail of Activity - Reinforcing
label | 8401053a-5b11-5a85-90f0-76604ece4ae7 |  | note | M
label | 0e5f8181-e775-56af-b2cd-f5f326fbcd02 |  | note | Minimum Test Frequency - Every 6m panels
label | 82649a37-d679-5ffd-960a-cc93a4e165c8 |  | note | Inspection / Test method - Visual Inspection
label | a4f4cf7b-0d59-5d10-8f3a-558bebb6355e |  | note | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL.
label | dc337b21-f635-53c1-88bb-c10f602aa760 |  | note | • MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | bffccc93-c699-5bea-bf40-02f856d4f879 |  | note | Record documents - QC Sheets
label | c41b5c21-6667-503d-a9a2-fb5b9c5f9507 |  | note | Responsibility - Contractor/Engineer
checkpoint-status |  |  | checkpoint | .9 - Walls (2)
label | 4e47ac8c-83a4-51fd-87bd-4e1478b10e8b |  | note | Detail of Activity - WSP INSPECTION
label | 20a79f12-c5d9-503f-a4ff-56566de0c22f |  | note | H
label | bb63a194-a49b-5908-a09b-4dd797a4700e |  | note | Minimum Test Frequency - Every 6m panels
label | d9cb24fe-d1c6-545a-8966-dc5ec413b332 |  | note | Inspection / Test method - Visual Inspection
label | a14e82c9-b673-5d3f-8f59-419c259ca1b5 |  | note | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL.
label | f241b69a-cbb1-5233-a933-0b189b7e164c |  | note | • MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | e395a9d3-e6f1-51d6-b2a6-795ec35dc9cd |  | note | Record documents - QC Sheets
label | e9aeac44-2853-5dfa-a6c0-c9f44da7518c |  | note | Responsibility - Contractor/Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .10 - Walls
label | 6058771e-20cf-53b0-be96-563f3a15b297 |  | note | Detail of Activity - Formwork
label | 7a79795d-8c45-5dd8-b334-ead9310a4fc4 |  | note | H
label | 80ea54c7-e2e8-5acc-a7c9-bb6859551411 |  | note | Minimum Test Frequency - Every 5m
label | a9d7bdbd-74ce-5388-ae8f-183f418cf8d3 |  | note | Inspection / Test method - Visual Inspection
label | 7f05ce1a-25e6-501c-aca0-b97913edc127 |  | note | Acceptance Criteria - As per drawing
label | ab97ead9-ca82-5e58-9d54-f390723035c2 |  | note | Record documents - QC Sheets
label | b21e4d79-b6c4-5097-ae26-2f2718f9f2d0 |  | note | Responsibility - Contractor
label | 0b64499c-48a9-566a-bdf0-34f7cb4a46b7 |  | note | Comments - FORMWORK SUPPLIED BY DOKA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .11 - Walls
label | 46e64e3b-5146-51ee-8853-2aceac9ddeff |  | note | Detail of Activity - Dowels (greased & plain ended)
label | 426f4635-a1e3-5386-a8b8-708cd7c91ed3 |  | note | M
label | 66cb1b79-919a-504b-9b05-91a47e36f3f2 |  | note | Minimum Test Frequency - Every 300mm centers
label | 7f6af286-ce42-5be2-8033-4553fa6cfb9d |  | note | Inspection / Test method - Visual Inspection
label | a6cb24fd-bd20-5fe3-88ac-a536b51b02c0 |  | note | Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS SPACED AT MAXIMUM 5.0m INTERVALS OR A SUITABLE LESSER LENGTH IF REQUIRED
label | d0f9ac41-5179-582b-882f-e5ddc7b6166a |  | note | Record documents - QC Sheets
label | b7e1a74d-30c9-5ffb-8e00-3849d0a4414b |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .12 - Walls
label | 50b6cb17-41bc-536d-bc3d-5e86b6eeedfc |  | note | Detail of Activity - Finish / Joints
label | ade0cfb6-399d-5327-90f3-34e6de177970 |  | note | W
label | 7371f567-106b-5e1a-a657-186a7a45c897 |  | note | Minimum Test Frequency - All areas
label | 46d7ed1c-cebf-564e-b5b3-acfbe9ca4b8f |  | note | Inspection / Test method - Visual Inspection
label | 81000cbb-40e5-5185-aad8-e4b183c8da4c |  | note | Acceptance Criteria - Smooth, off shutter finish. Cut joints as appropriate.
label | 1bdeb65f-e261-5d90-9edb-663d4ad6df77 |  | note | Record documents - QC Sheets
label | 325170b0-b2c9-5191-8e4f-9fc7aede07c6 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .13 - Walls
label | 3fbd486d-54cc-5183-bc3a-ab308852378c |  | note | Detail of Activity - Concrete
label | 90c6bd8b-4b33-553a-b674-dacddd8f9159 |  | note | H
label | f7e0ad55-1d7a-595c-a706-172ba06a3ed9 |  | note | Minimum Test Frequency - All concrete orders
label | b1921a98-05a2-5ea4-a53b-28166690bbe1 |  | note | Inspection / Test method - Concrete Dockets
label | c31804e3-597b-5369-8382-f6a1371a1c24 |  | note | Acceptance Criteria - Concrete strength 25MPa, at 28 days
label | 3a137108-b4cf-5246-a1b0-0a311c0d3a3c |  | note | Record documents - Concrete Dockets
label | aa372659-38d0-547e-9845-4d3a958163b1 |  | note | Responsibility - Contractor
label | 78da034c-7982-5e7c-bd1b-96f03ac4e5a3 |  | note | Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE.
label | c1bb3056-cdae-5afe-8af6-5f56a291c502 |  | note | • ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .14 - Walls
label | 42cf30a2-e61d-54eb-b1f0-b09ced491e56 |  | note | Detail of Activity - Weep Holes
label | ca04536f-85c6-5d2c-a1b6-f70668afb9f7 |  | note | W
label | 6f13cab9-4a47-5226-a0af-69ee471fa0bf |  | note | Minimum Test Frequency - Every 2,000mm
label | c4cd8ab0-b3ac-55e9-a7fb-21cf345f2148 |  | note | Inspection / Test method - Visual Inspection
label | 7f91f5f1-6fb4-5bee-81c8-f266cdfa0266 |  | note | Acceptance Criteria - As per drawing
label | edc95259-8354-5ce9-a85a-b561c7a04495 |  | note | Record documents - QC Sheets
label | 77067acf-8bf7-5db0-8a6d-8569a3d0925c |  | note | Responsibility - Contractor
label | 1c0aae70-5147-5527-b6ae-e49a3d4330ce |  | note | Comments - 50mm Ø WEEPHOLES THROUGH WALL STEM AT 2.0m INTERVALS
checkpoint-status |  |  | checkpoint | .15 - Backfill
label | 6b8c2659-9613-518b-9b4d-6a12e4eb9ae3 |  | note | Detail of Activity - Backfill behind wall (Shared service trench)
label | 90894e4d-cfb3-5a10-b758-63387231c495 |  | note | W
label | 19d1e4d1-9f48-58e7-8b97-c661f08316f6 |  | note | Minimum Test Frequency - Refer to Shared Service Trench ITP
label | dec13276-aa40-59d5-82d3-e70df36b31a6 |  | note | Inspection / Test method - Refer to Shared Service Trench ITP
label | 700233e2-de26-579a-984f-9f7dee5d6276 |  | note | Acceptance Criteria - Refer to Shared Service Trench ITP
label | fc6067d1-c333-57b0-ab00-026544f9e3e6 |  | note | Record documents - Refer to Shared Service Trench ITP
label | 7478b117-ad73-5d87-97eb-f659f47ed3d4 |  | note | Responsibility - Refer to Shared Service Trench ITP
label | 2b706ddf-ed44-53a1-9342-b2fd0fb65a85 |  | note | Comments - Refer to Shared Service Trench ITP
checkpoint-status |  |  | checkpoint | .16 - Joints
label | ef6a5909-ac3d-5630-ab75-3a7276c09c74 |  | note | Detail of Activity - Completed Joints
label | e1970a41-905a-56c7-a279-dbd7dbb9af7b |  | note | W
label | 8d075182-8686-57ba-b1dd-1837712ba1c3 |  | note | Minimum Test Frequency - All concrete orders
label | e4cac294-e1f6-5b22-b2c4-9d1d350fcaee |  | note | Inspection / Test method - Visual Inspection
label | 007e08f5-0ba6-57e7-afb0-7ff3d622b650 |  | note | Acceptance Criteria - Concrete strength 25MPa, at 28 days
label | a9293d7f-f5c0-52f7-b684-49169de9908e |  | note | Record documents - Concrete Dockets
label | 92b9885d-5eee-58c8-8604-36bc2c0c5448 |  | note | Responsibility - Contractor
label | a4299cc5-9f65-5190-a576-e5bdfdda8996 |  | note | Comments - SIKAFLEX SEALANT OR APPROVED EQUIVALENT
checkpoint-status |  |  | checkpoint | .17 - Joints
label | e7f2342e-8db1-56e8-9063-6706fd3e3d7a |  | note | Detail of Activity - Joint formwork
label | 4e0a676e-a7a6-5432-a3cc-64c47e3aeb1d |  | note | W
label | 1f6f5164-a739-5597-8bf8-4ce1d1c00cae |  | note | Minimum Test Frequency - At joints between sections
label | 4ac12ac3-e3e1-5ea6-841d-14cbf60a5353 |  | note | Inspection / Test method - Visual Inspection
label | 4fa5380c-35ee-57d1-ac6a-1c12bd4d8bda |  | note | Acceptance Criteria - Smooth, off shutter finish. Construction joints as per drawing
label | 93bc5e15-1335-5a7d-b1c9-1492905e6176 |  | note | Record documents - QC Sheets
label | 8eec121a-cc8e-5c91-89c4-911f91c42267 |  | note | Responsibility - Contractor
label | 5cb34c23-c1c4-5716-a100-037d585346b3 |  | note | Comments - COMPRESSIBLE BOARD BETWEEN WALL SECTIONS
checkpoint-status |  |  | checkpoint | .18 - Subsoil drainage - front of wall
label | 76600f48-d781-5acd-9933-7362ebdbd338 |  | note | Detail of Activity - Subsoil drain - back of wall
label | 1d05c38c-59a4-5b96-aa6f-a96ccd434104 |  | note | H
label | bd84c01a-12f3-525d-89b0-c127e7f6f04c |  | note | Minimum Test Frequency - Length of wall
label | f20771cd-5601-5659-8766-1d1aa84b08af |  | note | Inspection / Test method - N/A
label | c6423d36-d7a4-5056-98a2-59a1b924966e |  | note | Acceptance Criteria - As per drawing
label | 66d91f69-e804-597e-99d3-79b5f5f6fd8c |  | note | Record documents - QC Sheets
label | 5f8b1a33-c913-5c92-a0c5-ebfaa4b9cb83 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .18 - Subsoil drainage - back of wall
label | 953a795c-d711-5872-8c41-5325c98eba00 |  | note | Detail of Activity - Installation of subsoil drain
label | 0c64a1e4-b204-59b1-a55d-6116e3dba580 |  | note | H
label | 3be016d3-1e42-5536-86de-1fdedc83a6e3 |  | note | Minimum Test Frequency - Length of wall
label | cf622e87-7684-56ce-8b59-551be59ab9e0 |  | note | Inspection / Test method - N/A
label | f9cda22d-7518-5ae9-83da-c5c45d798477 |  | note | Acceptance Criteria - As per drawing
label | b253e12b-828f-5547-bb64-cd81a4705348 |  | note | Record documents - QC Sheets
label | 21137880-ec12-5367-b8e2-da1876fb3304 |  | note | Responsibility - Contractor
label | 850e6ea3-9e3c-5eb8-8280-9f25bacc5e1b |  | note | Comments - 100Ø PERFORATED SUBSOIL DRAIN WITH 40/20 DRAINAGE AGGREGATE WRAPPED IN GEOTEXTILE OF STRENGTH CLASS B AND FILTRATION CLASS 2 TO TNZ F/7 SUBSOIL DRAIN TO BE LAID WITH 1% FALL AND DISCHARGE TO THE NEAREST STORMWATER SUMP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | .20 - Collate above documentation
label | 09fd92bd-e3af-5664-bc22-c8e0e7b976ff |  | note | Detail of Activity - Document review
label | 7c07a862-c05c-50a7-86fe-53d6403d8cf7 |  | note | H
label | 43096411-306b-55ef-8408-3a3d79302042 |  | note | Minimum Test Frequency - Each ITP
label | 95789fb6-9a94-5a4f-a060-77d5e5883b24 |  | note | Inspection / Test method - Review
label | b3c69935-dc1c-59c6-bf40-e2532ee391ed |  | note | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | 5868a199-2df7-58c2-bf70-aba087157c0b |  | note | Record documents - Review
label | 4e9dbd2d-bc23-5b1b-a50f-e5dadf42d8aa |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | .21 - As-built drawings
label | 39eb6dc4-0d62-5cf5-9fea-35e28a7e2f94 |  | note | Detail of Activity - Survey
label | 7e455253-bda0-5180-89f8-a831030f1fde |  | note | H
label | f8524b42-e7dd-59d8-86e7-7a4f2fdeac25 |  | note | Minimum Test Frequency - At completion of construction
label | 6d948b7c-4943-52d8-a085-540c002ae4c4 |  | note | Inspection / Test method - Asbuilts to besubmitted at the completion of construction, information to be captured
label | c6f81283-0f72-5c2a-84e5-f04c72183525 |  | note | Acceptance Criteria - Asbuilts reviewed and submitted
label | 1735577b-1016-5186-affe-757d5b85b9b0 |  | note | Record documents - In Eight record
label | f3c7c634-9123-53a2-a743-91f043bd6e79 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - Contractor
label | 451de089-1f68-51b4-b16b-b082c048853c |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 977027b8-95b4-50bd-b972-4dd6fbd3aeb1 |  | textbox | Contractor's Rep Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Client Final Inspection - BBO Engineer
label | e504052f-8467-5ef0-9127-3eff94ce8d34 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | effcd013-472b-5be1-86d2-2cdf0acc9ad0 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Streetlight Installations | itp |  |  |  | Yes | ITP - Streetlight Installations | bbc0fc4c-5a01-48b1-bb9d-8017d569a244
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 900.1 - Method Statement Development / Job Safety & Environmental Analysis
label | d414f2b9-4a66-5d37-ac1a-fe52fd6525e4 |  | note | Detail of Activity - Prepare shared services trench construction methodology and Job Safety & Environmental Analysis suitable for site (eg access, working areas, proximity to slopes, traffic and other site hazards, construction stages proposed)
label | 1a010bdb-680e-58dd-8ec8-6070049abe43 |  | note | H
label | 00deaf04-4650-5cbc-9e86-6849294a46ff |  | note | Minimum Test Frequency - NA
label | 1188b46b-c99e-5d69-ba2b-2af054766629 |  | note | Inspection / Test method - NA
label | 6c93b706-fe16-5191-91e7-20c7a6f32a51 |  | note | Acceptance Criteria - Method Statement and JSEA Completed and signed by relevant authority.
label | 58acf872-4885-50d2-bc13-c65790c53d3c |  | note | Record documents - MS & JSEA
label | ce1d5d51-a685-58d6-a126-396b7ec457e4 |  | note | Responsibility - Contractor
label | 12ed2918-189b-525b-aaae-318b3fda41f7 |  | note | Comments - Method Statement and Job Safety & Environmental Analysis to be provided to Engineer for review prior to commencing excavation on site.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.2 - Drawings and Specifications
label | 67331a00-02bd-5db5-b0af-b6172b641065 |  | note | Detail of Activity - Check drawings are for construction and latest revision. Check Specification is for construction and latest revision
label | 187fb9c6-72e8-5a97-b882-f39c48757aaf |  | note | H
label | 7afac494-0e89-5949-9b1d-5222c468590d |  | note | Minimum Test Frequency - NA
label | 6d938523-bb51-5d20-9748-b3acaac6b0c6 |  | note | Inspection / Test method - NA
label | 49a5a329-5cde-5c9f-ab9b-f7202958af9d |  | note | Acceptance Criteria - Drawings and Specification are the latest revision.
label | 02f2ee57-b913-5c18-b7d1-683385cbe0f2 |  | note | Record documents - IFC Drawings and Specification
label | e87f65c0-b245-52fe-9369-9eef67c3da73 |  | note | Responsibility - Contractor
label | 19f12a57-1720-5039-b569-9534b2dc9683 |  | note | Comments - Up to date drawings and specification to be reviewed before construction.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.3 - Power Connection
label | 1f0f723a-be1f-5348-9454-20aeb129e18e |  | note | Detail of Activity - Ensure power supply is organised and is undertaken by an experience and competent contractor.
label | a32642bd-ecec-5ddf-aaf7-eae9ad7a5eae |  | note | M
label | 1cf1867d-53c6-523e-a193-9fd50a440a35 |  | note | Minimum Test Frequency - Once
label | c76372d7-b15a-5e7e-8670-9a224cf9efe9 |  | note | Inspection / Test method - NA
label | 4a67c5a9-bffc-5b66-9f14-df9f1353c0b3 |  | note | Acceptance Criteria - Unison to supply power to streetlight bases, subcontractor connecting streetlights to the network to be "approved" by the local electricity network company.
label | df6238d9-75a6-5ef9-8253-0447c61bb01a |  | note | Record documents - Unison Documents
label | 08165805-58a3-5aff-b325-eb2f1055641e |  | note | Responsibility - Sub-Contractor
checkpoint-status |  |  | checkpoint | 900.4 - Survey Set Out
label | 8c232815-4458-5b61-ae6d-be8cd0a840c1 |  | note | Detail of Activity - GPS Setout of the shared services trench location as per the construction drawings.
label | c11d40c8-dcbf-5d01-b735-f06040cfa77f |  | note | M
label | 2e4da4f0-37f4-5cf4-bc60-4a76b406896d |  | note | Minimum Test Frequency - All shared trenches.
label | b417927b-7598-58b9-abb7-dc9d1f59a049 |  | note | Inspection / Test method - Visual Inspection
label | 288d81f4-4f99-522c-8222-fa2e2154e16a |  | note | Acceptance Criteria - Streetlight set out locations do not clash with other features (i.e. existing/new services etc)
label | 6c5368e1-3613-52a7-b043-43ada135f488 |  | note | Record documents - Contractor's site diary and/or photos
label | ed4f34ea-3fdc-504b-8632-edb5e159c3d9 |  | note | Responsibility - Contractor
label | 5270b44a-1eaf-5897-8863-4be3aeaf9a6c |  | note | Comments - Setout location prior to commencing works.
checkpoint-status |  |  | checkpoint | 900.5 - Sediment Controls are in place for the particular section
label | 016dc589-0ae0-5066-814b-6196b9ab039d |  | note | Detail of Activity - Check ESCP and ensure any controls needed are in place before excavation.
label | ae49410b-7828-58ab-9f51-13054599158d |  | note | M
label | 32092b5d-9440-5dd4-a2ee-a9007caf703f |  | note | Minimum Test Frequency - once per section
label | 41749258-3715-5b47-bf71-871998b38c49 |  | note | Inspection / Test method - Visual Inspection
label | 4f324c0a-aa50-5d0b-8f8e-42d437026ec7 |  | note | Acceptance Criteria - Erosion and Sediment controls are in place prior to starting works.
label | 06fb647e-5cda-5e81-8ccd-1ff9d0dee94b |  | note | Record documents - Contractor's site diary and/or photos
label | 5fe64dc8-9762-57a0-980b-8a03a5f9e9bd |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | Construction and Finshing
checkpoint-status |  |  | checkpoint | 900.6 - Pole
label | c89e3f54-403e-525b-892f-542b5fdd8439 |  | note | Detail of Activity - Assembly
label | 3716f053-7187-5abf-9b21-9cda590aff3c |  | note | M
label | fc8d96ed-3dba-577a-a27e-d8a934dda855 |  | note | Minimum Test Frequency - each pole
label | 5697e374-cb45-5f41-a987-a90d8c00306d |  | note | Inspection / Test method - Visual Inspection
label | eac331bf-d6e1-5038-8c2f-72388deb3bf1 |  | note | Acceptance Criteria - Confirmation by contractor/installer of correct assembly per manufacturers instructions.
label | b1d5352b-d0f0-5e5e-ade6-f2f11a671812 |  | note | Record documents - COC/QC Sheet
label | 984e03ac-e8f7-5078-a0e3-45af5042d653 |  | note | Responsibility - Sub-Contractor
checkpoint-status |  |  | checkpoint | 900.7 - Pole
label | 5cd868fc-d328-51e3-b178-de96c155379c |  | note | Detail of Activity - Installation
label | f03813af-2239-553f-9147-0b4d2212abd1 |  | note | M
label | 690287a1-a5a6-5f64-a86c-c80bf324831c |  | note | Minimum Test Frequency - each pole
label | ae3b1f3c-b2a6-52d5-b956-d13d4e4f2bd9 |  | note | Inspection / Test method - Visual Inspection
label | 59618769-441b-55b8-94c3-9eb854a8d2f5 |  | note | Acceptance Criteria - Installation to be 90 degrees to kerb and channel, pole tilt to be within 2o. Confirmation by contractor/installer of correct installation to manufacturers specification by contractor/installer.
label | b9e2e9f1-c8d2-57b9-bde1-04f96f91010d |  | note | Record documents - COC/QC Sheet
label | a845c3e2-9299-5aba-b52a-e73add4ee599 |  | note | Responsibility - Sub-Contractor
checkpoint-status |  |  | checkpoint | 900.8 - Pole
label | 719ad8c7-0577-5dd8-b9fe-daeb92e2cce7 |  | note | Detail of Activity - Type
label | 0b04bb9a-5693-5964-be1d-c213c34f419a |  | note | M
label | 65abc90a-3ac2-5bf3-ba14-57c1ad56d07c |  | note | Minimum Test Frequency - each pole
label | 6834813b-948c-5a1e-81c7-ed14cdf247cc |  | note | Inspection / Test method - Visual Inspection
label | 15fc758b-ffac-51d4-8a96-170b35df87eb |  | note | Acceptance Criteria - Ensure the correct pole type is installed per the latest IFC drawings.
label | e5124b32-cd8a-55e4-8786-4bf2188387ca |  | note | Record documents - COC/QC Sheet
label | 5748cda8-91a5-5133-a59c-3ed418272298 |  | note | Responsibility - Sub-Contractor
checkpoint-status |  |  | checkpoint | 900.9 - Pole
label | 51cff38d-dd69-5359-a134-da452d20e536 |  | note | Detail of Activity - Footings
label | 04c3a93c-7db5-5a68-88ed-c9e99594ae18 |  | note | M
label | d19f30ac-e46f-5899-8da4-e7e61afe675f |  | note | Minimum Test Frequency - each pole
label | 64a0e303-b112-52ba-a5ba-fcba8c3aeff0 |  | note | Inspection / Test method - Visual Inspection
label | 3b2a2c51-eb36-540d-93a7-195f622cc762 |  | note | Acceptance Criteria - Ensure poles are founded securely and have are adequatley backfilled to suit site conditions. Confirmation by contractor/installer of correct installation to manufacturers specification by contractor/installer.
label | db85b59d-8994-5581-9c3a-dedc66ec607e |  | note | Record documents - COC/QC Sheet
label | 695f50f2-973f-5c3f-b8e5-7ae23ebd8249 |  | note | Responsibility - Sub-Contractor
checkpoint-status |  |  | checkpoint | 900.10 - Pole
label | e5da7f97-ec60-522e-8fdd-06a133950dc9 |  | note | Detail of Activity - Earthing
label | 2d8fb11b-6fe0-5e0c-8745-6e82cd6b85aa |  | note | M
label | b4fd993c-e3c7-52ef-a682-d23b1b3af920 |  | note | Minimum Test Frequency - each pole
label | 362089a4-4724-5172-9e46-81375beb8b79 |  | note | Inspection / Test method - Visual Inspection
label | f57fbb7c-dd2f-5375-867b-c26c859c9b65 |  | note | Acceptance Criteria - Confirmation by contractor/installer that all streetlights are earthed per installation requirements.
label | 14bbe73d-faa1-5873-9e5d-f639c9f2d631 |  | note | Record documents - COC/QC Sheet
label | 5e288461-2479-5734-9d0c-3ac1d100a0f6 |  | note | Responsibility - Sub-Contractor
checkpoint-status |  |  | checkpoint | 900.11 - Luminaire
label | eedcbc72-9408-5b51-a3af-cdd535a5c2e0 |  | note | Detail of Activity - Type
label | 0859dbde-f450-5976-a1ad-7dafc8ba1e38 |  | note | M
label | 7d9259f5-624e-5f72-8b99-6abc93f843c8 |  | note | Minimum Test Frequency - each luminaire
label | 1db88edb-4341-5314-90a1-a404f9e378ab |  | note | Inspection / Test method - Visual Inspection
label | c3d07d46-a132-5823-a6a8-1a47b5113664 |  | note | Acceptance Criteria - Ensure the correct luminaire type is installed per the latest IFC drawings.
label | 623a1bbc-fb73-5a7f-805d-73cd5e4e9383 |  | note | Record documents - COC/QC Sheet
label | f0cc09ea-fc1c-5377-99a9-917a151b1028 |  | note | Responsibility - Sub-Contractor
checkpoint-status |  |  | checkpoint | 900.12 - Luminaire
label | 97b0c9e4-5a13-5225-8c6a-7e328cf5f4e7 |  | note | Detail of Activity - Tilt Angle
label | 73f2339c-b9f7-5680-a7d4-f31c86101dfa |  | note | M
label | a41713f1-7039-5b72-93b7-078eb64bea6b |  | note | Minimum Test Frequency - each luminaire
label | 301e8cfa-1a20-5829-834a-29bc657f6ead |  | note | Inspection / Test method - Visual Inspection
label | 20956629-faa3-5799-b7e9-7158ab3f5abc |  | note | Acceptance Criteria - Ensure the correct luminaire tilt angle is installed per the latest IFC drawings. +/- 2O
label | 5c307be9-97e0-5c7c-9dae-588439a8b9d1 |  | note | Record documents - COC/QC Sheet
label | 1881efeb-e5b4-53fe-8283-53bbdfae1a5d |  | note | Responsibility - Sub-Contractor
checkpoint-status |  |  | checkpoint | 900.13 - Electrical Testing
label | c16412e0-f2a5-5974-97af-3761edf70ead |  | note | Detail of Activity - Test relevant
label | a1793610-5661-5a8b-ae4b-1146c8b909c5 |  | note | H
label | f6df00ea-da55-5e19-a977-98747eb523eb |  | note | Minimum Test Frequency - each pole
label | 60e39ac3-5c53-5c57-b459-ddc7e99aa169 |  | note | Inspection / Test method - Inspection / Audit
label | 61a45217-31d4-5c77-b48f-5353987e3990 |  | note | Acceptance Criteria - Confirmation by contractor/installer that streetlights and circuits have been satisfactorily tested in accordance with Electrical (Safety) Regulations 2010.
label | d35e47a2-7563-5c2f-8013-65075a85d1ee |  | note | Record documents - COC Sheet
label | 427e84c7-2dec-5423-9dcd-5896996eff2d |  | note | Responsibility - Sub-Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.14 - Electrical certificate of compliance and electrical safety certificate
label | 8b518037-935f-5b1e-a7de-85c582f43163 |  | note | Detail of Activity - Complete COC
label | 67759ae5-0ba1-5e1b-be62-d466651e91ee |  | note | H
label | 1a8207d9-7d33-55f4-a662-65d62f526d4c |  | note | Minimum Test Frequency - minimum once per Zone
label | 0f8b4a4b-208f-596b-8b18-c2e1020ee99c |  | note | Inspection / Test method - Inspection / Audit
label | aee5c649-02d4-50ed-beaa-e641f0464cbc |  | note | Acceptance Criteria - Submit COC.
label | 2bdee312-12f1-58f7-a105-05015334a74f |  | note | Record documents - COC Sheet
label | 6d6a4c52-f64f-5711-b831-75c131aab133 |  | note | Responsibility - Sub-Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | 900.15 - Collate above documentation
label | 8f2150c5-290c-53ac-b18a-d832ac5aa4e9 |  | note | Detail of Activity - Document review
label | 91d1d555-10b1-59cb-a2ce-f956b6aba0a3 |  | note | H
label | 35d01c54-6641-5eb7-9da3-bfb65129c959 |  | note | Minimum Test Frequency - Each ITP
label | 4e439697-3b74-5078-beb0-b617794fd993 |  | note | Inspection / Test method - Review
label | 2cfb554c-fba7-5469-98cf-3e424c3b5a08 |  | note | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | 65f41e82-90df-59c1-867b-d49e00d3cfb2 |  | note | Record documents - Review
label | 9a1708c7-3039-51e5-9697-ccd175cac9e7 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 900.16 - As-built drawings
label | dd0c6cbc-0d84-5094-9e4b-cabe3a16bce4 |  | note | Detail of Activity - Survey
label | 7c7fd80f-de2a-511c-8e79-5216948848db |  | note | H
label | e3416704-ca98-5fc5-84a0-c9ea81f7c9bb |  | note | Minimum Test Frequency - At completion of construction
label | 89764132-5456-578f-b848-ff5183268f18 |  | note | Inspection / Test method - Asbuilts to be submitted at the completion of construction, information to be captured regularly.
label | 41504d50-640b-5886-8247-b26169bee6b4 |  | note | Acceptance Criteria - Asbuilts reviewed and submitted (i.e. showing final location of all poles).
label | 9349bf5f-0955-59b9-a033-6f4f1b5d7df7 |  | note | Record documents - In Eight record
label | 9b11e97e-f6ec-5484-9aa2-b387705b1323 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - Contractor
label | 41f8b730-459f-5ca0-b08f-ebcef93760e9 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 645cb222-a3f0-5821-afca-683509d5c9aa |  | textbox | Contractor's Rep Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Client Final Inspection - BBO Engineer
label | 0c4a06c0-2fc5-5e0c-8e56-32f51f7d2530 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 03d20708-f507-5d3a-9a75-a61c1d4dc0c6 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Shared Services Trench | itp |  |  |  | Yes | ITP - Shared Services Trench | e1370c48-9e34-4fa9-8753-6adc9c2eadb1
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 100.1 - Method Statement Development / Job Safety & Environmental Analysis
label | d52f9343-0408-50ca-804b-5befb797cd59 |  | note | Detail of Activity: Prepare shared services trench construction methodology and Job Safety & Environmental Analysis suitable for site (eg access, working areas, proximity to slopes, traffic and other site hazards, construction stages proposed)
label | a746fd45-9d61-5a93-a689-9252bb779e53 |  | note | H
label | 35b9cdaa-7b5d-5aba-9e92-7b6aab78483c |  | note | Minimum Test Frequency: NA
label | 56372370-82e3-5eec-977a-d18075136a0b |  | note | Inspection / Test method: NA
label | fd5dad64-e9ba-5a7d-8ca1-f1a3c4a139a4 |  | note | Acceptance Criteria: Method Statement and JSEA Completed and signed by relevant authority.
label | 17db8fe7-7448-540e-bbd6-e7e809547641 |  | note | Record documents: MS & JSEA
label | 34650602-ec83-55f8-8bff-b62341cbd092 |  | note | Responsibility: Contractor
label | cfb7d730-8324-590d-9b49-1ac99af46f11 |  | note | Comments: Method Statement and Job Safety & Environmental Analysis to be provided to Engineer for review prior to commencing excavation on site.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 100.2 - Drawings and Specifications
label | b783f199-622d-5caf-98f9-4cd3509b3ec6 |  | note | Detail of Activity: Check drawings are for construction and latest revision. Check Specification is for construction and latest revision
label | d00dd963-8752-55af-af34-4a3f811ccb9c |  | note | H
label | b14c8c6a-b0fa-567b-ad0f-51a6fb690609 |  | note | Minimum Test Frequency: NA
label | 21bfa70e-9823-5ddd-abb2-ca0ababea69b |  | note | Inspection / Test method: NA
label | 5d8f42ff-c31c-5ea6-999c-ede6ff4ed825 |  | note | Acceptance Criteria: Drawings and Specification are the latest revision.
label | 1dddb281-9f9d-543c-9383-259654c29e3f |  | note | Record documents: IFC Drawings and Specification
label | c8d02ccd-e924-5df0-950d-d2701c0f4b19 |  | note | Responsibility: Contractor
label | a6dab572-5fc5-550f-931c-b2c89da666e0 |  | note | Comments: Up to date drawings and specification to be reviewed before construction.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 100.3 - Ducting / Piping
label | c1135a14-0814-5b42-a45f-b6986871cae2 |  | note | Detail of Activity: Power, Telecommunications and Gas ducting / piping to be provided by the service provider.
label | b41a26b1-9657-5208-be71-ba8e1906da88 |  | note | W
label | 790a459c-e1df-5972-b47e-27e273ae151e |  | note | Minimum Test Frequency: NA
label | 5f9ad357-bb7d-5466-90c1-1ace9e51ec18 |  | note | Inspection / Test method: NA
label | 285ce73e-2f52-543d-ba09-d045c9ffdb8c |  | note | Acceptance Criteria: All ducting / piping is to be provided by service provider
label | 32a46830-1b0a-59bd-bfea-cb79e04bc230 |  | note | Record documents: Contract Documents
label | db51b181-0ad4-53cb-92c9-2067e170f68d |  | note | Responsibility: Unison, Chorus & Gas
label | 606ff985-28ba-58f8-85f0-9dca66c0bbfa |  | note | Comments: Ensure ducts are ordered and being delivered when needed
checkpoint-status |  |  | checkpoint | 100.4 - Service Pits / Chambers
label | 1b45b1ba-bdc3-5bc5-a915-4a43c2b44c80 |  | note | Detail of Activity: Service pits / chambers to be provided by the service provider.
label | a463a6a8-e0d8-5882-984b-4215699912ac |  | note | W
label | 73435f88-66de-5a3f-8c95-5d15ad8143b0 |  | note | Minimum Test Frequency: NA
label | 1bfe900a-f947-56bb-be71-1362df58171f |  | note | Inspection / Test method: NA
label | 0e4e863a-5fe2-52d0-864d-9a6e4340976f |  | note | Acceptance Criteria: All service pits / chambers are to be provided by service provider
label | bd66fb62-54c3-52e0-bd84-00487904b1af |  | note | Record documents: Contract Documents
label | 6d0c987a-bc3b-5c0b-999b-90e411b575f9 |  | note | Responsibility: Unison, Chorus & Gas
label | 0806ba6b-1b31-5641-ab35-d3451c8991a4 |  | note | Comments: Ensure service pits / chambers are ordered and being delivered when needed
checkpoint-status |  |  | checkpoint | 100.5 - Tape / Mag Slab
label | 8fd54965-5391-592a-864d-5c526dd644f2 |  | note | Detail of Activity: Warning tape / mag slabs to be provided by service provider
label | c64d8cb1-1c47-5e60-814b-f3401818fd8d |  | note | W
label | e32884f8-f922-557d-8ecb-b9347d13f7c9 |  | note | Minimum Test Frequency: NA
label | 6184aa06-7ce5-5c7d-8d03-0978bcf8d93e |  | note | Inspection / Test method: NA
label | 2daf8c70-29e2-54c0-833e-f2253903f658 |  | note | Acceptance Criteria: Warning tape / mag slabs to be provided by service provider
label | 5d2a0039-2a98-56ab-98b4-9669827c5f52 |  | note | Record documents: Contract Documents
label | 4839c1cc-500a-59c1-9519-d60f6620fea8 |  | note | Responsibility: Unison, Chorus & Gas
label | 1e0d1a3d-54c3-5c00-ae0b-c07e5e8a235d |  | note | Comments: Supplied by services provider.
checkpoint-status |  |  | checkpoint | 100.6 - Survey Set Out
label | 91eafdcf-6d14-5dd1-9e95-ae63b195aceb |  | note | Detail of Activity: GPS Setout of the shared services trench location as per the construction drawings.
label | dfd011e7-8ef5-54ef-bc37-e608f78bab70 |  | note | W
label | 9becb08e-42e0-5f36-b67c-1841a41d2df9 |  | note | Minimum Test Frequency: All shared trenches.
label | 5f92234e-18b0-5661-9c07-df2f54229c53 |  | note | Inspection / Test method: Visual Inspection
label | 5e089d83-fb4e-5913-8129-173b51be989d |  | note | Acceptance Criteria: N/A
label | 2f0654cf-8dc8-577f-b976-64e315eaec7a |  | note | Record documents: Contractor's site diary and/or photos
label | 334a3396-ba34-5c89-ae61-d32759f3edde |  | note | Responsibility: Contractor
label | 3ceae959-8a46-507f-bb4c-67daa1b3a256 |  | note | Comments: Setout location prior to commencing works.
checkpoint-status |  |  | checkpoint | 100.7 - Sediment Controls are in place for the particular section
label | adcb36ca-158d-5097-bbf0-97b1451db633 |  | note | Detail of Activity: Check ESCP and ensure any controls needed are in place before excavation.
label | 06aa0448-3edc-5b96-80ab-4c7b323c7146 |  | note | M
label | b812460b-f0b5-5e40-8018-939e3f58f35a |  | note | Minimum Test Frequency: once per section
label | 977f7e25-5ea0-5d9b-afe4-92fc47d74ca1 |  | note | Inspection / Test method: Visual Inspection
label | 0187263c-c7c2-56f5-bb12-9bf4260a2240 |  | note | Acceptance Criteria: Erosion and Sediment controls are in place prior to starting works.
label | e008f9b1-612e-5299-ac8e-36fdcb7d061e |  | note | Record documents: Contractor's site diary and/or photos
label | 0933bc53-98c1-5195-98b0-220e61d952d2 |  | note | Responsibility: Contractor
checkpoint-group |  |  | section | Construction and Finishing
checkpoint-status |  |  | checkpoint | 100.8 - Excavation of trench
label | 944acbca-652d-5fc9-82f4-16773bf0619b |  | note | Detail of Activity: Confirm trench excavation is to the correct dimensions
label | c86d6e16-3e6a-599f-841b-a849ae582980 |  | note | W
label | 516f269f-9cf3-53fe-8a40-ef0a548750d1 |  | note | Minimum Test Frequency: Every 20 lineal meters.
label | 9be6304b-1cb0-5271-a773-d4d25ed6e2d6 |  | note | Inspection / Test method: Visual Inspection with tape measure.
label | eb75479a-4e35-5b50-a4ff-df5f69ccc795 |  | note | Acceptance Criteria: Formation materials in accordance with design assumptions.
label | 46881c51-b44a-554b-bea8-e9c95a1fa7d6 |  | note | Record documents: Contractor's site diary and/or photos
label | 0d5889b5-c71c-5847-97bc-89e5e36a97af |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.9 - Installation of Ducts
label | b489e469-d656-5d64-8fc9-08bf3be41d08 |  | note | Detail of Activity: Temporary Capping
label | 72208796-7c1b-5551-b55c-5921e5e98cc7 |  | note | W
label | 5437b37d-42a8-5fc4-9e69-7bec51e9c186 |  | note | Minimum Test Frequency: At the end of each day.
label | fafe8602-c958-5463-b5fb-a266a5d9e4d3 |  | note | Inspection / Test method: Visual Inspection
label | c41740c2-b4ca-5cd3-887d-1c320ed5231d |  | note | Acceptance Criteria: Ensure any open ends of ducts are temporarily capped to prevent ingress of dirt.
label | 4c4e3ecb-9c87-5348-b13c-f7f3a7f93bed |  | note | Record documents: Contractor's site diary and/or photos
label | 65f3bbcc-0686-5632-9ceb-c8bea3d70bc3 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.10 - Installation of Ducts
label | 586b15f1-d6a1-504d-a63e-1ac18f16b5fa |  | note | Detail of Activity: Duct Spacings
label | d32bfc39-4938-5af2-81a8-7be480307d02 |  | note | W
label | d1303286-3751-5092-a90b-a13d53655b31 |  | note | Minimum Test Frequency: Every 20 lineal meters.
label | 789950f0-2636-512f-ae06-4f5be8bdcb76 |  | note | Inspection / Test method: Visual Inspection with tape measure & photo.
label | da31d5d5-ef2c-5d03-8768-3d77c5ff4025 |  | note | Acceptance Criteria: Check ducts are spaced as shown in the trench cross section.
label | 08fc0278-8c5a-539e-98ce-81fc44e58e74 |  | note | Record documents: Contractor's site diary and/or photos
label | 06cb35ee-ecb7-5099-98d2-2cc90e05d205 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.11 - Installation of Ducts
label | 89c9f853-d097-59cc-a525-1b5fa2b26ddd |  | note | Detail of Activity: Good for purpose check
label | bd4b43db-46e2-52e5-9830-1f5be8fbeb61 |  | note | W
label | 6ea738d4-69df-5e34-bf5e-810fb6268eb0 |  | note | Minimum Test Frequency: Every 20 lineal meters.
label | 0764ded3-4104-57bc-9250-b3678f72be88 |  | note | Inspection / Test method: Visual Inspection
label | c1891e6d-135b-5dfd-b66c-70dfcff129cc |  | note | Acceptance Criteria: Prove. (i.e. laid straight with no kinks, correctly connected, not squashed/damaged, clear of blockages and any materials such as dirt and cement)
label | aa81f576-8256-5bba-8e82-fb7afcb88530 |  | note | Record documents: Contractor's site diary and/or photos
label | 923671dd-5fac-5657-8060-853d50238034 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.12 - Installation of Ducts
label | da30fb25-fad8-55bd-9387-f461d5095e46 |  | note | Detail of Activity: Protective Tape / Mag Slabs
label | 59081a89-4755-5814-9f06-e1304dbae44f |  | note | W
label | fb32e2d0-f8dd-5f74-a3e9-221524abf835 |  | note | Minimum Test Frequency: Every 20 lineal meters.
label | ddfac55b-6b87-5577-9a34-e7ac38b8a638 |  | note | Inspection / Test method: Visual Inspection
label | 0cdb8232-a4e1-5276-9724-cdd73b656c86 |  | note | Acceptance Criteria: Placed in trench as indicated in drawings
label | d93ec248-5543-5c4d-9e55-3c01e1f69b9c |  | note | Record documents: Contractor's site diary and/or photos
label | 0bf191ba-d3cb-5c7d-886d-001dfa4222bd |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.13
label | a96c7ad5-7b2a-59b2-b6aa-2f33919ac0fb |  | note | Detail of Activity: Compaction
label | 3557cc6c-97be-54a1-b893-52795e1ad478 |  | note | H
label | f444e8c5-5337-5492-9050-48635c4a3293 |  | note | Minimum Test Frequency: Every 20 lineal meters.
label | 565eff4c-6c72-5156-95c8-67d1d18ae96a |  | note | Inspection / Test method: Clegg Test
label | a201fa26-0a95-5162-b93f-aa5ee886d849 |  | note | Acceptance Criteria: Top of trench in berm. CIV ≥ 15.
label | c8888937-6ffe-5770-9908-6fd22aa5a9c8 |  | note | Record documents: Scala/Clegg QC sheet
label | 0fa93df0-6b54-57e5-975b-3354dfa0e928 |  | note | Responsibility: Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 100.14
label | 0bb6b3f8-503b-5e5b-8c57-89f13eaa3236 |  | note | Detail of Activity: Layer Thickness
label | 0963df86-56ee-57ee-bd37-966e85b8b50f |  | note | M
label | f7357e82-224d-58ef-a297-f19a27b1e381 |  | note | Minimum Test Frequency: Every 20 lineal meters.
label | 4284bdab-d4b1-5559-9378-bb6db2e86476 |  | note | Inspection / Test method: Visual Inspection with tape measure & photo.
label | 0aa0ba52-0023-558a-8cd8-40c836be5dfe |  | note | Acceptance Criteria: Layers ≤ 300mm thick
label | a6c2dee6-ff4c-511f-a17d-6e9eb729250c |  | note | Record documents: Contractor's site diary and/or photos
label | 13d20b4b-2b59-589e-8ff7-03371f385f12 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.15 - Pavement Layer Construction
label | 8c37175c-5078-501c-b393-1200b366abe4 |  | note | Detail of Activity: Subgrade
label | 9d3e0d94-51c5-59f9-8384-65b08452209a |  | note | M
label | 8a1512cf-9eb0-5bb3-9e38-1706974e8692 |  | note | Minimum Test Frequency: Every 20 lineal meters in pavement.
label | 0db043f8-2ac4-5291-bdfa-868b709a7c31 |  | note | Scala Test
label | e05d2ff3-0e5f-5ff6-8fcc-746651161337 |  | note | Acceptance Criteria: Scala 500mm deep. Target = 3 blows per 100mm.
label | 0092dd7d-b075-5115-a3ef-49f6c056011c |  | note | Record documents: Scala QC sheet
label | eac23ca3-1122-5951-b995-1dcdfbc72efe |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.15.1 - Pavement Layer Construction
label | d6c021b2-50af-5b6f-b5f1-75a9e194ca9f |  | note | Detail of Activity: Subbase
label | d3da921a-5b80-5b72-82d6-cc92cafcb096 |  | note | M
label | 8c33dfb7-2ab5-559c-8355-501628f51069 |  | note | Minimum Test Frequency: Every 20 lineal meters in pavement.
label | 9ec937e7-5a05-5291-820e-87caba207855 |  | note | Clegg Test
label | a9cdd4b6-21f4-5d65-b671-483aa0ad2248 |  | note | Acceptance Criteria: In road (granular) clegg every 300mm lift after thermal backfill. CIV ≥ 20.
label | 43414843-69e6-5741-a484-82b74b825724 |  | note | Record documents: Clegg QC sheet
label | b329b8ba-4805-5750-97bd-6550d3527be7 |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.15.2 - Pavement Layer Construction
label | 0149b2bf-72b0-5847-88bf-7251ec50d7af |  | note | Detail of Activity: Basecourse
label | 1d9179ef-c60e-5f03-88bb-1ce2ec5dbb83 |  | note | M
label | 76dfcb64-6730-5288-9934-3339bd81c839 |  | note | Minimum Test Frequency: Every 20 lineal meters in pavement.
label | 9ce15986-7bb8-5a33-ac0e-5aaeb9e5f966 |  | note | Clegg Test
label | 458c1c00-ffbd-58b4-b45d-57a1b00f7d71 |  | note | Acceptance Criteria: In road (granular) clegg every 300mm lift after thermal backfill. CIV ≥ 35.
label | 58e1fd57-db7c-59e7-8939-ca3b2417e244 |  | note | Record documents: Clegg QC sheet
label | d2fc887a-37bd-535f-a2ab-0b7c0997a2cc |  | note | Responsibility: Contractor
checkpoint-status |  |  | checkpoint | 100.16 - Finished Surface
label | fa2f6ad4-a1b8-55c1-929f-1d873cdd7c68 |  | note | Detail of Activity: Visual Inspection
label | b000732a-b8e0-5578-a1e3-b9c5c91a6b41 |  | note | M
label | eca696a4-dda3-5030-bdf2-c51364b179b5 |  | note | Minimum Test Frequency: All filled trench surfaces
label | 4d44339c-191a-5373-b9bf-9452bd591956 |  | note | Visual Inspection
label | 258a9d04-3958-5741-aff4-4addcc64ae50 |  | note | Acceptance Criteria: Left appropriate for temporary or permanent use (as applicable). I.E. temporary sealed, left flush or ramped with surrounding area and maintained.
label | 80b3aeb7-1112-5563-a375-7ce7f7f11b42 |  | note | Record documents: Contractor's site diary and/or photos
label | bdf7dad0-18ca-5bc3-9730-a94644cd42f7 |  | note | Responsibility: Contractor
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | 100.17 - Collate above documentation
label | c0489889-e6d9-55f0-903c-c578a88b218d |  | note | Detail of Activity: Document review
label | 7a3f857d-aad9-5d94-b3ed-efd8dc77f03b |  | note | H
label | 30f4d8f2-46f3-5d9e-851b-aa6bd59d588e |  | note | Minimum Test Frequency: Each ITP
label | 8ed650af-8521-53c6-855d-2c19af41d6f5 |  | note | Review
label | 59f24eb0-33af-5f0b-90a1-33345dcaa920 |  | note | Acceptance Criteria: All above documentation is shown as attached to this work pack.
label | 3228fb03-f5c9-5880-9e35-7fbde2b83ee5 |  | note | Record documents: Review
label | a4168edd-dc43-5142-865c-43f4fd9b4faa |  | note | Responsibility: Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 100.18 - As-built drawings
label | 857ca7ef-bd82-538e-b51b-27bc296ea91f |  | note | Detail of Activity: Survey
label | c06ad5cb-339a-5f78-aa17-6b962549025b |  | note | H
label | 173646fd-b510-58b6-94b1-bc7ea782b13e |  | note | Minimum Test Frequency: At completion of construction
label | a4b47731-c905-5314-b1a8-044104ea807c |  | note | Asbuilts to be submitted at the completion of construction, information to be captured
label | 9a103b79-1dc3-593f-a882-68184401f0dc |  | note | Acceptance Criteria: Asbuilts reviewed and submitted
label | 535bd078-10fb-5ddb-b795-7c81c0048c9b |  | note | Record documents: In Eight record
label | 1707528c-ec41-5beb-b34f-6d42626bb857 |  | note | Responsibility: Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 8b9cc965-0e0a-59e6-981b-deda5e98f736 |  | textbox | Contractor's Rep Name:
text | ce0f743d-4f04-5bde-a1fb-786791c0bd15 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Concrete Works |  |  |  |  | Yes | ITP - Concrete Works | e5058e26-62ec-4413-82ef-dfdeabaa3d53
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | .1 - Survey Set Out
label | f5c75a8f-cb04-5751-b309-86fd58d4c014 |  | note | Detail of Activity - GPS Setout of the watermain as per the construction drawings.
label | 8003f692-1a43-5a61-9f58-5360b32cb52e |  | note | Action - W
label | f9b45156-f179-50b7-be97-49cb2e5b3063 |  | note | Minimum Test Frequency - All lengths of watermain and connections
label | a03e3d8e-a5a5-593d-ab48-46c46103846f |  | note | Inspection / Test method - Visual Inspection
label | 77543751-c045-5d30-8eaf-a8dbd41b68da |  | note | Acceptance Criteria - N/A
label | f06d0505-ede5-5d53-b713-1dd3a8efcdd4 |  | note | Record documents - Contractor's site diary and/or photos
label | c7f0e722-09d5-5f00-8854-7170c9998859 |  | note | Responsibility - Contractor
label | 3cd400d9-4b4b-5f83-9c24-c10c5c2563ec |  | note | Comments - Setout location prior to commencing works.
checkpoint-status |  |  | checkpoint | .2 - Materials Approvals
label | 58346c7b-10a1-518f-b1a7-f0f2d5df8a9c |  | note | Detail of Activity - Submit testing data for the following materials: - AP65 - GAP 40 - GAP 20 - Hardfill
label | f760f0dd-a719-52fb-aeb9-9ecf1b301c7c |  | note | Action - H
label | f099d4b8-7c24-5dc7-aac1-10b4a8beca09 |  | note | Minimum Test Frequency - Once for each material
label | d518c7a1-c31c-5dcf-9361-e280db692b0f |  | note | Inspection / Test method - Quarry Testing Data
label | 5be2152a-e095-5f02-8f6e-38377cd65187 |  | note | Acceptance Criteria - Engineer's Acceptance
label | 55b8055b-7e17-5e83-ba6f-257a35608cce |  | note | Record documents - InEight Records
label | c128ce03-f44d-5b17-b68e-2883f6058fb9 |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | Construction and Finishing
checkpoint-status |  |  | checkpoint | .3 - Kerbs
label | 13245d2e-66a8-5d67-bf98-b7666f7e8c26 |  | note | Detail of Activity - Subgrade Cut / Base Thickness
label | a6fa2713-76f9-5230-8322-6a338d1394cb |  | note | Action - H
label | c3d0e8cf-4293-531f-a845-a428ed73e6a6 |  | note | Minimum Test Frequency - Every 20m
label | 38b45cae-3f38-5bd3-8e43-26d13f1200dc |  | note | Inspection / Test method - Visual Inspection
label | b0e5fc63-cc03-5066-a1b7-f12c65e5f4c4 |  | note | Acceptance Criteria - 530mm from TOK. Tolerance: - 30mm / +0mm
label | f46a62f0-9aa0-5a59-8195-c2049b31a66c |  | note | Record documents - QC Sheets/String Sheets
label | dcf5b5ba-cb69-5b1b-ad11-75bec3bf695f |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .4 - Kerbs
label | 624f931b-dff7-5be1-85b2-d7ed56851d72 |  | note | Detail of Activity - Subgrade Testing
label | 31512d06-55a0-513f-99d6-d7511e399002 |  | note | Action - H
label | 089034df-a984-5bae-b622-8eef133d817e |  | note | Minimum Test Frequency - Every 20m
label | 74b20bd6-f11d-58ec-96a5-d4322606ba6a |  | note | Inspection / Test method - Scala Penetrometer
label | 255df7d9-0ec2-56f5-8bde-b13c032cbc44 |  | note | Acceptance Criteria - ≥ 3 blows per 100mm. 500mm depth. ≥ 3 blows per 100mm - no undercut. 2-3 blows per 100mm - 200mm. 1-2 blows per 100mm - 300mm. <1 blow per 100mm - 450mm undercut
label | 8e5614e0-ce12-59da-b59a-ad6713daffd4 |  | note | Record documents - QC Sheets
label | 2012c03e-e708-59f4-b374-2c57c66cfa92 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .5 - Kerbs
label | b18038c3-303f-5247-a085-70837b54ae11 |  | note | Detail of Activity - Undercats
label | 4180333e-315a-5353-946f-edd802079e1a |  | note | Action - H
label | 9d91a2cf-9e91-5e6d-b2d9-1ee76cf23a0f |  | note | Minimum Test Frequency - Locations where scalas results are <3 blows/100mm
label | 3c389b4f-b98d-56e7-8e98-32ab8c4cf9be |  | note | Inspection / Test method - N/A
label | a5c745e1-77bd-564f-ba37-b7ee04ff58ac |  | note | Acceptance Criteria - ≥ 3 blows per 100mm. 500mm depth. ≥ 3 blows per 100mm - no undercut. 2-3 blows per 100mm - 200mm. 1-2 blows per 100mm - 300mm. <1 blow per 100mm - 450mm undercut
label | 4f7849c1-6b3b-557f-87ff-8a9a4b613cd0 |  | note | Record documents - QC Sheets
label | f3bb20a1-17b6-5ad3-b188-3620ae575f42 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .6 - Kerbs
label | b1299469-fe9f-59b1-a4a6-284f3ac8dd58 |  | note | Detail of Activity - Subbase Backfill/Prep Heights (AP65)
label | bd18301c-8d20-53ec-9c24-e4c02788c7ba |  | note | Action - W
label | 64495d5a-674e-5198-91f9-887743998144 |  | note | Minimum Test Frequency - Every 20m
label | a26021d1-d83e-5c3c-b580-3b5ab2924ed6 |  | note | Inspection / Test method - Visual Inspection
label | 0e7880cc-24be-5e4e-8e3c-187c6dcac60d |  | note | Acceptance Criteria - 230mm from TOK. Tolerance: - 10mm / +0mm
label | 88102fd8-93b5-52e0-8c37-a5afd1d7cfc5 |  | note | Record documents - QC Sheets/String Sheets
label | 27c73dd4-fde4-5924-89cc-cb2deb2429e2 |  | note | Responsibility - Contractor
label | 40f7e529-3abc-5f13-8765-adb26b7b3155 |  | note | Comments - Roughly to height with AP65, then can make up final prep height with max 50mm GAP20.
checkpoint-status |  |  | checkpoint | .7 - Kerbs
label | 083e3381-f674-5537-8ad6-2c75505279b3 |  | note | Detail of Activity - Subbase Backfill/Prep Testing (AP65)
label | d608ae4b-33b2-5cf5-bac7-8edda9282eda |  | note | Action - H
label | e60034a7-74eb-5af7-b282-d0f314c0a7db |  | note | Minimum Test Frequency - Every 20m
label | 55d4c7e1-e584-5f9d-bfe2-54f340819ee5 |  | note | Inspection / Test method - Clegg Hammer
label | 29befaa9-bded-5399-8287-bd61af2dddc8 |  | note | Acceptance Criteria - CIV ≥ 20
label | 3d647035-c7b7-5fe8-bdef-44a6b4625ea6 |  | note | Record documents - QC Sheets
label | 14717c6b-d494-57c1-8988-278156543f17 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .8 - Kerbs
label | b2696eb8-7a74-50c5-a149-7956eb96f3fb |  | note | Detail of Activity - Stringlines
label | c0306407-31bd-5a08-a7a0-cd11dd665e8c |  | note | Action - W
label | 0e1a95a3-14e7-5531-a087-6b98e96acbf8 |  | note | Minimum Test Frequency - Along each alignment
label | 07b01ad2-a320-5f64-b261-aef87f5e1d7e |  | note | Inspection / Test method - Visual Inspection
label | 9cc5aff9-27a0-5caf-84a5-7501f520dae7 |  | note | Acceptance Criteria - All stringlines are set per design layout/levels and eyed in to create smooth transitions.
label | 34a507d5-adc6-5645-a94d-57978e378314 |  | note | Record documents - QC Sheets
label | 789bd1ce-52f2-5189-93ca-b7238ccdd120 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .9 - Kerbs
label | 366e0a4f-59e6-5cdb-bb00-9b1cc0b0af9d |  | note | Detail of Activity - Kerb Pours
label | 3bc0a545-0a90-5630-a587-fbd1df6161d6 |  | note | Action - H
label | afa9fff6-9fad-59e3-80f0-1c70c826f46a |  | note | Minimum Test Frequency - All concrete orders
label | 3f965983-5508-5645-9713-e5d57e680c20 |  | note | Inspection / Test method - Concrete Dockets
label | 4ff9616d-dbca-5d20-96b4-b4b82b6125b0 |  | note | Acceptance Criteria - Concrete strength 25MPa at 28 days
label | aadb1ddc-24a0-5218-aa50-6d67f948bbac |  | note | Record documents - Concrete Dockets
label | 234e4418-e659-5ca4-914b-6b85591d0610 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .10 - Kerbs
label | 62f5a570-6454-510c-97ad-1624086164b1 |  | note | Detail of Activity - Kerb Alignment/Levels
label | 0a82ecf9-0775-5910-8117-cd00c9eb515c |  | note | Action - H
label | a3cc9571-9eb7-5aa4-a859-da0f7f598557 |  | note | Minimum Test Frequency - Every 20m
label | 13dc8168-8b59-5438-bd27-70202ed0ffe3 |  | note | Inspection / Test method - Visual Inspection
label | e1a21ad3-a697-5cb6-bc0a-9ac17ee1bc84 |  | note | Acceptance Criteria - Vertical: ± 5mm Horizontal: ± 10mm Straight Edge: ≤3mm
label | fd0bca5f-d444-5000-a06d-baa57484bf67 |  | note | Record documents - QC Sheets
label | 1a74e85f-8018-510c-b78c-906d694635a7 |  | note | Responsibility - Contractor
label | 1ab345de-6b25-57ee-8463-d191755c369a |  | note | Comments - As builts will be provided.
checkpoint-status |  |  | checkpoint | .11 - Kerbs
label | 9853c27d-0a94-560c-a6c2-d65e77c8fb26 |  | note | Detail of Activity - Expansion/Contraction Joints
label | be55e462-e8de-55fd-beae-1b0965d9d644 |  | note | Action - W
label | 9f5de29c-c77a-559c-9501-6461fadda84c |  | note | Minimum Test Frequency - Every 3m
label | aabeb67f-66b1-5dd9-a052-a9c71acc5e4a |  | note | Inspection / Test method - Visual Inspection
label | 962bd7cf-7b8c-5b34-93b9-762ef75c4cd8 |  | note | Acceptance Criteria - ≥50mm deep joints formed at 3m (max) spacings.
label | a76a42ba-88ea-518e-958a-4cf1753d82f8 |  | note | Record documents - QC Sheets
label | fc7fd826-5cc4-50fa-959e-f4b7bdaa055d |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .12 - Footpath/Shared Paths
label | 816f3731-fed4-55ab-adbb-692c6175a25c |  | note | Detail of Activity - Subgrade Cut / Base Thickness
label | acd5d173-24fd-561b-8443-06fb341b6ab3 |  | note | Action - H
label | ebf55326-bdee-5b37-971c-10059e46fca8 |  | note | Minimum Test Frequency - Every 20m
label | 9ee2e73f-93ec-506d-b3ef-b81ddbfbc4dd |  | note | Inspection / Test method - Visual Inspection
label | fb3b7a89-21e2-5e41-9288-4d024b769745 |  | note | Acceptance Criteria - 150mm from FL Tolerance: - 30mm / +0mm
label | b7edeeb8-b367-5542-b989-dd77aa8273ed |  | note | Record documents - QC Sheets/String Sheets
label | 50f10567-1685-5ff2-9a7f-c997d4b0769a |  | note | Responsibility - Contractor
label | 1f4dd979-98dc-5cff-95f0-82010da22d1b |  | note | Comments - Check for multiple services within the construction area. Compact with plate compactor
checkpoint-status |  |  | checkpoint | .13 - Footpath/Shared Paths
label | 074e149b-ebbb-5a86-8a52-a2477bed39f4 |  | note | Detail of Activity - Subgrade Quality
label | b740a6a0-40a6-556c-901c-b879e0bec4b4 |  | note | Action - W
label | cccca54f-5e64-5176-a9e8-020b81e4706b |  | note | Minimum Test Frequency - All areas
label | aefb27ec-efd2-5df7-b931-9fab3af42b2c |  | note | Inspection / Test method - Visual Inspection
label | 8a2c0269-da9e-5863-9ffa-c939973a4a8e |  | note | Acceptance Criteria - No areas of significant subgrade weakness present.
label | 2a35769e-11dc-5e4b-8803-c41ddb8b3ac2 |  | note | Record documents - QC Sheets
label | 44410a77-7c46-57a0-b0c7-b85273881bd9 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .14 - Footpath/Shared Paths
label | 3a555e98-61a3-5415-9cec-618c854bdc75 |  | note | Detail of Activity - Base/Prep Heights (GAP20/Hardfill)
label | 81a43f52-cca9-5185-afe7-1175905f9e17 |  | note | Action - W
label | 8adcf18b-0159-58bd-95c0-9e3e78d5f43c |  | note | Minimum Test Frequency - Every 20m
label | a6d2efa4-2161-53b0-b7ee-97f18347049c |  | note | Inspection / Test method - Visual Inspection
label | 17c12a86-bcf7-5723-9bcc-bf3b0ce0a52b |  | note | Acceptance Criteria - 2% max fall to road or as per drawings. Tolerance: - 10mm / + 0mm
label | d4808565-d1ee-5b32-889b-0700e9674e57 |  | note | Record documents - Stringsheet
label | 73480f89-f771-5ad8-b1cc-ec8be17a675a |  | note | Responsibility - Contractor
label | ed1fc84d-18dd-583e-b1d8-66f8d4e7c81b |  | note | Comments - Roughly to height with Hardfill, then can make up final prep height with max 50mm GAP20 if required.
checkpoint-status |  |  | checkpoint | .15 - Footpath/Shared Paths
label | f42e9089-5cb3-5b53-995d-20897a1c57de |  | note | Detail of Activity - Basse/Prep Testing (GAP20/Hardfill)
label | ade24fba-d43e-5501-9c3b-af4cad38ee86 |  | note | Action - H
label | a011e8e4-81f8-5884-b2d4-1b230d670000 |  | note | Minimum Test Frequency - Every 20m
label | 59a5ea35-c19b-53a2-b29c-c6b2c801b7a9 |  | note | Inspection / Test method - Clegg Hammer
label | fde6aa37-7298-5dc5-a0df-b710d4887e49 |  | note | Acceptance Criteria - CIV ≥ 12
label | a1273fe9-74d7-5266-b09d-816515ecf3ab |  | note | Record documents - QC Sheets
label | 0c5c0548-943f-5862-b09c-276b557a4449 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .16 - Footpath/Shared Paths
label | ed6b4937-12a9-5e60-afb1-c0bd619c52f8 |  | note | Detail of Activity - Concrete Pours
label | 355e5cae-dc9e-59f8-bdea-3cbd89df8931 |  | note | Action - H
label | 01aefaa2-2767-548e-b9c1-06d8d6b53ae5 |  | note | Minimum Test Frequency - All concrete orders
label | 7bbecba5-d67b-5279-9124-2da625934d98 |  | note | Inspection / Test method - Concrete Dockets
label | 0fb20e31-cca1-52bb-a551-9774e3cb7cf9 |  | note | Acceptance Criteria - 100mm concrete strength 20MPa, 3% black oxide, at 28 days
label | e5f4e1de-69fa-58cf-9698-f27745df5dfb |  | note | Record documents - Concrete Dockets
label | 71cf51ea-800b-5ca6-acf2-d28565744dc0 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .17 - Footpath/Shared Paths
label | cda58710-aa0d-5094-a44e-a234936fbf81 |  | note | Detail of Activity - Finish / Joints
label | 229a3b29-97e0-57a2-b348-21a3c32d63d2 |  | note | Action - W
label | 4f6188cf-a536-5e2d-86cf-ce4eee08d461 |  | note | Minimum Test Frequency - All areas
label | 7ca3c2c5-a959-59fd-b2d2-4fe301b15f10 |  | note | Inspection / Test method - Visual Inspection
label | ec343a5c-1d9f-556a-893f-c88aff698bcf |  | note | Acceptance Criteria - Broomed finish. Joints cut at 4m centres.
label | fa9d8719-771b-5921-874c-fa3a0f80814c |  | note | Record documents - QC Sheets
label | 64211c12-a65a-565e-b952-5bf3761f3f15 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .18 - Residential Vehicle Entrances/Driveways
label | dc403529-a4a5-5c21-8e8c-f647597a7bbd |  | note | Detail of Activity - Subgrade Cut / Base Thickness
label | c59d376a-9009-50a9-b378-79f813c2c902 |  | note | Action - H
label | 936df976-d0eb-5353-8a7d-466bcf230038 |  | note | Minimum Test Frequency - Once per entrance
label | 205fd7b5-134d-57d9-8d03-bd59029992ed |  | note | Inspection / Test method - Visual Inspection
label | 93bc0d82-2384-5f05-a9ed-22c3abee6e5c |  | note | Acceptance Criteria - 175mm down from adjacent tie in surfaces. Tolerance: - 30mm / + 0mm
label | 5e43ad0f-5cd8-5b90-9127-91daf05ec1c4 |  | note | Record documents - QC Sheets/String Sheets
label | 79c1c8d9-fa6b-5c94-a172-4d1290d38646 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .19 - Residential Vehicle Entrances/Driveways
label | c2624ad2-e4b9-5346-bb6a-b82c51687b55 |  | note | Detail of Activity - Subgrade Quality
label | 0489c15f-322b-587b-a3ca-dac644683d94 |  | note | Action - W
label | 1ea17e0a-8933-5bd5-9fb6-024f4d1692d6 |  | note | Minimum Test Frequency - All areas
label | 8e8ea391-80a5-5a97-8286-ff90e0661683 |  | note | Inspection / Test method - Visual Inspection
label | 24f5dc18-0af4-5752-af2c-12d6b65ccab0 |  | note | Acceptance Criteria - No areas of significant subgrade weakness present.
label | a2f18ffd-9c69-56b1-bd1f-bf219a628971 |  | note | Record documents - QC Sheets
label | 33d4b4c0-d0df-5546-a267-c3a557e28abd |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .20 - Residential Vehicle Entrances/Driveways
label | 34c5f6d5-8d0b-5633-aba7-39e9f259687b |  | note | Detail of Activity - Base/Prep Heights (GAP20/Hardfill)
label | ced01e33-aa98-5e99-afa3-f7d50b137787 |  | note | Action - W
label | 083e16b8-2052-5b6c-a199-2f4b0a8a4c60 |  | note | Minimum Test Frequency - Once per entrance
label | 5268e16d-cb7a-5624-8608-3c7adc0f7717 |  | note | Inspection / Test method - Visual Inspection
label | f144c3b1-5e22-5e0a-81c6-e0bfbdb3674e |  | note | Acceptance Criteria - 125mm down from adjacent tie in surfaces. Tolerance: - 10mm / + 0mm
label | c9874c61-962d-53d5-acc9-44429bf95698 |  | note | Record documents - Stringsheet
label | d119bb7b-7b74-51e6-ac07-189d05c6162f |  | note | Responsibility - Contractor
label | 181d2575-e885-5b16-ad5a-ad58c82bc5e9 |  | note | Comments - Roughly to height with GAP 40 Hardfill, then can make up final prep height with max 50mm GAP20.
checkpoint-status |  |  | checkpoint | .21 - Residential Vehicle Entrances/Driveways
label | 325b42cb-c51d-55c2-b495-50a2253d256d |  | note | Detail of Activity - Base Prep Testing
label | ec2583c8-d44f-5b19-ada6-1e70c6f4bbf7 |  | note | Action - H
label | 7899c920-d51b-5a7f-b2bd-6a59f87c8299 |  | note | Minimum Test Frequency - Once per 10m
label | 810fef35-1ee8-5608-9f9e-c078b0907ea0 |  | note | Inspection / Test method - Clegg Hammer
label | 5116c842-f091-567f-a072-2c227d957c20 |  | note | Acceptance Criteria - CIV ≥ 12
label | c2ebd8d0-19c2-5d7f-a491-55ac50e4793d |  | note | Record documents - QC Sheets
label | caa2a509-a7a6-50ef-a201-7128d690b009 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .22 - Residential Vehicle Entrances/Driveways
label | 1cea6029-63e9-5ae2-a4e7-ecae39d5602c |  | note | Detail of Activity - Base Prep Testing Concrete Pours
label | 7f08c0dc-5030-576f-8e49-5a36afa9f816 |  | note | Action - H
label | c91ca4ad-b570-542d-b2fa-bf06f273034d |  | note | Minimum Test Frequency - All concrete orders
label | d5d12fc1-a4c7-57b2-9b15-5c1abd9d0e8c |  | note | Inspection / Test method - Concrete Dockets
label | 5b34d393-6b9e-5bcc-b4af-c436dd3a6973 |  | note | Acceptance Criteria - 125mm concrete strength 20MPa, 3% black oxide, at 28 days
label | c8c3e0a0-7cf9-589d-8eaf-0342b4d9033f |  | note | Record documents - Concrete Dockets
label | a0a81683-104a-5607-aec8-584b18171350 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .23 - Residential Vehicle Entrances/Driveways
label | fbd11047-a9b4-5d03-bb29-7c103ed539ca |  | note | Detail of Activity - Finish / Joints
label | 4814538e-5f89-5fde-9739-86a15c9f2866 |  | note | Action - W
label | 0b8c2123-b299-5805-9793-3ab291d1a00a |  | note | Minimum Test Frequency - All areas
label | c68ac48c-0ec7-59cb-80ac-07d712fe9ca5 |  | note | Inspection / Test method - Visual Inspection
label | f5c5e56d-3433-5001-ad13-556cfb3f3634 |  | note | Acceptance Criteria - Smooth, broomed finish. No depressions for ponding to occur. Cut joints as appropriate.
label | b1fcda2a-226a-5217-bb43-96a49bffa9f5 |  | note | Record documents - QC Sheets
label | 929da907-d1a3-5fdc-aecb-ad0ef30d9aa9 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .21 - Industrial Vehicle Entrances/Driveways
label | b2844c89-d6d5-55f8-aa08-2d1f910dc447 |  | note | Detail of Activity - Subgrade Cut / Base Thickness
label | 902c9a2a-4bd1-5a59-981b-c708bb1ead18 |  | note | Action - H
label | cf9b12f6-300e-5cb8-9c29-3d8d7e7d0fe1 |  | note | Minimum Test Frequency - Once per entrance
label | 14e2b36f-983e-53c1-8bfa-d6541ea8e12b |  | note | Inspection / Test method - Visual Inspection
label | 3eaa9fe8-4c32-5734-b098-7c61951c376b |  | note | Acceptance Criteria - 250mm down from adjacent tie in surfaces. Tolerance: - 30mm / + 0mm
label | a04b0357-347b-5a21-9746-273e342a16e6 |  | note | Record documents - QC Sheets/String Sheets
label | 8ef85525-bed2-5929-8202-11371e9ecabf |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .22 - Industrial Vehicle Entrances/Driveways
label | e11f2e6b-e7a9-5851-b939-2b849b0a0be6 |  | note | Detail of Activity - Subgrade Quality
label | cbd86c6e-4ed9-565f-b809-61283edee69b |  | note | Action - W
label | ba82af71-3391-5d4d-a74b-6025240184ee |  | note | Minimum Test Frequency - All areas
label | 0edeccf8-ff10-5263-b002-ebcfe3ba3a21 |  | note | Inspection / Test method - Visual Inspection
label | 80337723-a580-5272-b0a5-7efe574ed4f9 |  | note | Acceptance Criteria - No areas of significant subgrade weakness present. Minimum CBR of 5%. Scala ≥2 blows per 100mm to 200mm depth.
label | 922318ad-9cab-50a8-a4c8-035c229662af |  | note | Record documents - QC Sheets
label | 97e5c377-4b65-57db-864f-c453b80626fb |  | note | Responsibility - Contractor
label | 8e888598-3c51-528d-91eb-1f887b14b5c5 |  | note | Comments - See notes on Drawing D3.3.4
checkpoint-status |  |  | checkpoint | .23 - Industrial Vehicle Entrances/Driveways
label | 62c6028c-ca90-5371-a0ce-5628a343b673 |  | note | Detail of Activity - Base/Prep Heights (GAP20/Hardfill)
label | 6f040918-dc97-5dec-ba04-5a5bb433d47e |  | note | Action - W
label | a9062448-6a24-5391-96a0-c7795955e84a |  | note | Minimum Test Frequency - Once per entrance
label | ae0d5002-ad55-5ffd-8d05-b4daf72720b8 |  | note | Inspection / Test method - Visual Inspection
label | 5b3241f5-9279-53ac-8f64-51e823ecafae |  | note | Acceptance Criteria - 175mm down from adjacent tie in surfaces. Tolerance: - 10mm / + 0mm
label | e213b2b5-e881-55bd-b5de-08ba36967712 |  | note | Record documents - Stringsheet
label | d6c3875b-d9bb-5e37-bac2-1c4ffc331a50 |  | note | Responsibility - Contractor
label | cc03adf6-1a84-5443-848e-ec190cc845aa |  | note | Comments - Roughly to height with GAP 40 Hardfill, then can make up final prep height with max 50mm GAP/AP20 if required.
checkpoint-status |  |  | checkpoint | .23 - Industrial Vehicle Entrances/Driveways
label | 72fd03c0-f032-50f7-9b0d-1e8ce78d1c20 |  | note | Detail of Activity - Base Prep Testing
label | 2f928aba-1c39-54d8-9840-e94d81032d79 |  | note | Action - H
label | 83ae1d9d-69f3-5962-9d92-ea04b921b4c6 |  | note | Minimum Test Frequency - Once per 10m
label | 59b203e0-5bf6-5f34-9b63-54f3c83cb9c7 |  | note | Inspection / Test method - Clegg Hammer
label | d63f33e4-e422-5308-831c-c3031928cf2e |  | note | Acceptance Criteria - CIV ≥ 12
label | 9ee36b61-e113-54f4-b67c-fa5dec3cdecc |  | note | Record documents - QC Sheets
label | 18e64185-e727-517d-831a-5a903ffcdaf6 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .21 - Industrial Vehicle Entrances/Driveways
label | 82aedfee-30ea-551b-aaa2-8441339ecd59 |  | note | Detail of Activity - Reinforcing
label | a4090f4b-d759-53fe-85b6-bf85abfa2adf |  | note | Action - W
label | 4ce893a4-1b99-5d5b-a4c4-0b552c3f24f6 |  | note | Minimum Test Frequency - Once per industrial driveway
label | 519be7e6-d587-53d6-8291-942468acc086 |  | note | Inspection / Test method - Visual Inspection
label | a902ea97-e7fd-5635-aadf-8653ccbb949c |  | note | Acceptance Criteria - Reinforcing as per Drawing D3.3.2 on RITS Case A
label | f3a26f75-5744-5622-a279-a91e4cd148aa |  | note | Record documents - QC Sheets/ photos
label | 61fcb003-4bd5-50a9-9e92-ab0b03c72611 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .20 - Industrial Vehicle Entrances/Driveways
label | 45a9d32d-a554-5314-9db2-019944d2a743 |  | note | Detail of Activity - Concrete Pours
label | 0075f8ad-e5d2-5145-a359-34f466c9c91b |  | note | Action - H
label | 91c5464e-51d1-5b27-8d68-5bcebf47cb91 |  | note | Minimum Test Frequency - All concrete orders
label | 748e4248-1093-52f7-9f3d-a41dc290ad44 |  | note | Inspection / Test method - Concrete Dockets
label | 1be6a055-70d2-526b-80e3-404d523b1786 |  | note | Acceptance Criteria - 175mm concrete strength 20MPa, 3% black oxide, at 28 days
label | 8b3014a7-30e4-5880-bedd-e1d161e84df1 |  | note | Record documents - Concrete Dockets
label | ad1ea6ea-1827-5066-aea2-92be164f8bf7 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .21 - Industrial Vehicle Entrances/Driveways
label | 33f7d1ec-aca4-5fb0-b672-ab1ddcec50c9 |  | note | Detail of Activity - Finish / Joints
label | f4b61302-7914-5b4f-afef-b52fc0afbd71 |  | note | Action - W
label | 04a91a1b-e843-51e1-b8ab-1cf3f0541ed7 |  | note | Minimum Test Frequency - 2
label | 880b7891-d72d-5840-87da-aa6c6a5ba5d0 |  | note | Inspection / Test method - Visual Inspection
label | 0c0f52c5-56ad-509c-b4b1-5d3c57893a52 |  | note | Acceptance Criteria - Smooth, broomed finish. No depressions for ponding to occur. Cut joints as appropriate.
label | 2fb184a1-13f4-5eb5-ae1d-ea21a1ffcd3a |  | note | Record documents - QC Sheets
label | 614149c4-237e-5224-b3ac-577fa5a02e60 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .22 - Concrete Island Infills
label | 96afed2b-c22c-59bc-8b2b-70d51d7ae176 |  | note | Detail of Activity - Base Prep Testing (GAP40)
label | 65f1579b-dd7d-5e48-96ba-9d139a6b5014 |  | note | Action - H
label | c90203b1-fd04-5374-aac4-6c6704531ca9 |  | note | Minimum Test Frequency - Once per 10m
label | 6e44dbc1-0889-53e7-9f53-08a71485f647 |  | note | Inspection / Test method - Clegg Hammer
label | 1a47a7eb-4f60-5209-886b-83ea6f5cf49f |  | note | Acceptance Criteria - CIV ≥ 12
label | bf2ac183-b73e-5e0e-b005-53f1472cd351 |  | note | Record documents - QC Sheets
label | 884e35c3-18bc-599e-aaa1-53a7a8ecc949 |  | note | Responsibility - Contractor
label | 50c20b97-791b-59c4-bb0a-0754caa46fda |  | note | Comments - GAP40 material to be used.
checkpoint-status |  |  | checkpoint | .23 - Concrete Island Infills
label | ae241010-8431-5d42-b9cb-20399055ece4 |  | note | Detail of Activity - Concrete Pours
label | 38af56b7-7986-550a-927d-2ccfc5ec5a08 |  | note | Action - H
label | 6cdfc31a-e5e7-5613-9fc7-5bf0bf8bcde7 |  | note | Minimum Test Frequency - All concrete orders
label | 91e902d7-c8c7-5897-b10a-c4e606e3c90a |  | note | Inspection / Test method - Concrete Dockets
label | 09ce59ec-8350-589a-aed4-f3ebeb286957 |  | note | Acceptance Criteria - 100mm concrete strength 20MPa, coloured "Indian Summer".
label | b5527ff3-0cbf-5650-9641-0f35f89ff8da |  | note | Record documents - Concrete Dockets
label | 680ed385-a755-5f6b-9111-c7ef1d52d819 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .23 - Concrete Island Infills
label | 2cf0313a-97b4-5a42-a745-1bdfd65fd6b5 |  | note | Detail of Activity - Finish / Joints
label | c20d41ed-06ad-5f35-84fe-b3e014e3a244 |  | note | Action - W
label | ef8be291-9d15-59a1-b707-c1811b90c787 |  | note | Inspection / Test method - Visual Inspection
label | 67dc5912-3054-5bb5-8634-08cd31591d4a |  | note | Acceptance Criteria - Smooth, broomed finish. No depressions for ponding to occur. Cut joints as appropriate.
label | 28fb46db-a4a7-5387-abc5-d016f5f43c62 |  | note | Record documents - QC Sheets
label | 41051d6a-82f4-5dc5-9c30-7b0fdd3a1e5d |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | .34 - Collate above documentation
label | 1b35b020-89d0-5d3d-8a63-e7770b9b00db |  | note | Detail of Activity - Document review
label | f50013f5-7e26-533a-91b3-d5d6dd84619b |  | note | Action - H
label | 8c042186-ea6e-5c7f-a722-7609b5eff72d |  | note | Minimum Test Frequency - Each ITP
label | a582139c-b29b-57af-a441-12e65e5aceda |  | note | Inspection / Test method - Review
label | 3d7def3d-9af1-5929-8107-215defcff183 |  | note | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | 7cf27542-56c9-5129-abe4-e5530f76768b |  | note | Record documents - Review
label | 0976ca14-36e4-5e45-aea8-5b611e5352c8 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | .35 - As-built drawings
label | 3201b760-eabc-5fae-b581-d18fdf561c1f |  | note | Detail of Activity - Survey
label | 31bdd527-588a-5b04-84bc-6be572f7d09e |  | note | Action - H
label | 14c7c0a9-4063-5cf3-bed7-4adf2532a4a3 |  | note | Minimum Test Frequency - At completion of construction
label | 6367ca51-3f05-5cbf-a148-5bcb1e1b4cce |  | note | Inspection / Test method - Asbuilts to be submitted at the completion of construction, information to be captured
label | 95e20c7c-1177-531b-bf33-da80bed69f62 |  | note | Acceptance Criteria - Asbuilts reviewed and submitted
label | 81f18eb5-afa3-53cb-a2fb-8b4f356433e4 |  | note | Record documents - In Eight record
label | d9cc23c7-9f94-5bb4-bd25-2d70a5be6a9a |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | Client Final Inspection - Contractor
label | ff9cb0d1-a6f0-5ded-8c6b-27da5e68b596 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 6fe542a5-92c0-5d80-8d25-fe834d994d5b |  | textbox | Contractor's Rep Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Client Final Inspection - BBO Engineer
label | 84275209-4543-5e29-95b1-f7f5489cfdca |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 109a825f-9d1d-59ae-9b4d-8f67560f72bb |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Stormwater | itp |  |  |  | Yes | ITP - Stormwater | ef523cf2-7cfb-44bb-b47e-ee74f56151d0
checkpoint-group |  |  | section | 300 - Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 300.1 - Mark out works
label | 88f70b34-1144-5c98-810b-d0dd5cc8a36c |  | note | Detail of Activity - Set out and mark up proposed drainage features by surveyor
label | 1a5bff04-8b3f-5105-a750-616250815e91 |  | note | Action - H
label | 93a17f29-990c-5384-a652-d40ff24ee69d |  | note | Minimum Test Frequency - All drainage features
label | b664c61d-0add-5867-bff9-c0f755a7acc1 |  | note | Inspection / Test method - Visual Inspection
label | 792863ad-3413-58a1-a2d1-8383e99893fa |  | note | Acceptance Criteria - Completed
label | ecb55629-f50a-51f5-9eff-253e0a8f405e |  | note | Record documents - Contractor's site diary
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.2 - Underground services
label | 3f24e591-c19b-5e13-95db-2156a14f6be1 |  | note | Detail of Activity - Identify and positively locate services
label | 41d6845f-02d9-5de4-b0b0-977b87b35e23 |  | note | Action - H
label | 429d2dc0-43bf-541d-9812-7b75a4a95f2e |  | note | Minimum Test Frequency - All drainage features
label | 6cc8f3e9-e22b-5f98-bcdd-aaf9e710a598 |  | note | Inspection / Test method - Hydoexcavation / potholing
label | 53842e8b-4422-56fe-ad14-61daa48f2ee7 |  | note | Acceptance Criteria - Completed
label | 67b2b610-a74f-5684-a1b9-92bd8daa5c73 |  | note | Record documents - Ground Disturbance Permit
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.3 - Precast Concrete Pipes
label | e874887e-2982-5888-8bee-9bb635f507ba |  | note | Detail of Activity - Ensure all precast concrete pipes are Class 2 or Class 4 RCRRJ
label | fd187925-f642-5fbe-92f2-7078eeb120cc |  | note | Action - H
label | 72cc16ac-d630-59e5-8ed4-73049d7cd946 |  | note | Minimum Test Frequency - 1 per culvert size/type
label | b27efbd2-8762-515f-9c49-bd1de0731636 |  | note | Inspection / Test method - Supplier Docket
label | 1549bb42-fd9d-56d6-aff7-d679dea2f2b8 |  | note | Acceptance Criteria - Completed
label | 8daf4ad5-4a5d-57a5-8999-dfadbb183c8a |  | note | Record documents - QC sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.4 - Precast headwall/wingwall units
label | 006f792f-bc5f-5e01-b9b9-4caaa1082a4f |  | note | Detail of Activity - Ensure headwalls and wing walls are precast units
label | fbef72a2-b61f-5664-8438-b9a9d0de5682 |  | note | Action - H
label | 79eab5be-6ecf-53c6-af9c-209008a05e4b |  | note | Minimum Test Frequency - 1 per wingwall type
label | 52b2f07f-0f1d-5f97-9619-dfda8e2d4f91 |  | note | Inspection / Test method - Supplier Docket
label | 6375c19f-80a9-5cee-9ba4-5bfabcfa9be2 |  | note | Acceptance Criteria - Completed
label | c66df634-36e9-5eae-af7f-656dd3438e05 |  | note | Record documents - QC sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.5 - Precast manholes
label | d54b7681-5d29-559a-8f1f-6ec2b911baf8 |  | note | Detail of Activity - Ensure all stormwater manholes are precast and have hinged lids if in carrageway
label | 1aba234e-85fe-5814-9583-a09737f48876 |  | note | Action - H
label | 9d905ce8-0143-56d7-9ac8-c2eed128ae20 |  | note | Minimum Test Frequency - 1 per manhole size/type
label | 14ee4267-b946-54ce-a40c-717b0aa8be7c |  | note | Inspection / Test method - Supplier Docket
label | de4cc9c2-cf30-5877-be7d-f6ba2b83e1f1 |  | note | Acceptance Criteria - Completed
label | 784b8d9d-e0da-5525-a480-f877b0043401 |  | note | Record documents - QC sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.6 - PVC Pipes
label | 724add80-cc2b-57c8-9681-d6f8cddeefcc |  | note | Detail of Activity - Ensure all stormwater pipes with int dia. Smaller than 380mm are PVC-U SN16 to AS/NZS 1260
label | deab4497-9c33-5d75-8b94-915763b0271c |  | note | Action - H
label | 2ba7ff59-c423-5161-bde0-62b9f02fedfd |  | note | Minimum Test Frequency - 1 per culvert size/type
label | 60c55a2b-25ad-56a6-a60a-f86fa3ac4fdf |  | note | Inspection / Test method - Supplier Docket
label | 31406b82-99f1-5b2b-9f1f-1e369ad2f50d |  | note | Acceptance Criteria - Completed
label | 76fcb39e-ac58-54bd-904e-9755c4193776 |  | note | Record documents - QC sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.7 - Precast catchpit
label | a3be36cc-6484-5027-b0b7-5fbe5a8ec7d1 |  | note | Detail of Activity - Ensure all catchpits are pre cast and class D rating.
label | 346d5656-4e8f-5e0b-9ac6-d3d95a2f2efb |  | note | Action - H
label | 151def1e-b814-5b63-b2ea-5ab573903a61 |  | note | Minimum Test Frequency - 1 per catchpit size/type
label | 2d0d6dbb-4516-5ffc-a376-2dfbf020f4c2 |  | note | Inspection / Test method - Supplier Docket
label | d0bd4ad9-529a-5572-836c-d62d9db2fc42 |  | note | Acceptance Criteria - Completed
label | e704d776-afbe-5549-805d-a8a41286bf5f |  | note | Record documents - QC sheet
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.8 - Drainlayer Qualification
label | 827bbe8c-3b6e-5d91-8e89-53cba1dbb4ce |  | note | Detail of Activity - Drainlayer to be appropriately registered and skilled to undertake the work.
label | 730fb8fa-6e09-582e-975e-df0b327e5706 |  | note | Action - H
label | bf3e8c36-3ff5-5f59-9e50-286da5d91ecf |  | note | Minimum Test Frequency - Once at start of the project
label | 9b1ff3ca-3b30-5316-a1a8-ffdbdb1461a7 |  | note | Inspection / Test method - Drainlayer Cert
label | 44322fff-5179-517a-8dd0-72ac50b11e45 |  | note | Acceptance Criteria - Current certificate
label | 49e8d0f4-02c5-5634-beb4-7adde2cdf941 |  | note | Record documents - Drainlayer Cert
label | c3cbc47c-dfb7-5f03-995e-b981b34cbfbb |  | note | Comments - Ensure the supplier has a current drainlaying certificate prior to starting works
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Construction and Finishing - Pipes
checkpoint-status |  |  | checkpoint | 300.9 - Determine Subgrade Strength
label | 21e62a35-8603-568e-bde4-3626ce925550 |  | note | Detail of Activity - Determine bearing strength of subgrade
label | 0ff97b87-71db-5289-b96a-a7826453d39f |  | note | Action - H
label | 3764217c-14a0-5ad3-8fd4-90c5c0d267e4 |  | note | Minimum Test Frequency - 1 per 6m length of trench base; or 1 per drainage structure
label | 95f7dd7d-7eff-5fb9-b5e5-c5ee2fbe88f3 |  | note | Inspection / Test method - Scala Penetrometer (NZS 4402.6.5.2).
label | dc0d3887-d8ec-5472-a772-d56ef01bc163 |  | note | Acceptance Criteria - Scala to 300mm depth:
label | fcf8a48d-3140-51a1-b61f-de5ebdf9e2bf |  | note | - 3 blows per 100mm = no undercut
label | 7c3e02ea-8587-52fe-beff-85278dadbc4a |  | note | - 2 blows per 100mm = undercut 200mm and replace with GAP40 hardfill
label | 4b637749-225d-5b34-b3f1-b9c4ccb962fe |  | note | - 1 blow per 100mm = undercut 300mm and replace with GAP40 hardfill
label | 5138f154-5198-58dc-b401-f227c336ddc3 |  | note | - <1 blow per 100mm = undercut 450mm and replace with GAP40 hardfill
label | c9c3df5a-226e-5042-b965-bdd7d859f67a |  | note | Undercut to be lined with Bidum A29 or similar approved.
label | b019aee6-2a73-5afb-b026-4c81e1632be5 |  | note | Record documents - QC sheet
label | 4a94b457-1e9a-5f27-abdf-98a45b1f3c65 |  | note | Comments - Note: this supersedes 18.3.6 in specification
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.1 - Pipe bedding
label | 6be56150-fa41-5658-9cb7-ec0a4e21dae5 |  | note | Detail of Activity - Bedding
label | c09cbcdf-dd89-55f0-bbea-69e4e5b8ad96 |  | note | Action - M
label | 78cbc979-34b4-5918-bc3c-5b0aeddbc3d0 |  | note | Minimum Test Frequency - 1 per 6m trench
label | 48d26c33-b15d-5871-81bb-73b0c133e366 |  | note | Inspection / Test method - NZS 3725:2007
label | 5fa5db33-2cd6-5a4d-92e2-805befbe9e66 |  | note | Acceptance Criteria - In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | b0aa0258-0d9c-5058-b6be-81fda2b7aa8d |  | note | Record documents - QC sheet
label | 595c83df-32c0-5425-a157-90d387917cce |  | note | Comments - GAP 40 hardfill to be used or suitable as dug material
checkpoint-status |  |  | checkpoint | 300.11 - Pipe installation
label | b9a4fcec-31cf-540c-8bde-e308ddd8943c |  | note | Detail of Activity - Installation tolerance
label | 6e5f94ce-0ef1-5d1e-b6bf-f1339e84ee54 |  | note | Action - M
label | 4b37075e-eeed-5190-b54e-7a6623afa3c8 |  | note | Minimum Test Frequency - Each SW line
label | e7dbea3d-c366-55d0-9d59-3abc03ddf410 |  | note | Inspection / Test method - As Builts
label | e2514f1a-bb8b-54b8-9780-5da3e6c03a69 |  | note | Acceptance Criteria - ±10mm of invert level and ±50mm of Horizontal Alignment
label | 0e842997-0d90-594c-acf6-63b7e4738183 |  | note | Record documents - As Built survey
label | cde2df4c-db88-53ba-93cd-db25a0127d88 |  | note | Comments - There needs to be a rule developed with min and max grades to allow working around existing services. (Stage 1 was min 0.5%, max 10%)
checkpoint-status |  |  | checkpoint | 300.12 - Pipe haunching
label | 2945c7bf-fc32-51ae-be4a-94ec70ebf10e |  | note | Detail of Activity - Haunching
label | aedc18f5-273a-5de9-88e3-53b948bedf0f |  | note | Action - M
label | 8bd15e4b-bfd9-5ba0-b703-29d055c50f18 |  | note | Minimum Test Frequency - 1 per 6m trench
label | 1020e807-57a3-51d3-83e5-8a9a4048bc6c |  | note | Inspection / Test method - NZS 3725:2007
label | 4bd56b4e-ca97-58d5-ab32-4b0e47c38fe9 |  | note | Acceptance Criteria - In Accordance with HS2, Minimum haunching depth of 0.3D, CIV Value on compacted haunching ≥ 15
label | 2516054b-1b5b-535d-80d7-0d46366d12ef |  | note | Record documents - QC sheet
label | 20da5508-ce89-5984-8b4c-696b5d7daaf3 |  | note | Comments - GAP 40 hardfill to be used
checkpoint-status |  |  | checkpoint | 300.13 - Trench backfill
label | e0a29964-76c6-529c-a484-534027ebdcb9 |  | note | Detail of Activity - Backfilling in berm
label | 8fad556f-ce5a-5550-9ef2-c01b2acf3859 |  | note | Action - M
label | 6abc67b6-4ef4-5f1e-9785-cee7d2d55d2f |  | note | Minimum Test Frequency - 1 per 6m trench
label | 249cd8be-6936-5b2a-ae90-1efae2ac268a |  | note | Inspection / Test method - Clegg Hammer
label | bc4e3b81-7b4e-54d0-a98c-871908967ef4 |  | note | Acceptance Criteria - Top of trench in berm. CIV ≥ 15.
label | a102512b-4e70-5936-8087-bd4b6b24a26b |  | note | Record documents - QC sheet
label | 7af6e72c-dfd3-55f8-84c2-cfec902074d2 |  | note | Comments - GAP 40 hardfill to be used or suitable as dug material
checkpoint-status |  |  | checkpoint | 300.14 - Pavement Layer Construction if in road.
label | e23626e8-04f9-5026-b09c-68aa295403da |  | note | Detail of Activity - Subbase
label | abc01643-9ba1-5382-af62-29208f664325 |  | note | Action - M
label | 4b8bac94-03ef-57ca-852b-df407c852aef |  | note | Minimum Test Frequency - 1 per 6m trench
label | ac19a542-e14f-51df-82a2-4ee7cc8c129a |  | note | Inspection / Test method - Clegg Hammer
label | e36476db-4a0e-5eb2-97af-dd3f4d9c4f6a |  | note | Acceptance Criteria - In road (granular) clegg every 300mm lift after thermal backfill. CIV ≥ 20.
label | cd2b38ed-5bc8-559d-8e64-a7d82d7f79fe |  | note | Record documents - QC sheet
label | bdf237f8-6a1e-59c5-90d2-a7ee5a669d56 |  | note | Comments - GAP 65 to be used
checkpoint-status |  |  | checkpoint | 300.14 - Pavement Layer Construction if in road
label | 9192d116-d610-5910-9907-e37c9de76eb9 |  | note | Detail of Activity - Basecourse
label | 25a5e423-f048-5b0d-8aa6-1d35d80dcc3e |  | note | Action - M
label | e122fe04-bc31-516a-80bb-f302e2d0db66 |  | note | Minimum Test Frequency - 1 per 6m trench
label | 5bf165c4-5709-5653-8398-cdfe143a75ec |  | note | Inspection / Test method - Clegg Hammer
label | 74dd4d0d-0723-50ea-8cdb-bb5adb64751e |  | note | Acceptance Criteria - In road (granular) clegg every 300mm lift after thermal backfill. CIV ≥ 35.
label | 4b2fd817-0b07-51e3-b697-11ce3ff96ec1 |  | note | Record documents - QC sheet
label | e7bed752-f7f2-57e4-be17-1eb724e4c1fe |  | note | Comments - AP 40 to be used
checkpoint-status |  |  | checkpoint | 300.15 - CCTV Inspection
label | b9d5f6d4-5afe-5c84-9c75-be1bd15ffb84 |  | note | Detail of Activity - Visual record of Existing works
label | 771d0134-d237-583d-87cd-86e05dacfd05 |  | note | Action - W
label | 0f1c0f87-9b5c-530f-b202-199f4f9a1c5d |  | note | Minimum Test Frequency - All drainage pipelines
label | e5844215-ee7c-5c2b-b4d0-6575839c1a29 |  | note | Inspection / Test method - CCTV Inspection
label | 06914a51-2615-5bc2-a487-109397b6aa84 |  | note | Acceptance Criteria - No significant cracks, level deformation, faulty joints
label | 18caad08-c21a-539c-8b61-b6b267bbe76a |  | note | Record documents - CCTV Footage
label | f2b14d79-144b-5312-bda8-150f8fedc9c5 |  | note | Comments - CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practical Completion
checkpoint-group |  |  | section | Construction and Finishing - Structures (manholes, head walls, catchpits etc.)
checkpoint-status |  |  | checkpoint | 300.16 - Determine Subgrade Strength
label | 7683217d-9a44-5b64-9a65-e35794a32cac |  | note | Detail of Activity - Determine bearing strength of subgrade
label | a11bd312-fb05-5542-8310-967e9857ce65 |  | note | Action - H
label | d71ed650-7b5a-5630-9b99-6a9b480c1ba8 |  | note | Minimum Test Frequency - 1 per structure
label | 4c9fc981-a103-537c-9472-87314ec05f4d |  | note | Inspection / Test method - Scala Penetrometer (NZS 4402.6.5.2).
label | 81658df7-d459-51e4-a9d0-585ac47c47d0 |  | note | Acceptance Criteria - Scala to 300mm depth:
label | af150453-cf6e-5448-9886-7ce87d839d9e |  | note | - 3 blows per 100mm = no undercut
label | 8a9d907a-c73b-522c-be08-0aae3fd1b983 |  | note | - 2 blows per 100mm = undercut 200mm and replace with GAP40 hardfill
label | 266e875d-ec4d-508f-884e-78ef632920ca |  | note | - 1 blow per 100mm = undercut 300mm and replace with GAP40 hardfill
label | d338f3f0-5ecc-5559-810e-e08a2760335a |  | note | - <1 blow per 100mm = undercut 450mm and replace with GAP40 hardfill
label | e6d83e53-bf79-525f-aee1-8f92520856a9 |  | note | Undercut to be lined with Bidum A29 or similar approved.
label | 2cb05704-910a-5974-8301-d5417b685ae7 |  | note | Record documents - QC sheet
label | 5fbc24f1-387b-5884-bd84-d5cf1bb4b4f0 |  | note | Comments - Note: this supersedes 18.4.2 in specification
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.17 - Structures (manholes, head walls, catchpits etc.)
label | 0a395c56-b416-526a-9cbb-e6e513dad176 |  | note | Detail of Activity - Visual inspection of concrete components
label | 57e3a55e-4716-504a-b7a4-fa85ab4e2803 |  | note | Action - W
label | b450388a-3250-56d4-a126-c294bca9ddc6 |  | note | Minimum Test Frequency - 1 per structure
label | 5a0f2836-2024-5c1b-a1d4-5eecbb1b81a5 |  | note | Inspection / Test method - Visual Inspection
label | 3dbfa385-e781-5079-b1fa-3f13447aea78 |  | note | Acceptance Criteria - No visible damage, especially around collars and joints
label | bc3d7e92-ac4a-5ecf-9863-c383db3632ea |  | note | Record documents - QC Sheet
checkpoint-status |  |  | checkpoint | 300.19 - Structures (manholes, head walls, catchpits etc.)
label | 4af9c0b1-3429-565b-9a8b-2d78c54e179c |  | note | Detail of Activity - Bedding
label | 7d77c28a-e94b-5824-b196-7f747d0db3f2 |  | note | Action - M
label | 085aa586-9dbc-5a81-83ad-ebded7033e58 |  | note | Minimum Test Frequency - 1 per structure
label | d7d52274-2590-561f-a7c4-b970f62823d7 |  | note | Inspection / Test method - NZS 3725:2007
label | 66d5c860-3bbe-5919-baae-ec70b7483a2f |  | note | Acceptance Criteria - In Accordance with HS2, Minimum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15).
label | 63f4b123-74fb-595b-a3ae-20f73e36f6dd |  | note | Record documents - QC sheet
label | 6228c143-d103-594f-bcd3-5c69ff4252e3 |  | note | Comments - GAP 40 hardfill to be used or suitable as dug material
checkpoint-status |  |  | checkpoint | 300.2 - Structures (manholes, head walls, catchpits etc.)
label | 0496b91e-7880-5019-a760-c520c6a26b5c |  | note | Detail of Activity - Backfilling in berm
label | f7b77d14-65b4-55d9-bd3d-a702d7ae2266 |  | note | Action - M
label | ade208e1-abcd-57a1-93d1-1f81513ec8e7 |  | note | Minimum Test Frequency - 1 per structure
label | 20ccda2f-bf9b-5037-8b4c-0a6871590a86 |  | note | Inspection / Test method - Clegg Hammer
label | 420bf99e-86a2-55c8-859b-c131bec57d08 |  | note | Acceptance Criteria - Top of trench in berm. CIV ≥ 15.
label | 0c5c2f8b-ce4d-587a-92e6-afaf4857386a |  | note | Record documents - QC sheet
label | 727b0cb6-6458-59de-93ad-8c4193a949b3 |  | note | Comments - GAP 40 hardfill to be used or suitable as dug material
checkpoint-status |  |  | checkpoint | 300.21 - Structures (manholes, head walls, catchpits etc.) Pavement Layer Construction if in road.
label | 210f74b4-8a5c-58ab-8adb-bf539f5b1e0d |  | note | Detail of Activity - Subbase
label | 7adbe8db-2432-5899-9cbc-0ab2384f5396 |  | note | Action - M
label | 3cf828ae-6e4f-5c7b-9800-6f1b94a07653 |  | note | Minimum Test Frequency - 1 per structure
label | c62e2fc4-c3a3-5f02-ac32-d89233d848eb |  | note | Inspection / Test method - Clegg Hammer
label | a9eb44f7-26a1-5be2-9bff-e1ba60938ff3 |  | note | Acceptance Criteria - In road (granular) clegg every 300mm lift after thermal backfill. CIV ≥ 20.
label | 8cd543d8-22b3-5e36-b8dc-8a12fb039560 |  | note | Record documents - QC sheet
label | abaa892f-17d4-5a7f-b520-a7a60eed67df |  | note | Comments - GAP 65 to be used
checkpoint-status |  |  | checkpoint | 300.21 - Structures (manholes, head walls, catchpits etc.) Pavement Layer Construction if in road
label | e8a25cfc-566b-57e1-be91-547c5adbc969 |  | note | Detail of Activity - Basecourse
label | 6c056e27-f909-5c54-af95-d99c48fce009 |  | note | Action - M
label | e187959e-c613-5122-abc5-c76cabdbb410 |  | note | Minimum Test Frequency - 1 per structure
label | 6ec2708e-be65-513d-b923-479e5fd27fcb |  | note | Inspection / Test method - Clegg Hammer
label | 0c8a74ec-4f02-5856-9ed6-5bbe05f10555 |  | note | Acceptance Criteria - In road (granular) clegg every 300mm lift after thermal backfill. CIV ≥ 35.
label | 69e97259-b782-5b5e-9c79-fe326b0830fa |  | note | Record documents - QC sheet
label | ef162a32-d651-514a-a9d9-0b3e14166be5 |  | note | Comments - AP 40 to be used
checkpoint-status |  |  | checkpoint | 300.22 - Structures (manholes, head walls, catchpits etc.)
label | 60af820c-852a-5acf-8461-96ba79b049d9 |  | note | Detail of Activity - Installation tolerance
label | 3cf1ac13-4638-5b6d-b21b-5a1f40519806 |  | note | Action - M
label | 18885689-658d-5577-8839-79e5b86c7942 |  | note | Minimum Test Frequency - 1 per structure
label | 2519f021-0f1c-520a-983d-112b9359cbc7 |  | note | Inspection / Test method - As Builts
label | fd2d5178-162d-552e-b6ef-e3e8c020960c |  | note | Acceptance Criteria - All MH lids and grates to be flush with the surrounding finished ground level.
label | fffdc858-84e6-50f7-8427-523b091fab04 |  | note | Tolerances: ±Half a pipe length longitudinally and ±150mm laterally.
label | df0c03c1-7260-55c6-b6e2-f1144674f26e |  | note | Record documents - QC sheet
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | 300.23 - Collate above documentation
label | 019b0429-c7ee-5e91-91b4-3139064811b8 |  | note | Detail of Activity - Document review
label | 585929dd-d5d0-5d99-b1d9-0c361042b01d |  | note | Action - H
label | 38faefd3-198d-510e-b006-2fd3513242b1 |  | note | Minimum Test Frequency - Each ITP
label | 2728af98-5d30-5392-a01c-d5f80190e5e4 |  | note | Inspection / Test method - Review
label | 5e5fedf4-e95f-55c5-8bc5-f01c4d2c4ff4 |  | note | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | e59302e7-c569-59dd-8759-7c6a92ecb837 |  | note | Record documents - Review
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 300.24 - As-built drawings
label | 90d42a18-3fd3-597b-b219-1a0f6bc3ba49 |  | note | Detail of Activity - Survey
label | c9303ebd-cb87-57a6-af53-8b73009acb51 |  | note | Action - H
label | 67647060-391d-5850-9795-6449ef2db7c0 |  | note | Minimum Test Frequency - At completion of construction
label | 10b312c5-e1d2-5f09-9451-2c03522ea4cd |  | note | Inspection / Test method - Asbuilts to be submitted at the completion of construction, information to be captured
label | 4ef7d12e-f846-5789-bb07-569e03de6fe0 |  | note | Acceptance Criteria - Asbuilts reviewed and submitted
label | 0bf1cb7d-3d0d-584f-a0b3-3572a6145ad4 |  | note | Record documents - In Eight record
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | e05be1e4-0c07-5896-b15a-f263dae8a94d |  | textbox | Contractor's Rep Name:
text | cdf70162-ee8e-5a48-9670-0f5991060812 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - Type A Pavement |  |  |  |  | Yes | ITP - Type A Pavement | fb34c0f5-281f-4e52-be05-c8346d70ed7a
checkpoint-group |  |  | section | Pre-construction / Preliminary Compliance Requirements
checkpoint-status |  |  | checkpoint | 600.1 - Method Statement Development / Job Safety Analysis / Enviro Site Specific Plans
label | c2726a76-e489-5811-81fa-6381c667d214 |  | note | H
label | 6c202b21-7a90-52db-8a6a-946fe8f21b1d |  | note | Minimum Test Frequency - Prior to Construction
label | 25e50b94-4d23-5319-9599-c9c3bfd9612b |  | note | Acceptance Criteria - Method Statement and JSEA Completed and signed by relevant authority
label | 8617fcb5-0bae-535b-b506-0eabe7c113d2 |  | note | Responsibility - Downer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.2 - Drawings and Specification
label | f37ad9ba-6446-551a-ab01-1daa780a9804 |  | note | H
label | c686c92a-bfd6-5604-9872-127e10c6becb |  | note | Minimum Test Frequency - Prior to Construction
label | 6c05991c-54d1-5bbe-a717-127427f58f19 |  | note | Acceptance Criteria - DWG’s and Specifications are of For Construction and latest revision. Reviewed and approved by Designer and Client.
label | 65e82b76-7aca-5f81-a594-4604fa170302 |  | note | Responsibility - Downer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.3 - Set out
label | ce150c01-94aa-5bb7-ac6c-cde88c704970 |  | note | H
label | b7438cf7-075c-5e71-82e9-3c19913a4efb |  | note | Minimum Test Frequency - Prior to Construction
label | a2d18603-e8c3-5c82-9e00-17f37fe86f31 |  | note | Acceptance Criteria - Set out as per latest Design Model / For Construction Drawings.
label | bd8f68ea-49af-5467-a793-d271e24782e6 |  | note | Responsibility - Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.4 - Material Approvals
label | a3f8087d-91fb-5f8a-b7fc-084e39b06ea3 |  | note | Detail of Activity - Submit testing data fir the following materials: - AP65 -GAP 40 -GAP 20 -Hardfill
label | 7f808833-a3a8-5ca3-a200-0e5f94cc8aff |  | note | H
label | 0c35a99c-aa92-5477-9bf9-acc1b04e4818 |  | note | Minimum Test Frequency - Prior to Construction
label | 20a08ccd-dd0f-5984-967f-272e24990df8 |  | note | Inspection / Test method - Quarry Testing Data
label | 90da3ed3-3128-5afb-aa86-e3f0f590183a |  | note | Acceptance Criteria - Material approvals to be sent to the Engineer. Refer Project Specs and Drawings;
label | 9b9746ed-52f6-50c0-b532-4ad76f46b2a2 |  | note | • Recycled Pavement/Subgrade Improvement Material:
label | e547f80c-bad3-5eb2-a5d1-38a2bc1a55dd |  | note | • AP40:
label | bff3b4cc-b4ed-50f1-99ed-7b14f39b3c06 |  | note | ○ CBR >20%
label | f2c0725f-acc1-5de0-8573-54bcd3885ae8 |  | note | ○ Sand Equivalent > 20
label | bf956759-a273-5053-8784-e9964e4e1a68 |  | note | ○ Grading < 35% passing 75um sieve
label | 4b6ebc20-7c54-5a24-b848-3b0ab0e47ac5 |  | note | • AP65:
label | 546e6e42-3415-5afc-97b0-5fd7463adf77 |  | note | ○ Crushing Resistance < 100kN
label | 49824382-d39f-5502-a082-9b8b4b2a79cc |  | note | ○ Weathering Quality Index of A,AB, AC, BA, BB or CA
label | 6622a025-494f-582c-b095-badf1cadd856 |  | note | ○ Sand Equivalent ≥ 25 if > 4% passing 75um sieve
label | 51fa911d-1487-5896-8e38-96ae370ab4ac |  | note | ○ CBR minimum 40 using heavy compaction
label | 3db17ce3-8792-53c5-bfaa-4f238093e599 |  | note | ○ Grading
label | f3368bd7-d9da-53e6-a048-900cfb94c807 |  | note | Responsibility - Designer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.5 - Underground Service Identification
label | 225acce5-118d-5209-a0c1-b1fb0eeeb344 |  | note | H
label | e45761f1-d936-5fa6-b1e8-17635bfd850b |  | note | Minimum Test Frequency - Prior To Construction
label | 23e3e9c0-9326-584e-a770-f2c141f1e6c0 |  | note | Acceptance Criteria - Ensure underground services are positively identified and asbuilt. Where this interferes with design permanent works, Service provider and Designer to be notified immediately.
label | 56e02775-1973-5fb7-b50d-6b24b7dd0b94 |  | note | Record documents - InEight Records
label | e238120d-130b-58cb-b651-e07c89493f62 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction and Finishing
checkpoint-status |  |  | checkpoint | 600.6 - Existing Pavement Assessment
label | 32e55853-8c6d-502b-81d1-fa626f6d489a |  | note | Detail of Activity - Confirm Pavement Depth
label | 57f68769-26f7-5a02-8ceb-583beeae8919 |  | note | H
label | a08cf6ba-569f-5e20-8e94-7e43a38848fa |  | note | Minimum Test Frequency - 50m centres
label | 1bdc1645-7fff-58d0-af89-8c5be4f89fb1 |  | note | Inspection / Test method - Test Pits / Visual Inspection
label | d6bec85d-2fcc-5585-9033-d677cdd1aebd |  | note | Acceptance Criteria - Mill 200mm. Dig/core test pits to confirm if existing pavement:
label | d809f270-cb9d-5cfe-9c0e-6be57a18a358 |  | note | – If existing underlying pavement is of sufficient depth (i.e. ≥250mm below mill surface/≥450mm below finished level), continue with "Existing Pavement" steps below (light green rows).
label | 3eaa8688-ada0-5c2a-bf33-f40b9e080234 |  | note | – If insufficient depth or poor quality, advise WSP Engineer, mill/excavate to 450mm from FL, and complete "Full New Pavement" requirements below (light blue rows for Recycled or Mixed Materials, light yellow rows for Engineered Material only - i.e. AP65,).
label | 11e68513-9e6f-5777-8ea6-ddcac301e572 |  | note | Record documents - QC Sheets
label | e0601623-140e-5939-80ab-279f6227713f |  | note | Responsibility - Contractor
label | c95065cb-d769-5b23-b5f9-bec7d038e5b8 |  | note | Comments - Existing pavement to measure 450mm from finished level (minimum). If not "Full New Pavement" requirements are to be followed.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.7 - Existing Pavement Assessment
label | 289549a8-f1fb-504b-9592-fc4919cc3eda |  | note | Detail of Activity - Beam Test
label | e3b6a946-c346-5417-92e1-9368603627c2 |  | note | H
label | dd53caed-8696-5481-80fc-e7f9a4559e6d |  | note | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | 2a6762fd-d9fa-534e-b545-19445d1366a1 |  | note | Inspection / Test method - Beam Testing
label | e74cd12e-8316-5c58-aa44-ca8bea169a01 |  | note | Acceptance Criteria - Review beam test results to determine if undercuts are required.
label | 889d8e53-f553-5588-8fb5-2f6daba79bd2 |  | note | <1mm:
label | 0b858ec3-f509-571e-b54d-df42b48ab118 |  | note | – No Undercut
label | b437824e-e2cb-5c07-9a81-78ebb195b4a5 |  | note | 1 - 2.5mm Beam Deflection:
label | 39aca4ef-dec8-5562-9e1f-66da60b5bf99 |  | note | – Undercut 50mm
label | 4c2c4247-e0c3-5fef-9da8-875bc11697c0 |  | note | – Backfill with 20/40 drainage aggregate
label | fcd76ec6-6277-5c2a-a837-61a71132ab7f |  | note | 2.5 - 5mm Beam Deflection:
label | 51b14359-f0b1-56b8-a61b-8b78da2ab05a |  | note | – Undercut 100mm
label | 493d7011-6072-520e-8e72-caa0e189d582 |  | note | – Backfill with AP65
label | 47d09477-1a47-50fc-8779-01a0ee52b386 |  | note | 5+ mm Beam Deflection:
label | 96a3e932-b7dd-5313-bc01-41ba23692d67 |  | note | – Undercut 200mm
label | 1f4c2c03-3045-59d4-827f-f546086dd813 |  | note | – Backfill with AP65
label | c7e88eb9-4389-58da-95d7-06571d12563e |  | note | Record documents - QC Sheets / Lab Result Sheet
label | d07d8783-dbed-5fb1-b11d-94bdfc0d14c2 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.8 - Existing Pavement Assessment
label | 7b1467ff-cfd8-5a19-83c5-961205c104f4 |  | note | Detail of Activity - Milled Surface Stringlines
label | aee57e4a-91bb-5194-8808-842c19b9280a |  | note | M
label | 11fa1042-4a97-5f74-9227-ceae6349ccac |  | note | Minimum Test Frequency - 20m centres
label | f5f1fb85-49de-50c7-8392-58ae5d619db6 |  | note | Inspection / Test method - Visual Inspection
label | 5b772d74-24b0-5b8b-b8bf-87d66d02fb48 |  | note | Acceptance Criteria - Finished Level – String Line, +20mm/-50mm (i.e. 20mm high, 50mm deep)
label | a992b9c9-59c5-57fe-bd75-21cc186efff9 |  | note | Record documents - QC Sheets (String Sheet)
label | c66754fb-9ea8-5948-b1a7-d902f8dbc809 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.9 - Existing Pavement - Subbase Stabilising (During Construction)
label | f459813d-fc8d-5ffc-a511-641c34d8e947 |  | note | Detail of Activity - Mat Samples (1m2 canvas)
label | b7701ea5-dd55-57a7-9b17-dbd723324107 |  | note | W
label | 900f9d82-5b6c-50d3-9a8b-57e548eddda5 |  | note | Minimum Test Frequency - 1 mat weighed every 400m2
label | fb5accd6-2f9b-5bbd-be05-9e90616bedb2 |  | note | Inspection / Test method - Mat Samples
label | d1106c0f-a56e-5226-a978-d44d4f4a2ed6 |  | note | Acceptance Criteria - Subbase to be stabalised with 3% cement.
label | 5762c107-f5c4-5946-ac64-4581529c4e92 |  | note | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
label | 8bf79774-6e6d-59db-b781-a042e5c06d47 |  | note | Record documents - QC Sheets
label | 34e4b454-ce41-505b-84f7-15cda6c90968 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.10 - Existing Pavement - Subbase Stabilising (During Construction)
label | 8bd3ba31-0e39-5953-9bbd-8d83c5eb13d6 |  | note | Detail of Activity - Plateau Density Test
label | ff5bb237-0dec-5443-88d9-8162ab8169d4 |  | note | W
label | 2cc2fab2-f3bf-505f-b29b-c2fcbd3d0bb1 |  | note | Minimum Test Frequency - 1 Plateau Density Test per lot
label | 44ff7ec6-7ffd-555d-9904-94480ec6fd4a |  | note | Inspection / Test method - NDM
label | a3362cdf-d355-5947-95e7-db51794201ae |  | note | Acceptance Criteria - Determine minimum number of roller passes required to reach peak compaction strength using both primary compaction and finishing compaction rollers.
label | 4a147b44-d354-5969-be85-dd8f9f41451b |  | note | Record documents - QC Sheets
label | 9d6bd9e9-803a-5a0f-b8a9-0936e278ae27 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.11 - Existing Pavement - Subbase Stabilising (During Construction)
label | e1e354af-ae20-568f-a985-d25b4c21eb31 |  | note | Detail of Activity - Stabilisation Depth
label | 836186d0-5f48-548f-bbe0-f21c78828962 |  | note | M
label | 2c9b6581-d832-5fdb-8c64-47ad63e682d5 |  | note | Minimum Test Frequency - Once per lot
label | e97a753e-2c43-5100-9b57-f5ecc93394be |  | note | Inspection / Test method - Visual Inspection (with tape measure)
label | 3a5f0161-073a-5e64-8819-63fca98ce742 |  | note | Acceptance Criteria - Stabilised to 200mm depth.
label | edf774f4-75cf-5bc6-813e-5b41808c171b |  | note | Record documents - QC Sheets (Photos)
label | 0d9b713d-c5d6-56af-836d-a3d606bea253 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.12 - Existing Pavement - Subbase Stabilising (Post Construction)
label | f389d0f1-7737-5d9f-969c-145e7604119a |  | note | Detail of Activity - Beam Test
label | e18dda01-84bc-5132-9a28-d0e568232ec0 |  | note | H
label | f6edc709-649a-5c2f-871e-bc08ef292cb9 |  | note | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | f94406e2-0275-510d-a4d3-3f73c42b1c81 |  | note | Inspection / Test method - Benkleman Beam
label | 69eeadb5-2e10-5a90-808a-b0f2783f2450 |  | note | Acceptance Criteria - ≤ 2mm deflection
label | ab50706e-57ca-5e98-9513-3d5fa9db1a33 |  | note | Record documents - IANZ Accredited Lab Results
label | 346b2b5c-e89e-5dfd-8a69-51586d143315 |  | note | Responsibility - WSP Laboratory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.13 - Existing Pavement - Subbase Stabilising (Post Construction)
label | 0f7ad1b3-d6e9-5d9c-8a75-e4aa333bc9d4 |  | note | Detail of Activity - Stabilised Depth
label | 73934d22-325f-5f82-8079-39ffa94a55a5 |  | note | M
label | a9dde6a0-8365-54e1-a77a-cce8483e65dc |  | note | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | 56d89fd2-df8e-5404-8266-40d7144e7fda |  | note | Inspection / Test method - Core Visual Inspection
label | 8580a489-7892-5280-ae5e-44a1f55d5b47 |  | note | Acceptance Criteria - Cohesivity (cores hold together to be removed)
label | cb538501-5718-58d7-a8b4-3cdd9504dd24 |  | note | • Grading of aggregate (i.e. good mix of different stone sizes)
label | 196fe2b3-142a-5b2f-ab3c-daa7cd2e33de |  | note | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
label | 019f6a44-f75a-523f-9c18-bd0c20eee380 |  | note | Record documents - QC Sheets (Photos / Coring Report)
label | a3cd9b6f-f815-5eb9-a174-b0731d516d07 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.14 - Existing Pavement - Subbase Stabilising (Post Construction)
label | f97701ac-ed81-5c3b-9c4f-20408c4141ea |  | note | Detail of Activity - Stringlines
label | c2139d7b-ecfa-5553-ba5e-a9e9fa75a95f |  | note | H
label | f21b8b3c-ad72-55fc-93cd-fa9eb9578048 |  | note | Minimum Test Frequency - Every 10m
label | 5c3d3c06-de26-54b7-9762-22b7424828d9 |  | note | Inspection / Test method - Visual Inspection
label | 95c95098-9f49-5e30-b27f-a891f17b5e6e |  | note | Acceptance Criteria - Layer Finished Level – String Line, each lane
label | 84ea6fa7-5c7c-5a7c-a511-85a396d52c4c |  | note | Tolerance: +10mm/-30mm
label | 944110a5-f9d2-54ef-9010-2d5788bc0b9a |  | note | Record documents - QC Sheets
label | bcc93889-2032-565f-ae66-4d12af9e2278 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.15 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Layer
label | 2c61409f-c598-5c86-8cb9-0b04384642f9 |  | note | Detail of Activity - Subgrade Levels
label | 811ebe5d-d1d5-5403-bc8e-866fc8fdab6e |  | note | H
label | 37f8140b-8ba7-5b3f-8658-04c847f4137a |  | note | Minimum Test Frequency - 20m centres
label | 44479b73-c4b7-5195-bc06-c9c33b0f0d8f |  | note | Inspection / Test method - Visual Inspection
label | 2fe8c885-245c-50f3-b735-b4666052b2a3 |  | note | Acceptance Criteria - Cut subgrade to 450mm below finished level.
label | 39397a02-ec1e-5174-9099-f3364d57d570 |  | note | • String line tolerance to be within +20mm/-50mm (i.e. 20mm high, 50mm deep)
label | 56686a5b-16b1-52ad-b0a7-bf7d781f3042 |  | note | Record documents - QC Sheets
label | f634e72d-235c-5eaa-938f-ca3f04f46c2c |  | note | Responsibility - Contractor
label | de7eb29a-ccb6-55b9-b4b4-1b63702c6ca2 |  | note | Comments - Remove to waste and excavate 530mm from top of kerb / 450mm from finished surface level.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.16 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Layer
label | f3b153cd-dd08-5304-8fa1-c84ec2bd427a |  | note | Detail of Activity - Scala Penetrometer
label | c732e24d-de06-52c5-b5a2-8669656ab446 |  | note | H
label | 6f1b8ca1-9c70-5ecb-8fd2-a616ef4a1787 |  | note | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2. 1 per 20lm
label | b778f1a3-b74e-5a5c-a9bd-98ab8e455dd3 |  | note | Inspection / Test method - Scala Penetrometer
label | 2b8437fb-8e32-5468-bde6-f940c805ed5b |  | note | Acceptance Criteria - Scala (bearing Strength on insitu subgrade) to depth 500mm, with the following requirement to be achieved;
label | cd559a83-240f-5eb5-9fbd-4e63aa95509c |  | note | • ≥ 3 blows per 100mm - No Undercut
label | 790cbf47-c766-5041-bba4-a2824c8d1151 |  | note | • 2-3 blows per 100mm - 200mm Undercut
label | 30e223ea-f6b6-597d-affe-2d5e8fdc7650 |  | note | • 1-2 blows per 100mm - 300mm Undercut
label | 365a7431-10ee-518c-9bdd-dbe66890084b |  | note | • <1 blow per 100mm - 450mm Undercut
label | 2addff43-c41e-5ee9-afcb-2ab076c4bf84 |  | note | Record documents - QC Sheets (Scala Sheet)
label | c7284a96-c3f9-5e3f-8969-885c0f8e54d9 |  | note | Responsibility - Contractor
label | 2f92d505-71d6-5cb0-8c37-b7330f226d67 |  | note | Comments - Scala results to meet or exceed per below:
label | 78bd1836-3049-57df-a66b-b3f79e0e93bb |  | note | • 0mm - 100mm - ≥ 3 blows per 100mm
label | 01b55db5-718e-5295-ae6d-b02f24aaece6 |  | note | • 100mm - 200mm - ≥ 2 blows per 100mm
label | e29fd9c8-431f-576a-9b61-7441c30c034a |  | note | • 200mm - 300mm - ≥ 2 blows per 100mm
label | 11545e1b-bb72-592e-bfc8-4fecf81e15df |  | note | • 300mm - 400mm - ≥ 1 blow per 100mm
label | 23f906a3-402c-5d6b-8819-9c0a7f3994b7 |  | note | • 400mm - 500mm - ≥ 1 blow per 100mm
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.17 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Layer
label | 65cf9cc1-403c-5f3f-9b66-1f614cedf9a5 |  | note | Detail of Activity - Proof Roll
label | b6f13b49-6648-5e43-97f7-fb8910ab7970 |  | note | H
label | 71d577c1-d684-5fb7-89a7-893ecededdca |  | note | Minimum Test Frequency - One per lot
label | 7e50b913-fcb1-5f62-90fc-ba090d7941ce |  | note | Inspection / Test method - Visual Inspection
label | 712dd514-4a84-5153-9e0c-0a6813bd41d2 |  | note | Acceptance Criteria - Proof roll – Check for uniformity, soft areas to be undercut
label | 169ec0c0-9fae-5e77-b5d1-e7bd897fcb9d |  | note | • 200mm and backfilled with recycled pavement, AP40 Hardfill or AP65.
label | bdd6dd6d-0187-5f97-a3f5-282abad53282 |  | note | Record documents - QC Sheets/Site records
label | 1cd4b33a-b394-58a4-a5d6-a6064bd2d49d |  | note | Responsibility - Contractor
label | 7c2ef8fc-40d4-54da-beec-6f43e481fb7c |  | note | Comments - Backfilled with recycled pavement (millings), Hardfill or AP65.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.18 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Improvement Layer
label | ce78968c-38c5-5a06-a8d5-a4ad142273c3 |  | note | Detail of Activity - Undercut Measurements
label | 22a204ac-505c-5a41-8804-f79d144f0019 |  | note | M
label | de85dad5-fc5a-59b1-8717-0e65c5eabab6 |  | note | Minimum Test Frequency - Every undercut section
label | 941b4870-1dc1-5ffa-9268-8eadea39fced |  | note | Inspection / Test method - Visual Inspection
label | 85baeb5d-2807-5f32-bfce-59c21ef730e8 |  | note | Acceptance Criteria - Measure and record undercut area and depth
label | 2cd50e0b-bc92-50be-80d8-4d5a03edfade |  | note | Record documents - QC Sheets/Site records
label | 7e79c4ac-2cbd-5f5e-b616-952cbcf9a499 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.19 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Improvement Layer
label | 2d304fd1-1b1c-5e0f-aed3-daf5a89252f5 |  | note | Detail of Activity - Scala Penetrometer
label | 3f3427f1-b10c-5e4c-a0a8-5098712a6d55 |  | note | H
label | 18d4efb5-ff93-5c1b-b54f-882d8ca4ae6e |  | note | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2. 1 per 20lm
label | 910cf240-e588-51a3-9fcd-1bfd93d241f8 |  | note | Inspection / Test method - Scala Penetrometer
label | 2207d305-b90b-5fe1-a70e-1160615beeaf |  | note | Acceptance Criteria - No Target required, For Record purpose only
label | e00d99a1-32a1-5c7f-b783-e815e86e92af |  | note | Record documents - QC Sheets (Scala Sheet)
label | 6a7cca46-43d0-59af-8fc2-a1c643958f96 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.20 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Improvement Layer
label | b2ee98b2-49ae-5b85-8163-cce276883ce0 |  | note | Detail of Activity - Backfill Layers
label | 0bff48b5-1fac-5b2c-8869-2752ad7e87d1 |  | note | M
label | bd9a3d70-9396-53fb-be4d-7fad4ca6ce6d |  | note | Minimum Test Frequency - Every 20m
label | ab338bdd-3822-5c80-8d67-ca542700085e |  | note | Inspection / Test method - Visual Inspection
label | 80567def-9a4a-5382-a039-956b93188964 |  | note | Acceptance Criteria - Backfill and compact in 160mm-200mm layers
label | f867ba57-a998-595f-8827-2e657b31f47b |  | note | Record documents - QC Sheets
label | e4f2af8e-4080-5f24-a062-1c9d968ec9c0 |  | note | Responsibility - Contractor
label | 9300cf89-e5e4-54b1-9494-47d975fe4cc3 |  | note | Comments - Use recycled pavement (millings), Hardfill or AP65 if available.
label | 91cecc92-2ef1-577f-a8f4-375877955ea1 |  | note | • We propose to use proof roll instead of NDM testing because of the variablity of the recycled material and the bitumen content in it making it hard to test.
label | 51edae0b-0da9-5845-afdd-b4959cc21a25 |  | note | • This supersedes clause 22.2.1 in the project Specification.
checkpoint-status |  |  | checkpoint | 600.21 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Improvement Layer
label | 291d25db-14fb-5915-bcf7-e6d99bbf1d5d |  | note | Detail of Activity - Beam Test
label | e5b46503-210f-57d3-bf90-621f46107aa1 |  | note | H
label | aad514bc-6fcb-56a0-a1ae-1559cdd96189 |  | note | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | 72d4babb-669b-5adb-8a98-c169a4ece187 |  | note | Inspection / Test method - Beam Testing
label | db5f6844-1676-5951-98ea-9f4bb6597da3 |  | note | Acceptance Criteria - ≥ 2 mm
label | 70cb22e4-04a1-56d2-ad60-891d8011c46c |  | note | Record documents - QC Sheets / Lab Result Sheet
label | 30338469-115d-5ef5-89ee-cd821ee6ea7e |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.22 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Layer
label | 64bd6246-a993-5c9e-8870-bcc425e45fb4 |  | note | Detail of Activity - Construct Subbase
label | e67ee3ed-4364-5a79-b786-4591a9e60793 |  | note | M
label | 418fb241-5dc3-5c6e-8224-ef9ea6f0d95c |  | note | Minimum Test Frequency - Per Lot
label | ce31d987-98f9-587d-b2f6-9cb46d750f3f |  | note | Inspection / Test method - Visual Inspection
label | f10313f8-3356-5419-9a90-169d391dafeb |  | note | Acceptance Criteria - Construct subbase with 200mm of millings and top up with AP65 if needed. (330mm below TOK) Add 50mm of 20-40 drainage material.
label | e4c02d52-5de4-5746-9f59-32b28a015fb0 |  | note | • (280mm below TOK) Ensure material is compacted and enough volume to be stabilised.
label | e0170402-87b7-588b-8e66-480a6a9f97f9 |  | note | Record documents - QC Sheets
label | c98c40e5-54ec-5412-9143-17718aeff984 |  | note | Responsibility - Contractor
label | a7e16b8b-7576-51cd-8f18-863343d131cf |  | note | Comments - Check each layer with strings
checkpoint-status |  |  | checkpoint | 600.23 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Stabilising (During Construction)
label | e98e7922-0f6f-5456-aa5c-243adab143db |  | note | Detail of Activity - Mat Samples (1m2 canvas)
label | f0c391cc-fbc6-5bdf-89cb-a48e55626da8 |  | note | W
label | 588d7e81-6707-500c-a8dc-40de485b8c31 |  | note | Minimum Test Frequency - 1 mat weighed every 400m2
label | d1b7bd79-862a-5f7c-9dbb-92172bc6a17e |  | note | Inspection / Test method - Mat Samples
label | 51256104-74f8-5a14-97ba-68130a09e21e |  | note | Acceptance Criteria - Subbase to be stabalised with 3% cement.
label | 7b0b4cfc-38d9-5a08-9b0c-d75a4f3198f9 |  | note | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
label | e31973ed-961b-519c-81d3-6459ed3c509e |  | note | Record documents - QC Sheets
label | 93fcf078-1b7d-5623-873b-4d566cbb8f8f |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.24 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Stabilising (During Construction)
label | 36311214-fff9-5e67-af41-ec117e443275 |  | note | Detail of Activity - Plateau Density Test
label | 6f86a5a1-c6ac-58d5-8cab-cabc30d33895 |  | note | W
label | e52f80d0-f01d-5040-9884-88462fb4b6a9 |  | note | Minimum Test Frequency - 1 Plateau Density Test per lot
label | a5c73744-e49e-58bc-8a33-ba4287ec26be |  | note | Inspection / Test method - NDM
label | 44ff8de8-8ae8-5509-9a94-64ad459a8071 |  | note | Acceptance Criteria - Determine minimum number of roller passes to achieve peak/maximum density using both primary compaction and finishing compaction rollers.
label | fe2f3a01-ec66-5d3a-86e6-c2059e67f84b |  | note | Record documents - QC Sheets
label | 887bbf20-1031-5508-8913-254a65cb28d6 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.25 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Stabilising (During Construction)
label | 7e221ecc-4dd6-5e22-8ccd-928220b604a9 |  | note | Detail of Activity - Stabilisation Depth
label | 1d878bb6-d355-58e4-ac81-27c5d7ab91c7 |  | note | M
label | 8c5ba6cd-d97e-5bb3-b930-658d304765a2 |  | note | Minimum Test Frequency - Once per lot
label | 12b79692-bc73-5e27-b7fa-4dd8e3ce2b7d |  | note | Inspection / Test method - Visual Inspection (with tape measure)
label | bf0a2530-7235-5644-be69-71bd109076dc |  | note | Acceptance Criteria - Stabilised to 200mm depth.
label | ec30ebff-bab6-507f-84ce-c14f6bd2f5b7 |  | note | Record documents - QC Sheets (Photos)
label | e701733d-2d0e-5d61-9673-2d70ac53025e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.26 - Full Depth New Pavement - Recycled/Mixed Material - Stabilised Subbase (Post Construction)
label | 35e56896-9bd0-5593-9501-99b03a361a73 |  | note | Detail of Activity - Beam Test
label | 219afd89-8058-5741-825b-1860cdf3953b |  | note | H
label | 0ae28c80-8fb7-55e6-b0f3-d28b0d2c67c8 |  | note | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | d28376c5-63f1-5880-add7-133dd82745ed |  | note | Inspection / Test method - Benkleman Beam
label | 43c58c1a-9030-58c8-8241-aef1c79aaacb |  | note | Acceptance Criteria - ≤ 2mm deflection
label | 9406f1ce-fe7a-51ab-b579-96eb00e06704 |  | note | Record documents - IANZ Accredited Lab Results
label | 2258bd90-4ae1-5c72-a554-7dac133949b5 |  | note | Responsibility - WSP Laboratory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.27 - Full Depth New Pavement - Recycled/Mixed Material - Stabilised Subbase (Post Construction)
label | 3875069f-ed3f-5819-8333-6ba0ca2a1502 |  | note | Detail of Activity - Stabilised Depth
label | 1a62f0a1-ebea-57c9-8974-1575c99aae09 |  | note | M
label | 368cf98a-256b-564b-9cb9-a967221b2f15 |  | note | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | 18b2356e-2a7f-51a0-84f8-1e3a99e950d7 |  | note | Inspection / Test method - Core Visual Inspection
label | 056154ab-edf3-56fc-89f6-733f1966927a |  | note | Acceptance Criteria - Cohesivity (cores hold together to be removed)
label | 77c4ea6c-efff-5db9-9b62-c1666deebbfc |  | note | • Grading of aggregate (i.e. good mix of different stone sizes)
label | 082b8aae-0fde-5399-b89b-dab6ea4be8ce |  | note | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
label | 0faf8872-6196-5a8f-bf81-f610e5242401 |  | note | Record documents - QC Sheets (Photos / Coring Report)
label | 92f46203-1399-5e60-be15-355845640df4 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.28 - Full Depth New Pavement - Recycled/Mixed Material - Stabilised Subbase (Post Construction)
label | 2dca50a8-6e32-5f4d-a9da-38282ab7b02b |  | note | Detail of Activity - Stringlines
label | 930680e5-0465-59f6-8071-6942c13af4ab |  | note | H
label | 7b4ca272-8adf-52e0-adc0-fac0cc9c9722 |  | note | Minimum Test Frequency - Every 10m
label | 5ea7ea4d-8967-5713-b22a-3ddee2eb24bb |  | note | Inspection / Test method - Visual Inspection
label | bbc026bb-894a-5765-97db-c8ae7faefa73 |  | note | Acceptance Criteria - Layer Finished Level – String Line, each lane
label | 5e34d0c4-efb0-5781-8f7d-2903640d22ba |  | note | • Tolerance: +10mm/-30mm
label | edcbd633-cb75-58b4-a0a1-789fc1edc611 |  | note | Record documents - QC Sheets
label | 7f05089e-fed8-5823-81e6-5f63aeccfe0b |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.29 - Full Depth New Pavement - Engineered Material - Subgrade Layer
label | 42bfd64d-a7fd-5e86-90d4-30ed4a3b0f2b |  | note | Detail of Activity - Subgrade Levels
label | 7768ddc1-4d60-56ca-a62c-950d74d773b4 |  | note | H
label | 4198515f-8fcb-5ebe-a751-4b62f2efb21c |  | note | Minimum Test Frequency - 20m centres
label | ef6bebc9-c16b-50e6-9487-3014b60de7e7 |  | note | Inspection / Test method - Visual Inspection
label | 32b0e7d0-ff1c-58de-a15d-3a0cb8420635 |  | note | Acceptance Criteria - Cut subgrade to 450mm below finished level. String line tolerance to be within +20mm/-50mm (i.e. 20mm high, 50mm deep)
label | 614d8f76-b10f-5c8d-a6b9-f448d0e30b26 |  | note | Record documents - QC Sheets
label | 1c21c9f2-0a2b-5c93-8217-cfc2a6185b72 |  | note | Responsibility - Contractor
label | de564291-630a-5e3e-87e1-91e30983e46c |  | note | Comments - Remove to waste and excavate 530mm from top of kerb / 450mm from finished surface level.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.30 - Full Depth New Pavement - Engineered Material - Subgrade Layer
label | 4a1fd2e3-b1bc-5495-92b3-6c645f8640eb |  | note | Detail of Activity - Scala Penetrometer
label | 6f080aad-5d83-5324-9dc1-47d69b639a58 |  | note | H
label | 640d23bd-f820-59f3-9954-923484b1fa06 |  | note | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2. 1 per 20lm
label | 5ef390cb-0e77-519d-9776-08c08854c19e |  | note | Inspection / Test method - Scala Penetrometer
label | c3443b16-9176-5def-9f71-be027a0ac8b1 |  | note | Acceptance Criteria - Scala (bearing Strength on insitu subgrade) to depth 500mm, with the following requirement to be achieved;
label | 3f8c352e-40b6-5e22-a42d-5069af79e9f8 |  | note | • ≥ 3 blows per 100mm - No Undercut
label | f14ffdb0-ac52-569b-9559-00ba8554d54d |  | note | • 2-3 blows per 100mm - 200mm Undercut
label | 0ddd8e6c-e474-55d4-9a43-86743a9331aa |  | note | • 1-2 blows per 100mm - 300mm Undercut
label | f3c7e530-da3c-5874-bd32-2809e896f56d |  | note | • <1 blow per 100mm - 450mm Undercut
label | f652b5f6-2643-5568-bcbc-bb45954ea4b7 |  | note | Record documents - QC Sheets (Scala Sheet)
label | 425b6642-694b-555e-895e-fc4e7255bc88 |  | note | Responsibility - Contractor
label | abb61cbb-b3e3-583a-bf4c-31c2f1f4015e |  | note | Comments - Scala results to meet or exceed per below:
label | d4f9a127-3658-538a-89f8-1dca1228ab50 |  | note | • 0mm - 100mm - ≥ 3 blows per 100mm
label | 1427ed0e-9eb4-5807-b45e-29483eaab27e |  | note | • 100mm - 200mm - ≥ 2 blows per 100mm
label | eb3e8cfd-4971-5b24-a44e-280d0e260014 |  | note | • 200mm - 300mm - ≥ 2 blows per 100mm
label | d77cde2b-43ca-5ab9-b7bd-7502129d88a9 |  | note | • 300mm - 400mm - ≥ 1 blow per 100mm
label | ecbfd9f3-6124-55a0-8c67-10112b2bbb26 |  | note | • 400mm - 500mm - ≥ 1 blow per 100mm
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.31 - Full Depth New Pavement - Engineered Material - Subgrade Layer
label | d15377fa-c605-5152-8155-0e59095768f8 |  | note | Detail of Activity - Proof Roll
label | 465f1a02-7a56-5dd0-b457-7b08630296b1 |  | note | H
label | 744072f1-14d4-5f15-a2b6-4eb39b4f6568 |  | note | Minimum Test Frequency - One per lot
label | 19f4f0bf-f6b4-534a-9720-96a86c9597d9 |  | note | Inspection / Test method - Visual Inspection
label | d0688353-5ab0-5ac8-9891-cb0941c2962f |  | note | Acceptance Criteria - Proof roll – Check for uniformity, soft areas to be undercut 200mm and backfilled with recycled pavement, AP40 Hardfill or AP65.
label | d0fa40a8-8c96-519f-bc88-154a495a9518 |  | note | Record documents - QC Sheets/Site records
label | 9ccee945-4d8b-5c2a-90b7-ed53e02367ca |  | note | Responsibility - Contractor
label | 6fd0f55a-e06f-50d5-af39-dc8f2e7d2623 |  | note | Comments - Backfilled with recycled pavement (millings), Hardfill or AP65.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.32 - Full Depth New Pavement - Engineered/Quarry/AP65 Material - Subgrade Improvement Layer
label | b69bfe85-c15d-5239-9dac-e3a8ffcc204d |  | note | Detail of Activity - Undercut Measurements
label | 2ccb2d3a-57f8-5330-ac35-8991ea47c78b |  | note | M
label | 69264776-672c-5e0a-8b75-6d126a9b1874 |  | note | Minimum Test Frequency - Every undercut section
label | 333d3c1c-a306-589f-9ca4-006876c6392b |  | note | Inspection / Test method - Visual Inspection
label | 5154171a-da4c-5e18-8ffc-22f41ea54b8e |  | note | Acceptance Criteria - Measure and record undercut area and depth
label | df951ebf-af08-5d68-9577-ab99b8e91f7f |  | note | Record documents - QC Sheets/Site records
label | 7dd31d88-32c5-57a3-90d2-a0d861b77814 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.33 - Full Depth New Pavement - Engineered/Quarry/AP65 Material - Subgrade Improvement Layer
label | cd837f7f-09b4-520a-a276-d7e76404915b |  | note | Detail of Activity - Backfill Layers
label | b221f0db-7b0e-50cf-a370-d8d5b4d818c9 |  | note | M
label | 08cbc2b0-7cf8-518e-b3c2-7e3491a5f329 |  | note | Minimum Test Frequency - Every 20m
label | 3ef20e0a-c5ed-5e95-b9f4-e5dbbfcc4e99 |  | note | Inspection / Test method - Visual Inspection
label | 7961a2ed-1532-5702-b596-de83b393e4ec |  | note | Acceptance Criteria - Backfill and compact in 160mm-200mm layers
label | f2a39ec2-a88d-5a9f-848e-6f2ca6aec729 |  | note | Record documents - QC Sheets
label | 958c08e4-c7d9-50dd-8a0e-c2f9e805172f |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.34 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | 618ae097-3a73-5e46-9148-d37f8ef82901 |  | note | Detail of Activity - MDD and OWC
label | 6b8a82a4-49f7-5906-9d70-3aed6424a643 |  | note | M
label | 8cda657c-ca77-5519-aaa7-48c0c964ebac |  | note | Minimum Test Frequency - MDD and OWC 1 test per 5000m² laid
label | 9f1ed805-f1a0-5573-8278-abfecc196b8c |  | note | Inspection / Test method - Laboratory Test
label | 9538c244-deb8-5f03-a78d-c1dfb73f8007 |  | note | Acceptance Criteria - Report value only
label | e318d436-0b25-5f89-96ba-60ca2f42c07b |  | note | Record documents - IANZ Accredited Lab Results
label | 32d01e67-657b-5431-905f-a0ba3df5fa11 |  | note | Responsibility - WSP Laboratory
checkpoint-status |  |  | checkpoint | 600.35 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | 6cb3c12b-5732-5953-b845-470520e21d97 |  | note | Detail of Activity - Mat Samples (1m2 canvas)
label | a8ba2e8a-b3e5-54d0-ad51-050cd0374b05 |  | note | W
label | 3ce86450-9e3d-5620-ae93-1cd40b70e047 |  | note | Minimum Test Frequency - 1 mat weighed every 400m2
label | 2e523c7f-a08f-51e6-ad9e-b3f6319409ee |  | note | Inspection / Test method - Mat Samples
label | 2e920809-349c-581f-80a6-99603dfe5923 |  | note | Acceptance Criteria - Subbase to be stabalised with 3% cement.
label | 55ec50d8-9838-5ace-adaf-9fe009526824 |  | note | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
label | e2dccbc2-ea4a-51cc-8cd4-42872cfaf9e0 |  | note | Record documents - QC Sheets
label | e9f9a318-d33f-5516-9902-7ae2b8ef034a |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.36 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | fa1802dd-851a-55c3-81a4-5f5cfd5ba497 |  | note | Detail of Activity - Plateau Density Test
label | 7f75416d-b626-52c2-9512-59b432c85713 |  | note | W
label | d1629ceb-3318-5b00-848b-4f9e8a6e0a9c |  | note | Minimum Test Frequency - 1 Plateau Density Test per lot (take samples from behind stabiliser as required - min 3 - for lab testing to determine moisture correction)
label | 9fd2f2d9-a4fe-5e0b-ab3a-3973317aa7dd |  | note | Inspection / Test method - NDM
label | dd6f903d-3722-5899-819e-4ae24f1d8bec |  | note | Acceptance Criteria - Determine minimum number of roller passes required to meet 95% MDD using both primary compaction and finishing compaction rollers. Report values. Used for moisture contect correction
label | 10cb1fc3-d267-5b10-b4f9-080c5adbfd09 |  | note | Record documents - QC Sheets
label | f1b28e45-38fa-5658-bf59-a6c951f95a1d |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.37 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | 90390d05-7389-5b33-899c-98601f38f867 |  | note | Detail of Activity - Stabilisation Depth
label | 16183671-2630-527c-ac15-3ff7a83be209 |  | note | M
label | 84c7be24-1d08-531a-b539-baa36cc7b669 |  | note | Minimum Test Frequency - Once per lot
label | 361c81d2-7223-5bb3-8c1a-1bc69b54aa7b |  | note | Inspection / Test method - Visual Inspection (with tape measure)
label | 17de9454-97df-5019-8269-ab51583652d4 |  | note | Acceptance Criteria - Stabilised to 200mm depth.
label | 28b6d2ca-d16d-5604-95d1-4b07e6a3b5ac |  | note | Record documents - QC Sheets (Photos)
label | 8479ffbf-a885-5912-a0fc-12f9d24ab2ed |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.38 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | 4929b0bf-de10-59ec-a98f-30fb30d72ee3 |  | note | Detail of Activity - Indirect Tensile Strength (ITS)
label | d5e4a247-8577-512d-b6f5-3034905cfe49 |  | note | H
label | bff185b8-7cdc-578d-8401-411341294394 |  | note | Minimum Test Frequency - Two (2) soaked & two (2) dry ITS - taken by IANZ accredited lab technician behind hoe
label | 37caa3d2-562c-58e5-8181-773a131547eb |  | note | Inspection / Test method - Laboratory Test
label | bfacafcb-2beb-55f2-9338-280e11ff4427 |  | note | Acceptance Criteria - Dry ITS > 500 Kpa
label | 500f4c06-41fe-5848-baf5-d1a440c9b931 |  | note | • Soaked ITS >450 Kpa
label | 45599dc7-f66a-516e-83a1-c8f648921e05 |  | note | Record documents - IANZ Accredited Lab Results
label | 48792935-3440-5b70-b032-2af8b6aa3ccb |  | note | Responsibility - WSP Laboratory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.39 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | 9625e209-e457-56c7-aedb-2228356a67e5 |  | note | Detail of Activity - Stabilised Subbase Compaction
label | ed72c5eb-51ef-5b05-ab9f-66a00c80ea90 |  | note | H
label | 9f2824a5-3527-5c5a-90a0-659386edd1fc |  | note | Minimum Test Frequency - Backscatter NDM (1 per 200m2)
label | 2be55372-69eb-5380-a96a-4ba52091d811 |  | note | Inspection / Test method - NDM
label | 3b6da5e7-f7a0-5e63-82d8-6e5bb486bd4f |  | note | Acceptance Criteria - Mean ≥ 95% MDD, Min ≥ 92%
label | aae78294-eb06-5209-b312-e09fbc128874 |  | note | Record documents - IANZ Accredited Lab Results
label | 3db68ab6-6eee-56cd-bf37-7cb8982d014b |  | note | Responsibility - WSP Laboratory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.40 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | 81aa6ae4-7a66-53bf-8b12-66eff52c8b83 |  | note | Detail of Activity - Stabilised Subbase Compaction
label | 324ac552-991e-51a0-b11a-b30dbe32ac78 |  | note | H
label | 621dcb7a-9c66-5120-8503-68cbb4b19eb5 |  | note | Minimum Test Frequency - Direct Transmission NDM (1 per 200m2)
label | dc0aa6dd-1efe-5aad-bb03-72c38f86afa2 |  | note | Inspection / Test method - NDM
label | efde717e-670b-5a52-b57b-b57efe014712 |  | note | Acceptance Criteria - Tests to be completed at 100mm depth increments starting at 200mm depth. Check for consistency/uniformity in test results.
label | 187aa51d-5698-5f73-88fc-02a95cb194ad |  | note | Record documents - IANZ Accredited Lab Results
label | f43a83d5-a495-572e-ab15-ad492de9e3bd |  | note | Responsibility - WSP Laboratory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.41 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | 7db767c6-da8f-58cf-bcd3-885d550be96d |  | note | Detail of Activity - Stabilised Depth
label | bca86924-9eb7-52a2-b8eb-3bb021dcaf09 |  | note | M
label | f395fefb-9e45-5d01-80cd-7264aff5f8be |  | note | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | 5124546f-3e1f-59c9-82d5-24a6b5a15f15 |  | note | Inspection / Test method - Core Visual Inspection
label | f48e00d6-fbab-503d-8e67-30a9f04e03a5 |  | note | Acceptance Criteria - Cohesivity (cores hold together to be removed)
label | 2abc3b19-2ed4-5648-a1fd-7f0e10dee4fc |  | note | • Grading of aggregate (i.e. good mix of different stone sizes)
label | f9409159-a61c-55aa-9b3b-008b629ad68e |  | note | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
label | e09691de-9b68-50ae-a690-e01a8a5638a2 |  | note | Record documents - QC Sheets (Photos / Coring Report)
label | c2e2afd4-c400-5a1a-81ef-26bb3a3a568e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 600.42 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | c44de04c-9e89-507e-8296-7370b712bdae |  | note | Detail of Activity - Indirect Tensile Strength (ITS)
label | ffd551a9-1155-5f12-8fab-00876a5ae554 |  | note | H
label | 045b1e93-2d8b-5630-badf-5918c1f8ffae |  | note | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | 5d341c1b-f1ee-5cec-aa06-1dbce1c88203 |  | note | Inspection / Test method - Laboratory Test
label | 11884a86-963a-5679-b10b-2de9588de9ad |  | note | Acceptance Criteria - Target lab results.
label | eeab60c1-c5fa-5449-86a0-26bc704d4c34 |  | note | • Tolerance: Lab result +/- 25%
label | 4b8cd7b6-d238-5bdd-927f-86c4b070ddb0 |  | note | Record documents - IANZ Accredited Lab Results
label | 1db6dbef-3706-5a1e-b2db-b507839fc708 |  | note | Responsibility - WSP Laboratory
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.43 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | 2011d1ce-d39f-5b5c-9593-13ea83986c6f |  | note | Detail of Activity - Stringlines
label | 51c256fa-6129-5b00-930a-224a401cf8e0 |  | note | H
label | f11591d4-24fe-5f05-b871-f575b0ce5071 |  | note | Minimum Test Frequency - Every 10m
label | 8319c522-827c-50c9-b35b-9cd293b8bba0 |  | note | Inspection / Test method - Visual Inspection
label | cd22a1dd-f1ce-5f09-92af-24bf129cb289 |  | note | Acceptance Criteria - Layer Finished Level – String Line, each lane
label | 12845ad7-9dda-55e1-a75c-c20094926d64 |  | note | • Tolerance: +10mm/-30mm
label | d05a0251-d860-5138-b139-b30453c61026 |  | note | Record documents - QC Sheets
label | 69eed1d5-86ec-5453-9099-0ca525979d11 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Close Out
checkpoint-status |  |  | checkpoint | 600.44 - Collate above documentation
label | 8c00f146-043c-5461-b4ed-a20ef49f6f34 |  | note | Detail of Activity - Document review
label | 3d7e0f49-a08f-5c4f-bb84-fcbb73f22175 |  | note | H
label | ec20ef89-156b-5ed6-bc08-ec43c9a0aa42 |  | note | Minimum Test Frequency - Each ITP
label | 2044eaaa-b53a-58fd-a0a1-1b0ad70a88b9 |  | note | Inspection / Test method - Review
label | 310fc3ff-c2fa-5e39-a292-c05f5778f2d9 |  | note | Record documents - N/A
label | f5cef2b6-27f4-52df-81b5-c343ea901b39 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.45 - As-built drawings
label | 55ffdd7d-96d8-57f8-a8b2-1a02e73f1393 |  | note | Detail of Activity - Survey
label | 7b0b220c-09ff-5c3a-8d0d-f99360046934 |  | note | H
label | 340175bc-3360-59ff-8225-0c4e15a94458 |  | note | Minimum Test Frequency - At completion of construction
label | f4b62825-2235-585d-a636-56511b776fc8 |  | note | Inspection / Test method - As-built to be submitted at the completion of construction
label | 65b9fcca-9e4c-5105-bbc1-636464c65d4a |  | note | Acceptance Criteria - As-built to be submitted at the completion of construction
label | fa0344f0-9df9-52e1-96bc-e8c2fed3aa4a |  | note | Information to be captured: Maintain Redline drawings through works.
label | 4e46fbff-85b6-5ed7-90db-b2ae44a3be69 |  | note | Record documents - N/A
label | 1b1a6f25-3ab9-5fec-9723-c54b92eb3a38 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 600.46 - RAMM Data
label | 0e996535-e545-54e2-aa3e-e6150516b186 |  | note | H
label | 27bc3fc8-f84c-579e-a290-1569135d90af |  | note | Inspection / Test method - Info to be submitted by the completion of project construction
label | 6d225c4d-ebad-5685-bb57-e363bbd154e6 |  | note | Acceptance Criteria - Information to be captured:
label | 5f47788f-fb02-5b6f-a844-97783b469cce |  | note | Record documents - N/A
label | c81f7858-9e43-53b3-b486-2583772f9afe |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - Contractor
label | 33457026-5890-5eb9-a3ce-ebba6f05faf5 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | 2e4c11e4-01e8-56df-94f9-b62ff23dd355 |  | textbox | Contractor's Rep Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Client Final Inspection - BBO Engineer
label | 8800c338-fcb8-51e2-832e-8a8d72db8d27 |  | note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | a208933b-a537-5efc-82c0-cfe89b2b0f42 |  | textbox | BBO Engineers Rep Name:
holdpoint |  |  | signoff | Add Signature