## MSE Wall
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - 12/08/2021
|  |  |  | Project: Kopaki Bridge Replacement |  |  |  |  | Date submitted: 12/08/2021
|  |  |  | Construction Process: General Contract |  |  |  |  | Prepared By: Inframax Construction
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 200 - Earthworks |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
MSE 200 | Setout, Materials and Preparation
MSE 200.1 | Earthworks methodology (prior to commencing site works) | Prepare earthworks construction methodology suitable for site (eg access, working areas, proximity to slopes, traffic and other site hazards, construction stages proposed) | H | NA | NA | N/A | Methodology | Contractor | Methodology to be provided to Engineer for review prior to commencing excavation on site.
MSE 200.2 | Material suitability (prior to bringing fill to site) | Confirm imported fill material suitability | H | As per Drawings and Specification | As per Drawings and Specification | As per Drawings and Specification | IANZ Report | Contractor | Results to be provided to Engineers Geotechnical Representative for review prior to commencing excavation on site.
MSE 200.3 | Mark out and approve | Set out and mark up of extent of earthworks | H | All earthworks areas | Visual Inspection | N/A | Contractor's site diary | Contractor | Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
MSE 200.4 | Excavation to formation level (prior to fill placement) | Confirm excavations are suitably trimmed and benched. | H | All earthworks areas | TNZ F/1:1997 | Formation materials in accordance with design assumptions. | Contactor's Site Diary | Contractor | Joint walkover with Contractor and Engineers Geotechincal Representative.
MSE 200.5 | Suitability of excavation formation for compaction | Confirm the excavated soils are adequate to support construction plant and allow compaction of engineered fill. | H | Test on a on a 10m grid / maximum lineal distance between tests is 10m | Scala Penetrometer (NZS 4402.6.5.2) for cohesionless soil and shear vane test for cohesive soil. | For approval by Engineer. Where forms Subgrade as per Pavement Design Drawings and ITP | Contractor's site diary | Contractor | Results to be provided to Engineers Geotechnical Representative for review prior to filling.
MSE 200.6 | Suitability of excavation formation for compaction | Confirm the excavated soils are adequate to support construction plant and allow compaction of engineered fill. | H | All earthworks areas | Proof roll or as agreed with Engineer | Formation soils do not heave and no significant visual deformation under wheel load | Contractor's site diary | Contractor | Where the excavation formation soils are not adequate a working platform (SIL Layer) or undercut of unsuitable soils may be required. As instructed by Design Engineer.
MSE 200.7 | Sediment Controls are in place for the particular section |  | M | Once per section | Asbuilts completed | NA | Asbuilts | Contractor | Forward asbuilts to Downers
Construction and Finshing (Granular Fill)
MSE 200.8 | Testing of placed material | Density of placed material | W | Unless otherwise in Specification or on Drawings, test every 300mm fill height on a 10m grid | Nuclear Density Meter (NZS 4402:4.2.2 Heavy Compaction) or alternative agreed with Engineer | Minimum field density of 90% of maximum dry density (MDD) obtained by static compaction for the first 500mm above thestripped and prepared ground surface. | IANZ Report & Contractors Report | Contractor | Test results to be provided to the Engineers Geotechnical Representative for review. Prelim tests in conjunction with IANZ Lab, compared to Contractors NDM Results, provided results are consistently within 1% of IANZ, acceptance for Contractor to Report NDM's thereafter on mutual agreement. On request by ER
MSE 200.8 |  | Density of placed material | W | Unless otherwise in Specification or on Drawings, test every 300mm fill height on a 10m grid | Nuclear Density Meter (NZS 4402:4.2.2 Heavy Compaction) or alternative agreed with Engineer | Minimum field density of 98% of maximum dry density (MDD) obtained by vibrating compaction from 500mm above thestripped and prepared ground surface. | IANZ Report | Contractor | Test results to be provided to the Engineers Geotechnical Representative for review. Prelim tests in conjunction with IANZ Lab, compared to Contractors NDM Results, provided results are consistently within 1% of IANZ, acceptance for Contractor to Report NDM's thereafter on mutual agreement. On request by ER
MSE 200.9 |  | Density of placed material | W | All Engineered Fill at 300mm lifts, 1 Test per 50m2/lift. | Scala Penetrometer (NZS 4402.6.5.2) for cohesionless soil. | Minimum CBR 10 as correlated against NDM's | Contractor's site diary | Contractor | Correlated against NDM's by "in field testing" Witnessed by Engineers Representative and signed off in daily diary
MSE 200.10. | Surface Finishing | Check geometry of the placed fill is in accordance with the design. | H | All earthworks area | Survey, TNZ F/1 1997 | Geometry is in accordance with design drawings (fill surface and batter slope profile, removal of any excess fill). All points within 30mm of a 3m straight edge with no points above design level. No ponding of water. | Suvey, Stringline dips @5 points across carriageway @ 20m spacings | Contractor | Joint walkover between Contractor and Engineers Representative.
Supply and laying of GEOGRID
MSE 200.11 | Confirm GEOGRID Material | GEOGRID supply | M | Designer Approval | Documentation | CMW Geosience Design approval | Certificate in contractor's site folder | Contractor | Source properties:
MSE 200.12 | Placing Geogrid Material | Orientation and Placing of material | M | Unless otherwise in Specification or on Drawings, each layer of grid | Visual Inspection | Gregrid to be placed flat or 1% fall to rear of wall. To be wrinkle free. | Photo & site record | Contractor | By visor by site Forman/Supervisor.
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.