## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | MSE Wall ITP | itp |  |  |  | Yes | MSE Wall ITP
section | Setout, Materials and Preparation
checkpoint | 200.1 - Earthworks methodology (prior to commencing site works)
label | Detail of Activity: Prepare earthworks construction methodology suitable for site (eg access, working areas, proximity to slopes, traffic and other site hazards, construction stages proposed)
label | Action: H
label | Minimum Test Frequency: NA
label | Inspection / Test method: NA
label | Acceptance Criteria: N/A
label | Record documents: Methodology
label | Responsibility: Contractor
label | Comments: Methodology to be provided to Engineer for review prior to commencing excavation on site.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 200.2 - Material suitability (prior to bringing fill to site)
label | Detail of Activity: Confirm imported fill material suitability
label | Action: H
label | Minimum Test Frequency: As per Drawings and Specification
label | Inspection / Test method: As per Drawings and Specification
label | Acceptance Criteria: As per Drawings and Specification
label | Record documents: IANZ Report
label | Responsibility: Contractor
label | Comments: Results to be provided to Engineers Geotechnical Representative for review prior to commencing excavation on site.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 200.3 - Mark out and approve
label | Detail of Activity: Set out and mark up of extent of earthworks
label | Action: H
label | Minimum Test Frequency: All earthworks areas
label | Inspection / Test method: Visual Inspection
label | Acceptance Criteria: N/A
label | Record documents: Contractor's site diary
label | Responsibility: Contractor
label | Comments: Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 200.4 - Excavation to formation level (prior to fill placement)
label | Detail of Activity: Confirm excavations are suitably trimmed and benched.
label | Action: H
label | Minimum Test Frequency: All earthworks areas
label | Inspection / Test method: TNZ F/1:1997
label | Acceptance Criteria: Formation materials in accordance with design assumptions.
label | Record documents: Contactor's Site Diary
label | Responsibility: Contractor
label | Comments: Joint walkover with Contractor and Engineers Geotechincal Representative.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 200.5 - Suitability of excavation formation for compaction
label | Detail of Activity: Confirm the excavated soils are adequate to support construction plant and allow compaction of engineered fill.
label | Action: H
label | Minimum Test Frequency: Test on a on a 10m grid / maximum lineal distance between tests is 10m
label | Inspection / Test method: Scala Penetrometer (NZS 4402.6.5.2) for cohesionless soil and shear vane test for cohesive soil.
label | Acceptance Criteria: For approval by Engineer. Where forms Subgrade as per Pavement Design Drawings and ITP
label | Record documents: Contractor's site diary
label | Responsibility: Contractor
label | Comments: Results to be provided to Engineers Geotechnical Representative for review prior to filling.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 200.6 - Suitability of excavation formation for compaction
label | Detail of Activity: Confirm the excavated soils are adequate to support construction plant and allow compaction of engineered fill.
label | Action: H
label | Minimum Test Frequency: All earthworks areas
label | Inspection / Test method: Proof roll or as agreed with Engineer
label | Acceptance Criteria: Formation soils do not heave and no significant visual deformation under wheel load
label | Record documents: Contractor's site diary
label | Responsibility: Contractor
label | Comments: Where the excavation formation soils are not adequate a working platform (SIL Layer) or undercut of unsuitable soils may be required. As instructed by Design Engineer.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 200.7 - Sediment Controls are in place for the particular section
label | Action: M
label | Minimum Test Frequency: Once per section
label | Inspection / Test method: Asbuilts completed
label | Acceptance Criteria: NA
label | Record documents: Asbuilts
label | Responsibility: Contractor
label | Comments: Forward asbuilts to Downers
section | Construction and Finshing (Granular Fill)
checkpoint | 200.8 - Testing of placed material (1)
label | Detail of Activity: Density of placed material
label | Action: W
label | Minimum Test Frequency: Unless otherwise in Specification or on Drawings, test every 300mm fill height on a 10m grid
label | Inspection / Test method: Nuclear Density Meter (NZS 4402:4.2.2 Heavy Compaction) or alternative agreed with Engineer
label | Acceptance Criteria: Minimum field density of 90% of maximum dry density (MDD) obtained by static compaction for the first 500mm above thestripped and prepared ground surface.
label | Record documents: IANZ Report & Contractors Report
label | Responsibility: Contractor
label | Comments: Test results to be provided to the Engineers Geotechnical Representative for review. Prelim tests in conjunction with IANZ Lab, compared to Contractors NDM Results, provided results are consistently within 1% of IANZ, acceptance for Contractor to Report NDM's thereafter on mutual agreement. On request by ER
checkpoint | 200.8 - Testing of placed material (2)
label | Detail of Activity: Density of placed material
label | Action: W
label | Minimum Test Frequency: Unless otherwise in Specification or on Drawings, test every 300mm fill height on a 10m grid
label | Inspection / Test method: Nuclear Density Meter (NZS 4402:4.2.2 Heavy Compaction) or alternative agreed with Engineer
label | Acceptance Criteria: Minimum field density of 98% of maximum dry density (MDD) obtained by vibrating compaction from 500mm above thestripped and prepared ground surface.
label | Record documents: IANZ Report
label | Responsibility: Contractor
label | Comments: Test results to be provided to the Engineers Geotechnical Representative for review. Prelim tests in conjunction with IANZ Lab, compared to Contractors NDM Results, provided results are consistently within 1% of IANZ, acceptance for Contractor to Report NDM's thereafter on mutual agreement. On request by ER
checkpoint | 200.9 - Testing of placed material
label | Detail of Activity: Density of placed material
label | Action: W
label | Minimum Test Frequency: All Engineered Fill at 300mm lifts, 1 Test per 50m2/lift.
label | Inspection / Test method: Scala Penetrometer (NZS 4402.6.5.2) for cohesionless soil.
label | Acceptance Criteria: Minimum CBR 10 as correlated against NDM's
label | Record documents: Contractor's site diary
label | Responsibility: Contractor
label | Comments: Correlated against NDM's by "in field testing" Witnessed by Engineers Representative and signed off in daily diary
checkpoint | 200.10 - Surface Finishing
label | Detail of Activity: Check geometry of the placed fill is in accordance with the design.
label | Action: H
label | Minimum Test Frequency: All earthworks area
label | Inspection / Test method: Survey, TNZ F/1 1997
label | Acceptance Criteria: Geometry is in accordance with design drawings (fill surface and batter slope profile, removal of any excess fill). All points within 30mm of a 3m straight edge with no points above design level. No ponding of water.
label | Record documents: Suvey, Stringline dips @5 points across carriageway @ 20m spacings
label | Responsibility: Contractor
label | Comments: Joint walkover between Contractor and Engineers Representative.
holdpoint | AUTHORITY HOLDPOINT
section | Supply and laying of GEOGRID
checkpoint | 200.11 - Confirm GEOGRID Material
label | Detail of Activity: GEOGRID supply
label | Action: M
label | Minimum Test Frequency: Designer Approval
label | Inspection / Test method: Documentation
label | Acceptance Criteria: CMW Geosience Design approval
label | Record documents: Certificate in contractor's site folder
label | Responsibility: Contractor
label | Comments: Source properties:
checkpoint | 200.12 - Placing Geogrid Material
label | Detail of Activity: Orientation and Placing of material
label | Action: M
label | Minimum Test Frequency: Unless otherwise in Specification or on Drawings, each layer of grid
label | Inspection / Test method: Visual Inspection
label | Acceptance Criteria: Gregrid to be placed flat or 1% fall to rear of wall. To be wrinkle free.
label | Record documents: Photo & site record
label | Responsibility: Contractor
label | Comments: By visor by site Forman/Supervisor.
checkpoint | Final Sign Off
label | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | BBO Engineers Rep Name:
holdpoint | Add Sign Off