## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 034733ab-ef33-4031-9e3f-a3d104ea4ae0 |  | checklist | MSSB Checklist |  |  |  |  | Yes | MSSB Checklist | 030d15f1-ae6d-46df-bfad-62fae48c66a5
checkpoint-status | fdda469f-53dc-48b1-9b28-d769133a4b6b |  | checkpoint | MSSB mounted in position
checkpoint-status | 43e7890e-ee2f-4dd2-9864-c61cb66dfc35 |  | checkpoint | MSSB Fitted off
checkpoint-status | 7570f40c-3982-4985-b0f9-d5aeaf290dca |  | checkpoint | Main power connected to MSSB
checklist-flat | 57b083f4-5725-48d5-96e4-80a16c51da93 |  | checklist | AC Outdoor unit (Stand Alone) Fit Off |  |  |  |  | Yes | AC Outdoor unit (Stand Alone) Fit Off | 0fee66bb-0685-482e-b705-a9118cf7f6f9
checkpoint-status | 8f98a261-1e3a-4c1b-809a-d9d06a967270 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | d5e92525-e9c2-4057-8f07-c0717148663e |  | checkpoint | Condensate drains installed to tundish/waste point provided
checkpoint-status | 2fdd568e-1c3f-4bc1-b86a-9d07b80e1d91 |  | checkpoint | System pressure tested to 400PSI
checklist-flat | a08afa86-44cc-4923-8608-366acbe9e085 |  | checklist | Evap Commissioning |  |  |  |  | Yes | Evap Commissioning | 12923190-279c-4e2f-adf5-245c265e4810
checkpoint-status | 8cc2c3ea-ebfa-4d09-8626-d02f988653dc |  | checkpoint | Unit Operational, checked for vibration and noise
checklist-flat | 10841c81-50a5-4838-ae84-f752177449d8 |  | checklist | ERV Fit Off |  |  |  |  | Yes | ERV Fit Off | 14aa35d0-4b37-4d80-98be-f11703110d20
checkpoint-status | 815da8a6-783d-4416-b9c8-7c92a946a4b1 |  | checkpoint | Grilles/louvres installed
checkpoint-status | 5c971705-8d91-424b-ace6-8a511170c3d5 |  | checkpoint | Filters installed and are removable
checkpoint-status | 3b17b044-31e3-435b-b17c-c43069ba4b59 |  | checkpoint | Check drain fitted of at tundish with air break
checklist-flat | 74e8731c-0e46-415e-8438-f31d5ad789d3 |  | checklist | Defect |  |  |  |  | Yes | Defect | 153aa49a-6df5-4a15-9f4d-ab7ab12f003c
checkpoint-status | cf1a5178-b4d5-4dd5-b063-cf5256547014 |  | checkpoint | Defect rectified
checklist-flat | 07b9839b-b749-44f7-a23a-a5f20ed3f413 |  | checklist | Demo & Decommission |  |  |  |  | Yes | Demo & Decommission | 16510bdd-10c2-4e2f-b387-9bbd6f7e620f
checkpoint-status | 4c6697e5-ed6f-42d5-9866-4256c00b34a1 |  | checkpoint | Electrical isolated and made safe
checkpoint-status | c609bd3c-8c07-41f8-86de-a07b36aac814 |  | checkpoint | All Rubbish Removed Area Clean And Tidy
checklist-flat | a67ed9a6-a510-470c-adc8-3e6cb23bd636 |  | checklist | Radiators (HHW) Fit Off |  |  |  |  | Yes | Radiators (HHW) Fit Off | 16fddc7f-5a1c-46b0-a2d8-d4ca4a20d021
checkpoint-status | 7e7d6ab1-aaf1-4014-8b4c-cd44534585e7 |  | checkpoint | Radiator Installed c/w pipework covers
checkpoint-status | cd211ebb-3f19-4b53-97e5-c46751929e3b |  | checkpoint | Checked for leaks
checkpoint-status | 84425abc-00e1-4e43-b2d5-9197c274d7cf |  | checkpoint | Low temperature cover installed (As Applicable)
checklist-flat | 5cc95f74-a5e8-4e62-b35f-7bf9c417a92f |  | checklist | CHW FCU Rough In |  |  |  |  | Yes | CHW FCU Rough In | 186d30ad-4f5f-476f-a263-efe2d23dfee4
checkpoint-status | 50d03e39-1eca-43a5-a1c1-3941cd8aa03b |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | b75e5d11-7a1c-4e3f-8d98-fce74bb1cf7e |  | checkpoint | vibration mounts installed
checkpoint-status | a944af24-b9bd-4913-8189-3f39d2908985 |  | checkpoint | CHW pipework roughed in and connected to unit
checkpoint-status | 9fa16ff2-ae37-4f46-a6ed-f6531e1af382 |  | checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
checkpoint-status | 6dfaa509-3449-419f-97fc-727312d8c2aa |  | checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint-status | 35085f57-ad60-4bc8-bed2-a2948a0e315e |  | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checkpoint-status | b66b893f-6113-4758-b403-9b04660e80c1 |  | checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
checklist-flat | 3ad1c1b4-4a4a-403d-ab32-ab6c2e2537ee |  | checklist | AHU Rough In |  |  |  |  | Yes | AHU Rough In | 205f79fb-1bb7-46b9-96d7-7e1c9b5c1f44
checkpoint-status | d4d49fb5-b79c-412e-b0eb-79b01ef0244f |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 9355f474-be54-408e-b93e-c83db6130ef2 |  | checkpoint | Vibration mounts installed
checkpoint-status | aa10c39b-b4ab-4fd3-9436-172d18aa7b9f |  | checkpoint | Pipework roughed in
checkpoint-status | 4ed93ae2-9669-468c-a84b-f1759ca78c4a |  | checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
checkpoint-status | cb1f8279-dad5-4d14-b221-9538829c3c2e |  | checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint-status | 0f8523ce-51ae-4a97-b47e-5f68b8be5eca |  | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checkpoint-status | 5cc67e38-c135-4613-919b-0ddfcad7982e |  | checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
checklist-flat | 49f925ae-d47e-4add-8692-2c5aa4152c24 |  | checklist | Fans Rough In |  |  |  |  | Yes | Fans Rough In | 2488a520-0777-43b2-b32b-7883d6c76bef
checkpoint-status | 3c670083-f4fd-476f-bfd9-4f65b113f47a |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | c1034c61-f9ee-4707-aecc-27ffafaf9370 |  | checkpoint | Vibration mounts installed
checkpoint-status | 03824a5b-1b73-4890-80b0-9a0605745536 |  | checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint-status | 9bef7bc3-baac-44ca-bacb-281173ee1518 |  | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checkpoint-status | 7b7c4e1c-fce9-43c6-8343-4307cff8a9f5 |  | checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
checklist-flat | e76c0405-349f-46f9-ad71-24f241cb91af |  | checklist | Fans Fit Off |  |  |  |  | Yes | Fans Fit Off | 25271de2-6830-4dee-9560-49057116db8a
checkpoint-status | 14f86820-303b-44ec-bfa9-80f599bfb2f7 |  | checkpoint | Filters installed and are removable
checkpoint-status | 7f8dd19e-0fb0-41e7-b4a9-668aa96160de |  | checkpoint | Grilles/louvres installed
checklist-flat | 3bf38588-a95e-4b6f-a98d-1ae5601ade84 |  | checklist | Drafting & Design Issues |  |  |  |  | Yes | 3. Drafting & Design Issues | 373230cb-83fe-415b-9922-cc5cc7947e0f
checkpoint-status | 84b84eda-c655-4e56-be60-9ae6f11ef2a0 |  | checkpoint | Attach photos, files and comments as required - pass once complete
checklist-flat | 822195a1-6521-4a88-95d6-ff73f049b9ea |  | checklist | Working Permits |  |  |  |  | Yes | Working Permits | 3c44c493-e99d-4b0b-80ae-e36915741ed9
checkpoint-status | c4b7721b-5fd5-472d-ac3f-26d725427cff |  | checkpoint | Please take a photo of work permit
text | 2a8e4ea0-cbe1-5016-ab61-3e82581e4972 |  | textbox | Description of Permit
text | 462cf60e-d48c-5187-86b5-9fa500afdf88 |  | textbox | Work Area
checklist-flat | 0d13e5ca-12f7-42bb-aedf-0420ed3534fa |  | checklist | ERV Commissioning |  |  |  |  | Yes | ERV Commissioning | 414d27c3-f2bc-4bda-a5c0-fb02e1dcc842
checkpoint-status | 2bfaedb1-1414-4287-a027-799ef6dbc3cb |  | checkpoint | Unit Operational, checked for vibration and noise
checklist-flat | f290939a-e2e3-4287-8fba-84052b0fb7c9 |  | checklist | Package Unit |  |  |  |  | Yes | Package Unit | 46aa9ecc-7742-4666-88f2-cd5f9587f6bd
checkpoint-status | 7f7e7792-ed6e-4c70-9046-a78235ac2e03 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 03fc97a6-fa69-45e7-934a-a0a614cd7631 |  | checkpoint | Vibration mounts installed
checkpoint-status | 4d4ecf69-1c76-4ae6-a8bb-1204ffb6e027 |  | checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint-status | 74d876be-02cf-4357-acd9-518d7362dfd6 |  | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checkpoint-status | a48b844a-e589-4292-9574-e1664a5812d0 |  | checkpoint | Overflashings installed
checkpoint-status | f5afb926-0cb4-4f6b-9fbf-50cdf0ce44a5 |  | checkpoint | Drains installed to waste point
checkpoint-status | d8f72c6c-fade-4ca8-8a38-ec11de8c830d |  | checkpoint | Operation tested
checklist-flat | 3ab68c76-b81b-4348-a2bf-6bfd9a31105d |  | checklist | Cassette Fit Off |  |  |  |  | Yes | Cassette Fit Off | 46ece6bc-1243-4c07-9f8b-1c20d469feec
checkpoint-status | 7c048cdb-6faa-4f72-9be8-c9f3c6dde6ef |  | checkpoint | Fascia fitted square and plugged loom connected
checklist-flat | 035c8fce-bc01-4100-9334-cb34da41019c |  | checklist | Pumps |  |  |  |  | Yes | Pumps | 475e4e84-bd49-4822-b4f7-a26589b6328b
checkpoint-status | 53a4792c-4fd4-4078-a2c1-30e07ed983b8 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 5b23e368-3aea-4f7c-8fb7-03e4221fa329 |  | checkpoint | Vibration mounts installed
checkpoint-status | c4d1e601-099b-4e03-9e0b-a6ef3492b1a2 |  | checkpoint | Pipework connected and no leaks
checkpoint-status | e6f7ac41-a028-4c31-bde6-e8b722f4d62a |  | checkpoint | Operation tested
checklist-flat | 87787526-66b3-4aad-8e19-f3d2336c85e7 |  | checklist | ERV Rough In |  |  |  |  | Yes | ERV Rough In | 49621d80-afd2-4d32-b3bd-52b3bace127c
checkpoint-status | 1e282085-1a3c-43fa-a538-d793d6626588 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 40775078-059a-4f00-8bf9-acf65a89021a |  | checkpoint | Vibration mounts installed
checkpoint-status | 160f4ab9-f2c4-429d-bca9-f5b5f7d6f732 |  | checkpoint | Pipework roughed in
checkpoint-status | f46e0ea5-3e55-4d67-a65a-804cce8f9bce |  | checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
checkpoint-status | 1ef8558c-08b5-4367-aaad-86ae3a31099a |  | checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint-status | add8625a-8e9b-4bb9-b508-c4ebbf0f12cc |  | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checkpoint-status | 9fdadcc3-45e7-4d36-a622-409bdc22b0df |  | checkpoint | Cowls installed
checkpoint-status | bc2c4e69-3228-41d4-aaab-c8b9dc411d84 |  | checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
checklist-flat | 823f32ba-694a-483e-8b78-e8feaad068db |  | checklist | Evap Cooler Fit Off |  |  |  |  | Yes | Evap Cooler Fit Off | 4afdd047-2b74-4260-85fd-a37eb308e49b
checkpoint-status | 5b89e699-4fdd-4f30-88b5-5a2c5be82f6c |  | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checkpoint-status | 83ed0af8-fdd9-4127-b6a3-73ab1210a180 |  | checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
checklist-flat | 3dbb37e9-cceb-4f7c-bc11-84e855bfc63b |  | checklist | AC Ducted Unit Fit Off |  |  |  |  | Yes | AC Ducted Unit Fit Off | 516693be-0fb9-4996-a814-ab529ec408bc
checkpoint-status | 872f3b7d-94c3-4fdc-b02e-af6c255b74fb |  | checkpoint | Grilles/louvres installed
checkpoint-status | ef675a52-de42-4f74-bc92-7b1d85d19fb7 |  | checkpoint | Filters installed and are removable
checkpoint-status | 555d2991-2899-4be9-8364-6d8f7ea0f61d |  | checkpoint | Condensate drains installed and terminated to correct location and tested
checklist-flat | 52e48eb6-ae98-4700-b75e-447ae6def884 |  | checklist | AC Branch Box Rough In |  |  |  |  | Yes | AC Branch Box Rough In | 5538d3ee-fa06-4262-a6ea-be0ce3f8a410
checkpoint-status | 2a56285b-94aa-4716-a517-ffa4a7dfbe62 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 4bad18f8-a72b-4e68-a352-fdf06315da45 |  | checkpoint | Model Number correct & Labelled
checkpoint-status | 6277e309-d378-4518-bf92-ac98f33cba41 |  | checkpoint | Vibration mounts installed
checklist-flat | 815d5d97-3b43-4b7f-a487-b08bf22c4d87 |  | checklist | Cassette Pipework & Drains |  |  |  |  | Yes | Cassette Pipework & Drains | 5db70aa4-103d-4e54-b77e-729ef34b006c
checkpoint-status | a692dbba-ee7e-4b66-bbfb-138d8eade170 |  | checkpoint | Condensate drain installed including hose clamps
checkpoint-status | 38b08c19-90f6-451c-b486-607ccf9914a9 |  | checkpoint | Refrigeration pipework installed including insulation over flare nuts
checklist-flat | 869bd84d-8c0a-494f-877b-d29babab10d1 |  | checklist | AHU Commissioning |  |  |  |  | Yes | AHU Commissioning | 5e8bf32c-9dbe-4eb2-8972-1b8097f0c982
checkpoint-status | 01a04037-2bff-4ed3-9921-c1d397ca690f |  | checkpoint | Unit Operational, checked for vibration and noise
checklist-flat | d645931d-05cb-4e36-a006-56809ba39ad6 |  | checklist | Day Rate Works |  |  |  |  | Yes | 2. Day Rate Works | 5ecedb5e-2ed2-45a1-8661-f35b07aec314
checkpoint-status | 228602cc-90ed-46ad-85db-70742435b6f6 |  | checkpoint | Attach photos, files and comments as required - pass once complete
checklist-flat | bef8551e-5e3e-4544-bf13-ec19dc630c35 |  | checklist | Installation Overview |  |  |  |  | Yes | Installation Overview | 63a9708c-5d12-45eb-a979-a3fd7df958ed
checkpoint-status | 23dd710a-a8a6-46c9-a0a5-6fa94ef2ab4f |  | checkpoint | Installation progress - Weekly Photo's of highlighted plans required
checklist-flat | 5df31f1d-8236-4c0b-a35d-7a3ca6ea6d71 |  | checklist | Project Details |  |  |  |  | Yes | Project Details | 65db39e8-93d9-442e-af9c-ffecb731a5a2
checkpoint-no-status | c050a4c4-0290-4836-882c-02ab741b46b5 |  | checkpoint | Project Details:
text | 0942e37c-46a5-5f75-97ef-46ad200f48bc |  | textbox | Project Number:
text | abfedd4a-43be-58eb-be1d-13abad4c6cd9 |  | textbox | Builder:
text | 8872de2a-caa9-5624-955e-b4ffaed92814 |  | textbox | Project Manager:
checklist-flat | b3e8b1a1-a2a7-4a88-a43a-c9428e887f86 |  | checklist | New Checklist: |  |  |  |  | Yes | 0. Add New Checklist | 6e3eb524-192e-475e-a7dd-864644779ed8
checkpoint-status | d78a024d-f1d9-4e2b-91ff-26b86b435d73 |  | checkpoint | Attach photos, files and comments as required - pass once complete
checklist-flat | e6e6d3fe-b147-4d50-9d77-7793d656394c |  | checklist | Rangehood Rough In |  |  |  |  | Yes | Rangehood Rough In | 75881159-e889-4e15-aeac-1dd245a88c47
checkpoint-status | a005bd49-49b7-46fe-89aa-c359d2435615 |  | checkpoint | All weatherproof louvre installed as per drawings, including sealed & cleaned
checkpoint-status | 4dd5f0c5-d271-439e-b319-c3938d104268 |  | checkpoint | All solid ductwork installed as per drawings, including flexible / Spiral Duct connections
checkpoint-status | 8c216233-3ca7-479c-9148-d2fb7b9c3a8a |  | checkpoint | All flexible ductwork installed
checklist-flat | fa840b39-a6ca-43d9-b2d8-2fa1066635c0 |  | checklist | Auto Refill Units |  |  |  |  | Yes | Auto Refill Units | 775be619-a767-4d1a-abcc-b48c5fc60fb3
checkpoint-status | 473bedff-9487-40d0-901d-0ab0c0c13955 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | b3701c04-26b6-42db-9ae8-0be722c466e8 |  | checkpoint | Pipework connected and no leaks
checklist-flat | 9422038a-a55e-4845-8d03-b6d8d4904b47 |  | checklist | AC Outdoor unit (VRF) Fit Off |  |  |  |  | Yes | AC Outdoor unit (VRF) Fit Off | 7981a346-e463-4b56-8a34-2ffb36689259
checkpoint-status | 8958a197-5a64-410f-ab1a-4947e657df11 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 3747ead3-0b96-4094-bbcd-296ac5874c8d |  | checkpoint | Vibration mounts installed
checkpoint-status | 26ff4d47-bebf-470a-9968-c77bb4ea863a |  | checkpoint | Condensate drains installed to tundish/waste point provided
checkpoint-status | 1f9dbccf-e883-4603-8115-f42381ebb850 |  | checkpoint | System pressure tested to 400PSI
checklist-flat | 5edc75b6-3c8f-4470-b01c-581b2bc564fc |  | checklist | AC Outdoor unit (VRV) Commissioning |  |  |  |  | Yes | AC Outdoor unit (VRV) Commissioning | 7e095644-c941-4636-accd-ad82d8cc49ab
checkpoint-status | 1b5f9103-940b-40e1-8aa4-ed74bddd510a |  | checkpoint | System evacuated and valves opened - Photo of vac stat required
checkpoint-status | 344de243-1bed-4327-914a-f7e1d05ca4f5 |  | checkpoint | Operation checked
checklist-flat | 6062ebda-33ce-4e87-b020-e2dbf3aba4cd |  | checklist | Toolbox Meetings |  |  |  |  | Yes | Toolbox Meetings | 80bcdd52-916e-4522-82bf-f0ec1bf9cd5b
checkpoint-status | f232dc52-f17a-4a6e-8f5d-6a0eee874bf5 |  | checkpoint | Toolbox/Pre start Talks
text | 74bc5935-ffbe-50d4-9a54-28006b34fbfc |  | textbox | Workplace:
text | 79a69737-f89f-5139-941a-ecbc87be2405 |  | textbox | Subject of Talk:
text | f7a35581-a749-543a-ae4b-d916a9ccd968 |  | textbox | Presented By:
text | e8b23741-0d6a-5e11-9b12-7d0965f87a3e |  | textbox | Duration:
label | 6ff8007f-80e2-5701-89e4-0a28f4d611ea |  | note | Persons Present
text | 99c51870-18f8-5525-a59b-64c0c497ea34 |  | textbox | Name:
text | 0eceabce-12d9-5845-ad8a-d3930a09f8cc |  | textbox | Name:
text | 5343772f-2894-55a1-b77b-cd1ebaf25fd3 |  | textbox | Name:
label | a92fa7b6-846a-55e6-9d06-f6a0080f7c9e |  | note | Points Raised/Comments:
label | 700d7082-47de-5d14-bb3d-b43e6c769969 |  | note | Corrective Action
text | 14b6bd4e-163d-5b05-8eb0-fd40edd309f2 |  | textbox | Action:
text | 02426721-1751-5e34-9b49-3d0a5770685e |  | textbox | Action By:
checkpoint-status | 1058edee-4705-4e41-b063-af5b5b428f2c |  | checkpoint | Action Completed Sign Off:
label | b17b0d54-5a6e-58db-95d7-909349f54a36 |  | note | Corrective Action
text | 31d16baa-a6a8-55bc-9a32-afbbb70fc1e8 |  | textbox | Action:
text | b38e1240-8ebb-5eef-9699-f02cf420f693 |  | textbox | Action By:
checkpoint-status | 2d3d8845-aecb-4ba0-8345-f03e1d748c08 |  | checkpoint | Action Completed Sign Off:
label | 539155a6-70ca-5066-8f80-ac2bae6fe3d8 |  | note | Corrective Action
text | bd569ca6-72a9-5cb2-8f28-200e24b30429 |  | textbox | Action:
text | 3bc1946c-8c0f-5dd0-8aa5-63171d4864f2 |  | textbox | Action By:
checkpoint-status | 1159ed7f-9af5-445a-a81c-3fd7e2b607ea |  | checkpoint | Action Completed Sign Off:
checklist-flat | ac389f47-ca27-4000-b9a3-a0b2b4351451 |  | checklist | AC Outdoor unit (Stand Alone) Commissioning |  |  |  |  | Yes | AC Outdoor unit (Stand Alone) Commissioning | 83ac3c26-f0aa-471d-93a9-bfec2062d158
checkpoint-status | 0950a556-9b3b-4ce6-aa79-53c533318758 |  | checkpoint | System evacuated and valves opened
checkpoint-status | 54a3be58-435a-4e1f-8cef-680c64fff6ff |  | checkpoint | Operation checked
checklist-flat | ba962811-16be-48d9-b1f8-9fe36956648c |  | checklist | AC High wall mounted Rough In |  |  |  |  | Yes | AC High wall mounted Rough In | 84746529-9d9b-4034-8e9c-6200822a5517
checkpoint-status | 0005aa13-e01e-4466-b631-4a0e3c04ad9f |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | eee58aac-3f84-47ed-90a3-2967cc3977fb |  | checkpoint | Refrigeration pipework roughed in to correct location
checkpoint-status | 314a62c0-1da5-4d05-9145-b7e1781fa20e |  | checkpoint | Condensate drains installed to tundish/waste point provided
checklist-flat | ca79d26e-d48d-4299-8391-4bc04f9023cd |  | checklist | As Built Markups |  |  |  |  | Yes | 4. As Built Markups | 87e435ef-e787-4423-8a0c-987a538614a7
checkpoint-no-status | d35017bd-bb81-4af3-ba52-90a06b4d4a28 |  | checkpoint | Drawings
checklist-flat | 9d1c53de-fb47-4c92-b396-74e7d5b90bcd |  | checklist | Chiller |  |  |  |  | Yes | Chiller | 8a3e7821-046d-48c2-ae55-32f2df47f97e
checkpoint-status | 37f2497d-9c5a-4d58-899e-cdd4d9eff0c8 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 918f9820-0717-43c7-bcc3-ff8ef12496a6 |  | checkpoint | Vibration mounts installed
checkpoint-status | 2b3bc09b-5ac0-44aa-a734-1b303c9d9a14 |  | checkpoint | Pipework connected and no leaks
checkpoint-status | af4ec6ce-e535-4a44-bab0-e32960fedef7 |  | checkpoint | Operation tested
checklist-flat | aa42ed5c-81d4-4c7f-b202-848722305d4b |  | checklist | Flexible Connection & Cushin Heads |  |  |  |  | Yes | Flexible Connection & Cushin Heads | 8cd88007-2e0b-4e44-b989-48c50d293c21
checkpoint-status | 58809c94-6bbc-4a4f-bd4a-babd5cdc5ed5 |  | checkpoint | All flexible connections & cushion heads are Installed s per drawings, including ductwork connections.
checklist-flat | f222ca00-89cf-4bb5-a337-673055b67e1f |  | checklist | Boiler |  |  |  |  | Yes | Boiler | 8eca0dc9-49d5-4757-9fcc-23ce17434b53
checkpoint-status | 8f749443-7735-4c9b-ae1c-07db4aa829b3 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 94252a86-8ed3-4ee0-9a6e-8f9e810b5dd4 |  | checkpoint | Pipework connected and no leaks
checkpoint-status | b36a42c9-38e3-4e5d-a33f-168ace52f5c4 |  | checkpoint | Gas connected and leak tested
checkpoint-status | 90ffe017-da16-4ed2-b32b-44b443a51404 |  | checkpoint | Flue installed
checkpoint-status | 150585a4-ba71-4c27-8e16-7232ed87b370 |  | checkpoint | Operation tested
checklist-flat | cc8c2794-8ed1-48b0-8cda-bf623c2a9228 |  | checklist | Builders Works & Site Issues |  |  |  |  | Yes | 1. Builders Works & Site Issues | 90c3b8b9-dbde-41ce-843f-4b81078a98e2
checkpoint-status | 07fd980e-ab72-46d7-914d-58247d9564f2 |  | checkpoint | Attach photos, files and comments as required - pass once complete
checklist-flat | 625f8747-3934-42ee-b258-9397c69c8cf7 |  | checklist | AC Outdoor unit (VRF) Commissioning |  |  |  |  | Yes | AC Outdoor unit (VRF) Commissioning | 930c9373-1d0c-4556-91cb-710cc8ea2702
checkpoint-status | 6d06e06b-3712-48ba-b878-75a9dbaea6be |  | checkpoint | System evacuated and valves opened - Photo of vac stat required
checkpoint-status | 4004141a-a486-4c36-95ae-015661111389 |  | checkpoint | Operation checked
checklist-flat | 503d72c6-a60b-41d0-9024-a181e43674c4 |  | checklist | VAV |  |  |  |  | Yes | VAV | 964bac3c-667d-4ab9-a0a7-a16ad8ebab23
checkpoint-status | 70965d72-9650-42ae-ac17-0207526cf42e |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | ac8c32fd-9039-4ab7-8976-350c7bd4c7be |  | checkpoint | VAV installed, Model Number correct & unit Labelled
checklist-flat | d91902bc-dd69-4151-9ab9-36e51ebf2e4a |  | checklist | Fire Damper & Pipework Penetration Checklist |  |  |  |  | Yes | Fire Damper & Pipework Penetration Checklist | 99ae8ac9-31ad-4af0-b378-440f818d751d
checkpoint-status | 26acd9de-1bd3-410a-9c48-21bf03dfee55 |  | checkpoint | Fire treatment was installed correctly as per the Drawing, sealed and labelled with Photo on both sides.
checklist-flat | 64c46bc3-33cf-4c38-9bf2-66f3051b61c3 |  | checklist | Ductwork Fit Off |  |  |  |  | Yes | Ductwork Fit Off | 9a12fc7f-93ab-4b00-b710-00c49e107d1c
checkpoint-status | 53a27209-7ad7-45d3-9934-2cf67718963e |  | checkpoint | Ductwork in correct location & Clean
checkpoint-status | 10fbca89-1cbf-40d7-b1b2-9af91b1796ef |  | checkpoint | Grilles/louvres installed as per drawing
checklist-flat | e0b2e316-57f7-4548-b3db-df8465ebe362 |  | checklist | Refrigeration Pipe |  |  |  |  | Yes | Refrigeration Pipe | a2fb57d9-2499-41ff-8337-c3ac1c99c8ab
checkpoint-status | 293259e2-68d9-48f9-b0ea-72d043921060 |  | checkpoint | Pipework installed as per Schematic and Shop Drawings
checkpoint-status | 164ff5ec-2a8a-41dc-8243-e24045c60e66 |  | checkpoint | Actual Pipe Meters Recorded on schematic
checkpoint-status | bbd97c5f-3584-484f-8a23-8cbda0bcea33 |  | checkpoint | Pipework Pressure Tested @400 psi
checklist-flat | 2e0007d8-fd17-4e82-8ddb-86c8257dd8d3 |  | checklist | CHW & HHW Pipework |  |  |  |  | Yes | CHW & HHW Pipework | a4b64ebf-f396-4295-b6bc-6a15185a11c5
checkpoint-status | 96c438ae-a990-46c0-bca0-b0a96fedf114 |  | checkpoint | Pipework installed as per Shop Drawings & Schematic
checkpoint-status | 1c94e20d-6969-488c-bdaf-33d996491a7d |  | checkpoint | Pipework Pressure Tested
checkpoint-status | 0b85b9ab-bf5a-418d-b278-1d2d89679417 |  | checkpoint | Pipework checked for leaks & Labelled correctly
checkpoint-status | 7330fc3f-1e7a-4785-8b0d-6643304f621f |  | checkpoint | Pipework lagging and cladding complete
checklist-flat | 78779263-b254-4c8b-9961-147d42d0615d |  | checklist | AC Ducted Unit Commissioning |  |  |  |  | Yes | AC Ducted Unit Commissioning | a8f06a11-81ab-4d37-b6b4-eb2953301d70
checkpoint-status | 5ccbbe22-35f9-45b2-b41e-88a887bebd1c |  | checkpoint | Check Operation of unit
checkpoint-status | 0ed29502-cd57-486c-a37d-bce69060bf7e |  | checkpoint | Check for noise and vibration
checklist-flat | a637a2f9-d3b7-4c0f-9ea1-01c7cc5632ba |  | checklist | Fan Commissioning |  |  |  |  | Yes | Fan Commissioning | ae4b627a-e5cd-41a0-a7c6-9c2b3a102f7c
checkpoint-status | 06409bdb-c10d-4b0f-aced-4fc2d8ab5088 |  | checkpoint | Check for noise and vibration
checklist-flat | acca4552-240b-4d6f-92ef-0a11fbf28619 |  | checklist | SWMS |  |  |  |  | Yes | SWMS | b37a57d1-913e-47f6-90e3-181637c4c1ce
checkpoint-status | 94b22329-c5d6-4808-a9ce-fb20ca5a1106 |  | checkpoint | SWMS & Safety Plan submitted
checklist-flat | 86f9b232-248f-44e0-a310-6e752c239d62 |  | checklist | Delivery Docket |  |  |  |  | Yes | Delivery Docket | b7fcf3f3-58f3-4193-a8d3-dd95c2d695ac
checkpoint-status | 97d803ed-e1c8-48ed-8e7b-ca91cf1b47d8 |  | checkpoint | Please take photo of delivery docket
text | f5e7c8b7-ba8b-51fa-8121-16b96fc015eb |  | textbox | Date
text | 0f6ca699-e0d2-5d9e-95a6-08a17440b0de |  | textbox | Work Area
text | c22f862a-a92d-5436-8ac6-f335089309ba |  | textbox | Material
text | 397f7e0a-235a-516c-9279-84146406fa93 |  | textbox | Supplier/Subcontractor
checklist-flat | c6e4d51d-bb0b-4550-8b37-5746af3cd7e1 |  | checklist | Demo |  |  |  |  | Yes | Demo | b8efa7ab-d816-4982-95bd-2a1881690983
checkpoint-status | 2320841a-3033-4d1a-86de-2146f3397aff |  | checkpoint | All flexible connections & cushion heads Demo as per drawing.
checkpoint-status | 2bc1fe51-576c-4a4e-922a-82dc3a5e4885 |  | checkpoint | All Rubbish Removed Area Clean And Tidy
checklist-flat | 62078cae-77f8-4351-9e8a-77a51947d522 |  | checklist | Expansion Tank |  |  |  |  | Yes | Expansion Tank | baedfcc5-b919-479b-a41f-9f09e5d7c574
checkpoint-status | 4ddf8d69-0d1f-4c1d-a361-765941602f22 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 9b6a8933-99a9-4d55-97a9-47b7ce68e46b |  | checkpoint | Vibration mounts installed
checkpoint-status | 77fe6fe0-c265-492d-929a-a2a43ce3031c |  | checkpoint | Pipework connected and no leaks
checklist-flat | 1a722e14-0fa1-475a-9a6e-0eb173069f81 |  | checklist | Cassette Rough In |  |  |  |  | Yes | Cassette Rough In | bbcdc7b4-3f8c-4549-a38a-00c447f9879e
checkpoint-status | c0cfa030-fbc8-407c-b5da-f9b2268a7455 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 50057ef9-2d09-411f-a9ad-a813ef366605 |  | checkpoint | vibration mounts installed
checkpoint-status | 92eae2f8-ff51-4cad-b813-5eed85bb1298 |  | checkpoint | Condensate drain installed including hose clamps
checkpoint-status | 6f32af9e-acbb-4598-b0fe-beefb36a40fd |  | checkpoint | Refrigeration pipework installed including insulation over flare nuts
checklist-flat | 282bab21-a254-4586-be7e-af44ca4fb178 |  | checklist | Evap Cooler Rough In |  |  |  |  | Yes | Evap Cooler Rough In | d103d67a-6df9-4a0c-839c-18ffc546706c
checkpoint-status | 65ba5261-69db-43af-91c8-002a44043f14 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | e0ed6db3-3781-48a0-b255-7f27465f21ce |  | checkpoint | Vibration mounts installed
checkpoint-status | 81f04ed4-039d-4286-85fc-1beaceb1e50c |  | checkpoint | Water connection complete
checkpoint-status | cbe74106-8bf5-412c-90d4-1a37dffdc28b |  | checkpoint | Drain to point of discharge installed
checkpoint-status | 6d5c5b9d-dd81-4f7e-bc68-916600c50203 |  | checkpoint | All solid ductwork installed as per drawings, including flexible connections
checklist-flat | 8e970044-63b8-4d28-a930-d8019d61afc6 |  | checklist | Ductwork Rough In |  |  |  |  | Yes | Ductwork Rough In | d40f18e5-ac4e-4f8d-bf24-7793875f9bcd
checkpoint-status | 2a9beed6-3a2e-44b8-bc0e-675e6d090e77 |  | checkpoint | All weatherproof louvre installed as per drawings, including sealed & cleaned
checkpoint-status | 87d4c1eb-ab66-4bda-8c78-2fd3b6a47793 |  | checkpoint | All solid ductwork installed as per drawings, including flexible / Spiral Duct connections
checkpoint-status | 888e2e46-d8ff-4665-bc21-cabd4d8f79b8 |  | checkpoint | All flexible ductwork installed
checkpoint-status | 44abf9ef-69bc-4a0f-8ad4-0e298195d11e |  | checkpoint | All cushion heads installed and setout noted
checklist-flat | e8f9044c-848d-4a33-8998-4932492edaff |  | checklist | AC High wall mounted Fit Off |  |  |  |  | Yes | AC High wall mounted Fit Off | d9a33d62-6da6-4c60-9a55-8f30eae07ef8
checkpoint-status | 2b83028d-b9c9-4307-9f04-53a9b130106e |  | checkpoint | The wall mount was fitted off and checked for level
checkpoint-status | 4782654b-bfbf-4310-a48e-c3a52ea5f1b7 |  | checkpoint | Condensate drains terminated at tundish and tested
checklist-flat | 524f652d-86b0-464c-8603-48c6392e4647 |  | checklist | Cassette Commissioning |  |  |  |  | Yes | Cassette Commissioning | e33020ff-1845-4775-a049-a8f417acb09d
checkpoint-status | a9ae52e8-0a5c-4b5e-9274-ff93d49f550f |  | checkpoint | check drain fitted of at tundish with air break
checkpoint-status | 39138717-4be7-4f47-af0e-228bc148354d |  | checkpoint | Check Operation of unit heat/cool & louvre operation
checklist-flat | 6b893e87-0739-4b80-8b9a-e3cf17e5de54 |  | checklist | CHW FCU Fit Off |  |  |  |  | Yes | CHW FCU Fit Off | e538b487-2ef8-4981-ad1c-4a2e6040d71d
checkpoint-status | d9313d29-24dd-44e1-b1b9-845eb55b49eb |  | checkpoint | Grilles/louvres installed
checkpoint-status | 9df514f1-abd1-4905-81a4-2f5733eae117 |  | checkpoint | Filters installed and are removable
checkpoint-status | 77c96f63-35a9-4327-b9a9-fda331b1aa16 |  | checkpoint | Check drain fitted off at tundish with air break
checklist-flat | 10a7f5c5-78c1-447f-a3d4-849d122ef22d |  | checklist | Branch Box Pipe & Drains |  |  |  |  | Yes | Branch Box Pipe & Drains | e5accd87-28c4-4f75-b488-71bbcd783c51
checkpoint-status | 4f400f81-4efb-4160-b01d-42aad112ac57 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 8896a47c-19f0-48d9-a633-1705041c0d95 |  | checkpoint | Refrigeration pipework roughed in
checkpoint-status | 66e26e9a-a129-467a-84d3-8ead93dbe5ef |  | checkpoint | Condensate drain pipework installed and hose clamps fitted
checklist-flat | 14cd7e67-cdf4-4a07-9f52-544f7e6e01b4 |  | checklist | Radiators (HHW) ROUGH IN |  |  |  |  | Yes | Radiators (HHW) ROUGH IN | e60935df-040f-4768-94a9-f544a489c903
checkpoint-status | e619f39c-a87d-4124-80fd-ce731e4ccfca |  | checkpoint | backing plate installed prior to plaster
checklist-flat | 50d7a0d3-f047-4125-8e15-a982bb1086cb |  | checklist | CHW FCU Commissioning |  |  |  |  | Yes | CHW FCU Commissioning | e7de9f7d-9fc8-493e-8a48-fd49609df1b6
checkpoint-status | 8cb44bf6-b98a-4a2c-9afc-c91e9cf7e492 |  | checkpoint | Check Operation of unit
checkpoint-status | fbdffe31-9dc4-47e7-a96f-9fd1473e9023 |  | checkpoint | Check for noise and vibration
checklist-flat | 07d574e1-abf8-485f-a699-2b0e5b391ff0 |  | checklist | AC Ducted Unit Ductwork |  |  |  |  | Yes | AC Ducted Unit Ductwork | f419b829-108c-46e6-b901-a7364866cee1
checkpoint-status | 88fa1823-2d83-4130-a937-f10c4da49fe1 |  | checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint-status | 45e33dde-2638-471d-9fb2-4b803c170548 |  | checkpoint | Grilles/louvres installed
checklist-flat | bb93c342-4c31-4661-8f77-b00ad450ae7e |  | checklist | AC Ducted Unit Rough In |  |  |  |  | Yes | AC Ducted Unit Rough In | fa2932f8-b710-4ace-9983-e2af97f73bae
checkpoint-status | d114aee2-56d7-482e-8a4f-2ad0bbf38599 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 132ba72a-7f87-4883-93b1-3993efef0f65 |  | checkpoint | Vibration mounts installed
checkpoint-status | e796a804-cea2-484f-a462-bae02e909cfc |  | checkpoint | Pipework roughed in
checkpoint-status | f1df9885-e13d-45ce-ad92-ec9991eb68ac |  | checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
checkpoint-status | 556b5824-c192-4280-bf7f-8006d6100b26 |  | checkpoint | All solid ductwork installed as per drawings, including flexible connections
checkpoint-status | 9a1901a9-81c8-45ac-9c2c-13afe46022e7 |  | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
checkpoint-status | d9825fdd-3b4c-404a-acc8-2a25f3219548 |  | checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
checklist-flat | 8dce07c4-d382-44d2-a6b8-8f54d9b0fe08 |  | checklist | AHU Fit Off |  |  |  |  | Yes | AHU Fit Off | fcad5c27-045e-410e-a375-f0af2c43b962
checkpoint-status | 8017fcf6-e302-4cce-98c6-8777e3d62e93 |  | checkpoint | Grilles/louvres installed
checkpoint-status | e7e7b1b6-fba3-48da-a658-26b76b3af0c8 |  | checkpoint | Filters installed and are removable
checkpoint-status | 8b06a42b-f0e9-48d0-ab78-e94eee010db5 |  | checkpoint | Condensate drains terminated at tundish and tested
checklist-flat | a37a2b61-7e63-4ae5-b153-03e2b34f459b |  | checklist | AC Outdoor unit (VRV) Fit Off |  |  |  |  | Yes | AC Outdoor unit (VRV) Fit Off | fdafba66-623f-428e-84e4-997dbabff72e
checkpoint-status | da93a32f-fdfd-4de4-8c2c-a006cc933cc7 |  | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
checkpoint-status | 9df7dbe0-19f8-4ba6-8cb7-3c97d526e862 |  | checkpoint | Vibration mounts installed
checkpoint-status | 2839d32a-3b5d-444f-9c83-0d94a2b45072 |  | checkpoint | Condensate drains installed to tundish/waste point provided
checkpoint-status | 318213e0-9980-424e-9ec3-941a3edbc1ce |  | checkpoint | System pressure tested to 400PSI
checklist-flat | 8becf761-0807-4fd2-b5b7-e3498b15e04a |  | checklist | Roof Cowl (RC) |  |  |  |  | Yes | Roof Cowl (RC) | ff64ec55-caeb-4856-a8e5-0d2afc019be5
checkpoint-status | f752e88c-8a69-43ad-99fe-0d3e56571455 |  | checkpoint | RC Model Number correct, installed & RC Labelled