## Table 1
3.0 SUBCONTRACTOR INSPECTION AND TEST PLAN (ITP) REVIEW (One to be completed per ITP and retained in Subcontractor file)
Project |  |  | MQT - Medibank Fitout | [9 empty] | Date: |  | 2023-03-24
Company Name |  |  | Express Interiors Pty Ltd
Activity |  |  | Ceiling and Partition
ITP Title |  |  | Express ITP - No.1 Partition Walls Checklists Submitted? Yes / No
Project Spec / Rev |  |  | Revision A
| Requirement | [10 empty] | Initial Review |  |  | Final Review |  |  |  | Comments
| Does the ITP: | [10 empty] | Comply Y / N |  |  | Comply Y / N
1 | Reference project specifications and relevant Australian Standards?
2 | Sequentially list all the required tests and inspections from the project specifications and Australian Standards?
3 | Include the requirements from Lendlease’s Project Lessons Learnt and CiDD Alerts and Guidelines?
4 | Indicate responsibility for materials receipt inspection?
5 | Identify frequency of activity, responsibility for conducting verification, method of verification, acceptance criteria?
6 | Identify the type of verification i.e. Hold Point, Witness Point, Review.
7 | Indicate the records that will be provided to evidence compliance? (e.g. Material Certification, Verification Checklists, certificates of compliance)
8 | Has the ITP been sent to the relevant Project Consultant for review, approval and addition of their Hold Points/Witness Points?
9 | Does the ITP indicate specific first-of-type inspections for each type of install
| Do the Inspection or Test Checklists (ITCs): | [10 empty] | Comply Y / N |  |  | Comply Y / N
9 | Have page numbering, revision and space to record related drawing number and revision?
10 | Reference the ITP, and do line items reference line no’s from the ITP?
11 | Identify who should be doing the inspection?
12 | Provide details of traceability and certificates of compliance on completion of sections of the works and for materials (where appropriate)?
[6 empty] | Name | [6 empty] | Signature | [7 empty] | Date
Lendlease Project Engineer
Subcontractor Project Manager
Lendlease Construction Manager
Inspection Plan Checklist
Partition Walls Doc.Ref-ITC-001-Rev1
Project Information
Name: |  |  |  | MQT – Medibank Fitout | [5 empty] | Work: | [5 empty] | All applicable
Address: |  |  |  | 699 Collins Street, Docklands VIC 3008 | [5 empty] | Location:
Head Contractor: |  |  |  | Lendlease | [5 empty] | Drawing Ref. :
Details
PECOMMENCEMENT | [13 empty] | STATUS
SPECIFICATION / DRW No. | [13 empty] | OK |  |  | N/A |  |  | DATE
DESIGN & COMPUTATIONS
SAMPLES
MATERIALS MEET SPECIFICATION REQUIREMENTS
CHECK FOR DAMAGE
MAINTAIN SUITABLE STORAGE
PREINSTALLATION OF SHEETS
MECHANICAL SERVICES
ELECTRICAL SERVICES
COMMUNICATION SERVICES
FIRE SERVICES
HYDRAULIC SERVICES
GAS PIPING
FIRE STOPPING
INSTALLATION REPORT
Item 1: SET OUT
Item 2: FURRING CHANNEL
Item 3: METAL STUD WALL
Item 4: NOGGINGS
Item 5: DEFECTON HEAD
Item 6: SERVICE CHECK FOR PRE-INSTALLATION
Item 7: LININGS
Item 8: CAULKING
Item 9: INSULATION
Item 10: STOPPING
Item 11: SANDING
Item 12: CLEAN UP
Item 13: PATCHING
Item 14: MATERIALS RECEIPT INSPECTION
N.C.N. / C.A.R.
FINAL INSPECTION
WITNESSED BY: |  |  |  | NAME |  |  |  | SIGNATURE |  |  | POSITION | [6 empty] | DATE
SUBCONTRACTOR: | [10 empty] | Foreman
BUILDER:
OTHER:
COMMENTS:
*This document will be provided to evidence compliance to applicable works
Scope: Partition Walls | [6 empty] | ITP Document No.: 1 | [11 empty] | Revision No. A |  |  |  | Date of Revision: 24/03/2023
Project Name: Melbourne Quarter Tower – Medibank Fitout | [18 empty] | Organization Name: Lendlease
Project Address: 699 Collins Street, Docklands VIC 3008
Prepared by
Name: Austin Han | [6 empty] | Position: Contract Administrator | [11 empty] | Signature: |  |  |  | Date: 24/03/2023
Approved by
Name: Greg Edwards | [6 empty] | Position: Construction Manager | [11 empty] | Signature: |  |  |  | Date: 24/03/2023
Level: | [14 empty] | Room No./Area:
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item |  | Activity |  |  | Reference Documents |  |  |  | Acceptance Criteria | [10 empty] | Frequency |  | Verification Records/Comments | Inspection By
[23 empty] | Subcontractor | Lendlease | Client
1 |  | Set out walls |  |  | Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE _1) |  |  |  | Partition Plan and Partition Wall Details approved by Lendlease. Architectural Specification – 0522 Partitions And Linings Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002 | [10 empty] | Each location |  | Visual Checklist | S | S
2 |  | Furring channel to walls |  |  | Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE _1) |  |  |  | Partition Plan and Partition Wall Details approved by Lendlease. Architectural Specification – 0522 Partitions And Linings Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002 | [10 empty] | Each location |  | Visual Checklist | S | S
3 |  | Metal stud wall frame |  |  | Architect drawings (MQT_ID series) |  |  |  | Partition Plan and Partition Wall Details approved by Lendlease. Architectural Specification – 0522 Partitions And Linings | [10 empty] | Each location |  | Visual Checklist | S | S
[5 empty] | Architect Specification (MQT_IS_SPE _1) Refer to Lendlease CiDD for All Alerts and Guidelines for Smoke doors and Baffle |  |  |  | Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002
4 |  | Noggins | [6 empty] | As per scope of work. Studco Wall design & installation manual Volume 3.2 Architectural Specification – 0522 Partitions And Linings Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002 | [10 empty] | Each location |  | Visual Checklist | S | S
5 |  | Check no screws in deflection head | [6 empty] | No screws in deflection head | [10 empty] | Each location |  | Visual Checklist | S | S
6 |  | Service Check for pre- installation of sheets |  |  | Service Sign- off checklist |  |  |  | All service checklists are signed off by relevant trades | [10 empty] | Each location |  | Visual Checklist | S | HP
7 |  | Sheet all walls |  |  | Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE _1) Refer to Lendlease CiDD for All |  |  |  | Partition Plan and Partition Wall Details approved by Lendlease. Check wall types before installation (F/R, Acoustic, Wet Area, PBD etc). Architectural Specification – 0522 Partitions And Linings Boral installation manual revision 2016. Batts insulation installation guide. Australian Standard: AS/NZS 2589.1:1997 | [10 empty] | Each location |  | Visual Checklist | S | S
Alerts and Guidelines for Fibre Cement and Smoke doors and Baffle
8 |  | Caulking | [6 empty] | Boral installation manual revision 2016 Australian Standard: AS 1530.4-2014, AS4072.1-2005, AS1157-1972 | [10 empty] | Each location |  | Visual Checklist | S | S
9 |  | Check insulation in walls |  |  | Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE _1) |  |  |  | Partition Plan and Partition Wall Details approved by Lendlease. Batts Insulation Installation Guidelines Architectural Specification – 0819 Insulation and Barriers Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 : 1999, AS/NZS1530 Part 1: 1994 | [10 empty] | Each location |  | Visual Checklist | S | S
10 |  | Stopping to walls |  |  | Refer to Lendlease CiDD - Alerts and Guidelines for Setting Compounds for Plasterboard |  |  |  | Boral installation manual revision 2016. Australian Standard: AS/NZS 2589.1:1997 | [10 empty] | Each location |  | Visual Checklist | S | S
11 |  | Sanding to walls | [6 empty] | Boral installation manual revision 2016. Australian Standard: AS/NZS 2589.1:1997 | [10 empty] | Each location |  | Visual Checklist | S | S
12 |  | Clean up | [6 empty] | Waste all cleaned. Tools and materials placed well. | [10 empty] | Each location |  | Visual Checklist |  | R
13 |  | Check walls for patching |  |  | Architect drawings (MQT_ID series) Architect Specification |  |  |  | Partition Plan and Partition Wall Details approved by Lendlease. | [10 empty] | Each location |  | Visual Checklist | S | S
(MQT_IS_SPE _1)
14 |  | Materials Receipt Inspection |  |  | Refer to ITP No: 5 Incoming Goods
Comments:
Date of Inspection: | [14 empty] | Carried out by:
*This document will be provided to evidence compliance to applicable works