## Table 1
3.0 SUBCONTRACTOR INSPECTION AND TEST PLAN (ITP) REVIEW (One to be completed per ITP and retained in Subcontractor file)
Project |  |  | MQT - Medibank Fitout | [9 empty] | Date: |  | 2023-03-24
Company Name |  |  | Express Interiors Pty Ltd
Activity |  |  | Ceiling and Partition
ITP Title |  |  | Express ITP - No.2 Suspended Ceiling Checklists Submitted? Yes / No
Project Spec / Rev |  |  | Revision A
| Requirement | [10 empty] | Initial Review |  |  | Final Review |  |  |  | Comments
| Does the ITP: | [10 empty] | Comply Y / N |  |  | Comply Y / N
1 | Reference project specifications and relevant Australian Standards?
2 | Sequentially list all the required tests and inspections from the project specifications and Australian Standards?
3 | Include the requirements from Lendlease’s Project Lessons Learnt and CiDD Alerts and Guidelines?
4 | Indicate responsibility for materials receipt inspection?
5 | Identify frequency of activity, responsibility for conducting verification, method of verification, acceptance criteria?
6 | Identify the type of verification i.e. Hold Point, Witness Point, Review.
7 | Indicate the records that will be provided to evidence compliance? (e.g. Material Certification, Verification Checklists, certificates of compliance)
8 | Has the ITP been sent to the relevant Project Consultant for review, approval and addition of their Hold Points/Witness Points?
9 | Does the ITP indicate specific first-of-type inspections for each type of install
| Do the Inspection or Test Checklists (ITCs): | [10 empty] | Comply Y / N |  |  | Comply Y / N
9 | Have page numbering, revision and space to record related drawing number and revision?
10 | Reference the ITP, and do line items reference line no’s from the ITP?
11 | Identify who should be doing the inspection?
12 | Provide details of traceability and certificates of compliance on completion of sections of the works and for materials (where appropriate)?
[6 empty] | Name | [6 empty] | Signature | [7 empty] | Date
Lendlease Project Engineer
Subcontractor Project Manager
Lendlease Construction Manager
Inspection Plan Checklist
Suspended Ceilings Doc.Ref-ITC-002-Rev1
Project Information
Name: |  |  |  | MQT – Medibank Fitout | [5 empty] | Work: | [5 empty] | All applicable
Address: |  |  |  | 699 Collins Street, Docklands VIC 3008 | [5 empty] | Location:
Head Contractor: |  |  |  | Lendlease | [5 empty] | Drawing Ref. :
Details
PECOMMENCEMENT | [13 empty] | STATUS
SPECIFICATION / DRW No. | [13 empty] | OK |  |  | N/A |  |  | DATE
DESIGN & COMPUTATIONS
SAMPLES
MATERIALS MEET SPECIFICATION REQUIREMENTS
CHECK FOR DAMAGE
MAINTAIN SUITABLE STORAGE
PREINSTALLATION OF SHEETS
MECHANICAL SERVICES
ELECTRICAL SERVICES
COMMUNICATION SERVICES
FIRE SERVICES
HYDRAULIC SERVICES
GAS PIPING
FIRE STOPPING
INSTALLATION REPORT
Item 1: CEILING FRAMING
Item 2: BULKHEAD FRAMING
Item 3: TRIMS OUT ACCESS PANEL
Item 4: INSULATION
Item 5: SERVICE CHECK FOR PRE-INSTALLATION
Item 6: LININGS
Item 7: STOPPING
Item 8: SANDING
Item 9: ACCESS PANELS
Item 10: PENETRATIONS
Item 11: CLEAN UP
Item 12: PATCHING
Item 12: MATERIALS RECEIPT INSPECTION
N.C.N. / C.A.R.
FINAL INSPECTION
WITNESSED BY: |  |  |  | NAME |  |  |  | SIGNATURE |  |  | POSITION | [6 empty] | DATE
SUBCONTRACTOR: | [10 empty] | Foreman
BUILDER:
OTHER:
COMMENTS:
*This document will be provided to evidence compliance to applicable work
Scope: Suspended Ceilings | [6 empty] | ITP Document No.: 2 | [10 empty] | Revision No. A | [5 empty] | Date of Revision: 24/03/2023
Project Name: Melbourne Quarter Tower – Medibank Fitout | [17 empty] | Organization Name: Lendlease
Project Address: 699 Collins Street, Docklands VIC 3008
Prepared by
Name: Austin Han | [6 empty] | Position: Contract Administrator | [10 empty] | Signature: | [5 empty] | Date: 24/03/2023
Approved by
Name: Greg Edwards | [6 empty] | Position: Construction Manager | [10 empty] | Signature: | [5 empty] | Date: 24/03/2023
Level: | [14 empty] | Room No./Area:
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item |  | Activity |  |  | Reference Documents |  |  |  | Acceptance Criteria | [7 empty] | Frequency |  |  |  |  | Verification Records/Comments | Inspection By
[23 empty] | Subcontractor |  | Lendlease | Client
1 |  | Frame ceilings |  |  | Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2) Refer to Lendlease CiDD – All Alerts and Guidelines for Suspended Ceilings |  |  |  | Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease. Studco installation guide. Architectural Specification – 0531 – Suspended Ceiling Australian Standard AS/NZS 2785:2000 | [7 empty] | Each location |  |  |  |  | Visual Checklist | S |  | S
2 |  | Bulkhead framing |  |  | Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2) |  |  |  | Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease. Studco installation guide. Architectural Specification – 0531 – Suspended Ceiling Australian Standard AS/NZS 2785:2000 | [7 empty] | Each location |  |  |  |  | Visual Checklist | S |  | S
3 |  | Trim out access panels |  |  | Architect drawings (MQT_ID series) |  |  |  | Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease. | [7 empty] | Each location |  |  |  |  | Visual Checklist | S |  | S
[5 empty] | Finishes Schedule (MQT_ID_SCH_2) |  |  |  | Architectural Specification – 0531 – Suspended Ceiling Australian Standard - AS1530.4:2014
4 |  | Insulation to ceilings |  |  | Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2) |  |  |  | Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease. Batts insulation installation guide Architectural Specification – 0819 Insulation and barriers Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 : 1999, AS/NZS1530 Part 1: 1994 | [7 empty] | Each location |  |  |  |  | Visual Checklist | S |  | S
5 |  | Service Check for pre- installation of sheets |  |  | Service Sign-off checklist |  |  |  | All service checklists are signed off by relevant trades | [7 empty] | Each location |  |  |  |  | Visual Checklist | S |  | HP
6 |  | Sheets to ceiling |  |  | Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2) Refer to Lendlease CiDD – All Alerts and Guidelines for Suspended Ceilings |  |  |  | Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease. Studco installation guide. Architectural Specification – 0819 Insulation and barriers Australian Standard AS/NZS 2785:2000 | [7 empty] | Each location |  |  |  |  | Visual Checklist | S |  | S
7 |  | Stopping to ceilings |  |  | Refer to Lendlease CiDD - Alerts and Guidelines for Setting Compounds for Plasterboard |  |  |  | Boral installation manual revision 2016. Architectural Specification – 0531 – Suspended Ceiling Australian Standard AS/NZS 2785:2000 | [7 empty] | Each location |  |  |  |  | Visual Checklist | S |  | S
8 |  | Sanding to ceilings | [6 empty] | Boral installation manual revision 2016. Architectural Specification – 0531 – Suspended Ceiling Australian Standard AS/NZS 2785:2000 | [7 empty] | Each location |  |  |  |  | Visual Checklist | S |  | S
9 |  | Fit access hatch frame |  |  | Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2) |  |  |  | Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease. Architectural Specification – 0531 – Suspended Ceiling Australian Standard - AS1530.4:2014 | [7 empty] | Each location |  |  |  |  | Visual Checklist | S |  | S
10 |  | Cut out for lights |  |  | Architect drawings |  |  |  | Reflected Ceiling Plan approved by Lendlease | [7 empty] | Each location |  |  |  |  | Visual Checklist | S |  | S
11 |  | Clean up | [6 empty] | Waste all cleaned. Tools and materials placed well. | [7 empty] | Each location |  |  |  |  | Visual Checklist |  |  | R
12 |  | Check ceilings for patching |  |  | Architect drawings |  |  |  | Reflected Ceiling Plan approved by Lendlease | [7 empty] | Each unit |  |  |  |  | Visual Checklist | S |  | S
13 |  | Materials Receipt Inspection |  |  | Refer to ITP No: 3 Incoming Goods
Comments:
Date of Inspection: | [14 empty] | Carried out by:
*This document will be provided to evidence compliance to applicable works