## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP 02 - Suspended Ceilings | [5 empty] | ITP 02 - Suspended Ceilings - Rev A
checkpoint | 1 - Frame ceilings
label | Reference Documents - Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2)
label | ○ Refer to Lendlease CiDD – All Alerts and Guidelines for Suspended Ceilings
label | Acceptance Criteria - Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease.
label | ○ Studco installation guide. Architectural Specification – 0531 – Suspended Ceiling Australian Standard AS/NZS 2785:2000
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 2 - Bulkhead framing
label | Reference Documents - Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2)
label | Acceptance Criteria - Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease.
label | ○ Studco installation guide. Architectural Specification – 0531 – Suspended Ceiling Australian Standard AS/NZS 2785:2000
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 3 - Trim out access panels
label | Reference Documents - Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2)
label | Acceptance Criteria - Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease.
label | ○ Architectural Specification – 0531 – Suspended Ceiling Australian Standard - AS1530.4:2014
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 4 - Insulation to ceilings
label | Reference Documents - Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2)
label | Acceptance Criteria - Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease.
label | ○ Batts insulation installation guide Architectural Specification – 0819 Insulation and barriers Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 :1999, AS/NZS1530 Part 1: 1994
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 5 - Service Check for pre-installation of sheets
label | Reference Documents - Service Sign-off checklist
label | Acceptance Criteria - All service checklists are signed off by relevant trades
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Sheets to ceiling
label | Reference Documents - Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2)
label | ○ Refer to Lendlease CiDD – All Alerts and Guidelines for Suspended Ceilings
label | Acceptance Criteria - Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease.
label | ○ Studco installation guide. Architectural Specification – 0819 Insulation and barriers Australian Standard AS/NZS 2785:2000
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 7 - Stopping to ceilings
label | Reference Documents - Refer to Lendlease CiDD - Alerts and Guidelines for Setting Compounds for Plasterboard
label | Acceptance Criteria - Boral installation manual revision 2016. Architectural Specification – 0531 – Suspended Ceiling Australian Standard AS/NZS 2785:2000
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 8 - Sanding to ceilings
label | Acceptance Criteria - Boral installation manual revision 2016. Architectural Specification – 0531 – Suspended Ceiling Australian Standard AS/NZS 2785:2000
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 9 - Fit access hatch frame
label | Reference Documents - Architect drawings (MQT_ID series) Finishes Schedule (MQT_ID_SCH_2)
label | Acceptance Criteria - Reflected Ceiling Plan, Ceiling Details and Finishes Schedule approved by Lendlease.
label | ○ Architectural Specification – 0531 – Suspended Ceiling Australian Standard - AS1530.4:2014
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 10 - Cut out for lights
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Reflected Ceiling Plan approved by Lendlease
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 11 - Clean up
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Lendlease - R
checkpoint | 12 - Check ceilings for patching
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Reflected Ceiling Plan approved by Lendlease
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 13 - Materials Receipt Inspection
label | Reference Documents - Refer to ITP No: 3 Incoming Goods
checkpoint-no-status | Comments:
date | Date of Inspection:
text | Carried out by: