## ITP - Pavement
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # GT4-ITP-009
[11 empty] | Revision : 01 | Date : 31/05/2023
Client: |  | Hobart International Airport Pty Ltd |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Project Mercury Early Works At Hobart International Airport |  | Container Farm Construction |  | Name: | Zac Buick | Name: | Tristan Black |  | Name:
Contract No: |  | MER-EW-001 |  | Specifications:
|  |  |  | Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Hobart International Airport |  | Date : | 2023-05-31 | Date : | 2023-07-27 |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Independent QA Verifier | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Site/Project Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing works | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP` | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Site/Project Engineer | N/A |  | N/A
1.3 | Plant and Equipment |  | Prior to commencing works | Plant and equipment used in the Works are appropriate to achieve specification requirements and is inducted | N/A | Visual Inspection | This ITP signed | IP | Site/Project Engineer | N/A |  | N/A
1.4 | Service Locating and Proving |  | Prior to commencing works | The Contractor should familiarize themselves and all personnel on site with the location of all existing services on and adjacent to the site and ensure that all services are fully verified and evaluated against the proposed works. All due care shall be taken to protect existing services, structures, and works in and around the site and adjoining streets | Project Specification Section 1.2.1 | Visual Inspection | This ITP signed | HP* | Site/Project Engineer | N/A |  | N/A
1.5 | Protection and Remoal of Services |  | Prior to commencing works | Before demolishing and removing any part of the works with electrical wiring, gas or water pipes, conduit, telecommunications, or similar items, the Contractor shall notify the Superintendent and relevant authorities to ensure that these items are out of service and can be removed safely. | Project Specification Section 1.2.1 | Visual Inspection | This ITP signed | HP* | Site/Project Engineer | N/A |  | N/A
2 | Clear & Grubbing
2.2 | Tree Removal |  | Each Lot | The clearing shall consist of removal from the area designated in the drawings of all trees, standing or fallen, and other vegetation, boulders and rubbish and shall include the grubbing out of all stumps and tree roots to a depth of 600mm below the natural surface or 400mm below the finished cut surface, whichever is the lower, and disposing of all spoils resulting from the clearing and grubbing. Any holes left after grubbing shall be filled and compacted to the same density as that of the surrounding undisturbed soil. | Project Specification Section 4.5 | Visual Inspection | This ITP signed | HP* | Site/Project Engineer | N/A |  | N/A |  | `
2.2 | Mulching and Chipping |  | Each Lot | All tree trunks, branches and stumps smaller than or equal to 400mm in diameter, including leafy material, shall be mulched (unless noted otherwise) and neatly stockpiled in a site to be determined by the Superintendent. | Project Specification Section 4.6 | Visual Inspection | This ITP signed | HP* | Site/Project Engineer | N/A |  | N/A
2.3 | Stripping of topsoil |  | Each Lot | The existing topsoil shall be stripped from all areas to be earthworked, prior to the commencement of the earthworks, and stockpiled on site. Topsoil is defined as the layer of surface material containing humus, roots, plants and organic material exceeding one percent by weight. | Project Specification Section 4.7 | Visual Inspection | This ITP signed | HP* | Site/Project Engineer | N/A |  | N/A
3 | Excavation
3.1 | Earthworks |  | Each Lot | Excavation shall include the removal of all materials encountered below natural ground level, including all obstructions of any nature that interfere with the proper execution and completion of the work. | Project Specification Section 4.2.1 | Visual Inspection | This ITP signed | IP | Site/Project Engineer | N/A |  | N/A
3.2 | Subgrade Preperation |  | Each Lot | The sub-grade shall be trimmed to an even surface free from loose material. Remove roots, boulders and other unsuitable materials such as silt or organic matter as directed by the Superintendent. Grade depressions to drain to the edge of the formation. Where the subgrade is unable to support construction equipment or it is not possible to compact the overlying pavement because of a high subgrade moisture content the Contractor shall refer to the project specification for treatments. | Project Specification Section 4.13 | Verify | This ITP signed | HP* | Site/Project Engineer | N/A |  | N/A
3.3 | Survey Conformance |  | 1 per project | The subgrade formation surface shall be finished within the following tolerances: — Variation from a 3 m straight edge 10 mm | Project Specification Table 4.3 | Verify | Conformance Report | SCP | Site/Project Engineer Surveyor | N/A |  | N/A
4 | Placement of Crush Rock
4.1 | Placement |  | Each Lot | Once the sub-grade has been approved, crushed rock shall be evenly spread in layers no thicker than 150mm | Project Specification Section 6.8.1 | Visual Inspection | This ITP signed | IP | Site/Project Engineer | N/A |  | N/A
4.2 | Material Quality |  | Each Lot | The material should be spread without segregation and between approved edge boards or kerbs. The crushed rock should not be spread on waterlogged sub-grade, and any soft spots or areas with mixed materials must be dug out and replaced with approved material. | Project Specification Section 6.8.1 | Visual Inspection | This ITP signed | IP | Site/Project Engineer | N/A |  | N/A
4.3 | Testing and Proof Roll |  | Each Lot | Rolling must be performed to eliminate bumps and irregularities, with the finished surface being true to the required grades and cross-section. The crushed rock must show no movement under a six-tonne smooth steel-wheeled roller, and the minimum compaction achieved must be 100% of the Standard Maximum Dry Density in the base course and 98% in the sub-base course. The thickness specified is the minimum required. | Project Specification Section 6.8.1 | Verify | Test Report | TP | Site/Project Engineer | N/A |  | N/A
4.4 | Shape |  | Each Lot | The shape of the road must be checked frequently during final shaping and compacting and corrected as necessary by grading under the direction of an experienced foreman. The crossfall, super-elevation, and smoothness of the grade must be checked using a straight edge and built-in level. | Project Specification Section 6.8.2 | Visual Inspection | This ITP signed | IP | Site/Project Engineer | N/A |  | N/A
4.5 | Conformance |  | Each Lot | The following construction tolerances must be achived by the contractor | Project Specification Table 4.3 | Verify | Conformance Report | SCP | Site/Project Engineer Surveyor | N/A |  | N/A
5 | Asphalt Path Placement
5.1 | Asphalt Mix Specification |  | Each Lot | The bitumen grade is to be Class 170. The bitumen is to conform to AS 2008 and the current Austroads Guide to Pavement Technology Part 3. Aspahlt to be a 30mm compacted depth of 7mm NS type L asphalt | Project Specification Section 6.5.3 | Visual Inspection | This ITP signed | IP | Site/Project Engineer | N/A |  | N/A
5.2 | Placement |  | Each Lot | The temperature of the pavement to be surfaced should be at least 10 degrees Celsius, and no rain should fall during the placing of the mix. The surface must be dry. Asphalt should be placed at a rate that will provide the required compacted thickness shown on the drawings. | Project Specification Section 6.9.2 | Visual Inspection | This ITP signed | IP | Site/Project Engineer | N/A |  | N/A
5.3 | Jointing |  | Each paver run | Joints must be waterproof and formed as necessary to ensure a smooth and even profile over the joints without ridges or depressions. Joints must be in accordance with AS 2150 Section 12.6. | Project Specification Section 6.9.2 | Visual Inspection | This ITP signed | IP | Site/Project Engineer | N/A |  | N/A
5.4 | Compaction |  | Each Lot | Rolling procedure to be confirmed by contractor on site. If the asphalt begins to shove or crack, rolling must not continue until the cause is determined, and corrective measures are taken. During all rolling operations, drums and wheels of rollers must be kept wet with water and be clean. | Project Specification Section 6.9.2 | Verify | Test Report | TP | Site/Project Engineer | N/A |  | N/A
5.5 | Layer Thickness |  | Each Lot | Asphalt thickness to be 30mm with a construction tolerance of + 5mm or - 0mm | IFC Drawings | Verify | This ITP signed | IP | Site/Project Engineer | N/A |  | N/A
5.6 | Tolerances |  | Each Lot | The following construction tolerances must be achived by the contractor | Project Specification Table 4.3 | Verify | Conformance Report | SCP | Site/Project Engineer Surveyor | N/A |  | N/A
6 | Concrete Ramps
6.1 | Concrete Mix Design |  | Each Lot | The concrete used must adhere to AS 3600 and must be obtained from a concrete supplier that conforms to AS 1379. It should possess a minimum characteristic strength of 25 MPa (N25), a maximum aggregate size of 20mm and a slump of 60mm. | Project Specification Section 5.5.5 | Verify | This ITP signed | HP* | Site/Project Engineer | N/A |  | N/A
6.2 | Reinforment |  | Each Lot | Reinforcement to be SL72 Mesh as per the drawings | CV-130 | Verify | This ITP signed | IP | Site/Project Engineer | N/A |  | N/A
6.3 | Placement |  | Each Lot | Contractor to ensure concrete is adequetly vibrated during placement. | Work Procedure | Visual Inspection | This ITP signed | IP | Site/Project Engineer | N/A |  | N/A
6.4 | Tolerances |  | Each Lot | Concrete to adhere to the tolernaces of a class 3 finish | Work Procedure | Verify | Conformance Report | SCP | Site/Project Engineer Surveyor | N/A |  | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Fulton Hogan | Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent