## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | GT4-ITP-015 - Container Farm Construction | itp |  |  |  | Yes | GT4-ITP-015 - Container Farm Construction
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents: Drawings and drawing registers
label | Inspection / Test Method: Visual inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing works
label | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP`
label | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 1.3 - Plant and Equipment
label | Frequency: Prior to commencing works
label | Acceptance Criteria: Plant and equipment used in the Works are appropriate to achieve specification requirements and is inducted
label | Reference Documents: N/A
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 1.4 - Service Locating and Proving
label | Frequency: Prior to commencing works
label | Acceptance Criteria: The Contractor should familiarize themselves and all personnel on site with the location of all existing services on and adjacent to the site and ensure that all services are fully verified and evaluated against the proposed works.
label | ○ All due care shall be taken to protect existing services, structures, and works in and around the site and adjoining streets
label | Reference Documents: Project Specification Section 1.2.1
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 1.5 - Protection and Remoal of Services
label | Frequency: Prior to commencing works
label | Acceptance Criteria: Before demolishing and removing any part of the works with electrical wiring, gas or water pipes, conduit, telecommunications, or similar items, the Contractor shall notify the Superintendent and relevant authorities to ensure that these items are out of service and can be removed safely.
label | Reference Documents: Project Specification Section 1.2.1
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site/Project Engineer
date | Date Completed:
section | 2 - Clear & Grubbing
checkpoint | 2.1 - Tree Removal
label | Frequency: Each Lot
label | Acceptance Criteria: The clearing shall consist of removal from the area designated in the drawings of all trees, standing or fallen, and other vegetation, boulders and rubbish and shall include the grubbing out of all stumps and tree roots to a depth of 600mm below the natural surface or 400mm below the finished cut surface, whichever is the lower, and disposing of all spoils resulting from the clearing and grubbing.
label | ○ Any holes left after grubbing shall be filled and compacted to the same density as that of the surrounding undisturbed soil.
label | Reference Documents: Project Specification Section 4.5
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 2.2 - Mulching and Chipping
label | Frequency: Each Lot
label | Acceptance Criteria: All tree trunks, branches and stumps smaller than or equal to 400mm in diameter, including leafy material, shall be mulched (unless noted otherwise) and neatly stockpiled in a site to be determined by the Superintendent.
label | Reference Documents: Project Specification Section 4.6
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 2.3 - Stripping of topsoil
label | Frequency: Each Lot
label | Acceptance Criteria: The existing topsoil shall be stripped from all areas to be earthworked, prior to the commencement of the earthworks, and stockpiled on site.
label | ○ Topsoil is defined as the layer of surface material containing humus, roots, plants and organic material exceeding one percent by weight.
label | Reference Documents: Project Specification Section 4.7
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site/Project Engineer
date | Date Completed:
section | 3 - Excavation
checkpoint | 3.1 - Earthworks
label | Frequency: Each Lot
label | Acceptance Criteria: Excavation shall include the removal of all materials encountered below natural ground level, including all obstructions of any nature that interfere with the proper execution and completion of the work.
label | Reference Documents: Project Specification Section 4.2.1
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 3.2 - Subgrade Preperation
label | Frequency: Each Lot
label | Acceptance Criteria: The sub-grade shall be trimmed to an even surface free from loose material. Remove roots, boulders and other unsuitable materials such as silt or organic matter as directed by the Superintendent.
label | ○ Grade depressions to drain to the edge of the formation. Where the subgrade is unable to support construction equipment or it is not possible to compact the overlying pavement because of a high subgrade moisture content the Contractor shall refer to the project specification for treatments.
label | Reference Documents: Project Specification Section 4.13
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 3.3 - Survey Conformance
label | Frequency: 1 per project
label | Acceptance Criteria: The subgrade formation surface shall be finished within the following tolerances:
label | ○ Variation from a 3 m straight edge 10 mm
label | – – – – – – – – – –
label | Test/Record Frequency
label | – – – – – – – – – –
label | Finished subgrade level ¦¦ + 5mm or - 30mm (+0mm)
label | Sub-base width ¦¦ + 300mm and - 0mm
label | Finished sub-base level ¦¦ + 10mm or - 20mm
label | Basecourse width ¦¦ + 300mm and - 0mm
label | Basecourse thickness ¦¦ - 0mm
label | Finished basecourse level ¦¦ + 10mm or - 10mm
label | Thickness of AC ¦¦ + 5mm or - 0mm
label | Finished AC or brick paving level ¦¦ + 10mm or -10mm
label | – – – – – – – – – –
label | Reference Documents: Project Specification Table 4.3
label | Inspection / Test Method: Verify
label | Record of conformity: Conformance Report
label | SCP
label | Responsibility: Site/Project Engineer Surveyor
date | Date Completed:
section | 4 - Placement of Crush Rock
checkpoint | 4.1 - Placement
label | Frequency: Each Lot
label | Acceptance Criteria: Once the sub-grade has been approved, crushed rock shall be evenly spread in layers no thicker than 150mm
label | Reference Documents: Project Specification Section 6.8.1
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 4.2 - Material Quality
label | Frequency: Each Lot
label | Acceptance Criteria: The material should be spread without segregation and between approved edge boards or kerbs.
label | ○ The crushed rock should not be spread on waterlogged sub-grade, and any soft spots or areas with mixed materials must be dug out and replaced with approved material.
label | Reference Documents: Project Specification Section 6.8.1
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 4.3 - Testing and Proof Roll
label | Frequency: Each Lot
label | Acceptance Criteria: Rolling must be performed to eliminate bumps and irregularities, with the finished surface being true to the required grades and cross-section.
label | ○ The crushed rock must show no movement under a six-tonne smooth steel-wheeled roller, and the minimum compaction achieved must be 100% of the Standard Maximum Dry Density in the base course and 98% in the sub-base course.
label | ○ The thickness specified is the minimum required.
label | Reference Documents: Project Specification Section 6.8.1
label | Inspection / Test Method: Verify
label | Record of conformity: Test Report
label | TP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 4.4 - Shape
label | Frequency: Each Lot
label | Acceptance Criteria: The shape of the road must be checked frequently during final shaping and compacting and corrected as necessary by grading under the direction of an experienced foreman.
label | ○ The crossfall, super-elevation, and smoothness of the grade must be checked using a straight edge and built-in level.
label | Reference Documents: Project Specification Section 6.8.2
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 4.5 - Conformance
label | Frequency: Each Lot
label | Acceptance Criteria: The following construction tolerances must be achived by the contractor
label | – – – – – – – – – –
label | Test/Record Frequency
label | – – – – – – – – – –
label | Finished subgrade level ¦¦ + 5mm or - 30mm (+0mm)
label | Sub-base width ¦¦ + 300mm and - 0mm
label | Finished sub-base level ¦¦ + 10mm or - 20mm
label | Basecourse width ¦¦ + 300mm and - 0mm
label | Basecourse thickness ¦¦ - 0mm
label | Finished basecourse level ¦¦ + 10mm or - 10mm
label | Thickness of AC ¦¦ + 5mm or - 0mm
label | Finished AC or brick paving level ¦¦ + 10mm or -10mm
label | – – – – – – – – – –
label | Reference Documents: Project Specification Table 4.3
label | Inspection / Test Method: Verify
label | Record of conformity: Conformance Report
label | SCP
label | Responsibility: Site/Project Engineer Surveyor
date | Date Completed:
section | 5 - Asphalt Path Placement
checkpoint | 5.1 - Asphalt Mix Specification
label | Frequency: Each Lot
label | Acceptance Criteria: The bitumen grade is to be Class 170. The bitumen is to conform to AS 2008 and the current Austroads Guide to Pavement Technology Part 3. Aspahlt to be a 30mm compacted depth of 7mm NS type L asphalt
label | Reference Documents: Project Specification Section 6.5.3
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 5.2 - Placement
label | Frequency: Each Lot
label | Acceptance Criteria: The temperature of the pavement to be surfaced should be at least 10 degrees Celsius, and no rain should fall during the placing of the mix.
label | ○ The surface must be dry.
label | ○ Asphalt should be placed at a rate that will provide the required compacted thickness shown on the drawings.
label | Reference Documents: Project Specification Section 6.9.2
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 5.3 - Jointing
label | Frequency: Each paver run
label | Acceptance Criteria: Joints must be waterproof and formed as necessary to ensure a smooth and even profile over the joints without ridges or depressions. Joints must be in accordance with AS 2150 Section 12.6.
label | Reference Documents: Project Specification Section 6.9.2
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 5.4 - Compaction
label | Frequency: Each Lot
label | Acceptance Criteria: Rolling procedure to be confirmed by contractor on site.
label | ○ If the asphalt begins to shove or crack, rolling must not continue until the cause is determined, and corrective measures are taken. During all rolling operations, drums and wheels of rollers must be kept wet with water and be clean.
label | Reference Documents: Project Specification Section 6.9.2
label | Inspection / Test Method: Verify
label | Record of conformity: Test Report
label | TP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 5.5 - Layer Thickness
label | Frequency: Each Lot
label | Acceptance Criteria: Asphalt thickness to be 30mm with a construction tolerance of + 5mm or - 0mm
label | Reference Documents: IFC Drawings
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 5.6 - Tolerances
label | Frequency: Each Lot
label | Acceptance Criteria: The following construction tolerances must be achived by the contractor
label | – – – – – – – – – –
label | Thickness of AC ¦¦ + 5mm or - 0mm
label | Finished AC or brick paving level ¦¦ + 10mm or -10mm
label | – – – – – – – – – –
label | Reference Documents: Project Specification Table 4.3
label | Inspection / Test Method: Verify
label | Record of conformity: Conformance Report
label | SCP
label | Responsibility: Site/Project Engineer Surveyor
date | Date Completed:
section | 6 - Concrete Ramps
checkpoint | 6.1 - Concrete Mix Design
label | Frequency: Each Lot
label | Acceptance Criteria: The concrete used must adhere to AS 3600 and must be obtained from a concrete supplier that conforms to AS 1379.
label | ○ It should possess a minimum characteristic strength of 25 MPa (N25), a maximum aggregate size of 20mm and a slump of 60mm.
label | Reference Documents: Project Specification Section 5.5.5
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | HP*
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 6.2 - Reinforment
label | Frequency: Each Lot
label | Acceptance Criteria: Reinforcement to be SL72 Mesh as per the drawings
label | Reference Documents: CV-130
label | Inspection / Test Method: Verify
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 6.3 - Placement
label | Frequency: Each Lot
label | Acceptance Criteria: Contractor to ensure concrete is adequetly vibrated during placement.
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Visual Inspection
label | Record of conformity: This ITP signed
label | IP
label | Responsibility: Site/Project Engineer
date | Date Completed:
checkpoint | 6.4 - Tolerances
label | Frequency: Each Lot
label | Acceptance Criteria: Concrete to adhere to the tolernaces of a class 3 finish
label | Reference Documents: Work Procedure
label | Inspection / Test Method: Verify
label | Record of conformity: Conformance Report
label | SCP
label | Responsibility: Site/Project Engineer Surveyor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Date:
signoff | Sign ITP