## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Bored Retention Piles |  |  |  |  | Yes | ITP - Bored Retention Piles Rev 0 | 05ae92cc-5e81-402d-8818-4745329ca98b
checkpoint-status |  |  | checkpoint | 1. Existing Service search
label | ef77a697-1d2c-50e5-a376-da5c05affc72 |  | note | APPLICABLE STANDARD: N/A
label | 695acf88-0e16-5eb3-b3b7-f836a408dc0e |  | note | CONFORMANCE CRITERIA: Locate and Identify existing underground services
label | f40ec8f9-03ba-5ce0-8272-7d42ad0062cc |  | note | FREQUENCY: Entire Site
label | ca7992f7-cb78-5954-a642-e96b12c97459 |  | note | METHOD OF INSPECTION: Visual Inspection of drawings and identify
label | 7203f80b-ff99-5306-9fd4-54f81bbd895b |  | note | PERSONNEL RESPONSIBLE: Client
label | 050f13a5-c4cf-5dfa-97d2-a25534e79a07 |  | note | DOCUMENTATION & VERIFICATION: Service plans from client
holdpoint |  |  | signoff | SIGN OFF - LTE
checkpoint-status |  |  | checkpoint | 2. Piling Platform
label | 1c266290-ede3-5a05-84f3-bf6ecf3beac2 |  | note | APPLICABLE STANDARD: N/A
label | e2c0cd4e-84d5-5783-b98a-12795381d7bc |  | note | CONFORMANCE CRITERIA: Working platform adequate for piling rigs
label | 2875c64a-99bf-5425-a83b-3d19f5f99ba8 |  | note | FREQUENCY: Entire Site
label | 44319f31-4c88-5942-8542-0ea6e6f78280 |  | note | METHOD OF INSPECTION: DCP testing undertaken to confirm in situ soil adequate for Piling rig
label | 5901ff8b-b6a7-5c66-a1e6-d300457a9106 |  | note | PERSONNEL RESPONSIBLE: LTE Engineer, LTE Site Supervisor
label | e8babcb5-f631-5cf4-b69d-83162c3ac948 |  | note | DOCUMENTATION & VERIFICATION: DCP test results, Working Platform Certificate
holdpoint |  |  | signoff | SIGN OFF - LTE
checkpoint-status |  |  | checkpoint | 3. Pile Set out
label | 366a173c-8396-5b19-b280-68cdd83f17d8 |  | note | APPLICABLE STANDARD: Construction Drawings and Pile design document
label | 9984df3f-8231-5ce0-bfe0-fbf93993c72f |  | note | CONFORMANCE CRITERIA: Set-out of Pile locations as shown of drawings
label | 80c8ba23-98f7-5677-967e-af996d2c6d53 |  | note | FREQUENCY: Each pile
label | a95b4403-4f45-574a-affd-8a741ef581f2 |  | note | METHOD OF INSPECTION: Visual Inspection, survey set out
label | 2227b7d3-731d-5798-95eb-4381d4392f36 |  | note | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | 5f408d70-185e-5f22-878e-5080ec0fddda |  | note | DOCUMENTATION & VERIFICATION: Pile QA document
holdpoint |  |  | signoff | SIGN OFF - LTE
checkpoint-status |  |  | checkpoint | 4. Drilling pile
label | 8c918afd-1ff1-59c3-98dd-99b5a7419e2b |  | note | APPLICABLE STANDARD: Construction Drawings, Pile design document, Pile QA document, AS2159
label | 3893bdf5-6e96-5361-ad49-a1b1f8c10c07 |  | note | CONFORMANCE CRITERIA: Ensure hole dia, depth, all as per design documentation and QA document, hole within positional tolerance as per AS2159
label | 9c2aed73-5380-577a-9837-2ad0a009240a |  | note | FREQUENCY: Each pile
label | 3e827f20-5425-541d-a067-ef42d8874d05 |  | note | METHOD OF INSPECTION: Visual Inspection, tape measure
label | da8abaf7-7377-5620-ba7c-3988a39dfe72 |  | note | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | 9cd687af-6ac6-5801-b49d-b48b58ef55a1 |  | note | DOCUMENTATION & VERIFICATION: Pile QA document
holdpoint |  |  | signoff | SIGN OFF - LTE
checkpoint-status |  |  | checkpoint | 5. Placement of Reinforcement cage
label | 84631b9d-c8ef-5901-835d-df8fc5aa5266 |  | note | APPLICABLE STANDARD: Construction Drawings, Pile design document, Pile QA document, AS2159
label | e9b0e0ef-099d-573e-ab24-0d476730403c |  | note | CONFORMANCE CRITERIA: Reo cage as per design/Pile QA document, placed to correct RL, spacers used to ensure cover to cage
label | 5223d379-cde4-5dec-b5da-488cd4465bf0 |  | note | FREQUENCY: Each pile
label | 0219a2ad-7a03-59c0-a17e-bd6966e50abe |  | note | METHOD OF INSPECTION: Visual Inspection
label | 3bda58b7-87af-566d-a6c1-9c4776c2c550 |  | note | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | 69ac3702-2b0e-5b7a-b3e0-be35d9cbbf42 |  | note | DOCUMENTATION & VERIFICATION: Pile QA document
holdpoint |  |  | signoff | SIGN OFF - LTE
checkpoint-status |  |  | checkpoint | 6. Placement of Concrete
label | bd7f5590-2848-5268-bce5-49971eb95559 |  | note | APPLICABLE STANDARD: Construction Drawings, Pile design document, Pile QA document, AS2159, AS3600
label | 3573795a-9ed3-506c-9f67-537278b39a91 |  | note | CONFORMANCE CRITERIA: Concrete 50 MPa, superplasticised for piling application. Positively guided away from reinforcement during pouring. Concrete testing undertaken min 3 cylinders per 50m3 poured on site
label | d64ed144-3474-530e-a9b2-0727d577f7c3 |  | note | FREQUENCY: Each pile
label | b8d16b27-1d99-5cdf-95c1-cf82f32902e0 |  | note | METHOD OF INSPECTION: Visual Inspection
label | 4b448274-dbc2-526c-8fe3-54c74a5f85e6 |  | note | ○ Concrete dockets
label | 9902db3b-eb08-51e1-8cf0-5363d9ce074b |  | note | ○ Concrete test report
label | fd426d6d-22c6-5e18-bb93-dcf456300545 |  | note | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | d002b23f-ba24-5052-88f6-c73da83414a3 |  | note | DOCUMENTATION & VERIFICATION: Pile QA document
label | 51886cae-25f2-567d-81a1-d3a16507b91d |  | note | ○ Concrete dockets
label | 79a5f4be-115c-55e9-9c73-246b32c417f6 |  | note | ○ Concrete test report
holdpoint |  |  | signoff | SIGN OFF - LTE
checklist-flat |  |  | checklist | Shotcrete Walls |  |  |  |  | Yes | ITP - Shotcrete Walls Rev 0 | 2ac50c6c-207a-4a95-8ae7-e52556af7713
checkpoint-status |  |  | checkpoint | 1. Existing Service search
label | 0e299747-9b31-5179-b1b4-c7e46bda1259 |  | note | APPLICABLE STANDARD: N/A
label | 763ccf0a-15fd-54d3-a2a6-742f1a167bfa |  | note | CONFORMANCE CRITERIA: Locate and Identify existing underground services
label | a5f49215-00e3-594c-859b-fb66ed7412be |  | note | FREQUENCY: Entire Site
label | 0278ecfd-1a64-5cb5-b093-dd4130452b58 |  | note | METHOD OF INSPECTION: Visual Inspection of drawings and identify
label | 071695c8-936f-58f5-8c3f-7c6b1071d544 |  | note | PERSONNEL RESPONSIBLE: Client
label | 61d08ea0-c268-574d-98cf-b54f77e113c9 |  | note | DOCUMENTATION & VERIFICATION: Service plans from client
holdpoint |  |  | signoff | SIGN OFF - LTE
checkpoint-status |  |  | checkpoint | 2. Detailed Excavation of Shotcrete wall
label | 26a538df-364e-5566-9bcc-ac1da90fd746 |  | note | APPLICABLE STANDARD: Construction Drawings
label | b1d232cb-b348-510d-93e4-5a5ec825d01d |  | note | CONFORMANCE CRITERIA: Excavation to line/levels as per drawings
label | 35a3ef55-09d6-561d-b79d-7499c150b793 |  | note | FREQUENCY: Entire Site
label | 79ee9a52-b770-57f5-a2f6-bf2cd24bf864 |  | note | METHOD OF INSPECTION: Survey/setout
label | f9dd71c2-e87e-5997-a062-43d6e44dffa5 |  | note | PERSONNEL RESPONSIBLE: LTE
label | 171ee48e-c0d9-557d-831c-be3548d1ebab |  | note | DOCUMENTATION & VERIFICATION: This ITP
holdpoint |  |  | signoff | SIGN OFF - LTE
checkpoint-status |  |  | checkpoint | 3. Placement of dowels/mesh/stripdrain/starter bars
label | dcab7527-e8e6-54d4-bacb-6f19bce0852c |  | note | APPLICABLE STANDARD: Construction Drawings, AS3600
label | 31bb2e0e-72c3-59e0-83ea-11b97bfc0d6a |  | note | CONFORMANCE CRITERIA: Ensure stripdrain installed as per design
label | d4af4b7c-9f67-5489-921d-220546a62b16 |  | note | ○ Ensure reo placed as per design, mesh laps as per design drawings, dowels drilled and epoxied as per design drawings, starter bars as per structural drawings
label | e1cf0041-1c89-5a86-aeca-8d14a0c49e6c |  | note | ○ Ensure concrete cover as per design
label | ce390f77-7f2c-5cfe-bc53-e8fc005340db |  | note | FREQUENCY: Each pour
label | a5ab08a5-295e-57ef-a0fd-91500ed04ecc |  | note | METHOD OF INSPECTION: Visual Inspection, tape measure
label | 869bb4d7-ed3b-5345-a42c-3d0fe25d6d51 |  | note | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | f304b43c-2e65-5573-ad1c-e6c96ffbee33 |  | note | DOCUMENTATION & VERIFICATION: This ITP
holdpoint |  |  | signoff | SIGN OFF - LTE
checkpoint-status |  |  | checkpoint | 4. Placement of Concrete (shotcrete)
label | e29e7362-34aa-5d18-9834-230440923a11 |  | note | APPLICABLE STANDARD: Construction Drawings, AS3600
label | 2b94649e-6c07-59dc-a8d5-af001a9bbd69 |  | note | CONFORMANCE CRITERIA: Concrete strength as per design, Concrete testing undertaken min 3 cylinders per 50m3 poured on site
label | 838eaa1d-d1da-59c2-94e3-ba2c0eff70e3 |  | note | FREQUENCY: Each pour
label | 69526c8e-cb8c-5c19-a1f7-6b7c2f2af07b |  | note | METHOD OF INSPECTION: Visual Inspection
label | c84016cd-b573-57fa-b74b-0effa7693315 |  | note | ○ Concrete dockets
label | 2e3c28fd-9624-5107-b014-9c921efa1cc0 |  | note | ○ Concrete test report
label | 6f54ff5e-22ab-575d-92d2-39232c4ead33 |  | note | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | 4679b8bf-73d4-532e-8cc4-228cf6263e18 |  | note | DOCUMENTATION & VERIFICATION: Concrete dockets, Concrete test report
holdpoint |  |  | signoff | SIGN OFF - LTE
checklist-flat |  |  | checklist | Capping Beam |  |  |  |  | Yes | ITP - Capping Beam Rev 0 | b5006cdb-3449-4fee-85e8-0145a1cfbac1
checkpoint-status |  |  | checkpoint | 1. Existing Service search
label | f0da51b8-03a4-5aa4-9380-a5cccc7cbb1c |  | note | APPLICABLE STANDARD: N/A
label | 0b354fd0-7746-5f3e-9ac1-7744f227f2ca |  | note | CONFORMANCE CRITERIA: Locate and Identify existing underground services
label | 4f4bee83-8777-5667-a28c-ad31694aa400 |  | note | FREQUENCY: Entire Site
label | 53027a6e-67b6-570b-8225-10ee727aa5cf |  | note | METHOD OF INSPECTION: Visual Inspection of drawings and identify
label | aae204e8-ad85-5a4d-b3ac-15f03c92f519 |  | note | PERSONNEL RESPONSIBLE: Client
label | c5ae0c11-dba5-54db-9e1a-57b4756d397a |  | note | DOCUMENTATION & VERIFICATION: Service plans from client
holdpoint |  |  | signoff | SIGN OFF - LTE
checkpoint-status |  |  | checkpoint | 2. Detailed Excavation of Capping beam
label | 196392bc-36c4-5e70-b0dd-ddd62bf8f962 |  | note | APPLICABLE STANDARD: Construction Drawings
label | 62c3d5ce-ac60-5383-91e5-b66278bb87b4 |  | note | CONFORMANCE CRITERIA: Excavation to line/levels and dimensions as per drawings
label | 816758b7-030d-5bd9-83ed-56c767eaada4 |  | note | FREQUENCY: Entire Site
label | 25057f6a-446e-5f10-955b-95967f505671 |  | note | METHOD OF INSPECTION: Survey/setout
label | 98cb29b7-bfd2-5f08-87f6-9189f411c9b3 |  | note | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | f3d8a277-2568-5b4e-8a78-cee3d6107fb3 |  | note | DOCUMENTATION & VERIFICATION: This ITP
holdpoint |  |  | signoff | SIGN OFF - LTE
checkpoint-status |  |  | checkpoint | 3. Placement of Blinding (if required)
label | b1ac1e79-30da-548e-8c80-c0598fd5f0fb |  | note | APPLICABLE STANDARD: Construction Drawings
label | e0acbd30-f5a5-5ad4-a640-2b2389d7426d |  | note | CONFORMANCE CRITERIA: Blinding placed to correct level
label | 466af128-9137-5b7c-887b-f4074f52a8f8 |  | note | FREQUENCY: Each pour
label | 2bf08117-1e69-5c7f-839a-29f3264510d0 |  | note | METHOD OF INSPECTION: Visual Inspection, survey set out, laser level
label | c61d7347-4b78-530f-ab25-0ebf90642ebd |  | note | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | 37cb4a74-17cc-5dbe-9bbc-30ffbd96be0b |  | note | DOCUMENTATION & VERIFICATION: This ITP
holdpoint |  |  | signoff | SIGN OFF - LTE
checkpoint-status |  |  | checkpoint | 4. Placement of reinforcement
label | bd7a2007-5b5c-56b9-9462-48711ef599c2 |  | note | APPLICABLE STANDARD: Construction Drawings, AS3600
label | 137523cd-1dbe-5c87-a7cb-0c5ed02d0e8e |  | note | CONFORMANCE CRITERIA: Ensure reo placed as per design, main bar and side bar laps as per design drawings, lig spacing as per design drawings, starter bars as per structural drawings
label | ab2f251a-d703-5db0-94a3-aea862799d37 |  | note | ○ Ensure concrete cover as per design
label | 733febca-e3f2-5667-87af-1b887555cffc |  | note | FREQUENCY: Each pour
label | bced64ad-2b2c-5797-9215-ebb26b5c54c0 |  | note | METHOD OF INSPECTION: Visual Inspection, tape measure
label | d3c60ece-50a2-510b-aec9-0f2b8d628840 |  | note | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | 0e571040-7dc8-5cab-a5df-de323db4767d |  | note | DOCUMENTATION & VERIFICATION: This ITP
holdpoint |  |  | signoff | SIGN OFF - LTE
checkpoint-status |  |  | checkpoint | 5. Placement of Concrete (shotcrete)
label | 8f9798c9-519c-5d80-95fe-356db1f68bd2 |  | note | APPLICABLE STANDARD: Construction Drawings, AS3600
label | c11f6bda-c580-5b4a-b54f-3f8d6bb18b0f |  | note | CONFORMANCE CRITERIA: Concrete strength as per design 40 MPa and 50 MPa, Concrete testing undertaken min 3 cylinders per 50m3 poured on site
label | ffac4d4d-e25f-5724-a2a7-afe87396bbcb |  | note | FREQUENCY: Each pour
label | d1f0e8f0-3b31-5f06-b4f6-adc6cb73adad |  | note | METHOD OF INSPECTION: Visual Inspection
label | 5b5045fc-c0cc-568e-bef7-0d7f7475453c |  | note | ○ Concrete dockets
label | d83d5949-8b8c-55b0-a0ce-946090cb5225 |  | note | ○ Concrete test report
label | d8bc1d38-6960-5319-a8c2-66930329fef6 |  | note | PERSONNEL RESPONSIBLE: LTE Site Supervisor
label | 598f12f0-4fdf-54c2-9645-caeb309b0f56 |  | note | DOCUMENTATION & VERIFICATION: Concrete dockets, Concrete test report
holdpoint |  |  | signoff | SIGN OFF - LTE