## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV-CPD-Hot Mix Asphalt (Supply and Install)
ITP Description: |  | Hot Mix Asphalt (Supply and Install)
Discipline (e.g. CIV/STR/RAIL: |  | CIV-CPD
Revision Number: |  | 0
Revision Date: |  | 2023-08-22
ITP created by: |  | Ahmed ABDELSALAM
ITP approved for use by: |  | Pradeep TALASILA
Special Notes to ConQA Team : |  | ITP for Calder Park Drive/Holden Road
Inspection & Test Plan - Hot Mix Asphalt (Supply and Install)
[9 empty] | Revision: | 0
[9 empty] | Date: | 2023-08-22
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings Vic Roads 407 Vic Roads 404 Vic Roads 417 AS2150 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminary Works
2.1 | Mix Design & Trackless Tack Coat Approval | 407.09, 407.08(d) Mix Design Registration | Mix design and trackless tack coat to be used has been approved by project superintendent, prior to use | Approval Correspondance | Prior to commencing paving | HP | Project Engineer/ Supervisor | Completed ITP |  |  | Insert Text Box for Team Binder Approval Number
2.2 | Asphalt Placement and Lot Plan | Section 407.17 | "Asphalt placement and Lot plan to be created prior to commencement of works. The location of all joints shall be planned before work commences to achieve the specified offsets between layers and the final position of joints in the wearing course. Plan to specify start/end chainage, offset/lane and layer." | Verify | Each lot | IP | Site Engineer/ Asphalt Supervisor | Daily Lot Record | NA | NA
2.3 | Site Inspection and Base Condition | 407.17 AS2150 10.1 AS2150 10.3 | Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials. | Visual Inspection | Prior to commencing paving | WP | Asphalt Supervisor | Completed ITP |  |  | Insert Text Box for Team Binder Approval Number
2.4 | Ambient Conditions for Placing | 407.17 | The majority of the surface area to be paved has a temperature greater than or equal to the following: Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600 Wearing Courses: 10°C for conventional binders or 15°C for PMBs Where the above temperatures cannot be achieved, asphalt must be laid under the "Fulton Hogan Cold Weather Paving Plan" | Infrared Thermometer | Prior to commencing Paving | IP | Asphalt Supervisor | Completed ITP |  |  | Insert Text Box for Team Binder Approval Number
2.5 | Planning of Joints | 407.21 | Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints for the final Wearing Course are located on lane lines Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines.Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm. At the wearing surface where the new and existing pavement join, a hot applied bituminous crack sealant shall be applied. | Measure and mark out runs by tape measure or survey | Prior to commencing paving | WP | PE FHC | Completed ITP
2.6 | Tack Coat | 407.19 AS2150 11 | Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2. This rate is to be doubled on joints and chases. Tack coat must be allowed to fully cure . NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces Photographical evidence must be obtained (with an identifiable landmark) *from 1st July 2023, "trackless Tack Coat" must be used | Spray area and inspect | Prior to Commencing paving | IP | Asphalt Foreman | Completed ITP
2.7 | Submission of Primer Material documents (if applicable) | 408.08 c, e | The primer shall be cutback bitumen complying with the requirements of clause 408.08(c) and shall be water resistant, of uniform appearance and capable of providing a strong bond between the bituminous surfacing and the pavement. | Document Review | Prior to commencing works | HP* | Site Engineer/Project Engineer | Conformance Certificate uploaded to TeamBinder | NA | N/A | Insert Text Box for Team Binder Approval Number
2.8 | Application Rates for Primer (if applicable) | 408.13 a | At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent | Document Review | Prior to commencing works | HP | Site Engineer, NA | Application Rates uploaded to TeamBinder | NA | N/A | Insert Text Box for Team Binder Approval Number
3 | Asphalt Placement Works
3.1 | Commencement of placing | 407.23 | The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority. | Visual Inspection | Prior to Commencing paving | HP | Asphalt Supervisor / Superintendent | Completed ITP
3.2 | Delivery of Mix | Pavement Design Details 407.20 | The majority of the surface area to be paved has a temperature greater than or equal to the following: Base & intermediate courses: 5ºC for conventional binders or 10ºC for PMBs & Class 600 Wearing Course: 10ºC for conventional binders or 15ºC for PMBs Where the above temperatures cannot be achieved , asphalt must be laid under the "Fulton Hogan Cold Weather Placement Management Plan" | Check aspahlt delivery docket | Each lot | IP | Asphalt Foreman | Completed ITP
3.3 | Delivery of Mix | 407.11 Table 407.111 | Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C. | Visual Inspection & Delivery Docket | Each load | WP | Asphalt Foreman | Completed ITP
3.4 | Traceability | Fulton Hogan Quality Plan | Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer | Measure and Record on Daily Lot Record | Each lot | IP | Fulton Hogan Foreman/ Engineer | Completed ITP
3.5 | Layer Thickness and Level Control | Pavement Design Details 407.25(a),(b) | Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications | Dips using ruler or dip stick | Regularly during paving | WP | Asphalt Foreman | Completed ITP
3.6 | Spreading and Paver Stoppages | 407.25 © | All asphalt shall be spread with a purpose designed asphalt paving machine to form a uniformly smooth asphalt mat complying with the requirements of Clause 407.29 without segregation, tearing or gouging. In areas that are not accessible by a paver placement of asphalt by other means is permitted. The width of a single paving run shall not exceed 6 metres unless paving in echelon is proposed or procedures are in place to ensure that a uniform asphalt layer free of segregation can be achieved. The Contractor shall conduct spreading operations to ensure that the paver speed matches the rate of supply so that stoppages are minimised. If the paver is required to stop and asphalt in front of the screed cools to below 120C, a transverse joint shall be constructed. For asphalt work carried out on a road to be opened for traffic at the completion of work each day, each layer of asphalt shall cover the full width of the trafficked area. The requirements of Clause 407.21(f) shall be followed in respect of the treatment required for exposed edges. | Thermometer | If paver stops | WP | Asphalt Foreman | Completed ITP
3.7 | Surface Finish of Wearing Course | 407.29 (a) (i) | The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks | Visual Inspection | During paving and after final roll | WP | Asphalt Foreman | Completed ITP
3.8 | Kerb and Channel | 407.29 (a)(ii) | The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified | Visual Inspection & Measurement | During paving and after final roll | WP | Asphalt Foreman | Completed ITP
3.9 | Shape | 407.29 (a)(iii) | No point on the finished surface of the wearing course shall lie more than 4 mm below a 3 m straight edge laid either parallel to the centreline of the pavement or, except on crowned sections, at right angles to the centreline. For intermediate and base course layers, the distance below the straight edge shall not exceed 6 mm and 10 mm respectively. | Visual Inspection & Measurement | During paving and after final roll | WP | Asphalt Foreman | Completed ITP
3.1 | Alignment | 407.29 (a)(iv) | Where asphalt pavement is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside, the designed offset from centreline or design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25 mm in 10 m. | Visual Inspection & Measurement | During paving and after final roll | WP | Asphalt Foreman | Completed ITP
3.11 | Width | 407.29 (a)(v) | Where asphalt pavement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50 mm or greater than the design or specified width by more than 100 mm. The average width over any 300 m shall not be less than the design or specified width. | Visual Inspection & Measurement | During paving and after final roll | WP | Asphalt Foreman | Completed ITP
3.12 | Trafficking pavement after placment | 407.28, 404.14 | Trafficking or placement of asphalt over previously constructed layers is not permitted unless the majority of the previously constructed asphalt has a surface temperature of 50°C or less and Falling. | Visual Inspection & Thermometert | After final Roll | HP | Asphalt Foreman | Completed ITP
4 | Testing
4.1 | Compaction Testing (Open Graded Apshalt) | 417.12 | Accpetance of compaction shall be on a procedural basis | OGA/SMA Compaction Procedure | Per lot | TP | Fulton Hogan Laboratory Technician | Completed ITP
4.2 | Compaction Testing (Stone Mastic Apshalt) | 404.15, 404.14 OGA/SMA Compaction Procedure | Per lot, the Characteristic Density Ratio must meet the minimum limit of 96.0% For layers thinner than 25mm, accpetance may be on a procedural basis | Nuclear Density Test, OGA/SMA Compaction Procedure | Per lot | TP | Fulton Hogan Laboratory Technician | Completed ITP, Compaction reports
4.3 | Compaction Testing (Dense Graded Apshalt) | Section 407.27(a),(c.) 407, Section 173, Dense Graded Compaction Procedure | Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits: >50mm layer depth = 96.0% <50mm layer depth = 95.0% Additional Test must be undertaken on the longitudinal joints for wearing courses Test Lots 50m2-500m2, may be treated as a small area,in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0% Test Lots <50m2, compaction for all lots shall be accepted on a procedural basis Mix Types where total contract supply <300t, compaction for all lots shall be accepted on a procedural basis | Nuclear Density Test, DGA Compaction Procedure | Per Lot | TP | Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer | Completed ITP, Compaction rerports
4.4 | Level Conformance | 407.30, 407.29 | The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.30 (b) | Survey Results | Each Lot | WP | Surveyor | Completed ITP, Survey Conformance Results
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /