## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-050-CPD-RAIL-Calder Park-OHLE Installation | itp |  |  |  | Yes | ITP-050-CPD-RAIL-Calder Park-OHLE Installation - Rev 1 | 0d16b7a4-af42-4318-ab53-e8c45b46cb72
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | b7df6a49-54d7-57cf-921e-fb4555682e76 |  | note | Document Title: ITP-CPD-RAIL-Calder Park-OHLE Installation
label | 7fe286bd-4b9c-5eed-b7d2-ddf3c07f550e |  | note | ITP Description: OHLE Installation
label | bbab5c57-2d08-5c1f-828e-0366de5e1730 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 1dcd54fc-d22b-5a20-85ad-abb2ffeadd4b |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | 7926b4ef-e200-52d4-9c92-3845f9bb1ae8 |  | note | Revision Number: 1
label | d90ed7af-faed-5a1e-810c-ce1c3f61f380 |  | note | Revision Date: 24/07/2023
label | 2f11af77-9018-55f6-b9f5-8f2491537e2c |  | note | ITP created by: Kevin Liang
checkpoint-status |  |  | checkpoint | 1.1 - Overhead Line Electrification
label | 775a0b1e-c92a-513d-9a77-f92d7b520c11 |  | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
checkpoint-status |  |  | checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | e7953282-822e-5327-9fbd-3c2884ce06a7 |  | note | Reference - VRIOGS 001 AS 4100
checkpoint-status |  |  | checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
label | b705f63d-129d-5cad-8efb-461cd91b2213 |  | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1
checkpoint-status |  |  | checkpoint | 1.4 - Fabrication of Steelwork
label | 5c16f59e-2a3b-5d51-873f-cf6afd16d0bc |  | note | Reference - VicRoads Section 630 January 2023
checkpoint-status |  |  | checkpoint | 1.5 - Electrical Networks Standard Electrical Networks Principles and Performance
label | 08177b38-c8cf-564c-892c-bd6d722802ea |  | note | Reference - Structural Steel Work - Fabrication and Erection
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Structural Steel Components and Fasteners
label | 029dfd34-b50a-569f-a7cd-05f7c012e070 |  | note | Reference - IFC Drawings
label | 5632fa21-5519-5876-998d-8751084f31b6 |  | note | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | ab2345a8-6516-54e6-927f-7934525af411 |  | note | • Typically this consists of but not limited to:
label | 635ba4f0-5ea2-5762-a404-ab1e43c40894 |  | note | i. Completed fabrication ITP
label | 5e5ca6e7-c2eb-5bb9-9ecb-319799692cee |  | note | ii. Weld Procedure Specifications
label | 0a69420e-903a-51f9-9178-36c66a3e19d4 |  | note | iii. Weld Procedure Qualifications
label | 9ecffd6c-7482-5b95-b1fe-28a0b367cd9b |  | note | iv. Welder Qualifications
label | f946d9d7-1ec7-597f-87f5-9eac157dae47 |  | note | v. Material Certificates
label | e01955a7-113e-5b4f-a2c4-291b7bf8d187 |  | note | vi. Coating certificate(s)
label | 0dad601c-c8f7-5d83-8421-091e4e82ce80 |  | note | vii. Non-destructive Testing (NDT) Reports (if any)
label | 9d0c5e70-dde3-56d2-90bb-f5c85dd3a178 |  | note | viii. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | 749f4d78-0637-5bb4-963b-bf4857d9a10e |  | note | • Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
label | 8d4ebc6c-440e-5fb9-b3db-b63033213f51 |  | note | • Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252.
label | 20560b8d-5917-5ca1-814e-88d6f183e0ad |  | note | • All bolts nuts and washers are hot-dipped galvanized.
label | c8a61a7e-4572-5ff6-a50a-133136a4be54 |  | note | Collate: Structural Steel Quality Assurance Documentation.
label | 8a7df7f4-f2a1-57fe-a976-9a46b57545e4 |  | note | Attach: Collated QA documents in ConQA
label | 05f6388b-487f-5e03-a925-85fb9d5cc326 |  | note | Method - Document review
label | dfbcf741-d246-529e-8a59-0380af6f5546 |  | note | Frequency - Where applicable/ Each element
label | faf9a59f-2fce-54a9-9522-9adafb711d4b |  | note | Category - HP
label | 133b2be5-8601-5b00-8896-3244d9565109 |  | note | Responsibility - PE
label | ee4ef774-5114-53de-a293-a92c6e939b68 |  | note | Responsible person - MRPA Engineer
label | a673634f-12f3-57f7-aee0-baf4dd58a2fc |  | note | Verifying Documents - This ITP Signed Off
text | 21797d05-10e4-56c3-b344-a68dde6480e0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Bolted Connections Using Direct Tension Indicators (DTIs)
label | 698738ba-468a-5f98-9679-f91e263f6116 |  | note | Reference - AS4100 Clause 15.2.5.3 (a), AS5131 Clause 8.5.7 (a)
label | 5e8fdc3a-377a-50ea-8157-0db5c8c753d9 |  | note | Acceptance Criteria - Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
label | 0c423b1e-6833-500d-a588-0d17bef07db7 |  | note | i. technical data sheet or information on the product
label | acd47a5e-a2f0-513e-b729-ff4a033bde82 |  | note | Method - Document Review
label | f2f07875-8fb1-531f-a95b-ae21b656d50d |  | note | Frequency - Where applicable/ Each element
label | 47e25988-cd98-57a2-b86e-48ef806931dd |  | note | Category - HP
label | 1227b6f1-fad6-5d05-ae58-c2547960b6c7 |  | note | Responsibility - PE
label | 5300020b-6bec-5ce4-89b3-78238718ec4f |  | note | Responsible person - MRPA Engineer
label | d795bd97-50e2-5afc-8636-77e048c4e6cf |  | note | Verifying Documents - This ITP Signed Off
text | f2fc33fd-12f0-514c-b017-98cfec7cce33 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Overhead Wiring Small Parts Steel and conductor wires
label | 16162b97-9eac-5ebd-8b10-8d8db1f30b51 |  | note | Reference - Relevant MTM Standard Drawings
label | f38b1f7b-8983-5daa-a886-8ffe59c0d1b3 |  | note | Acceptance Criteria - Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings.
label | 12368912-23c3-58fd-878e-7137edfb4868 |  | note | • Deliveries are to be inspected to match the purchase order
label | 91f21825-3a45-5a2c-b9c3-8e9ff3a684da |  | note | Attach: Purchase order/Delivery dockets/Certificate of conformity
label | b51576b3-0083-57d3-a4da-f1a0f37b67c4 |  | note | Method - Visual Inspection and measurement
label | 6f2fe054-11a6-5da6-8f05-c271329b8ddc |  | note | Frequency - Upon delivery
label | 9a9ae8cf-589b-527f-9f82-463adc2b871a |  | note | Category - IP
label | 3b5d102a-2a2d-550c-89b5-c9d88bc5d296 |  | note | Responsibility - PE
label | d2b4931d-222f-5c52-9b6a-52185b512e35 |  | note | Responsible person - MRPA
label | 5f9347ac-56b2-541f-989b-490e654de5d7 |  | note | Verifying Documents - This ITP Signed Off
text | ed8f0551-649b-510d-85a0-4a0477377ce9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Grout
label | 16af3265-c4ba-5307-8917-132b741b0650 |  | note | Reference - IFC drawings
label | 63fef92b-a720-5223-ba1e-24d604d9459c |  | note | Acceptance Criteria - All grout under base plates shall be CONBEXTRA C or equivalent as approved. Approved grout to be Flowable shrinkage compensated with minimum 50 Mpa compressive strength.
text | 736c1915-f532-50df-bace-8e911ed4e1b1 |  | textbox | Enter: Teambinder Material Approval number
label | 80c87a6b-04aa-5906-bb55-0e4dd31f45fb |  | note | Method - Document Review
label | 4e488029-e58f-511c-bc6d-9ce332d0a827 |  | note | Frequency - Where applicable/ Each element
label | e904aa7f-86e1-5c81-af4e-c2b3a4e92814 |  | note | Category - HP
label | 79af41c1-3775-575d-9146-48753e39c0ea |  | note | Responsibility - PE
label | 5bd590e0-a147-5589-8269-588e9d8d9187 |  | note | Responsible person - MRPA
label | 9cff3a7f-18d9-51b3-bad7-9fa4afaefd4c |  | note | Verifying Documents - This ITP/Material Approval
text | 5349b714-ce56-5515-a8c6-38c47f49cf75 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Installation Methodology & Works Method Statement
label | c6587f6a-a357-5edf-bde9-03b72fe60ccf |  | note | Reference - AS5131 Clause 11.2.3
label | 8df0a5dc-e910-5e44-a3f4-ce954288e1e6 |  | note | Acceptance Criteria - Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
label | 226c4203-33a4-5c22-875c-72287ce67144 |  | note | – Transported to site;
label | 035476c6-c2c0-5c61-a1ec-9294a0c7b031 |  | note | – Handled on site;
label | bfebf7ee-1afe-56cb-866e-a4a3a8aa94d2 |  | note | – Installation Procedure (subcontracor ITP's);
label | 87fb6b1a-d92c-5a3d-ab47-96a69d25180d |  | note | Submission of Work Package Plan and MRPA approval and acceptance.
text | bb7ce7a4-5cb9-580e-a381-3e0c0969a9d5 |  | textbox | Enter: WAP number
label | 67879b4c-cc69-51ef-b074-21e640d73b84 |  | note | Method - Document Review
label | fe395e54-c5cb-5e85-ab45-dc862e65cd87 |  | note | Frequency - Prior to Works Start
label | 06bb3c0d-0308-506b-88b1-f70b645b233b |  | note | Category - HP
label | 03578780-31fd-523c-9d11-3f9c16e4d1e5 |  | note | Responsibility - MRPA/CAT5
label | afe8ccae-6cb9-5bc8-a904-ee1905908194 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 3500f4d0-88ed-5646-936a-5daa2484e8c0 |  | note | Verifying Documents - This ITP Signed Off
text | c8c4e938-babd-5ad7-b897-66c4bd018026 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Approval of IFC drawings
label | 368e71de-5229-5aac-9a5d-dff973d76941 |  | note | Reference - Contractor Design Management procedure.
label | 7455b354-e835-57d9-8785-a417392ab4dd |  | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
label | 9d83171d-72ba-51bf-80ad-71c1a3479543 |  | note | Method - Document/Drawings Review
label | c8117857-4586-536a-b053-7499a310d477 |  | note | Frequency - Prior to Works and at regular intervals.
label | 6606ad9b-2ba4-5d58-a610-c60c577db098 |  | note | Category - HP
label | 8900b961-9aa2-5f2a-9ad4-34a0d13e74ae |  | note | Responsibility - MRPA/CAT5
label | 3bdf8cd2-edcf-5538-81c2-7889f14f4cd7 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 8e5d91ff-6f63-5be4-adfc-457d932b6f3d |  | note | Verifying Documents - This ITP Signed Off
text | 880c9916-b058-5360-a555-0431c8be69c4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Cantilever assembled.
label | b850281a-3bc0-54a2-8a57-5e8c4546fb6b |  | note | Reference - Cantilever assembled as per IFC design.
label | 0618ae21-d518-56d9-8955-1b2a1b8b1ec1 |  | note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | 4a1f8606-369c-52a3-9f59-208154f61410 |  | note | Method - Visual, Document Review
label | 68669a8b-cee3-5b90-9d21-7f142c2b6857 |  | note | Frequency - Each Task prior to works start.
label | 6a92ed3f-c499-583e-8d0d-5d3a4f3453e5 |  | note | Category - IP
label | d3fad57c-002a-522c-b4c4-3e028e709cfa |  | note | Responsibility - CAT5/MRPA
label | 699579d4-0032-555f-8f81-2b8dcd88b034 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 003bc675-31a9-5700-b3ea-13ad08a6ce08 |  | note | Verifying Documents - This ITP Signed Off
text | 1925b685-0a9a-5940-8e82-12e40e52d9dd |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Mast Installation
label | d7fa4e75-f469-5ebc-81f4-87706b0cc63e |  | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | 4bd483c3-e3c9-5aca-b9d8-be3ce2ec148b |  | note | Acceptance Criteria - Work instructions in accordance to IFC design
label | 164f2b7b-93c7-56eb-b74c-aae44483a219 |  | note | Method - Measure, Visual
label | 55954879-c213-5dc8-8484-8997d9c968bf |  | note | Frequency - Each OHLE Structure
label | e5c5d5e6-12cd-50e0-b9aa-dae80c849b46 |  | note | Category - IP
label | 90803712-af54-5e9a-9960-b619c0bafdb0 |  | note | Responsibility - CAT5/MRPA
label | bae94ef2-b026-5f87-b2c8-709d4f3d0e58 |  | note | Responsible person - MRPA/CAT5 Engineer
label | e3944dd8-bddc-5fba-80ad-a08a8389b0bb |  | note | Verifying Documents - This ITP Signed Off
text | 185e3853-3b16-5fd8-8036-33e82070735c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Cantilever installed.
label | 72916c76-b4c0-5610-a03e-d6a497b0b3db |  | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | 2937d25a-6369-5345-a242-76e5efca9317 |  | note | Acceptance Criteria - Work instructions in accordance to IFC design
label | ae493b9b-a16c-5eeb-b0ec-f310510fd231 |  | note | Method - Measure, Visual
label | 8da15e91-9ceb-5b6c-9b7a-ffd9363377b1 |  | note | Frequency - Each OHLE Structure
label | 270fe969-e7d3-52be-99f0-ae19c188da46 |  | note | Category - IP
label | 1191c96f-1b99-59b5-90b9-72d440521b2e |  | note | Responsibility - CAT5/MRPA
label | 1a171ecb-2900-52a9-b704-33364a87b3cc |  | note | Responsible person - MRPA/CAT5 Engineer
label | a4619230-92ba-56a6-b7c6-2ee082f5dd14 |  | note | Verifying Documents - This ITP Signed Off
text | e876fabf-0620-57d8-b177-a3d4ef33efc5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Bearing type Joints TB Friction type joints TF
label | 5423b22f-52ba-53d2-855f-ac5ee8aaa96a |  | note | Reference - IFC Drawings
label | 573fad50-0d61-5bd4-8258-b4262d7dbe57 |  | note | Acceptance Criteria - BOLTS DESIGNATED TB & TF ARE TENSIONED AS PER AS 5131 and Table 8.5.6
label | 9fa1d3e7-495f-5740-a080-a6deff8bcd6c |  | note | – Bolt mark ups (in case of partial tensionening) should be visible for inspection
label | 6addbb4c-2134-58ac-928c-3d5aebcafda8 |  | note | – DTI squirts are to be visible for inspection
label | 6f02c5d0-2904-58ad-b685-2f8427d4d845 |  | note | Method - Visual
label | 8c6997de-b5dc-54e1-ab9f-968e9aeedf3c |  | note | Frequency - Where applicable/Each element
label | 93083ea4-055a-5c8f-90a3-f64fd557388b |  | note | Category - IP
label | 6ab03fce-e0d3-5242-848d-0cae03130dd4 |  | note | Responsibility - PE
label | 43fc32e5-896d-5442-a921-a59c2152e505 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 882665a2-68be-5e5c-9925-f66895636292 |  | note | Verifying Documents - This ITP Signed Off
text | 289b128e-cc79-5baf-9560-c4dbd08ea339 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Install SPS to correct height / position relative to track
label | 98eeb97b-55c3-5e5d-a63d-6f74b05346de |  | note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | d49bc80d-a8fa-5fc6-b0a3-891f4f7cc8ea |  | note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
label | ffc8eb28-0fe8-5436-938a-16daafa0a6ce |  | note | Method - Measure, Visual
label | a0e53f07-4bc6-56f8-82d8-38d6cea891c1 |  | note | Frequency - Each OHLE Structure
label | 89afd2e7-b989-53bd-822b-ae8eb97c176b |  | note | Category - IP
label | 4142806a-586a-553d-aa0c-3817ec479052 |  | note | Responsibility - CAT5/MRPA
label | 5342fb19-ee01-5b87-b0e5-ecf2b262b8c1 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 12cdb7dc-6e9d-5c57-a4f4-f747226f1b76 |  | note | Verifying Documents - This ITP Signed Off
text | caf7854a-3ef9-5e58-a8b0-cb96905f317e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Cantilever checked once installed.
label | 1d1e9baf-cf72-5ac7-acf9-689f4fffc6f4 |  | note | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet. CAT5/OHLE/CHK002
label | 60910551-84f1-5a67-a641-fbfd061eeb36 |  | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
label | aa35198b-efd7-508a-9532-0bb25081ff9f |  | note | Method - Measure, Visual
label | 5e068f40-e647-5429-a91a-afee2528e43c |  | note | Frequency - Each OHLE Structure
label | 175d8d21-7874-5005-b2f4-5907c7e057b1 |  | note | Category - IP
label | 5753d68e-1701-5c40-9c46-9660f5652712 |  | note | Responsibility - CAT5/MRPA
label | 072c91cc-ca8f-5d0d-b286-5216c49eafbf |  | note | Responsible person - MRPA/CAT5 Engineer
label | 8793ebca-4e73-544b-b07b-cf2a834632ba |  | note | Verifying Documents - This ITP Signed Off
text | 63ab84da-706f-55f9-91cf-a26a1003da38 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Base Plate Grout
label | 03cede83-307e-56ad-8ccf-75b63c65f8c2 |  | note | Reference - IFC Drawings
label | 9e171f96-5e9b-52a7-9b63-eb78f777b9a7 |  | note | Acceptance Criteria - Grout to be mixed as per manufacturer TDS.
label | aaf273a0-14bf-5430-8ddb-307cdbc70e28 |  | note | • Grout to be poured under base plate as per IFC drawings. Grout over pour is to be 6mm and cover area with Nom 50mm offset around the base plate.
label | c97fb2f9-f1df-5eb1-9535-cc73fd2225bf |  | note | Method - Visual
label | 8acb541d-f163-5920-88c8-7a8805e98d69 |  | note | Frequency - Where applicable/ Each element
label | e39559b0-e518-5720-b2c4-ef1288522170 |  | note | Category - IP
label | 7e36eb3f-15f3-5eda-9284-b2aa411ca2b9 |  | note | Responsibility - PE
label | 16d8ecfa-b5c2-5654-af1c-891dca27e6dd |  | note | Responsible person - MRPA/CAT5 Engineer
label | 4c091ce7-10b6-5890-be1e-a8c42a0232ce |  | note | Verifying Documents - This ITP Signed Off
text | 493d12cd-88c9-5e3d-9fce-7add77cfe733 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Installation of wire supports at the correct height and stagger
label | 539adbc3-dcf4-55ee-be2a-325571885060 |  | note | Reference - Install as per design
label | f69c7e4a-89e9-5854-ab64-106f8e7445fa |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | e99b72a1-7ad6-549f-b16f-04a4876f67a6 |  | note | Method - Visual
label | 36980f2f-bc58-5250-8346-3504777c7855 |  | note | Frequency - Each OHLE BWA Structure
label | d94c9af4-dddd-5192-b51a-c0dda5f3283b |  | note | Category - IP
label | 6845e37e-314d-563a-8c8f-5f225055964c |  | note | Responsibility - CAT5/MRPA
label | f6ed7c85-c1e6-5534-b7fb-cf5e6abc171f |  | note | Responsible person - MRPA/CAT5 Engineer
label | 7459bd7c-eabb-575a-85ca-b5fac33eac47 |  | note | Verifying Documents - This ITP Signed Off
text | cf0923e4-7127-5b39-9d22-5097963929dc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Install to correct tension
label | 782f3c8c-be77-5b78-9018-6e8e58a79fe2 |  | note | Reference - Install as per design
label | 7669bb2b-579d-580c-a199-73394edd8584 |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | 98b9bbde-42c8-52a4-9dea-ac8ce0e49df3 |  | note | Method - Visual
label | 34e054d9-fb74-5655-a983-e1f4d20bfc62 |  | note | Frequency - Prior termination
label | 113a1880-5aaa-58e0-90ee-c47659cf4bdb |  | note | Category - IP
label | ad11b4f3-8db6-5730-8b1e-3d67c693489b |  | note | Responsibility - CAT5/MRPA
label | 26b458b2-78e9-5eb0-bf17-88fdfcf6f51d |  | note | Responsible person - MRPA/CAT5 Engineer
label | da636222-c2a3-57bb-ad69-2fd8c2f56435 |  | note | Verifying Documents - This ITP Signed Off
text | 6570bee7-7c2e-5dc3-9ef9-186528384b97 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Defects/Temporary Works
label | b7fdcbb1-c935-54f3-9e03-139089ec12bc |  | note | Reference - IFC wiring layouts, cross sections and design drawings.
label | a331a43b-777a-5c6f-9fa7-0d269661b744 |  | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
label | 71d61591-7fe3-552f-9bc5-f2414166c90a |  | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
label | 7a67192f-51df-512a-a193-dd0c62120e27 |  | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | 8a1da561-485a-532b-a3ce-0ea94ea5000a |  | note | Method - Document Review, Visual
label | a9eca315-b848-5ef5-af84-69891bc8424e |  | note | Frequency - Each OHLE Structure
label | 4a478cd6-a6ab-5d50-b011-52df20e93f48 |  | note | Category - IP
label | 82272085-0e5c-5298-b092-111f410bc0d1 |  | note | Responsibility - CAT5/MRPA
label | bb855b39-aee0-59ad-841f-ef4a5e4f0924 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 1c15292f-aa0f-5156-b2e6-a69ec820e23c |  | note | Verifying Documents - This ITP Signed Off
text | d99ccbce-7b98-5cf4-903f-72a867c542a4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
label | a67cccf8-2a0d-5571-bd79-8cbf5c1980f8 |  | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
label | eb4f5970-6170-542c-be3b-03bfd0571f48 |  | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
label | 21dd5b86-030d-5d7e-926c-fe2a023f4d73 |  | note | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
label | a3c24381-e773-5a9f-89e3-7135dd09e59d |  | note | Method - Document Review, Visual
label | 12870edc-9409-5622-a011-eec68ce26af3 |  | note | Frequency - Each OHLE Structure
label | 1a3336ce-fb6f-5921-a6a9-ca628ac26423 |  | note | Category - IP
label | 41378d87-fec4-52bd-9b0f-47dc5501dff3 |  | note | Responsibility - CAT5/MRPA
label | 11adcea8-0168-568f-9074-00f930ead2b7 |  | note | Responsible person - MRPA/CAT5 Engineer
label | f0f70156-0135-5099-a9f5-c407ef1af77c |  | note | Verifying Documents - This ITP Signed Off
text | 0927b0a2-775a-5e13-91e3-c79ea5f94406 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | e55c9aba-0ac2-5905-9535-e7e494f72dbe |  | note | Reference - MTM Quality Management Plan
label | 208b0531-628b-532b-b163-79daa7369fd7 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | e091dedd-d16b-585a-9122-05ae465f02c3 |  | note | Method - Document Review
label | 85031bd7-60d9-5ae9-92ea-6eb70c964bff |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 4552a864-685b-546a-8df6-0e34156576c4 |  | note | Category - HP
label | 8ca1cd12-9e96-558b-a39c-f36f5f68b8ce |  | note | Responsibility - CAT5/MRPA
label | 7e7f0af0-24f5-5303-9d15-2cba98f82752 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 5fad917a-8b9f-56eb-b182-59cd7ce74386 |  | note | Verifying Documents - This ITP Signed Off
text | aadf3dfc-60a4-545a-b43b-9fb73f545a9b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | a8f47ae1-9e40-58c8-9e85-fffeff467ee2 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 2230d07b-e89a-59a5-a6b2-64156b49655c |  | textbox | Name:
text | 8a49cbd4-0edf-5503-9a02-a05e2b7fe0da |  | textbox | Position:
text | 34f1fedc-b615-5efb-b162-42491ff8e638 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation | itp |  |  |  | Yes | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | 1c13b79f-05b4-4abd-b61f-9be7a4ee36b9
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 54cbbd25-0217-5f93-8c04-32ab25705d02 |  | note | Document Title: ITP-048-CIV-Calder - Stormwater Drainage Supply & Installation
label | 42c73e1f-b4fe-5e17-a4e6-fe786d9930e6 |  | note | ITP Description: Stormwater Drainage Supply & Installation
label | 1072443b-4ce6-5d29-99dd-1e5558e3eec9 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 97538d00-08c4-5a58-9b5e-371d88c3ab2b |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 0b1049cc-c86a-56cf-a523-601b79eabb9d |  | note | Revision Number: 0
label | c5684dc8-88cd-5f91-a657-01aa964aac1f |  | note | Revision Date: 19/07/2023
label | 2c42a650-f171-5637-9c8a-f3c8221f848a |  | note | ITP created by: Ethan Caruana Smith
label | 3a4fd5a2-f344-530b-8cff-3ad6650804a5 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 049d257f-d67a-5254-9e87-432b7942d94f |  | note | Reference - VicRoads Section 701 (May 2020)
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 1373b251-3ace-5e65-b601-89dd12746253 |  | note | Reference - VicRoads Section 705 (June 2021)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 290abb78-b920-58d1-882c-07f26b057f92 |  | note | Reference - IFC Drawings - package 13
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Drainage Reinforced Concrete Pipes (RCP)
label | 5133ef34-9f0e-5f1c-a55a-73ea66b52c6f |  | note | Reference - Section 701.04, Section 701.05, Section 701.09
label | 60fa969a-ef98-52e5-badc-796c6863f8f3 |  | note | Acceptance Criteria - Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and Sections 701.05 & 701.09
label | 1d9b6d4d-27f2-5f39-b007-284f3632a292 |  | note | • Precast reinforced concrete box culverts shall comply with the requirements of Section 701.04
label | 04545dc0-1ab0-591f-8f08-70a29a845bb5 |  | note | • Rubber ring joints shall comply with the requirements of AS 1646
text | 38bbd1f4-2d65-5143-a9b1-6247293e3f6f |  | textbox | Enter: Teambinder Material Approval number
label | 93b9fe18-2b6f-5666-a865-555cefa2e92c |  | note | Method - Document Review
label | d79391aa-d611-5d18-aaa6-c67571466739 |  | note | Frequency - Each lot
label | 594117ee-77f5-5ab2-bb85-e26d59148d12 |  | note | Category - HP
label | bf3f0b6e-d05d-5464-8cf9-3c441e8eaa6e |  | note | Responsibility - Nominated Authority
label | 4878f0ce-de8f-51a7-82a5-2415a004563d |  | note | Verifying Documents - Teambinder Material Approval
text | 769d6910-4e6b-5e3d-a923-aa280010a925 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Drainage Flexible Pipes
label | 2719ec57-48eb-52f2-bf32-78fbf41e4fec |  | note | Reference - Section 701.08
label | 54afc51d-7959-5eca-a6ca-cee0aada02ec |  | note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
text | 1893723f-e63d-5060-b679-921de47f50ee |  | textbox | Enter: Teambinder Material Approval number
label | 5ad4e039-2896-55b3-8b69-ba5ce5ccb4d8 |  | note | Method - Document Review
label | 28c02fcd-976e-5151-b77e-bc0f9325dffb |  | note | Frequency - Each lot
label | a488a7ae-65cf-59ac-aa33-b0dcf57394c9 |  | note | Category - HP
label | cf212d1a-bc40-53da-b07b-9a464ca7db40 |  | note | Responsibility - Nominated Authority
label | 50a55385-8b8e-5017-90fc-cc6b36b4393b |  | note | Verifying Documents - Teambinder Material Approval
text | dfe786c1-a388-5026-97c3-63068e294d77 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Precast Drainage Pit
label | f0d33795-6cf4-5e2c-89b2-cb962804e517 |  | note | Reference - Section 705.07, Section 705.04, Section 705.09
label | 4259a9fd-ffa0-506a-b45d-85fb802bb345 |  | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
label | 0fbdbc27-1134-5b87-83d7-3d91964e65f6 |  | note | • All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
text | 5ff9ae96-528a-53c9-8c59-720be22cbb93 |  | textbox | Enter: Teambinder Material Approval number
label | 83dae22d-3dd4-539c-8ad9-b87f915e213b |  | note | Method - Document Review
label | b05605b5-c370-548e-a9bd-8a5b67ae4d42 |  | note | Frequency - Each lot
label | 9862f83a-a3a7-5540-ad14-a1b7d1b9ce5b |  | note | Category - HP
label | ce3276fb-1124-57dc-973d-69937c3ceade |  | note | Responsibility - Nominated Authority
label | 254f27fc-ce7e-51b3-b351-efb9371d71a8 |  | note | Verifying Documents - Teambinder Material Approval
text | 6deee45d-38ca-55a0-9dd0-bafda30155c6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Cast in Place Drainage Pit
label | b0c6263a-4906-5eeb-bed0-6a05159afefb |  | note | Reference - Section 705.06 IFC Drawings
label | 4c574fbf-66de-5d27-adc5-9762d785a5ce |  | note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | 7356e754-fcfb-5158-b07d-ab82d4f69446 |  | note | Method - Document Review
label | c8012b05-25d5-55fc-a331-524090c05bca |  | note | Frequency - Each lot
label | 2cd6f092-3b20-573f-8a36-6f31eb417ee7 |  | note | Category - HP
label | 1552e327-2f0f-5c95-8180-dd0104a1610f |  | note | Responsibility - Nominated Authority
label | 8583b9f9-0559-5e0c-9103-743cc4278ea2 |  | note | Verifying Documents - Teambinder Material Approval
text | adb3fb5f-7143-5e51-a951-971fe87f493f |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Drainage Pit - Step Irons
label | de1765f1-a411-599f-ab5a-14b9678c3e3a |  | note | Reference - Section 705.04, Section 705.12
label | 3e26662e-84bf-510e-b3f6-d42424d71596 |  | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | bee12f83-908c-5b48-82cd-93c14abc4787 |  | note | • Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
text | ba8abbd4-9dc4-55f9-80ee-e47b2f3f5d49 |  | textbox | Enter: Teambinder Material Approval number
label | 99b5df9e-9c16-547b-8db6-0e7acb88655f |  | note | Method - Document Review
label | 6272a703-8f4d-5f92-a46f-463b35b49417 |  | note | Frequency - Each lot
label | df43af24-e5f9-578b-a8d3-ea92460ea8a4 |  | note | Category - HP
label | 022e485b-8cd8-5a48-bfcd-facc399c0a54 |  | note | Responsibility - Nominated Authority
label | 0177011a-dcb4-5593-9ecf-79e631c2132f |  | note | Verifying Documents - Teambinder Material Approval
text | e7f9e350-cb0a-507b-870f-3d7359d1e940 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Drainage Bedding Material
label | 92e4115c-4958-5781-b554-bf6a0f20ebc2 |  | note | Reference - Section 701.09
label | 424a6ae9-cf56-542a-a746-425541df9ac4 |  | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | b7242711-1be5-5a69-a5ac-d51aae795379 |  | textbox | Enter: Teambinder Material Approval number
label | 8d2e688d-6ca9-52a8-88f4-53fe73f2d64f |  | note | Method - Document Review
label | a0500e5d-b26a-544a-99ad-58f9d349ad7c |  | note | Frequency - Each lot
label | a2331930-1dea-5021-a18b-54000a2ea669 |  | note | Category - HP
label | 8d52516d-7bc1-5423-9d05-8301e55b1d82 |  | note | Responsibility - Nominated Authority
label | 66026fc8-7e6c-56ba-be5c-c1ebfc74f4e0 |  | note | Verifying Documents - Teambinder Material Approval
text | df192745-9d6d-55fc-a48f-006c81689cff |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Drainage Backfill Material
label | a5660455-5648-51f1-b7fb-301f2a5deba1 |  | note | Reference - Section 701.09, Section 701.19
label | eb8c7bb1-a2ea-5db9-a7ec-0c8b9eaecb67 |  | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
label | e757e716-dab5-5cd7-895a-67df1ae343c8 |  | note | • Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
text | 61bf1fb8-75bd-5da6-8e72-349d8471ce1d |  | textbox | Enter: Teambinder Material Approval number
label | 864c98a8-82bb-565f-a93e-7b180f524d1c |  | note | Method - Document Review
label | 22480f11-8375-57bb-852a-5c1c1528c943 |  | note | Frequency - Each lot
label | 7b9585be-690d-5fb7-b91a-397f553be0af |  | note | Category - HP
label | 5f601394-7c21-52f9-8574-5e16fd000b39 |  | note | Responsibility - Nominated Authority
label | 16fe453e-e1eb-55ec-b9b6-45254763d6a4 |  | note | Verifying Documents - Teambinder Material Approval
text | 8eba1970-91ea-5481-8588-8c186a8afb48 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries-Documents
checkpoint-status |  |  | checkpoint | 3.1 - Subcontractor ITP (where required)
label | 0362af02-66ae-56aa-b8e3-143176e6cebc |  | note | Reference - Subcontractor ITP
label | 74fe2701-1e67-5a33-a25f-d5999fd059bf |  | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
label | f4da3484-f959-5392-9bc5-df6fa0c81d53 |  | note | Method - Document Review
label | e4b52356-3e31-5a47-80de-822155694525 |  | note | Frequency - Each Lot
label | 741383f5-65b6-5f2e-b248-01222b681a81 |  | note | Category - HP*
label | 9d7642fa-522e-5a59-95a5-399135116f82 |  | note | Responsibility - PE
label | e0f5210b-b100-5b1c-825c-947dbf860573 |  | note | Verifying Documents - Refer to ITP
text | 4587736f-0ffe-544c-8863-dc96ee2c1506 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out - Pits & Pipes
label | 70d94c64-0326-55f9-aed8-1e9443ff6694 |  | note | Reference - IFC Drawings Section 701.10
label | dd704398-4feb-5fd9-b7de-203238535d62 |  | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | 64d2893b-b9d5-5492-9634-59836d22c7a4 |  | note | • Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | 4d466f72-d787-5032-9238-749becd181fb |  | note | Method - Survey
label | 9756bab9-b149-5172-baf5-acee85f08548 |  | note | Frequency - Each Lot
label | 7d36971f-7c74-5382-98c2-bc8555c48b17 |  | note | Category - HP*
label | 8fc73ffc-44c2-519d-b384-d4c9b16b960b |  | note | Responsibility - PE
label | a721a0a8-2053-5220-8bf4-ddb3321ce645 |  | note | Verifying Documents - IFC drawings - package 13
text | 1af63d70-f385-5962-b8f5-e5fcb3ce30b0 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Pits - Excavation
label | caa95059-ace6-5199-9990-4ad82c896447 |  | note | Reference - IFC Drawings Section 705.05
label | 0df875a6-d97e-58ed-abce-9e62aba8665f |  | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
label | 005a2253-2af7-535b-b65c-d6f3aac7dcf4 |  | note | Method - Visual inspection, Measure
label | f0847ad8-fdc3-539b-9b13-d8141a2ac768 |  | note | Frequency - Each Lot
label | c320091e-83a4-50b1-960e-e9b2d0dc85ce |  | note | Category - IP
label | fba45ade-d691-57f9-b739-4c15f3139464 |  | note | Responsibility - SE
label | 0a3be269-25d8-5ce4-961b-34baa0fee62b |  | note | Verifying Documents - IFC drawings - package 13
text | 3f0fbeb9-cbf6-56bd-b405-b218c9fb5303 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Pits - Placement of Bedding Material
label | 609fab17-84d4-5385-b21c-c8c916a554e2 |  | note | Reference - IFC Drawings Section 705.05
label | f3e827c5-5f0a-5493-89aa-233561c74707 |  | note | Acceptance Criteria - Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
label | e9d78fb0-ba1d-5577-8796-a215571d5375 |  | note | • > 80mm for clay foundations
label | 8a7ca185-d9f1-571e-8179-dcfdbff540a0 |  | note | • > 150mm for rock foundations
label | e2ca7365-89fc-5740-88bb-0a1fe4cbb501 |  | note | Method - Visual inspection, Measure
label | 9b82bc28-c862-5f94-93af-31ff125b58b6 |  | note | Frequency - Each Lot
label | c3b42d33-2e82-5270-b05c-286292481427 |  | note | Category - IP
label | bda556e7-9678-564a-af54-601482fe6436 |  | note | Responsibility - SE
label | f466157f-630c-563e-b50f-0bf19e6e8284 |  | note | Verifying Documents - IFC drawings - package 13
text | 4011c2ae-7d9f-50c9-b6a9-a9c1e6354ce3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Pits - Bedding Testting
label | 30c88298-f054-5a0e-9947-59bb39746955 |  | note | Reference - IFC Drawings Section 701.20
label | efbe308c-b7fd-5388-9e83-ef80f4c80a3f |  | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | d8170177-29fc-5785-9e23-84c3c2dafca8 |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 29cc3f78-d7a9-56f9-89f3-a7e26d461c1c |  | note | Method - Compaction Test
label | 71aa1913-9300-510d-8913-56147226a8fb |  | note | Frequency - Each Lot
label | 7d473651-ab4c-56ab-86a1-2838bfdb5322 |  | note | Category - IP
label | e253adbc-c019-509f-9768-640f74766ada |  | note | Responsibility - SE
label | 00cc67cf-1598-58e7-b016-820aa2cb6e15 |  | note | Verifying Documents - Compaction test results
text | 181ec86c-9008-519a-8cfd-3f9fc4eb1ff1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Pits - Placement of Precast Drainage Pit
label | 8445a6b9-8a3d-514e-8157-37f9148cb128 |  | note | Reference - IFC Drawings Section 701.10
label | c6fb90dd-63b7-5bc1-a6bf-1c2728b8b0fb |  | note | Acceptance Criteria - Survey pick-up to verify:
label | ccfdefae-6536-5657-9d8b-dcd0e4f4e530 |  | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | 0bc0715d-666a-5418-93bd-ab4ddbc06334 |  | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | 42ae0187-5739-5608-b095-b759dd7ba63c |  | note | Method - Visual inspection, Measure
label | 3d954ba7-3fca-5eeb-bdfb-8de74a14d406 |  | note | Frequency - Each Lot
label | c6f71124-5932-5f7e-a29c-414e6a2fc497 |  | note | Category - IP
label | 4fa75a0f-ad76-5d98-bb8f-4493b007fd6f |  | note | Responsibility - SE
label | e3910c1c-1b87-513a-873b-512a664cf162 |  | note | Verifying Documents - IFC drawings - package 13
text | 173c371a-c9c3-5cdc-b815-cce2a719bfc8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Pits - Cast in Place Drainage Pit
label | 11b9adce-0de9-5265-981f-52b43044d990 |  | note | Reference - IFC Drawings Section 705.06, Section 610, Section 611
label | 66eb6791-a02b-5420-a903-48a950aef3e5 |  | note | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
label | 602e3814-ca47-5c16-9e5b-6384a1a445b4 |  | note | • Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | 1842684d-4e3f-5baa-b3a7-6face97eea13 |  | note | Method - Survey, Measure
label | 6a0db754-2204-5b87-b445-f024a2c0ebb7 |  | note | Frequency - Each Lot
label | fb5c4c5a-ebe5-5a27-be94-7fb7c2f09259 |  | note | Category - IP
label | 11db52ba-3dd5-5b3c-82db-c3e00b0c96d3 |  | note | Responsibility - SE
label | d2bd30c4-1f9f-52fe-ab8f-97a31689a72a |  | note | Verifying Documents - IFC drawings - package 13
text | 18e8b6c4-67ec-563b-816d-88c9c5d15c75 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Pits - Jointing & Drainage Connections
label | aef13145-6a72-51e8-a6c1-a49a24fa9dd2 |  | note | Reference - Section 705.11
label | 26eee097-7ab9-533a-bb3e-15befbbf2076 |  | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with Section 705.11.
label | a6d44c82-1458-5642-91dd-3f7239a9abe1 |  | note | • Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
label | a97984fa-5060-54a3-9cca-10a4c5b9f7ab |  | note | • Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | 4aa122b2-4eb3-5fbf-b6c1-3d502ab6295d |  | note | • Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | 85ebb87e-6876-54ab-a791-198b255482c0 |  | note | Method - Visual inspection, Measure
label | 2c0242e6-09e0-5907-9326-7f28423d5aa4 |  | note | Frequency - Each Lot
label | 12165db4-9657-537a-89fa-762c3e28be9e |  | note | Category - IP
label | 776ac49f-e001-513f-8e2b-e2e218704adf |  | note | Responsibility - SE
label | a68b4be4-f8fa-5ace-9228-c4a1650de199 |  | note | Verifying Documents - IFC drawings - package 13
text | 90747576-042a-5739-a315-5d5c7ba662eb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Pits - Shaping of Floor
label | 11a21eee-7f8d-5091-8e87-a3fe26b4dcb0 |  | note | Reference - Section 705.13
label | c3844a26-6931-5129-85bd-f4947853cc6f |  | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
label | 5fbcb750-2786-58ba-8e35-42be64ef7263 |  | note | Method - Visual inspection, Measure
label | 2f1c57e7-accf-5775-bcb9-21bdb4d2a645 |  | note | Frequency - Each Lot
label | 012e16f5-31dc-5eed-8a04-7e6e01bdd01c |  | note | Category - IP
label | 5279eeef-cf53-5055-a392-30e38e8e1431 |  | note | Responsibility - SE
label | 771a23d8-b310-5318-8cd3-28c3c1246ca3 |  | note | Verifying Documents - IFC drawings - package 13
text | b5efdb44-349e-5ed2-8fea-848691c36cd7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Pits - Step Irons
label | 40a287a2-a3d8-56ec-ade2-04c5881fbb4e |  | note | Reference - IFC Drawings Section 705.12
label | 20ceb859-c1dc-5169-aec8-a34318bd7296 |  | note | • Brimbank City Council Engineering Detail 275
label | 724e50b7-ddaa-5fdf-b350-a980cb98fb73 |  | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
label | 01ab8bb9-deea-5046-bafa-1bcd43095040 |  | note | • Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | 98f31534-53ac-502c-92ef-e19653b495cc |  | note | Method - Visual inspection, Measure
label | 169e9152-ac78-5188-8233-9a9bcd1bd1f3 |  | note | Frequency - Each Lot
label | 64427089-cd42-5da3-8cf0-83a58241e5d2 |  | note | Category - IP
label | 9b336f7f-c7b9-573e-bc89-19582b1842cd |  | note | Responsibility - SE
label | ad0afc5b-c6c1-5289-8523-68eb0d7aaa29 |  | note | Verifying Documents - IFC drawings - package 13
text | 3fea7099-4584-58e1-b04c-6222185ca8cc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Pits - Fitting of Covers
label | c974319c-a80a-55a8-90df-55f9cbf46fd6 |  | note | Reference - IFC Drawings Section 705.17
label | fa4568e0-8706-57b9-8ea3-66e2b131097e |  | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
label | 7e734e95-8d50-516c-b6c2-0d4f5d0d3ad0 |  | note | • Height shall be within 10mm of the design level.
label | 8cac3de9-c7b1-558e-9c08-87c7c76f56ca |  | note | Method - Visual inspection, Measure
label | 1bd06876-0670-5640-bc1e-97a7286bd1f2 |  | note | Frequency - Each Lot
label | e5b15a2b-280c-5f2f-8a8d-87edfee396e3 |  | note | Category - IP
label | fe506aea-af53-5eb5-9e98-071f3f1ebfc1 |  | note | Responsibility - SE
label | e2be20f2-4046-54c3-b10b-b0045cef53f5 |  | note | Verifying Documents - IFC drawings - package 13
text | 6a2b9740-d520-5755-bbcc-ac7a97bb5da0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Pits - Pit Lids
label | 0c45472c-5923-5b1c-86cd-21d85703da0a |  | note | Reference - IFC Drawings
label | fbc0a655-d3d6-501a-8f7c-d9bb2e23d3b7 |  | note | Acceptance Criteria - All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
label | 87cac1bf-cfc6-5b7f-b83e-af51beb10ab6 |  | note | Method - Visual inspection
label | c8be6773-b101-516a-8195-b8d4743f95f8 |  | note | Frequency - Each Lot
label | 12853f30-dfc1-521a-af48-b297d4951952 |  | note | Category - IP
label | 0003b34d-d6c8-5bd7-8814-0f49cbb1aa69 |  | note | Responsibility - SE
label | 10e02d3c-da54-5add-9402-954722e52bde |  | note | Verifying Documents - IFC drawings - package 13
text | 36a30aad-afd0-5ecc-b140-9b244fb9e3b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Pits - Backfilling Around Drainage Pits
label | 178e5b87-8106-5221-99a2-27e38afb9038 |  | note | Reference - Section 705.18
label | b131c02f-261d-57dc-b77a-974334f5c1f4 |  | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | cf2f2e73-08ae-50a3-9747-02ccf0ee94e8 |  | note | Method - Visual inspection, Measure
label | 6f61a433-63f9-55f9-867b-f61365bd85b5 |  | note | Frequency - Each Lot
label | 8ddcaab2-879c-5d47-b0d3-3f8344c33171 |  | note | Category - IP
label | 990993e6-7ca6-5e0c-b636-2ede6d5f79dd |  | note | Responsibility - SE
label | 58ed6474-63ee-503a-8879-c22329a96c36 |  | note | Verifying Documents - IFC drawings - package 13
text | c24005f5-35c8-5c2a-a895-2c956031df36 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 - Pipes - Trench Excavation
label | 70f598f8-8a81-51da-ba68-7e612d466779 |  | note | Reference - IFC Drawings Section 701.15
label | 3e383ca7-800f-530d-889d-6edad882bd3f |  | note | Acceptance Criteria - Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
label | da5cd7e0-3e89-54a4-b0a0-849a087fc333 |  | note | • > 300mm, < 600mm for RCP
label | 35dcaf5f-7278-551a-aef4-1ef908d3cfb7 |  | note | • > 150mm for Flexible Pipe
label | 939af018-0859-54ad-8d35-62179dd2f936 |  | note | • The base of the trench shall be compacted to refusal using mechanical plant.
label | afae5658-0092-52f5-9523-dd40c21b40ff |  | note | Method - Visual inspection, Measure
label | 6fe0ddd4-9fff-5ff9-a084-181a9f1bae48 |  | note | Frequency - Each Lot
label | 517bd21e-590a-57a8-a514-212e98cfb3c1 |  | note | Category - IP
label | cd68f300-3f13-5e97-a37d-f1d9e118998d |  | note | Responsibility - SE
label | 30de6eda-2a4b-53a4-bd58-e87c077dab9d |  | note | Verifying Documents - IFC drawings - package 13
text | 84b39d09-9072-509e-8217-361460d00cd1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 - Pipes - Bedding Placement
label | 39b60e51-97dd-55a5-9364-7ca2537d65df |  | note | Reference - IFC Drawings Section 701.16
label | c4a65476-e603-538b-84f6-fd22522a704f |  | note | Acceptance Criteria - Bedding material shall be provided and placed in the full width of the trench to the below minimum:
label | cd28d9ca-ab30-5164-8c8f-ebe9298a09dd |  | note | • > 100mm where D<1500mm
label | af9f4397-ef7a-59fc-8e41-e9dadf561ca0 |  | note | • > 200mmwhwere D≥1500mm
label | 73d173e5-cf31-5f96-841c-ba95e5df225f |  | note | • Bedding material shall be placed and compacted in layers <150mm loose thickness
label | 5f7b10ac-fad9-5b93-a873-db644544b6c8 |  | note | Method - Visual inspection, Measure
label | a57efc41-4bc3-5d88-b84e-04b49aceed04 |  | note | Frequency - Each Lot
label | 07897e3a-db62-5748-935c-407b60db9a71 |  | note | Category - IP
label | c706220d-d9f2-5fb6-9eeb-d061b57cc91b |  | note | Responsibility - SE
label | ea9b5601-a046-5122-9ee9-c8bd1c3e7a20 |  | note | Verifying Documents - IFC drawings - package 13
text | df3c6be1-a4d0-50c3-824a-93e0069aa5d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 - Pipes - Bedding Testting
label | fd0dd52e-857a-58e2-8649-bd8cfc704be3 |  | note | Reference - IFC Drawings Section 701.20
label | 2b30d468-d416-594a-a02a-335673a91ec8 |  | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | 0333d10c-86fe-53d3-9d6c-5a23e873a324 |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 71405129-e773-5876-bd01-f48f9913bf23 |  | note | Method - Compaction Test
label | fe6f172a-98a1-50d8-8c3b-e4a8518cab43 |  | note | Frequency - Each Lot
label | d35efc8a-9dbe-5f16-81b4-484747d42ba4 |  | note | Category - IP
label | 972fd341-9d18-5f52-9ecb-53a24adf158a |  | note | Responsibility - SE
label | 6b8ca982-9103-56b3-9bf0-48fcf9a024d5 |  | note | Verifying Documents - IFC drawings - package 13
text | b2c83092-6cc7-569c-af07-f30299d1c5d7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 - Pipes - Placement of Pipe - RCP
label | 79d8d38a-8c0b-570f-b2c0-0dcc098127d6 |  | note | Reference - IFC Drawings Section 701.17, Section 701.20
label | bae2843e-abe2-5339-a10c-aaa431adfbc1 |  | note | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
label | 8bfb2d50-bc59-504b-ac94-4444a189b866 |  | note | • Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
label | d5cfe77b-5ea8-5053-8c24-6936ab3955a4 |  | note | • Gaps between spigot and socket are in accordance with the manufacturers specifications
label | 32855b46-f922-5c71-bc08-3dc9943694e9 |  | note | • The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
label | cb9033b3-5d19-563c-af50-19ac6dad9df9 |  | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | b25b3778-9de8-5ec8-92f2-098c4b9a581c |  | note | • The spacing for multiple row culverts shall be as shown in Table 701.171
label | 4a7b9c53-4688-5330-9298-59628ac15ded |  | note | Method - Visual inspection, Measure
label | 71644f2e-28ba-5aa0-9925-174ea148acf1 |  | note | Frequency - Each Lot
label | 8b2f2ee0-b87a-52cc-baee-41b1509db581 |  | note | Category - IP
label | 10359d91-0351-586c-bd3e-9e290ab0ea9e |  | note | Responsibility - SE
label | 70a78be1-2032-529a-abc6-448e838bc2fb |  | note | Verifying Documents - IFC drawings - package 13
text | e4ddb5ec-2cde-5844-aa05-b29ba0066518 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 - Pipes-Placement of Pipe - Flexible Pipe
label | b0c2ab9d-57ef-5ded-bd87-5d462dd85064 |  | note | Reference - IFC Drawings Section 701.17, Section 701.22
label | e5938a38-d81a-5eb0-b450-73409eaabd4a |  | note | Acceptance Criteria - All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
label | f768b84b-7c54-5236-889f-b1e3b4476fab |  | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | 3a05e9d5-9e77-5e8e-b599-40d900b42864 |  | note | Method - Visual inspection
label | a8adff73-e9f9-59fe-817d-d5fe06bfd66e |  | note | Frequency - Each Lot
label | 0c4031c2-804b-5b2d-ab33-78dd4d74afd3 |  | note | Category - IP
label | 5ee5fd6a-571c-5017-bbc8-e7e41cbc80d2 |  | note | Responsibility - SE
label | 35add517-2564-5d1c-8c5b-598fd9a4982a |  | note | Verifying Documents - IFC drawings - package 13
text | 6bd024ef-bd3f-526e-ac5f-13faab451d91 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 - Pipes - Lifting Holes
label | 9f8fea2c-7e03-5cb7-b418-e0678490dce8 |  | note | Reference - Section 701.18
label | 9441d552-ba94-5e23-8e17-a4e17b05e6c0 |  | note | Acceptance Criteria - Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | 18c2728b-2318-5b6f-8a38-ed0c0966679c |  | note | Method - Visual inspection
label | 4a7e31f8-4d8f-5369-be55-ebe430fb3c3b |  | note | Frequency - Each Lot
label | 97a30247-b025-5c03-ba08-c60ab50b72eb |  | note | Category - IP
label | 62dad747-3607-5570-9953-4f90c2f600a7 |  | note | Responsibility - SE
label | 73edc9ce-b190-59b3-96d5-7a2a7f4bfe68 |  | note | Verifying Documents - IFC drawings - package 13
text | 7f98c8f4-ed28-5bd9-85c2-1d7a63cd6758 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 - Pipes - As-built survey pick-up
label | 65fdd3d3-74b9-5c3d-ac92-a9b001b83678 |  | note | Reference - IFC Drawings Section 710.10
label | 4618d72f-c6c3-5b83-a951-b278234fa0ed |  | note | Acceptance Criteria - Each run of underground drainage shall be Survey verified prior to backfilling.
label | f45f9038-e968-52e2-9528-597f2c8c9ece |  | note | – Offset pits to kerb +/- 20mm
label | 69c4d7c0-316d-51b2-85cb-7691b8f5d11a |  | note | – Plan location pits not adjacent to kerb +/- 100mm
label | a0ef3f04-dcc0-59a9-aa86-aab81cccb5d3 |  | note | – Invert level of pipes at pits +/- 50mm
label | 9fa74f1a-7edc-5d7f-a50f-4764f6e59cb7 |  | note | – Departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
label | 15298798-008a-5250-8001-f19077b40ae3 |  | note | Method - Survey
label | cc50fb2d-9898-5685-9469-49c0814208f0 |  | note | Frequency - Each Lot
label | 04be207a-fdc3-5150-8148-4758b722583a |  | note | Category - IP
label | b886bd9e-2a22-5165-8ab8-8116b0a6d842 |  | note | Responsibility - SE
label | 69b97f1a-6cd7-5db9-b3b9-ff441fb04c83 |  | note | Verifying Documents - IFC drawings - package 13
text | 86c1c59a-15f4-5a3d-93db-c181d3d47b0a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 - Pipes - Backfill Placement
label | 96c3e9ad-2cf2-5da0-bc7e-b2c75dec5bcc |  | note | Reference - IFC Drawings Section 701.16
label | f5f8ae20-1eab-5d73-9a60-08db62f9a929 |  | note | Acceptance Criteria - Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
label | 1dcca698-0276-51bf-9c7f-904510874eec |  | note | • Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
label | 52a13dd8-f804-5253-a677-74458ba968eb |  | note | Method - Visual inspection, Measure
label | a5a123bf-c02c-5a61-8fa4-d5b8329843ac |  | note | Frequency - Each Lot
label | 620523bb-cb8a-5503-921f-ba0c1b50f821 |  | note | Category - IP
label | 21a28aab-c82e-5f7f-9a55-473cf9814576 |  | note | Responsibility - SE
label | d78ec0b4-ea00-5a74-b460-10451afce3a6 |  | note | Verifying Documents - IFC drawings - package 13
text | b9786838-80ea-5cf2-9292-e42323a83b22 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 - Pipes - Backfill Testing
label | 8811f545-8abb-5afe-88ce-e518460342bb |  | note | Reference - IFC Drawings Section 701.20, Section 701.29
label | dd8b82cb-edc1-51c2-8e40-5358f688259b |  | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | 5d9fc6f0-26a4-5fe1-9f56-27a0df218c6d |  | note | • Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | e956664b-a745-58b3-ac97-e575abf8c622 |  | note | Method - Visual inspection
label | 83d8a346-7eff-5697-b8be-515e585d7c0b |  | note | Frequency - Each Lot
label | 79333351-1ce3-5a6e-bc64-51c117c2376a |  | note | Category - HP*
label | a0ac511d-0776-5f38-aba3-ddf6079c7af2 |  | note | Responsibility - PE
label | a4d07d83-1238-553e-96be-e6d1e7055b4d |  | note | Verifying Documents - Test Report
text | 9e7bc270-69ba-507c-9581-2692faef88cd |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - Flushing & CCTV
label | 17cf6dc4-ffd9-58f3-8caa-43599bf28176 |  | note | Reference - Section 701.28, Section 701.30
label | 7a2e3fc4-2ec3-5d1f-9de3-f1c2d3f09c11 |  | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | 0196d779-71f3-5cb1-96fc-6489ea45a624 |  | note | • All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | 1bb3880f-6316-5a42-86f3-06eed6286cf8 |  | note | Method - Record Review
label | 3a614928-5cf0-5b09-8fd2-5980501e453a |  | note | Frequency - Each lot
label | 2ae0775d-f109-56e2-8b17-4477a4d707e5 |  | note | Category - HP
label | 8107d998-7373-5889-a53d-f261c7e3375c |  | note | Responsibility - Nominated Authority
label | 6b5144ec-2e05-589c-884a-15b88d90b78e |  | note | Verifying Documents - This ITP, CCTV Reports
text | 018228e7-c6cc-5d84-a54c-2a9283fbd8b2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - As Built Survey
label | 5ae75aaf-1fc7-55ef-8422-197163abcd43 |  | note | Reference - Section 701.10
label | eb0c283b-efc6-50fd-b6fd-e44f5ca7a3f3 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | 0daf43af-98e3-513e-9b61-8c5691b72d87 |  | note | Method - Document Review
label | aef88904-4655-56cd-9810-656ff45a04ea |  | note | Frequency - Each lot
label | 226820df-c873-550b-8a08-e0160c39bd54 |  | note | Category - IP
label | eac9f31f-3456-5e13-b090-746d8ad12d4a |  | note | Responsibility - SE
label | 44f70784-c4e8-5fcb-b1c0-ff5d37e03d7c |  | note | Verifying Documents - This ITP, As Built Survey Report
text | fd5647ac-8aaa-53c5-b3b1-9c7146501133 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Repairs to Damaged Pipes
label | 5c826723-4332-59bb-9928-c29a9ae8d1f8 |  | note | Reference - Section 701.31
label | ac6f870a-0c4e-5988-99d9-f52cb15564c7 |  | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | bc855816-e88d-5e84-b6dd-1c24e3b48324 |  | note | • cracks wider than 0.5 mm
label | 8b6ec901-b873-59bd-a22d-c069b359394f |  | note | • spalling of concrete
label | ee7a57f0-f606-5fb8-b3a3-27a20a7fcc4d |  | note | • exposed reinforcement
label | 9ff6ace4-128e-58d6-bc9e-dad75573ee49 |  | note | • joints that are not fully engaged.
label | 3433a168-f529-522d-9b6d-665d1f2f9877 |  | note | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
label | e9759370-b10d-56d8-8795-8cc307a6b86e |  | note | • longitudinal cracks greater than 2 mm
label | 06dbd597-5fb9-5295-b0aa-779fed4bfd60 |  | note | • circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | 175fd7da-d28f-549c-9b99-d0081892e58b |  | note | • circumferential cracks around part of the circumference with width greater than 4 mm
label | 5d0f3aef-6020-5939-a10d-e17701662b55 |  | note | • penetrations with area greater than 400 mm2
label | e10ab73e-53a4-5d2e-bae1-3b6de360d7bc |  | note | • pipe joints that are separated.
label | 59be98db-ed65-556e-8cf6-dbb1a2061371 |  | note | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | d88d4f68-1c3f-56b2-8991-66bd8b000fae |  | note | • hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | 88f9cc79-2105-5f81-bbe9-95e6f077588e |  | note | • fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | e6e48f47-bb14-5765-bea0-b4226013acbd |  | note | • spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | 86306aea-5613-5599-936d-9057b2570dc9 |  | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | e5ec0a41-5042-515d-9654-20ca187032e8 |  | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | 6c1c8195-eb9a-50c0-a326-17a106e6d995 |  | note | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | 5605e607-91ad-5733-bd00-f14e7e0b3534 |  | note | Method - Document Review for Repair Procedure
label | 137d3468-82d7-5237-b61f-da1ab4ecadaa |  | note | • CCTV Report Review
label | 547350de-2c03-5f8a-84e3-101ac965cad2 |  | note | • Visual Inspection
label | 4b666407-894c-52c9-a93c-952380abc867 |  | note | Frequency - Each lot
label | d2f08c4f-eddc-55ca-a910-080b21951b32 |  | note | Category - HP
label | db8ddab2-4209-5b17-b27a-77a46540bede |  | note | Responsibility - Nominated Authority
label | cafa6c1c-4aae-5ee3-9a3f-42ae8f8509ee |  | note | Verifying Documents - This ITP
label | e2e61f29-fb84-5a37-a460-a408025f1528 |  | note | • Approved Repair Procedure
label | 509ccef0-d07c-5800-9610-be976114bee3 |  | note | • Post Repair CCTV Report
label | d443fb15-0d16-550f-83f0-bd8026e838f1 |  | note | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | c7d5bb2b-f955-580a-a40a-08c3a1b4a4fc |  | note | Reference - MRPA Quality Management Plan
label | c8117e65-da6f-5d0c-b479-bca64f7a29b4 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | b4f7b8ec-2715-5aa0-918c-c35edcb1eb64 |  | note | Method - Document Review
label | 2c361a9d-44dd-5fd9-9279-71b9efba6107 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | af3425ee-b8f6-52bd-9bdd-48c0763597f0 |  | note | Category - HP*
label | 8bd8b407-dd98-50f3-af31-9b68a7f6e7c2 |  | note | Responsibility - PE
label | c028964f-9a00-5716-86a3-cc4329510172 |  | note | Verifying Documents - This ITP
text | 6c0773a2-4df4-5eae-9cdc-b6c2bd9bc598 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 07c78d4d-dac2-5838-aa89-0901f8469d86 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 01cb9db2-ff5c-5467-8414-8baf551cf698 |  | textbox | Name:
text | 2a3c7cfe-f7cb-5b59-98e2-1fc8d6afb192 |  | textbox | Position:
text | 0948c33f-18de-5c78-830f-2a6705494b3a |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-047-CIV-CPD-Type B FIll - Road | itp |  |  |  | Yes | ITP-047-CIV-CPD-Type B FIll - Road Rev 0 | 51c5fee6-4576-467f-8804-773232db449e
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 238556f2-d3ed-5e38-8819-595bae5bb9ac |  | note | Document Title: ITP-CIV-CPD-Type B Fill - Road (Supply and Install)
label | 81e5da89-722d-5bee-b7dc-d250fba7279d |  | note | ITP Description: Type B Fill - Road (Supply and Install)
label | 5cdb59e4-d014-50a1-bf0e-1336da646ba5 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | d3f3e526-429c-566f-bbd5-34cdf01a9821 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | abd8a9d9-f56a-5b5b-a672-295fda6b7aaa |  | note | Revision Number: 0
label | 40222268-4f3d-5113-b7a4-14074b27f432 |  | note | Revision Date: 12/07/2023
label | 493eec9b-49c6-5401-87f9-d957f9f1f1df |  | note | ITP created by: Matthew Dib
label | ab42a86f-254d-55d4-a7ff-6a2f1ae0fbcd |  | note | ITP approved for use by:
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | edc683c8-f320-55b9-834f-c07f3134b756 |  | note | Reference - Reference Documents:
label | 6e638777-99c5-5d30-a075-9b8b0b9b8ad1 |  | note | • IFC Drawings
label | 40837480-245a-5b56-a9ee-e3f3ce03cc5b |  | note | • VicRoads Standard Section 176 (10/9/2008)
label | a5a69f99-ae40-5245-a663-a3712ee6d651 |  | note | • VicRoads Standard Section 204 (29/12/2015)
checkpoint-group |  |  | section | 2. Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 - Material Supply
label | 5bca1668-9f42-5837-9e42-e66adb23a36e |  | note | Reference - General Notes on IFC Section 204.4 c), 204.06 e)
label | 22c27b38-db86-5311-81f6-88d111d60441 |  | note | Acceptance Criteria - Free of topsoil, deleterious &/or perishable matter and maximum particle size ≤ 150mm. Swell < 2.5%. CBR >2%. Material classified as expansive or silt, either before or after compaction, shall not be used as Type B.
label | 0692d139-f06f-516b-ab89-b5f24a72010a |  | note | Method - Doc. Review
label | 2f3e0c7f-bf6d-5ca2-a4fd-9cdf93388967 |  | note | Frequency - Prior to Commencement
label | 008aa88b-46f1-5fd6-989b-081ab234573d |  | note | Category - HP
label | d0dbadd4-555c-57ff-a969-8a6f9667cf92 |  | note | Verifying Documents - NATA Test Certificate
text | 084d9e2e-edc3-5058-996d-51ebddc9adf1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 - Survey Set Out
label | b66f58f6-cef8-5082-acff-4b9298880e99 |  | note | Reference - Design Drawings
label | 0ebadef1-db0c-5bf3-84c0-c1ea3251b301 |  | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | c10f054b-d450-5ce8-af36-eb7d7d391067 |  | note | Method - Visual Inspection
label | 0847cf5d-2649-566f-ba96-fde0e4c6fdbd |  | note | Frequency - Each lot prior to commencement
label | 098f8d9b-9b7f-5591-96c3-390b459c6dba |  | note | Verifying Documents - Signed ITP
text | ef60b33b-f6be-577f-bf69-2d1483de5bb8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Pre-Commencement of Fill Works
label | e3039a71-713c-53f1-9af6-05562d6272d1 |  | note | Reference - Section 204.10 (b)
label | d3bfd620-fa0d-5cc6-b51f-c285af4dbfe8 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | ec640253-d01b-5781-94da-a82eecd2ea37 |  | note | • The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
label | 4e4ea450-8446-5edb-ad83-a54974b78c11 |  | note | Method - Visual Inspection
label | d0150e17-9256-547f-ab34-41c47529f16c |  | note | Frequency - Prior to commencement of fill works
label | a386c6c4-5ec2-51ed-b113-07002385d512 |  | note | Category - HP
text | e6572f72-131f-55e2-aa3e-2105bbc3f657 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Placing of Fill
label | 7d9fdeda-899d-51e9-aec9-dbfe8f115cb9 |  | note | Reference - Section 204.10 (d) (iii)
label | f92d7b5d-bc50-5dbd-9ec7-32f4d64f6346 |  | note | Acceptance Criteria - Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted by superintendent.
label | 86f976d1-155c-55a7-9c2d-57ed4afdcca2 |  | note | Method - Monitor
label | 971e86c9-19b0-524e-a66b-c41cc36d39bc |  | note | Frequency - Each layer
label | f56628d8-dd7d-5216-82b4-2836d290a22e |  | note | Verifying Documents - Signed ITP
text | 3b1c324f-a7d7-558b-8cab-cc99d716052a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Keying of Layers
label | f0afdd0c-e977-5331-9ae1-56af5e71f307 |  | note | Reference - Section 204.10(d)(i)
label | d54e699d-8a3f-5542-8ea9-a182bf0d121e |  | note | Acceptance Criteria - Each layer of fill shall be keyed into the layer above by creation of a textured surface.
label | 5a91d9fb-6c7f-506b-9770-0e88fd10b298 |  | note | Method - Monitor
label | 4b942366-bc01-5f26-a4a1-5aebff614754 |  | note | Frequency - Each layer
label | e2bb6d05-4def-5368-bca7-8edf66877833 |  | note | Verifying Documents - Signed ITP
text | c9d555b7-6f4b-589d-a84a-3e4117a1d401 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Test Rolling
label | f493f69c-e8ca-5361-900e-ccc72642aef3 |  | note | Reference - Section 204.12, 173.03
label | 53a9c0bd-81fe-54da-aa45-9dc31c1aa494 |  | note | Acceptance Criteria - All layers of fill and cut floor level to be test rolled in accordance with section 173.
label | d7a90d11-1fdb-5d79-b83f-fd0143bb4001 |  | note | Method - Measure
label | 5ddb319f-a801-50c9-b315-756e65662db4 |  | note | Frequency - Each layer
label | 302117d3-3235-53fe-b064-b2475393ff1a |  | note | Category - HP
text | ece8beec-e611-5cc0-abc0-74473f4b54dc |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Post Compaction Testing
label | 3bc8ac1d-5a0a-5de8-843d-a9722f7278c3 |  | note | Reference - Section Table 204.131, 204.13, 204.14
label | 2013c772-f4a3-5ce2-8498-ec3c87bd33ad |  | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
label | 310298ae-e1e8-5a2c-b0e2-75a06ad3d1a2 |  | note | • Ripped and re-compacted material below Cut Floor Level
label | 0258f297-895e-5171-9ab7-cb0df3d61d76 |  | note | • Scale B: Characteristic Density Ratio 98%.
label | 00a4815c-97b7-5700-85ed-74fe92c0cd72 |  | note | Attach: Compaction Test Result:
label | 3e1f624a-12e2-5188-9d1c-738367d55eb4 |  | note | Method - Doc. Review
label | ca5cab5b-f876-512b-b59d-7d55994c3b2e |  | note | Frequency - Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142:
label | f9e2c15e-51d3-582d-bb5e-c7a535e5dabb |  | note | • Placed within 400 mm of top of Type B: Test every second lot of like material and work
label | 5b666f8c-ead5-5dd8-809f-0423141ee744 |  | note | • Placed more than 400 mm below top of Type B material: Test every third lot of like material and work
label | 0004700b-db54-5d70-a993-3ea51a41cca5 |  | note | Verifying Documents - NATA Test Certificate
text | a9b5fa6b-a981-51ef-a8fc-4909c93f4afd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Preparation of final surface
label | 922f2e93-472d-5bcb-bb03-e6af5ce713c6 |  | note | Reference - Section 204.15, 204.03 (g)
label | cdb7532a-2d15-5c1c-b11f-eb4a454f43d0 |  | note | Acceptance Criteria - The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | 4ed21aac-3691-52b8-9035-782109d3f6d8 |  | note | Method - Measure
label | ff9e752b-a906-59f0-a4c2-4428f536f81e |  | note | Frequency - Top layer
label | 8280b1da-7862-51dd-99ce-9c66983d3ac7 |  | note | Verifying Documents - Signed ITP
text | 2846b091-b387-5b2b-bc3b-5a4a483e0c7b |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Survey Conformance As Built
label | 51a6e5c6-33f2-5461-85cc-a34d4d4e8ba3 |  | note | Reference - Section 204.03 (e, g & h), 206.16
label | 5bc82fd6-fe59-5fde-93a3-e737b5ffde31 |  | note | Acceptance Criteria - Surface is not to be more than 15mm or less than 30mm from what is specified in IFC drawings
label | 2d739730-aaf9-5c24-8b49-82fcbfc48fcb |  | note | • The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 14dada8c-29a9-5bd2-a31e-a5a0c16aedfc |  | note | ○ Scale B:
label | 62fbedcf-dee2-58b6-8460-f416461b8ed8 |  | note | • Min. No. of Measurements Per Lot: 40
label | b209403a-1809-561e-a38e-a01e7c751ee7 |  | note | • Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm
label | f9703d19-d000-56b8-919c-70327fe919db |  | note | Method - Review
label | be49fb87-9e4c-546c-be01-caa0ca9b724f |  | note | Frequency - Each lot (Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2)
label | 2015a153-9c07-5d1b-b4eb-ff86f7a3c33e |  | note | Verifying Documents - Survey Conformance As Built
text | 1f60b95f-b271-50c5-a21b-573eece9dfcd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 6a73f30b-f38b-5841-81cb-d23808f59b39 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 7a6529d3-4dbf-5e67-9db7-dde56f98c9d7 |  | textbox | Name:
text | 4e6cd2a3-baed-5525-8d19-28adc8275395 |  | textbox | Position:
text | b16e5600-a36b-524c-b0d3-76c612120908 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-046-CIV-CPD-Type A Fill - Road | itp |  |  |  | Yes | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | 5619ea3c-44b4-4e95-b2c1-4e01cb32eab8
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 04dff166-9dd8-5bc0-a59a-6d9dfeab4b8a |  | note | Document Title: ITP-CIV-CPD- Type A Fill - Road (Supply and Install)
label | 2e328150-ad80-516e-90ef-cfa5581b235b |  | note | ITP Description: Type A Fill - Road (Supply and Install)
label | 618d6363-7516-56a8-bc30-f93990bc1cb0 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | c6fc5f5e-87ab-5ed9-9037-9a2da1063ac2 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | 9d8abf76-5441-508f-b4ab-ff9c7bf139bd |  | note | Revision Number: 0
label | 47651862-5031-5637-9ace-f624191e10e5 |  | note | Revision Date: 12/07/2023
label | 1dc6e926-8224-5b5f-98bc-351e3c12570b |  | note | ITP created by: Matthew Dib
label | 1b7a676d-c1ab-5969-ab57-fc41ae66b9c7 |  | note | ITP approved for use by:
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 76b0e669-abb6-57da-93a9-d2f32151a410 |  | note | Reference - IFC Drawings
label | 17f45917-1af6-5194-8ce2-c7eb44b5d63e |  | note | • VicRoads Standard Section 176 (Sept 2008)
label | 45139a27-a71a-59d0-8b16-e6cb4d8e27c3 |  | note | • VicRoads Section 204 (Dec 2015)
label | 9792e7d1-e930-5283-a6bc-3abe30abbce2 |  | note | • Code of Practice RC500.20
label | 034472c1-2d1e-5515-b42a-6e878b689075 |  | note | • Code of Practice RC500.5
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance
label | 425d55c8-ac7a-5e3c-80a0-5a62732e1bb3 |  | note | Reference - Section 204.04 b) Table 204.041
label | 12bc2454-34ed-533c-903a-799dc417c27c |  | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | 8b2ead9f-fbbd-57c1-ad67-49349d13ca4b |  | note | • Assigned CBR≥6%
label | 44a7512a-e04c-59a8-8f07-c3a5f3cfa629 |  | note | • Swell ≤ 1.5%
label | e7cedf62-c5d0-5880-9958-7cd69517a655 |  | note | • Permeability ≤ 5X10-9 m/s
label | 5b61e4c9-7631-5c03-8df6-c276a4bf0594 |  | note | ○ Grading:
label | ced8d0d9-6123-5eeb-a7a9-b008fd82c536 |  | note | • 75.0mm 100%
label | 7fe02200-0009-5e62-ba49-ad35ec2a67d2 |  | note | • 4.75mm 40-80%
label | 542a4241-58d6-5ff8-b8c1-ce46563063c8 |  | note | • 0.075mm 10-40%
text | 645f5910-ebe2-5f3e-bba0-aca3bde3739d |  | textbox | Reference: Material approval in Teambinder:
label | 262ef993-9f76-5abe-bc43-69c339a4526c |  | note | Method - Document Review
label | b15c6888-c8dc-554a-a7b3-b54199b8d25d |  | note | Frequency - Once, for each material type
label | 3e70129f-1de4-5578-84f7-25616b289e6a |  | note | Category - HP
label | d83b16af-9fee-5b03-992c-bcaadfd21eb1 |  | note | Responsibility - SE/Nominated Authority
label | 36dbf726-fae6-51be-8cbb-75c96e139482 |  | note | Verifying Documents - Supplier Material Conformance Certificate
text | f10e62c9-3d93-585e-99e9-23ab1a25c3d6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Pre-Commencement of Fill Works
label | b7c34647-c4b8-5264-b632-643e8b90fe78 |  | note | Reference - Section 204.10 (b)
label | 83cec521-af0a-5bf2-8ac8-9d3d7c3774c4 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | dc9ce301-7dc7-5746-b571-f1848c0bb5ba |  | note | • The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | 34e9a4d4-1068-5b00-8e19-607ce8381364 |  | note | • No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
text | cb38de53-c079-589b-a94a-edff130e8c5b |  | textbox | Reference: Fill foundation Preparation Lot Number:
label | 6dda44b0-7bb0-5bed-abcf-ab16a75ca024 |  | note | Method - Visual Inspection
label | 34151bf9-2f53-5ba6-bf60-cec811a9f0d3 |  | note | Frequency - Prior to commencement of fill works
label | e4fce539-17cb-587d-be43-2286b784a8f9 |  | note | Category - HP
text | 48a92bbd-9539-549e-be85-560f16c08a9d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out
label | e5ebfe17-8862-5c5f-a8a4-18a59590cf51 |  | note | Reference - Design Drawings
label | 87f58417-3fbf-587c-b476-4c591f6869f7 |  | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | 8ff901ff-a5e3-565c-8f67-35d13ab31e01 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | a6a95aba-ee65-5d8f-8cfd-49e14ec1dd08 |  | note | Method - Visual Inspection
label | a7c46065-950b-5a4e-9ec0-e40ab55b67a6 |  | note | Frequency - Each lot prior to commencement
label | b1bcb0f0-33d6-5450-adb8-b842858a8243 |  | note | Category - HP*
label | 6bb44688-09a3-5e41-913c-78a76f2d5dc3 |  | note | Responsibility - PE
label | 99750622-1290-5176-bca3-ab3e16be00a3 |  | note | Verifying Documents - Signed ITP Lot Map
text | e6f517fe-6fd6-51b1-aa95-41757524b20f |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Type A Fill/Verge Activities
checkpoint-status |  |  | checkpoint | 5.1 - Placing of Fill
label | 1daa79f5-f303-59e0-b236-475956a18fcc |  | note | Reference - Section 204.10
label | f67b7119-aa2e-5ad1-91e9-e3bb89aac3db |  | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted from superintendent.
label | 24a89339-3559-5662-bb67-6c574010486c |  | note | Method - Visual
label | 5d5a3776-69f9-50fa-80a0-ab756f9973ce |  | note | Frequency - Each Lot
label | ab05be17-4baf-56cf-b638-c38289087017 |  | note | Category - WP
label | ee424c06-5c39-5370-a601-9bee8d4afdf6 |  | note | Responsibility - SE/Site Supervisor
label | d080f5fd-2fc8-5584-8b91-5aad8ad54dab |  | note | Verifying Documents - Sign ITP
text | 8aaba3a5-1d61-5166-900f-113b3023cc3c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Test Roll
label | d9ee110f-b472-56b7-b77f-125fb67633a6 |  | note | Reference - Section 173.03 Section 204.12
label | 3244da56-85d2-5017-93b6-ee8b6b7a15c6 |  | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | 4ed78b09-a3f7-519f-8c54-47b8a50c6088 |  | note | Method - Test Roll as per 173.03
label | a138b451-7031-5529-96fd-3d301e729252 |  | note | Frequency - Each Lot/Layer
label | e89a4c19-1c76-5077-af45-5e27c9c23033 |  | note | Category - HP
label | d38ec773-74f1-55d9-b9a2-9cd5db202597 |  | note | Responsibility - SE/Nominated Authority
label | 02981694-87c2-5256-a20c-8e49c5c786ee |  | note | Verifying Documents - Sign ITP
text | 5ce69613-8788-57ef-96d9-3662c9721deb |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Compaction Testing
label | 2345172b-c4dc-5fc0-b677-86c1770cc283 |  | note | Reference - Table 204.131 Section 204.14 c) Table 204.142
label | efdc2cf0-ac0f-5777-a2c0-3797e550db0c |  | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
label | dc464198-3c8d-525a-83c1-23cd01bcf2cb |  | note | ○ Standard Compactive Effort
label | 5d77e4ed-762f-5225-887d-5e901b3d85a4 |  | note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
label | 3e931e7c-7501-52db-87cd-3557f35faf15 |  | note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | f68ca55f-d106-59ab-bc60-0e4104f87a4c |  | note | ○ Compaction and Moisture content
label | 0a4fbbda-42df-5b44-a819-f1b90582b889 |  | note | • Scale A: Characteristic Density Ratio 99%.
label | 246b59c3-8506-54d3-8b45-eea82a6debc8 |  | note | • Scale B: Characteristic Density Ratio 98%.
label | 98efe837-3fdd-5f78-9647-31295b0d6c7f |  | note | • Scale C: Mean Value of Density Ratio: 100%
label | e1c3675a-45b0-5a5e-8bb9-38e2771004a4 |  | note | • Lot size - the leser of one day's production or 5,000sqm
label | f2210a02-c083-5746-b46f-95aed580c343 |  | note | • Testing of every lot shall continue until three consecutive lots of like material and work have achieved the specified requirements in the first test. After satisfying this requirement and establishing a compaction procedure to the satisfaction of the Superintendent, the Contractor may seek the Superintendent’s agreement to reduce the frequency of testing of subsequent lots to every second lot of like material and work.
label | 08382353-c5fc-5872-9c71-070d54672054 |  | note | ATTACH: COMPACTION TEST RESULTS
label | 3bbbe73a-e118-5eb1-b8d7-dd31ac7607e6 |  | note | Method - Review Document
label | 70d3700f-88ef-5b56-bd3b-957b1bdcb693 |  | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | 08a3226f-b143-5885-9c8d-2e331a76ea1e |  | note | Category - IP
label | c921312c-d068-589c-bd92-701fb5c52a6b |  | note | Responsibility - SE/Site Supervisor
label | a6e81cf5-5b8a-58bc-8b44-14e84b9f13ab |  | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
text | ab47b4c7-fac8-5ba2-9bc4-23109f0e52ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Preparation of final surface
label | 9b24c781-0301-52f6-ab67-e82459f83e53 |  | note | Reference - Section 204.15, 204.03 (g)
label | d9b583c2-9cc2-5001-b028-5c0e42ac694a |  | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | e3862c83-ee01-5b3f-b68b-7542e6c9df6f |  | note | Method - Measure
label | ed4f6255-30b0-5f65-a6a2-8962ba80f072 |  | note | Frequency - Top layer
label | 8e9aadf0-3e0f-5adf-ac0c-832a23cadccb |  | note | Category - IP
label | 30467f77-3fb7-5cb7-962c-19975dfb9ced |  | note | Verifying Documents - Signed ITP
text | 04698542-b2f2-5ed2-bd23-77bde2230d16 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Post Compaction Material Property Testing
label | 360219e7-8bcc-589b-bf63-614e39f7cd68 |  | note | Reference - Table 204,041 Table 204.141 Section 204.14 a) or b)
label | c5851ff8-f55e-5ff4-8560-417a2be0e0e7 |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | d92164c7-d89d-587f-86da-e5e329550b1d |  | note | • CBR ≥ 6% and Swell ≤ 1.5%
label | 97818fc0-114a-535d-9fb6-993420c0fc26 |  | note | • Max Permeability = 5X10-9 m/s
label | 2b096aa2-ef1a-56dd-aa12-65a76eab51e1 |  | note | ○ Grading:
label | 96800a91-c8a3-58c7-884b-de2bd9442ebb |  | note | • 75.0mm 100%
label | afb008c9-0036-516e-b8cf-9c4861a3c406 |  | note | • 4.75mm 40-80%
label | 9c590be7-6107-5620-8381-a9436bbbede2 |  | note | • 0.075mm 10-40%
label | 7f6e35a9-9a2b-5143-ac14-0a4dac96d6bd |  | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | ffadd300-21a0-5226-a4c1-7e0bbabc0ff4 |  | note | ○ Scale B:
label | 40489fb7-1139-5dd5-a504-6fb97d8a396c |  | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | a7c3fa0a-ac3b-5b31-ae34-a32cb9fc650a |  | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 576fd385-bcd2-5b04-9904-40894963473f |  | note | Attach: Post compaction test results:
label | 1045710d-9dd8-56e0-990d-aeec79925c14 |  | note | Method - Review Document
label | b7948c2e-3816-5d25-b402-62acc2fb9b9b |  | note | Frequency - Refer to Section 204
label | ff151421-d598-5dec-9c60-a8d5fe8bdfca |  | note | Category - IP
label | f9cc41c8-e8e0-546a-90db-cb38e4a7fcf2 |  | note | Responsibility - SE/Site Supervisor
label | 9faa9b84-20a6-50fe-a579-9c01ba4ddff1 |  | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
text | 10a98b07-9aa8-55e9-bd5e-e3d392607aaa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Survey Conformance
label | be92c2fb-eb93-510d-ad19-d3aed14f3092 |  | note | Reference - VicRoads 204.03f,g and h
label | 5f6f6e39-fec8-5bac-8c43-0d16dc135843 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 127f48d8-796d-5558-8212-47324ccbf5a0 |  | note | ○ Level tolerances Scale A:
label | 4f6d068e-bd29-5623-9272-2ac784007c7a |  | note | • Range x = +5, -15mm
label | a90325d6-4ea5-5351-8008-7ab3ae0b1e48 |  | note | • Max S = 12 mm
label | 50e2cc4d-ccb9-5215-988d-37906fe414ad |  | note | • 80 measurements per lot
label | b5784200-319f-5d39-9358-fdbc4472de9f |  | note | ○ Level tolerances Scale B:
label | 1e48be07-2ece-59d0-a181-865f69f8893e |  | note | • Range x = +5, -25mm
label | 6bf99577-f270-5b07-be2b-6e781f5d3a49 |  | note | • Max S = 15 mm
label | 78e5e603-bcd8-5b88-9c2c-c59ba999fc93 |  | note | • 40 measurements per lot
label | 6be9b64d-98f4-5ca9-8e9f-8b6dae2b0327 |  | note | ○ Level tolerances Scale C:
label | 831a17ba-ddee-558a-82c1-ad599c8374ec |  | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | 7ee7365c-1cea-5223-b01a-771287295a7d |  | note | Method - Document Review
label | 764939f0-487d-5636-b284-ba7d78a18c19 |  | note | Frequency - Top of Type A/Verge
label | 3ec689ef-8188-5e9b-bbd1-584980ac0572 |  | note | Category - IP
label | 306d8828-0fd1-5736-a4b1-146ccef0a809 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 0f69f592-453b-5ba1-b218-17af3155d40d |  | note | Verifying Documents - This ITP, Survey Conformance Report
text | 144a076e-6143-5229-9c59-99f9713efa54 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 2a4e9695-02e3-5f4e-955c-f1cedfae2ddb |  | note | Reference - MRPA Quality Management Plan
label | 0ac6cd56-1ef4-51e4-88c4-29eb5eed1866 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | f1071e79-8b53-52ee-8683-6eec9fb98b76 |  | note | Method - Document Review
label | c2bc63fb-e42b-5ff0-a010-8fcf91dafb47 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 1ae8b622-83df-5c63-9ec3-331070490178 |  | note | Category - HP*
label | 7679b883-4ef0-5bf0-b1f7-f2a5f757dcf3 |  | note | Responsibility - SE/PE/SPE
label | 12643d86-9f7a-5016-b432-f3636c1a94af |  | note | Verifying Documents - This ITP
text | 97088407-c4b8-555b-b8e1-74b7a73d71ab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0ae9d3e5-fa94-57b3-9ab4-9dd60cdd2481 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c34cd726-4ca4-55d1-86af-c46580d04874 |  | textbox | Name:
text | ebc653a5-e87e-5d4d-8970-33127db15e24 |  | textbox | Position:
text | 360777e6-6e81-5d3a-96a4-efae52176481 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | CHK-006-STR&CIV-Material Inspection-Precast Panel | itp |  |  |  | Yes | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | 5b7df678-e46c-4437-a67a-50283502bd28
checkpoint-no-status |  |  | checkpoint | CHK-006-STR-RSS Walls-Material Inspection-Precast Panel
label | bce219b7-b6fa-509a-89b5-80ff6d021552 |  | note | Document Title: CHK-006-STR/CIV-Material Inspection-Precast
label | 62961c05-6e52-5a63-b493-048af47a0ceb |  | note | ITP Description: Material Inspection-Precast
label | 1ce143f2-b648-518a-a1db-efc1c77eb957 |  | note | Discipline (e.g. CIV/STR/RAIL): STR/CIV
label | 950d4f02-af4d-5973-8fd3-59ffecf085a5 |  | note | Revision Number: 0
label | 9764aeab-0311-54b9-84e6-b971cd585867 |  | note | Revision Date: 10/01/2023
label | 1ded3da7-3f02-5fbc-9bc2-21a0425b650f |  | note | ITP created by: Ethan Caruana-Smith
label | e2410e60-86e2-54b8-925a-ccfc60b3f660 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1 - Delivery Details
label | 344ce80b-5753-5523-99ce-a6912c3581d2 |  | note | Acceptance Criteria:
text | a629c0de-2f33-5d5b-9801-eef0646c48e9 |  | textbox | Enter: Delivery Docket Number:
text | ed7ab148-de7b-54b3-b413-51c9c9dce335 |  | textbox | Enter: Delivery Date:
text | ddedbcb2-125b-5b85-81e2-ec3c935c43df |  | textbox | Enter: Element ID (s):
label | 911be025-2d1e-53c1-8338-e99cd948bf6b |  | note | Attach: Delivery Docket and packaging Slip
label | 0abd2359-95c6-5244-b6de-bc4255069a93 |  | note | Method: Document Review, Visual
label | 5579b877-be7b-53ef-9bec-0c58b7f9e63c |  | note | Frequency: Each Delivery
label | 629ea501-4efe-56f3-9aff-dd2395b02250 |  | note | Category: IP
label | 9307766b-5bb3-5a46-9bbe-d1950bfcefb5 |  | note | Responsibility: PE/SE
label | 71260619-b205-5ca3-b0fb-7c403992e3e8 |  | note | Verifying Documents: This Checklist
text | e641c54a-db88-5a91-b836-ff6697681389 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Packaging Inspection-Quantity
label | 76bf541e-3bfb-549d-9e9b-a9b1fcd55d29 |  | note | Acceptance Criteria: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
label | 88a4e3e5-040b-5011-a92b-395c8276f2aa |  | note | Method: Visual
label | bcc67610-b032-5fa3-9471-d264cd7ea468 |  | note | Frequency: Each Delivery
label | e557bc2f-fdfa-5169-a109-7ca26a5b001a |  | note | Category: IP
label | 73c1b1ed-5ec6-50fc-8072-c59d35d829da |  | note | Responsibility: PE/SE
label | fd0d2c3f-cf93-5fce-a58c-d760a84fc116 |  | note | Verifying Documents: This Checklist
text | 140fa2d4-5566-520f-a50c-02b817f55816 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Packaging Inspection-Delivery Contents
label | 718f4e51-e2b5-52ab-bf55-0233fdd7bd68 |  | note | Acceptance Criteria: Do the contents of the delivery match the freight list/packaging slip?
label | 23f60db6-3ee5-5b2d-ab6c-fd7bffb8a9b2 |  | note | Method: Document Review, Visual
label | 8e04e7cb-e915-5601-9abe-816ead3a9461 |  | note | Frequency: Each Delivery
label | cc95b07b-7874-5dbc-aad4-a218ec958020 |  | note | Category: IP
label | cce42478-14e2-5252-adc0-705f2506bf9b |  | note | Responsibility: PE/SE
label | 5bca7a69-a2d7-5106-9e2a-72a8ea0c2b85 |  | note | Verifying Documents: This Checklist
text | 2bf60b37-269f-541d-be21-67294c071223 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Packaging Inspection-Birth Certificate
label | 35276d7d-24e2-5302-8605-48974734332f |  | note | Acceptance Criteria: Is the delivery accompanied by Precast items Birth Certificates?
label | 3c50eace-c753-54a6-8660-e9ab5f91cc31 |  | note | ○ Precast components are to be marked on the birth certificate.
label | 3f02192b-5489-5330-9035-2bc61686b8e2 |  | note | ○ Cast date and lot are to be marked on the birth certificate.
label | 6c87b04e-a44a-5f8a-80b1-48ee2c1b6b6b |  | note | Method: Document Review
label | 71133996-3eb3-5aed-bd0d-8473062cc67a |  | note | Frequency: Each Precast item
label | e347bacc-d21b-554d-a5eb-63c78e225738 |  | note | Category: IP
label | a458bbf2-2456-544d-815e-4a116ce3fcf7 |  | note | Responsibility: PE/SE
label | f454f1c5-4c26-5b5c-b7e2-7e726824dac6 |  | note | Verifying Documents: This Checklist
text | a8077aba-0b0f-5c84-9b5b-0a2020cb087d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Packaging Inspection-Transport
label | 208f2510-4016-5f4c-841f-c52ca7b1c3bb |  | note | Acceptance Criteria: Is the condition of packaging acceptable.
label | fc0a0845-30af-564b-ab57-b6a1815f2676 |  | note | ○ Precast items are protected from damage during the transport
label | 4a5e3b29-eee2-5e84-85c0-054fbacaf1c3 |  | note | Method: Visual
label | d3a33d85-a83d-53e9-9b70-e491657a3295 |  | note | Frequency: Each Precast item
label | 4eecb52b-2993-522e-9bfe-aa789a6b9534 |  | note | Category: IP
label | 805c2a14-74b4-533a-ae3c-2a408f40b3e3 |  | note | Responsibility: PE/SE
label | c20d38ea-0fcc-5cff-badf-4eeab1b27ab2 |  | note | Verifying Documents: This Checklist
text | b42deda3-3aaa-59a9-8819-0bb96f1ae887 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Fault IDs:
label | af9bf072-4f51-521f-94a1-83f10f055a9a |  | note | Acceptance Criteria: For each precast type delivered, check for the following:
label | 8541fd75-648b-55c4-afaa-ef964e5ff77a |  | note | 1 - Identification markings match the element type
label | c316d1fe-42e7-5560-ab05-b043d1ca8cf5 |  | note | 2 - Element fabricated as per drawings
label | 82259ea4-a5a5-59a9-8a2a-0616685da0f7 |  | note | 3 - Cracks
label | 851b6e38-d72c-541e-b19b-799c7d6b0ab1 |  | note | 4 - Spalling/Damage to concrete surface
label | 826a8a98-4894-558b-a698-aa0c9e299923 |  | note | 5 - Exposed Reinforcement
label | d78fc058-a6a2-5d28-a4a9-509d269f2086 |  | note | 6 - Damage to Anti-Graffiti coating
label | d1970c36-8287-543c-9c5d-d9c365cfee96 |  | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
text | 262ffce6-2486-5b9d-b791-74d50d690fa8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 1
label | 37482a30-1ad4-560e-8366-0ec4902552f2 |  | note | Reference: Item 6 on this Checklist
label | a65fdb1d-405a-5dc2-8fc2-375fe1f58e75 |  | note | Acceptance Criteria: For Each Precast type delivered:
text | 32800972-51f6-548e-9949-1f21a90503fd |  | textbox | Enter: Panel Identification:
text | 1bb34d5f-0a39-5091-9332-cf51e2cf6299 |  | textbox | Enter: Quantity:
text | c0b0aa8b-f59a-5943-b388-2dc4539679cd |  | textbox | Enter: Fault ID if any:
label | e7dbac52-3713-5b16-8ccc-0f6a360c87b5 |  | note | Method: Visual, Measure
label | fdbb5875-a28c-51aa-83f8-5763c3c8a6fb |  | note | Frequency: Each precast type delivered
label | e75086b1-a267-5767-a15c-d07a2118f337 |  | note | Category: IP
label | f930b2e1-c860-512b-80f7-89c775e2caa1 |  | note | Responsibility: PE/SE
label | a56cfd6a-d90c-56b1-86cd-4a9b472fdb5f |  | note | Verifying Documents: This Checklist
text | 98e84f62-b5d5-5e6f-87a6-b459537b992d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 2
label | dd3718ae-8a31-5703-bac3-58a624e8c7c8 |  | note | Reference: Item 6 on this Checklist
label | a511ad41-f344-538e-9ab7-597f812f962e |  | note | Acceptance Criteria: For Each Precast type delivered:
text | 0550e532-2b50-54a3-ad43-daa88b8ecd56 |  | textbox | Enter: Panel Identification:
text | 4d792993-ce62-5455-904a-40089d3bb480 |  | textbox | Enter: Quantity:
text | 66d327e0-5346-5fee-885f-4d4c074c33b9 |  | textbox | Enter: Fault ID if any:
label | 14125e41-4a60-52d7-b020-9ba921fba05b |  | note | Method: Visual, Measure
label | e8062087-ac7b-5c23-956c-211db93a9bf1 |  | note | Frequency: Each precast type delivered
label | 8e0f2283-293b-501a-906d-8d31b5cfb5ab |  | note | Category: IP
label | 6ba7b633-d848-5a01-9f5b-68d5b5515d5b |  | note | Responsibility: PE/SE
label | acbd4257-5087-5db4-85b2-d05d2c8a618a |  | note | Verifying Documents: This Checklist
text | 25d8f4b2-9d6e-59aa-8e6f-8927df7f9e21 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 3
label | 335bf7cb-77dd-565b-ac96-d07bafaf09be |  | note | Reference: Item 6 on this Checklist
label | e42fad3a-7a16-5e73-99a8-ae631da951a1 |  | note | Acceptance Criteria: For Each Precast type delivered:
text | fa43809a-d1a3-59cf-9517-28d0d61431ed |  | textbox | Enter: Panel Identification:
text | 0d0e22cf-8cf1-5325-aed6-4594fe24eb82 |  | textbox | Enter: Quantity:
text | 83dd9ba2-8bda-5467-ad0e-0731b8785de9 |  | textbox | Enter: Fault ID if any:
label | 4edd7b19-5fc0-5466-baa8-d8cec5e4feb0 |  | note | Method: Visual, Measure
label | d4ce2b9b-4c0b-56e5-97b6-a7a41d948ac1 |  | note | Frequency: Each precast type delivered
label | 688102aa-fe76-543f-b031-56e3e0ace731 |  | note | Category: IP
label | d9ceb319-3444-523b-a41a-cf92b3bfe3bf |  | note | Responsibility: PE/SE
label | 3109b6ba-21c0-5356-8bbf-fea3086df10f |  | note | Verifying Documents: This Checklist
text | 87c2f0ee-2ad9-52d8-95d4-ec5cc9283fc5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 4
label | 0d302f9d-fbf9-532d-9af0-e11652c024d5 |  | note | Reference: Item 6 on this Checklist
label | 06df5cff-6cb5-526c-ae61-8d74a1bc003d |  | note | Acceptance Criteria: For Each Precast type delivered:
text | 147f2266-9a23-5470-8f93-39abf8296e05 |  | textbox | Enter: Panel Identification:
text | 26223c47-0c3d-566e-969c-d937ddeb75b5 |  | textbox | Enter: Quantity:
text | 1a730ba1-1f74-5103-84c6-9cc1cf71ae43 |  | textbox | Enter: Fault ID if any:
label | 3f54e94b-763e-5f68-ab61-bef25e849b27 |  | note | Method: Visual, Measure
label | 4233fa42-2ed0-504f-b5b9-78b3fd5d7214 |  | note | Frequency: Each precast type delivered
label | 546e4603-0b33-5b75-816c-5bd8d1d66f17 |  | note | Category: IP
label | 4eaf04c8-1dfe-5073-9a20-5cfaba5aead9 |  | note | Responsibility: PE/SE
label | ec2151c7-b2e7-5e62-9da8-4e5fe60437ff |  | note | Verifying Documents: This Checklist
text | f9aca46b-b30d-5027-8165-b291842bd845 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check for Faults - 5
label | 849d9e62-b59a-53c0-84c1-97ee3f200dc8 |  | note | Reference: Item 6 on this Checklist
label | c98474e7-58ce-506c-b9cb-5a55bcec9e6d |  | note | Acceptance Criteria: For Each Precast type delivered:
text | 78352b2b-44b5-5ace-9f97-3af61f839659 |  | textbox | Enter: Panel Identification:
text | dce07498-f44f-5b95-aba0-51daf463fe2e |  | textbox | Enter: Quantity:
text | dde847dc-9ef9-5a83-b463-c1ea08bf8887 |  | textbox | Enter: Fault ID if any:
label | 7c0b39d2-b830-5219-8000-3e13af81b9e7 |  | note | Method: Visual, Measure
label | 61812628-a897-5161-8c0e-d00f22b6819e |  | note | Frequency: Each precast type delivered
label | 49b629f6-453e-5b61-851f-32f2ebac15de |  | note | Category: IP
label | 0565b5a9-e2f9-5a0d-af6c-0019e6f3beb6 |  | note | Responsibility: PE/SE
label | 93cc506e-37fc-51ad-9936-80129e34717a |  | note | Verifying Documents: This Checklist
text | 9499e010-7f54-5b56-ad3a-6fdc667b1797 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | a83172ee-8ad7-5893-bc6f-92943ea5b3d0 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c19cd29a-ae10-5504-8728-2f3c5f66ebc4 |  | textbox | Name:
text | fb7803d9-b823-5eb4-a4ff-cc4ffe6ae410 |  | textbox | Position:
text | a3c967d9-8366-56f9-b8b5-c56c995b9989 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-049-CPD-RAIL-Calder Park-OHLE Wire Regrading | itp |  |  |  | Yes | ITP-049-CPD-RAIL-Calder Park-OHLE Wire Regrading - Rev 1 | 7efa8c2e-b70e-48d9-bb2d-4b498511bc9a
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | a32b4918-940b-59df-b037-fa678be9004c |  | note | Document Title: OHLE-ITP-MRPA-Calder Park-OHLE Wire Regrading
label | b24f3662-d736-5c6d-8c24-1d295100b84e |  | note | ITP Description: OHLE
label | 25492ccc-2582-53b0-8943-12fa0f2c38ee |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | ad3f5baa-9994-5773-8391-035c461cc5bb |  | note | Discipline (e.g. CIV/STR/RAIL): OHLE
label | 2ff6095e-5e05-59bc-8c1a-3f3a106d120f |  | note | Revision Number: 1
label | 7b1e0a27-d0fd-585b-ab34-32628600583d |  | note | Revision Date: 24/07/2023
label | 76f350fc-106a-58a1-9353-3bfa21a11786 |  | note | ITP created by: Kevin Liang
checkpoint-status |  |  | checkpoint | 1.1 - Overhead Line Electrification
label | b0e71249-5732-5839-8aa7-204459f9897d |  | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
checkpoint-status |  |  | checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | 7779b8a7-1e6b-53c9-8f90-7b8dbcb2306a |  | note | Reference - VRIOGS 001 AS 4100
checkpoint-status |  |  | checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
label | 030b68d1-71cd-5c0e-9f23-0387c5c47313 |  | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1)
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Procurement Materials delivered/collected to stores/Site.
label | 54441720-fbb6-54e2-8cc1-9ca4f15bccfe |  | note | Reference - Contractor - Site Material Control procedure.
label | c0bce270-39db-5290-9909-bc2c47a7b758 |  | note | • Cat5 Material received -Calder Park Tracking sheet
label | 3b6ef55b-9201-5c65-a128-3585c4986c4e |  | note | Acceptance Criteria - Ensure materials are delivered/collected as required.
label | f4ee23b4-670b-593e-a89a-961727b3bc66 |  | note | • Certificates of Conformity provided by MRPA
label | bd78a38b-586f-5ad2-9406-72a4423dad64 |  | note | Method - Document Review
label | caab6fb3-90b0-5893-a66d-d122f9b1eee7 |  | note | Frequency - Once for each supplier, prior to works start
label | f955e49b-709c-51b7-bd0c-72cb3503037e |  | note | Category - IP
label | 30a7aad7-fe4b-5159-b948-7cb08e009544 |  | note | Responsibility - MRPA Issue, CAT5 Receive
label | bb90ef3a-5489-539e-a3ec-461a9040c153 |  | note | Responsible person - MRPA
label | 3ad1ec87-e13a-5674-9029-aa29982fd44b |  | note | Verifying Documents - This ITP Signed Off
text | df87d913-b5da-5e87-8523-c5a62b89408c |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Produce Work Package Plan
label | 647875d4-ab8c-5fa6-8e49-391202f8d49d |  | note | Reference - Work Package Plan
label | b7610fde-5ea1-56cc-a47e-805de3163062 |  | note | Acceptance Criteria - Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
label | def1689c-a197-56e6-aa61-18cc255c16bc |  | note | Method - Document Review
label | e2870b42-77a5-5e1b-84d1-5d9ad90f550d |  | note | Frequency - Prior to Works Start
label | 47a18377-211b-5f96-9465-1915acc64675 |  | note | • TBC in accordance with MTM Standards
label | c9c74a07-8335-5d37-b59c-c4950b67d386 |  | note | Category - HP
label | c95f874b-9c52-57d4-a123-382c705256e6 |  | note | Responsibility - MRPA/CAT5
label | 6358471a-4c1a-5c3b-b892-558e74d1ce70 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 2860e522-3ee5-5c5e-a9f2-a0971b13b4ad |  | note | Verifying Documents - This ITP Signed Off
text | a0b619fa-dc12-5c02-b0dc-232aa45ee6a2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Approval of IFC drawings
label | 25dbfc00-e399-5ca6-abde-bdd51077fc7f |  | note | Reference - Contractor Design Management procedure. MRP-DPK-060-00-ETN
label | c269feec-0bfd-5bcd-a7ae-31831e3339eb |  | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
label | 404e5e9a-64ee-5f13-af6d-60a00acf2835 |  | note | Method - Document/Drawings Review
label | d9b6a5e5-4e8f-5d34-8329-36b075237912 |  | note | Frequency - Prior to Works and at regular intervals.
label | 158fd854-05e8-5929-b1ff-e8ff8acf739c |  | note | • TBC in accordance with MTM Standards
label | f782056f-48db-56be-b252-bb05cab118de |  | note | Category - HP
label | c870d3db-8fde-5b4b-951d-4fdb1182d6c6 |  | note | Responsibility - MRPA/CAT5
label | bef60c99-85cf-5472-8b1c-1100aa422779 |  | note | Responsible person - MRPA/CAT5 Engineer
label | a50307b9-ad1f-5342-8248-d328ef67cd0f |  | note | Verifying Documents - This ITP Signed Off
text | 4699bce0-8eec-568f-8233-df558510a9b4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Task Specific Permits
label | f5693ae4-51d0-5bdc-b68c-01197ecbde09 |  | note | Reference - Working at height permit. OHLE SWMS
label | be6a0bfa-dd26-5850-a84b-e6a0ccba74dc |  | note | Acceptance Criteria - Ensure all task and activities have relevant permits issued and received.
label | 3eac8767-508d-59f4-9ee7-be71a87a6bbd |  | note | • Task Permits to be generated and signed off by appointed person.
label | 2547ba90-72b5-58a6-8515-04a29f67b073 |  | note | • Task specific documents - MTM to issue permit to enter/Isolation permits etc.
label | ec1b4d5c-2480-5ec2-9cd1-e3f9b8b800c8 |  | note | Method - Visual, Document Review
label | bd3bdf82-9a9d-5848-a0c7-3c9a5b8d5558 |  | note | Frequency - Each Task prior to works start.
label | 6620f226-5971-5a24-af39-b497cb6a2c99 |  | note | • TBC in accordance with MTM Standards
label | 40a14e7f-b66b-5731-91c6-ab61c1901611 |  | note | Category - IP
label | 6e65d00b-e6e7-5885-93fc-6577fc136f31 |  | note | Responsibility - CAT5/MRPA
label | 69bdd03a-23f7-564d-bf66-f14fd2b487f5 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 4bdad0fd-9bed-5fd3-b8ba-3d3c30b28a64 |  | note | Verifying Documents - This ITP Signed Off
text | 561ca558-88d3-5449-8222-081dd03ace9c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Cantilever assembled.
label | c6f514ff-5b85-5b76-ae5f-db71e1a92cc2 |  | note | Reference - Cantilever assembled as per IFC design.
label | 54410576-e071-54ff-b894-47642dcfb53c |  | note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | 7f70a447-3296-5b97-8bd5-2048bdd1bbe2 |  | note | Method - Visual, Document Review
label | a7662440-4f59-5384-9cc0-c18322251eed |  | note | Frequency - Each Task prior to works start.
label | 1717de01-4438-5896-9e4a-6cc21c133f83 |  | note | • TBC in accordance with MTM Standards
label | 66fb8fcd-5d20-5803-947d-2c01af582821 |  | note | Category - IP
label | 49523014-be97-58e2-8c29-29682e00ef57 |  | note | Responsibility - CAT5/MRPA
label | ec8d59bc-7c66-5544-9eef-38c773955d85 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 81932f57-0373-533d-bf5d-69ce22f26c5c |  | note | Verifying Documents - This ITP Signed Off
text | 63e8aec9-4f7f-5b12-b365-f2664527ba8e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Pre-Installation check
label | a91c08d8-6384-5fa7-8087-08a9303875c0 |  | note | Reference - IFC wiring layouts, IFC cross sections and BOQ.
label | e3b8e6f6-0331-5c47-9aa5-1c9618f488c3 |  | note | • Engineering Drawings Management Policy (IFC/As-built) L1-CHE-MAN-001
label | 4d69206f-9f12-5690-97ef-16cb37c70214 |  | note | Acceptance Criteria - Ensure that locations matches most relevant IFC drawings
label | 2679c460-2750-5b67-aaf7-ceb62daf332b |  | note | Method - Visual, Document Review
label | 0e3016a0-62c0-5177-949f-8ce5a19f84d5 |  | note | Frequency - Each Task prior to works start.
label | 5e5f481c-b1ff-5c60-af3d-4f1b54ea2fee |  | note | • TBC in accordance with MTM Standards
label | 27998cf5-0dc6-5138-847c-2ae77523d8fe |  | note | Category - IP
label | 7ba89816-325d-5da0-b30c-b8a1dd8c3559 |  | note | Responsibility - CAT5/MRPA
label | 04ebf7e0-da85-5683-8f77-13716a65ffc9 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 61814104-be95-57a7-b96d-314684428da6 |  | note | Verifying Documents - This ITP Signed Off
text | 88c96d68-69d4-520d-8f87-9c05a72db722 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Cantilever installed.
label | 46babaf0-d542-598d-b243-d16c8d31c5af |  | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | a0e36c4d-6bf9-510d-b641-fbdd9f666b6a |  | note | Acceptance Criteria - Work instructions in accordance to IFC design
label | f1dda229-c289-5dc6-b5bc-bc493e5eb90b |  | note | Method - Measure, Visual
label | 4b902408-c214-568f-833f-f2ffe38b040e |  | note | Frequency - Each OHLE Structure
label | f0dce753-f7e9-5016-ac82-1dcf63e778ea |  | note | Category - IP
label | 87b88d2d-ef3f-55d8-a17d-484bec024cf9 |  | note | Responsibility - CAT5/MRPA
label | dc03a787-ba63-5fe8-a9cc-39c40e54c438 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 8c039af6-eaec-53fe-8fae-14f26be2a424 |  | note | Verifying Documents - This ITP Signed Off
text | cbdf85a3-28cc-5a29-a0f1-c6d557a5142f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Install SPS to correct height / position relative to track
label | 3f49ec51-9932-514f-9d17-d8b2047e4e26 |  | note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | dcbc225e-93bf-5ae4-91a4-f1431fdef5ff |  | note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
label | e995ab48-9f4a-5fdc-a87c-8c29d0047dbc |  | note | Method - Measure, Visual
label | c5ee7828-1c17-5ea1-ae0a-201fc80dd52f |  | note | Frequency - Each OHLE Structure
label | bab6a7d8-c23b-504b-9816-35f7129d979e |  | note | Category - IP
label | 53bc6145-954b-5c67-91c5-7df31f70320e |  | note | Responsibility - CAT5/MRPA
label | 82b42f6e-d39a-53e6-ad04-6eaf22c66661 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 908bbc34-b7b1-568a-8f29-656ca5be4740 |  | note | Verifying Documents - This ITP Signed Off
text | 05777c99-1d8c-5e24-a52d-0175c6596b40 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Cantilever checked once installed.
label | acf75bd7-67eb-5787-a3e7-c23d8f3be8ab |  | note | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet.CAT5/OHLE/CHK002
label | 10373dc7-d52e-5cb4-8e0c-a2eeba8b1597 |  | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
label | 3e19309a-fb3a-5912-9c71-1862aa63d414 |  | note | Method - Measure, Visual
label | 9a8f3773-f711-5484-935f-a0025e4efe38 |  | note | Frequency - Each OHLE Structure
label | 3eef33ed-d060-5161-818a-67b77e065384 |  | note | Category - IP
label | 80e4972f-c054-579d-a4ec-64409289227d |  | note | Responsibility - CAT5/MRPA
label | 59773a61-49cc-5c46-8218-8c175358af61 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 262efde4-d01c-5504-a1b4-d422bb6fc0a4 |  | note | Verifying Documents - This ITP Signed Off
text | fd70e711-a0cf-5756-b39e-9479e50515b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Installation of wire supports at the correct height and stagger.
label | 0cfcd28f-03ee-56d3-9c6e-12b45a52ecf5 |  | note | Reference - Install as per design drawings.
label | e4efe236-000d-534c-8644-905b6ae8c1e6 |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | 5bcca83a-6398-53fc-9a89-0f11b0d4e902 |  | note | Method - Visual
label | 03b9fe89-920c-5c59-bd3d-3194104e6528 |  | note | Frequency - Each OHLE BWA structure
label | bb3c2c82-e2a7-5e35-9c20-b9cad02f8ec2 |  | note | Category - IP
label | 1c77a65b-a7b8-5fa5-b9e5-f764a2da5b8e |  | note | Responsibility - CAT5/MRPA
label | 9fab31a5-26b9-5f93-ba2c-af1437e999c1 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 3a6c2ea2-2def-5657-81c8-767ff34c380a |  | note | Verifying Documents - This ITP Signed Off
text | a15d33f4-22a2-5f9b-b57d-1f8b9ba971b2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Installation of small parts
label | 01a6bf55-fe0e-5dae-8cea-a806ac0f6a33 |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | ff75c1b3-9a05-5327-a803-83a409b6f2a3 |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | 5fe3c8d8-b4c5-538e-b3c6-70bd9f1b32e4 |  | note | Method - Measure, Visual
label | bae12386-ad01-5f14-ae96-021dd9689cda |  | note | Frequency - Prior termination
label | 049e82bc-b4c4-5efc-9ffc-ea355c0bd9a1 |  | note | Category - IP
label | 300b6b3a-112f-5c8b-a643-8f261499ad9b |  | note | Responsibility - CAT5/MRPA
label | 3d3a7935-ef13-5990-8128-3867d448141c |  | note | Responsible person - MRPA/CAT5 Engineer
label | bac1c9f5-f9e6-5bc6-b914-80fc885e216c |  | note | Verifying Documents - This ITP Signed Off
text | 8adb4494-5bf8-5d89-8fc3-a087a0ae59cd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Complete Clearance Checks
label | 96e12612-ca9c-5885-b9ac-ea845f610e0b |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | 8d8dd6ad-0c7c-5279-bfd3-9e5298846e68 |  | note | Acceptance Criteria - Visual inspection for clearance and wire staging from Hirail EWP
label | d4940203-2538-59aa-acc6-f58d35656e06 |  | note | Method - Measure, Visual
label | e87512dc-8f7d-55cd-9cb9-9f8a70d2416c |  | note | Frequency - Prior termination
label | e0f6ce63-5600-59a5-a195-1c99018bf51a |  | note | Category - IP
label | 15a4daf7-81fd-56af-91a2-8b51fd545ce5 |  | note | Responsibility - CAT5/MRPA
label | 0ecd002e-102c-5c4e-b7f6-d82cd9dcabf7 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 28ff49eb-cb96-5369-a071-2264c7ce497a |  | note | Verifying Documents - This ITP Signed Off
text | 2a42cc65-30bf-5c9d-a604-923a29fc6dc1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Complete Pan Run Test
label | 81a48cdb-b208-58b7-8f97-d9992f0d3c0c |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | 65116da3-f7c2-5698-bea3-4cd747d22d13 |  | note | Acceptance Criteria - Check for wire take up, clearance, stagger limits and pantograph interaction to the contact wire
label | 04e8a10e-15e7-50a2-8ec0-2506a6f4ba73 |  | note | Method - Measure, Visual
label | 27fc42ac-2c22-5399-b825-773b5a6d4b00 |  | note | Frequency - Prior termination
label | 3b7fe085-bbd2-50df-b813-7e8473721916 |  | note | Category - IP
label | 596278d9-8f1c-58bc-8afc-d3eff7febff7 |  | note | Responsibility - CAT5/MRPA
label | cc9798b7-c56e-5b0b-9612-51270f42fbbd |  | note | Responsible person - MRPA/CAT5 Engineer
label | 9b901689-cef1-59e9-9587-5de88a4d0297 |  | note | Verifying Documents - This ITP Signed Off
text | bd832821-46fb-53de-bc27-03938d98398e |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Defects/Temporary Works
label | eec8f481-2a40-502f-bc3b-44b3db3ac3b3 |  | note | Reference - IFC wiring layouts, cross sections and design drawings.
label | 98ef030a-e015-59fc-861a-d66f37749259 |  | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
label | e6cb15dd-ea29-5e22-94d3-6602589e7e20 |  | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
label | 640fe297-343f-55d0-9da0-a273f1af8169 |  | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | 4de6b930-d150-57d4-adf4-34d54d0e6d5d |  | note | Method - Document Review, Visual
label | d9f9dedd-c24d-53bf-b0dc-cb2364dce366 |  | note | Frequency - Each OHLE Structure
label | 3c96d655-8276-5b16-8eb8-982d5b411e5a |  | note | Category - IP
label | 90f688aa-dd5a-5007-86f8-604832b8845a |  | note | Responsibility - CAT5/MRPA
label | f2cf3eaa-589b-5e8c-8be7-7d4c955441bb |  | note | Responsible person - MRPA/CAT5 Engineer
label | e76874d9-3dcf-5f2e-9e56-653fda0eab08 |  | note | Verifying Documents - This ITP Signed Off
text | 52c032e1-d094-5125-9a04-2b491f96d651 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
label | 73fd6133-97c5-5748-b0e1-5c77ae4044cc |  | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
label | 90fca279-7bd9-5a24-ae89-1645d315c920 |  | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
label | 8f162cbd-862c-53e5-ba1f-e5836b38d5d9 |  | note | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
label | 26fe2918-5922-5ca0-966c-04d0b2be1918 |  | note | Method - Document Review, Visual
label | 9adac229-0d5e-5586-bb68-e2e8fc5630f2 |  | note | Frequency - Each OHLE Structure
label | 298e6225-2bdf-51e5-9c2a-5fe7706f7151 |  | note | Category - IP
label | 5f7262c5-45a7-5c09-9b34-c6efe70a3d5f |  | note | Responsibility - CAT5/MRPA
label | 2a95a4ec-feb4-53a3-8be8-9d26485dda4f |  | note | Responsible person - MRPA/CAT5 Engineer
label | de63686d-8807-57c4-a5ce-245df97f28d9 |  | note | Verifying Documents - This ITP Signed Off
text | 8ac3918d-1b09-5b6e-9c72-ddc29fd4ca8d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 34ef5da5-0fd8-5c77-a52f-1f90a7f17d3d |  | note | Reference - MTM Quality Management Plan
label | e30c34da-27c4-5d0d-8323-6e6871e15db0 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 20fdd725-2040-5c87-814d-52fc7256a97a |  | note | Method - Document Review
label | 50b5cab6-21ae-5c0a-8081-ab21758dac42 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 3e43dfd8-96ac-552e-b248-e9fb750b7f5a |  | note | Category - HP
label | d6071b4b-2cfb-5ef2-abe4-cadbdf8a2a75 |  | note | Responsibility - CAT5/MRPA
label | 57deea1c-4c99-5837-83d7-970e1b715070 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 121d5590-2517-53cb-bbc6-6938e940adc5 |  | note | Verifying Documents - This ITP Signed Off
text | 687d1eb8-2574-5c17-a9df-7c2123e8bf5d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 9b47ebcf-8d0c-5760-aaac-2b4d451d3fac |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 6819ad12-5e86-5f4f-a24e-08239dab2609 |  | textbox | Name:
text | 7b5045be-d17f-5b25-b8da-95c5214d527c |  | textbox | Position:
text | 49fce55a-18dc-5059-9808-a61c0ae69067 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-045-CIV-CPD-Subgrade Preparation - Road | itp |  |  |  | Yes | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | 9430c0e8-7582-45cd-bdc8-07b023f65665
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 7528f190-4343-5025-8b1e-528d2d9de0f6 |  | note | Document Title: ITP-CIV-CPD-Subgrade Preparation - Road
label | aaa761ab-3732-580d-9648-a5cd54f95c3b |  | note | ITP Description: Subgrade Preparation - Road
label | aab28051-4d93-54b3-b9ab-33ceaa561a9d |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 5c1d458b-4804-521b-9d62-ba7b625d9a5d |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | 437a1dda-629e-52a0-a8b0-041f8633de3c |  | note | Revision Number: 0
label | 60823dcb-b438-5709-8bc9-c8433430c392 |  | note | Revision Date: 12/07/2023
label | a034d993-29b4-56be-ad05-f59c38b94c9c |  | note | ITP created by: Matthew Dib
label | 1ec0b0cc-c1f5-56ae-8819-961862550527 |  | note | ITP approved for use by:
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 8001842c-e8f6-57fb-b222-6919b0f65418 |  | note | Reference - VicRoads Section 204
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 0b420d85-5188-58ba-ac75-13e88ef529d3 |  | note | Reference - VicRoads Section 173
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Non Dependent
checkpoint-group |  |  | section | 3. Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Non Dependent
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-Out
label | 92b8bc7c-0f24-5f3f-8d04-19e7fafeb1cd |  | note | Reference - IFC Drawings
label | 69784157-e96d-5af0-a8c3-23c13af41a7d |  | note | Acceptance Criteria - Area has been set out in accordance with the drawings
label | ff167d6c-9f9e-5592-83a3-fdff8f3589db |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | 3d41f110-1874-5e5b-9fc0-17cb21b10254 |  | note | Method - Verify
label | f5973371-b5eb-5762-bbc6-fb5d33154ed3 |  | note | Frequency - Prior to commencement of excavation
label | c8bfbfd9-1af2-56f2-bb39-627c5e221c96 |  | note | Category - IP
label | a9f9025a-de76-5f2b-b26a-50fd2d30869a |  | note | Responsibility - SE/Surveyor
label | 013ee332-2057-5223-a622-210662cf1ab3 |  | note | Verifying Documents - This ITP
text | 4e8b7852-b687-5215-a0c4-da98a49cf4f6 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
label | 2bdd789a-590b-550e-9877-560dadc46cd6 |  | note | Reference - Section 204.06 (c) Section 204.06 (e) IFC Drawings
label | ae0922c9-49c6-59c7-836d-69f6aacee5d7 |  | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | 592e1378-f6da-5917-b7c5-f14a0fc5ea75 |  | note | • Assigned CBR ≥ 2.0%
label | 753d4573-6990-5138-9b66-4f45131492e4 |  | note | • Assigned Swell less than 2.5%
label | 8bddbe8c-736c-579f-9c5a-00ffd80d1a99 |  | note | • If parameters are met, rip and re compact to a depth of 150mm.
label | 78fc6b54-23d9-51c4-b940-c7fc22f262c2 |  | note | • If assumed design parameters not met, remove 400mm of material and replace with conforming Type B fill.
label | 3badb9dd-e517-528a-9b45-d84c6c65f2c0 |  | note | • If existing material needs to be removed and replaced with Type B Fill, ITP-CIV Type A/B Fill - Road is to be utilised.
label | ecf92566-2511-5e3c-bb1c-2333101b8f72 |  | note | Attach: Laboratory testing Verification:
text | 9e84f50b-1a6b-52a6-936f-53c051b760cf |  | textbox | Enter: Type A/B fill Lot Number:
label | 55d72201-f997-533f-9d5e-23be8434b22c |  | note | Method - Verify-Document Review
label | b38f8eba-0704-5b66-8017-2847545f72b7 |  | note | Frequency - Each lot
label | 5f14b3dc-576a-55fe-9a2c-ecdcc7fee1d9 |  | note | Category - HP
label | 52ee2822-4898-58a8-a671-054db7a9d298 |  | note | Responsibility - PE/Nominated Authority
label | 8792767d-86cb-5c6c-9322-56454fb74e15 |  | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
text | ef8771b3-be1f-532d-b8ec-1311e5e3b26b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Material classified as silt
label | 47c295e5-d53c-5a3d-a69c-d45140037f47 |  | note | Reference - Section 204.04 b)
label | 9f071f05-e20a-54e7-a056-6f89f7791b07 |  | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
label | 70e04e18-557a-558c-8d71-cfbd719636e1 |  | note | Method - Document Review
label | 61dec7c8-c92d-5362-a773-10b7b0a7999a |  | note | Frequency - Prior to commencing
label | ba41a107-e41f-5fcb-96a7-c3cdb6951451 |  | note | Category - HP
label | 42a3433c-dfa3-542f-aacb-e1822486378c |  | note | Responsibility - SE/Nominated Authority
label | e0ad02b7-e98e-56bd-a674-652e4b9c2789 |  | note | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/ records
text | 642aac42-4690-574d-8057-d68303bb2756 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
label | 76b47cd4-cc3b-5c7e-8d87-f08bcf9d4089 |  | note | Reference - Section 204.06 f)
label | 64fc65df-f123-5d91-88dc-0572cd2ea923 |  | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | a6015c38-efbf-59e0-a517-764dff1cac5d |  | note | • Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | c38d6e61-adb1-5559-9d5e-62bce7fb5db4 |  | note | Method - Site Inspection/ Document Review
label | b31b64af-b876-5e40-9dd1-9751636574e6 |  | note | Frequency - Prior construction of the regulating layer
label | 77763d8a-60ce-5aaa-8330-e248b24ae92b |  | note | Category - HP
label | 6c53df8b-354d-5e58-8d6f-531e41aede24 |  | note | Responsibility - SE/Nominated Authority
label | b7aeb5ac-2283-560d-95d3-52cdc0f6a486 |  | note | Verifying Documents - This ITP
text | 0f1c4a40-bf8d-5e15-92eb-cfb1e25f2ce7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Unsuitable Material
label | 28637f27-eaf7-5be4-88da-777592a2daf8 |  | note | Reference - Section 204.07 d)
label | 4ee12dad-2e21-58a0-b273-0c7dbb8c729a |  | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | 6a657f8e-ae64-5f69-99a7-7e1e1b9866dd |  | note | Method - Visual inspection
label | ab393f88-697d-547c-891a-6d7e78973f03 |  | note | Frequency - Each lot
label | 77bad8b5-45a8-5f90-9c35-d663e4f73afc |  | note | Category - HP
label | 79f88cef-cac3-5aec-985f-506b9bbcf11a |  | note | Responsibility - SE/Nominated Authority
label | 341c15c8-e2e0-5dd3-b553-1cd4cc68d14e |  | note | Verifying Documents - This ITP
text | 25d2ce05-845f-5da8-89be-97ff1260146e |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Groundwater
label | ef343f13-e50b-5da7-8a84-e093c4d5a21c |  | note | Reference - Section 204.06 h)
label | 553a028e-a3f3-5266-bba5-6377136eed5f |  | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | 4224f83f-f9cb-5cff-89fe-b1c8fae0c323 |  | note | • The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | c5fcd095-4929-5abc-97ab-e5fe82d60455 |  | note | Method - Visual inspection
label | cb35badf-1863-5735-b1c1-ae4e765516b4 |  | note | Frequency - Each lot
label | a6f3a1bb-a48f-56d2-b31a-07b7f663ae6c |  | note | Category - HP
label | e8ec8778-934e-5ac4-b845-7d428923cdc7 |  | note | Responsibility - SE/Nominated Authority
label | 321c9b77-559f-5c77-8850-2e0d0029e0b2 |  | note | Verifying Documents - This ITP
text | 5cc29c93-d7de-5004-bc70-edbf8bd26523 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Cut to Fill Zones
label | ef28fff6-7581-5a5c-ab8f-4b05185198c4 |  | note | Reference - Section 204.06 g)
label | 3740c484-3c6b-54eb-8dab-33ba06d58700 |  | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A/B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A/B material.
label | d2067d64-9d70-5c10-a702-ce2fda4178e0 |  | note | Method - Site Inspection
label | 271825e0-9032-5c98-9acf-c4eaae8913d0 |  | note | Frequency - Each lot
label | d7fa463f-ff5d-555e-9341-fcaa58cf3328 |  | note | Category - IP
label | 62bf0744-cfab-555e-8ea4-d9958fe4b7e2 |  | note | Responsibility - SE/Site Supervisor
label | d21ae106-4872-528c-9664-04246baf6f04 |  | note | Verifying Documents - Sign ITP
text | b7853a3f-89bc-5801-a22c-68fc8e9429d2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Proof Roll
label | 5f3b3b00-da79-5f70-bc4b-e313b36e579d |  | note | Reference - Section 173
label | c4e504ad-695b-522c-b17a-cdcad9f2b836 |  | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | 508d3ee8-213d-5ad1-92a6-28c55123ebb8 |  | note | Method - Visual inspection
label | d5ffe7ed-e254-53b0-8069-3c6fcdcc8987 |  | note | Frequency - Each lot
label | 145e8b0f-9872-570e-b580-d47b7bda2c4e |  | note | Category - HP
label | c1ee7c7f-c73e-5f50-9a3b-a4dbb871bdf7 |  | note | Responsibility - Site Engineer/Superintendent
label | f8adeb94-f708-594a-9294-8b10a7ce524d |  | note | Verifying Documents - This ITP
text | e8841163-2d3a-5df2-8ae8-8b18e8c3f3dc |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 - Compaction Testing
label | d57adf16-9421-572e-b4b8-dbd82f284b34 |  | note | Reference - Table 204.131
label | e3dbf970-9030-5587-b14e-b74169b5bc7a |  | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
label | b4804177-9c95-573b-a756-31886a0486b0 |  | note | • Ripped and re-compacted material below Cut Floor Level
label | db61d721-c6bc-5d4f-a6a5-55b15a87f3cd |  | note | • Scale B: Characteristic Density Ratio 98%.
label | b1e2ed62-9bb6-5bb2-b4b5-7ed16ddf8a4b |  | note | Attach: Compaction Test Result:
label | ddc47195-8f0c-5643-bbef-4e37faa0410c |  | note | Method - Document Review
label | 69930ca9-0e1d-55ff-a6f9-30d727e58333 |  | note | Frequency - Each lot
label | d3d77cbc-48e6-56f9-a13e-105eff55b590 |  | note | Category - IP
label | b9a7605a-22a6-58d9-a440-590963cc44a0 |  | note | Responsibility - PE/SE
label | 89aa4ba2-bf69-581e-881f-28a966fd5d40 |  | note | Verifying Documents - Test Records, Lot Register
text | 6f29cbb8-4dd8-5399-beff-85aa39d1a2c5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Post Compaction Material Property Testing
label | 4ae9b3e7-8a12-54d1-99bd-faa1cdf30a9b |  | note | Reference - Table 204,041 Table 204.141 Section 204.14 a) or b)
label | f5710c54-1e84-5b92-a5f7-830085788686 |  | note | Acceptance Criteria - Material Properties:
label | ad89f386-e9d4-5372-a868-7501995be6f4 |  | note | • CBR ≥ 2% and Swell ≤ 1.5%
label | c2117359-31fd-5765-889a-e7bee849a3f2 |  | note | • Max Permeability = 5X10-9 m/s
label | f24e6698-1386-5684-8536-ba05524ad8e4 |  | note | ○ Grading:
label | c58faac6-e896-525c-a11d-55fd4d1a335d |  | note | • 75.0mm 100%
label | db326a2f-d598-5bfe-b546-f5ef655ae1e6 |  | note | • 4.75mm 40-80%
label | b0499f27-fb8b-5ad8-85de-454ec66c0d61 |  | note | • 0.075mm 10-40%
label | 7c059b4b-9219-5f86-96dd-eff2cc5ae94f |  | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | 38d1faac-8ac9-5314-adde-4296e4e314e8 |  | note | ○ Scale B:
label | 8afa9151-0146-5863-8d72-841d801468c2 |  | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 7c34bbba-08e2-5054-a1b8-c61bbc2bb70d |  | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | b7a7f372-b7b6-5ae6-a786-987a3bd8efa5 |  | note | Attach: Post compaction test results:
label | 062f77fc-d78d-5c47-accd-8dace84592d7 |  | note | Method - Review Document
label | 51f8bee4-78a0-5201-ac8e-2233a55008ff |  | note | Frequency - Refer to Section 204
label | 2cd4ef93-85d9-5248-a4a6-539e9e5531c9 |  | note | Category - IP
label | c9482379-d5c9-5c2d-8d50-965324b74aca |  | note | Responsibility - PE/SE
label | fc808f2e-1cdb-557e-b086-3b82c92e0284 |  | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
text | eff53af4-12f9-5149-be92-f8bd6bcd573e |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Survey Conformance
label | 20060779-5a77-5092-a6e5-776a091596b1 |  | note | Reference - VicRoads 204.03f,g and h
label | 7eed938e-9995-501a-8e5e-5519c55c9e4d |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 1387e5f0-f68f-5c45-b871-376cc627e08e |  | note | ○ Level tolerances (Scale B):
label | 35e26a69-1726-587b-809c-4f2b298e5382 |  | note | • Range x = +5, -25mm
label | 6bcc3e01-eab6-54a4-bf72-89385e157d83 |  | note | • Max S = 15 mm
label | 38ee0337-3c92-5ac5-aae1-6f4b2e1c27e9 |  | note | • 40 measurements per lot
label | bb92d6a5-2093-59f1-9499-c35b6b5307ca |  | note | Method - Review Document
label | a828d010-5c8f-5e91-8047-93f965d5abf3 |  | note | Frequency - Each lot
label | f3c686bf-6e0b-5acc-b9a5-848b18ffb438 |  | note | Category - SCP
label | 3d276712-2c98-546e-8762-4841d5a5806f |  | note | Responsibility - SE/Surveyor
label | 574bf915-86aa-51a6-8b38-61942295620c |  | note | Verifying Documents - Sign ITP, Attach Survey Report
text | a448b87e-fc1e-5e41-bf7d-a0b4996be48f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 25c9af64-aa07-5448-8829-5645b0a39ac1 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 490ce730-3f19-599e-8aee-2917414efb0e |  | textbox | Name:
text | 496d3e96-9853-5840-8843-b9f1cabca955 |  | textbox | Position:
text | f9b058e4-08e6-54d4-b8bb-1fc719ff9336 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-054-CPD-Subsurface Drainage (Supply and Install) | itp |  |  |  | Yes | ITP-054-CPD-Subsurface Drainage (Supply and Install) - Rev 0 | a8308ae8-b213-4b0a-8084-93b1ace135c7
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 5e756c66-1426-56ad-bf7f-1753be386bc2 |  | note | Document Title: ITP-CIV-CPD - Subsurface Drainage (Supply and Install)
label | 73872110-eeed-568c-904c-9ee0962d7bf2 |  | note | ITP Description: CPD - Subsurface Drainage (Supply and Install)
label | 7fadb68e-8521-588f-bd62-ea9b74570bdf |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 9b621f6c-1c7a-5cf1-914d-42a5b9ddaaba |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 67320dad-d3c2-56b5-8786-0005fbe7f61c |  | note | Revision Number: 0
label | c4bd4f24-ab79-5d8b-b974-2ef4aac0c609 |  | note | Revision Date: 27/07/2023
label | b30ab790-24ed-503a-b68b-c2c2fde9a83b |  | note | ITP created by: William McCuskey
label | ec15eb94-ec94-5b28-ac8b-9ee20565fcca |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 78b41507-92ed-5564-bfd9-55c03a69c0c5 |  | note | Reference - VicRoads Section 702 (May 2019)
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | b210e6dd-638b-545b-a55a-77e6ef489c0f |  | note | Reference - VicRoads Section 204 (Dec 2015)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | c66b22bf-ea71-5a53-b2df-34ee787eb1ac |  | note | Reference - VicRoads SD1611
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | c648f746-be2f-5579-b820-f820befa2368 |  | note | Reference - VicRoads SD1051
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | c705426b-171e-5974-80ad-5540e80d5731 |  | note | Reference - VicRoads SD1631
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Drainage Pipes
label | b5796c7a-541f-5723-9f2d-215166b00127 |  | note | Reference - IFC Drawings Section 702.04
label | b59b964d-521a-59e4-9fba-8c40dc4e1df2 |  | note | Acceptance Criteria - Subsurface drainage pipes:
label | 5bf33e40-132d-57c1-8ad1-f08f630c4473 |  | note | • Category 1, 100mm DIA Class 1000 corrugated perforated plastic pipe - with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
label | 6fe38e57-e807-5ac4-bf19-21b4adc60b77 |  | note | • Attach: Material Approval Ref Nos
label | be3b896d-f3c6-50b6-a212-c6c75d13b7b2 |  | note | Method - Verify, Document Review
label | ab29a124-7cf2-5af0-80d0-ec1615c7fea7 |  | note | Frequency - Each Lot prior to work start
label | e0a2a39a-e518-5e4e-9997-9ca32b6c200e |  | note | Category - HP
label | 0b05d7b5-87de-5d95-8771-0e3865fb76ca |  | note | Responsibility - Nominated Authority
label | 8df53096-0a8f-5576-aa62-3a60a7305861 |  | note | Verifying Documents - Conqa HP Release
text | f558844e-4de4-541c-8734-37d18c21271b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Granular Filter Material
label | 6779b815-7d29-5755-a92e-c96f3784728c |  | note | Reference - IFC Drawings Section 702.05 Table 702.051
label | dad02bcd-59a4-5e88-9b37-ce100f6c57e0 |  | note | Acceptance Criteria - Granular filter material:
label | 5b88e3b0-5c50-5ae3-b27e-fd7b1eda594e |  | note | • Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
label | d593be4c-2e48-56b9-b702-4c0f5b45efb6 |  | note | • Attach: Material Approval Ref Nos
label | 1e2016a8-85e4-5f7f-b748-5d420fd01a6f |  | note | Method - Verify, Document Review
label | 8ea1b184-d0d4-558a-ba31-80173c07d358 |  | note | Frequency - Each Lot prior to work start
label | 5dedc4f4-3633-57d2-82a0-a00432f60603 |  | note | Category - HP
label | dcbf3c06-0aac-5896-b0b3-88a90a5b4c89 |  | note | Responsibility - Nominated Authority
label | a371b996-a5f2-5d58-ba51-d11d5b68e904 |  | note | Verifying Documents - Conqa HP Release
text | 4e16d30d-4ab9-503d-bf2a-6cf8608c36ff |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - No Fines Concrete
label | 46b59dd1-10ec-512e-92e6-4cb8142855b5 |  | note | Reference - IFC Drawings Section 702.05
label | 984fa64e-635d-5c1e-84cb-956ca8cddcca |  | note | Acceptance Criteria - No Fines Concrete:
label | bea200ad-41ea-5d1c-90d3-def04ad1f310 |  | note | • Shall comply with 702.05 (e)
label | 0c1d1023-3442-588c-a5f0-946ec6e83b67 |  | note | • Attach: Material Approval Ref Nos
label | 20db4eed-3d07-5d5d-8c37-80cf5fa0f39d |  | note | Method - Verify, Document Review
label | be96de49-b1af-56fa-bbfa-c34228cdf7f9 |  | note | Frequency - Each Lot prior to work start
label | 00d61619-bd12-59d1-b1c9-e6d44cbbd858 |  | note | Category - HP
label | 1e334a40-5ed7-5d87-be37-1f4f44ee2d3c |  | note | Responsibility - Nominated Authority
label | 75ef8396-3798-58e8-83c5-81a00e143355 |  | note | Verifying Documents - Conqa HP Release
text | 1e2f92c6-a897-5c63-82cd-9cb3a010e5af |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Geotextile Filter
label | 6975b730-6514-574a-847f-c07265b61c08 |  | note | Reference - IFC Drawings Section 702.06 Table 702.061
label | e1dab299-9d25-5c3b-9514-a9ea410354c8 |  | note | Acceptance Criteria - Geotextiles:
label | b81b089c-1d18-5e17-ae36-3af162afbc38 |  | note | • Shall comply with 702.06
label | c41b3eb6-c018-519b-993b-9b3b9b8dc359 |  | note | • Attach: Material Approval Ref Nos
label | 8bfb0f32-0505-568a-8690-62fbb2046471 |  | note | Method - Verify, Document Review
label | 966e471d-df32-5d4e-a83c-1122b2ef1022 |  | note | Frequency - Each Lot prior to work start
label | f4824265-b9a1-5d20-abc7-ff9b44526a5d |  | note | Category - HP
label | 36750d5c-b5df-567e-8413-7aac74f38d75 |  | note | Responsibility - Nominated Authority
label | 9a3434a4-ee45-5b34-8ade-c75e4a715500 |  | note | Verifying Documents - Conqa HP Release
text | 12efcc18-34f6-50c9-92bb-9596ceabd1e9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - SSD Pits, Pit Lids, Flushout Risers
label | 5c6b4fc4-4d62-5dea-8df9-da2c691fc597 |  | note | Reference - IFC Drawings SD-1051 SD-1611 SD-1631
label | 5b389cc5-140b-5d97-8ce9-856b0e6907a6 |  | note | Acceptance Criteria - Subsurface drain pits: shall be Type S1 (as per SD 1611).
label | 1c2f7ac6-ec6b-5b2a-a3b0-55b4ccaf9fbe |  | note | • Pit Lids shall be: Type M3 circular lid (as per SD 1051) for Type S1 pit.
label | fa557a01-170a-594d-864d-bc00b8cf478b |  | note | • Flushout risers: As per SD 1631
label | 6019bf60-d1f3-56ee-ae61-85c769e9ff96 |  | note | • Attach: Material Approval Ref Nos
label | 4a6d949e-972c-53d7-b435-d4411b183324 |  | note | Method - Verify, Document Review
label | 52c285b4-ecd9-5fa1-9884-df41f4a40ce2 |  | note | Frequency - Each Lot prior to work start
label | 867df89c-512e-5d3d-9d34-60e57b063665 |  | note | Category - HP
label | c0a20f3f-6a6d-5c95-a5e0-931049ee4b54 |  | note | Responsibility - Nominated Authority
label | 8d1bb047-85db-5bf9-a3e4-5af829ba59ee |  | note | Verifying Documents - Conqa HP Release
text | d3e2311a-4415-51ac-a4b4-d0a0bec6641d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Check for correct documentation
label | 2fd21618-982d-5eb3-a309-4854d0b4bb90 |  | note | Reference - IFC Drawings
label | 934924aa-1824-59e4-b2c8-1fd9bb5f90d7 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | 27b65153-7293-5189-bc5f-a3fe349e9804 |  | note | – using the correct and complete set of drawings
label | 9cf63416-89b3-513c-a9dd-baca03312615 |  | note | – all drawings are the latest revision
label | 13f4817e-20fa-5c01-a9b8-136cc4e8437f |  | note | Method - Visual inspection
label | a6d9adf8-d0e4-55a9-a441-8f39c43fb9c1 |  | note | Frequency - Prior to commencing any activity
label | 7d80d9f9-abf4-531d-aba3-a5f7c124ffbe |  | note | Category - WP
label | ae54de58-32a0-5554-a4ae-f1059be70202 |  | note | Responsibility - SE/Site Supervisor
label | 9a6da605-2cf7-5923-b8ad-1107cee1c93e |  | note | Verifying Documents - This ITP Signed-off
text | 25148f33-f8c7-55da-9d6a-2ec3343457ce |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out
label | d888693a-661e-56b1-951e-7c66537b9931 |  | note | Reference - IFC Drawings Section 702.03
label | 83035189-e0e3-5b71-a892-4596c5fae006 |  | note | Acceptance Criteria - Survey to set out Subsurface Drainage line.
label | 153f7e79-367a-545a-aeb1-6b4e8d58c87c |  | note | Method - Visual inspection
label | bc1869bf-402c-56c5-97be-a667477b3970 |  | note | Frequency - Each Lot
label | 14e3dbda-a02f-5154-93fa-4c52479cfa5f |  | note | Category - IP
label | 3110ac88-9619-5fcc-b1e7-92121e2eeb2e |  | note | Responsibility - SE/Site Supervisor Surveyor
label | 41f41eaf-e3f7-5812-9782-8e0a505634e1 |  | note | Verifying Documents - This ITP Signed-off
text | 6c5d890b-5b97-51e6-a663-db355449eed3 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Trench Excavation
label | a70f40e5-c83c-5092-af9b-687336db85c2 |  | note | Reference - Section 702.08
label | c1972e48-14a2-5347-a70a-f8efa7b71d62 |  | note | Acceptance Criteria - The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
label | 1f8c4e72-ae3e-51a8-a24e-f09f72ce93d4 |  | note | • There shall be no departures from the grade of the base of the trench that would allow ponding of water.
label | a7594d55-9149-536c-a372-5c39d05e9ce0 |  | note | • Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
label | 3e680e9d-54ed-594a-a285-c9578648464e |  | note | • The base of the trench shall be inspected by a superintendent to verify compliance with 702.08 prior to placing beding in completed excavations.
label | bf24e9e5-2f4f-55d4-b834-378b9bf2d314 |  | note | Method - Visual Inspection
label | 71f94bb1-ab95-5798-ae7a-760e6fa2e3ba |  | note | Frequency - Each lot
label | 113f10ca-be7c-5ba9-b72c-cfaf36aa5b2a |  | note | Category - HP
label | ac4291d0-514c-5c55-87b2-1a340f68746b |  | note | Responsibility - SE, NA (Nominated Authority)
label | e2cd5145-e123-546c-a217-d743c0be25cb |  | note | Verifying Documents - Conqa HP Release
text | 50b66fa8-2394-5832-8011-24d090010baa |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Placement of bedding
label | b705b011-c4c7-566a-bfe3-88f4f70d48b9 |  | note | Reference - Section 702.09 (c)
label | 640a8ee6-9ed2-5220-9725-d461f324b59c |  | note | Acceptance Criteria - Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level.
label | 89c4c992-717e-58f9-9a9a-9ecf7fa7e5da |  | note | • Attach bedding material delivery dockets
label | 67f5b9d7-ac2f-58c0-9806-f5bf16ca17de |  | note | Method - Visual inspection
label | a2cf62e6-3529-55a4-af59-43bdfb7c4c20 |  | note | Frequency - Each lot
label | bec0046c-b2d9-5e19-8c71-eae115a3eca8 |  | note | Category - IP
label | 1a2791c7-5180-5028-9e80-9fa5a3f5366d |  | note | Responsibility - SE/Site Supervisor
label | bef3cdfb-41fa-5a3d-be76-d2b0fc53db1a |  | note | Verifying Documents - This ITP Signed-off
text | dde6bb55-f4fb-568a-bbbb-bfa81a73a63b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Pipe and Geotextile Installation (if required)
label | 033d5c9d-d831-5a78-91a9-3ec4ce74268c |  | note | Reference - Section 702.03, Section 702.09
label | fd373f6e-6746-54bc-8906-673a59283596 |  | note | Acceptance Criteria - Pipe shall be placed centrally in the trench on the prepared bedding and held firmly in place. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements.
label | aea4b5bd-5941-5867-bf1f-3fa36768f8cd |  | note | Attach Suburface pipe and geotextile delievery dockets (if applicable)
label | f28fbfe0-cd9b-5c39-932a-606cc405e543 |  | note | Method - Visual inspection
label | e5663bc4-61f3-50a7-bc21-d7c6ca51513c |  | note | Frequency - Each lot
label | 7519a3c7-9cab-5059-9d88-547e9951e09d |  | note | Category - IP
label | 6e3ad5b5-4d75-5c5f-b14d-a3ab4ff75622 |  | note | Responsibility - SE/Site Supervisor
label | 4b15a022-df71-5e5c-b7fa-d355262c2eac |  | note | Verifying Documents - This ITP Signed-off
text | 89544609-bb53-5633-b9d9-818a589bf8f8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Backfill Installation (Granular Filter Material)
label | a63ccf80-1165-5629-a90a-756a1962ceb8 |  | note | Reference - Section 702.09 (g)
label | 2d981ce4-a03b-5246-89b5-12dc73f81e94 |  | note | Acceptance Criteria - Material shall be placed moist and compacted in layers not exceeding 300mm.
label | 8de61911-e80c-5d78-940a-d87043b46a70 |  | note | • The method of compaction shall be in accordance with the procedures and reviewed by the NA.
label | 78e06ee3-78bf-54c0-9f96-8288788fbc29 |  | note | • Attach Backfill Delivery Dockets
label | 653253c0-fb8d-532b-ae11-e5d2f8a49dac |  | note | Method - Visual
label | ebfbd0ef-a68c-5eb7-964c-8eb30e4689fa |  | note | Frequency - Each lot
label | 69191e75-fad4-5cf8-9472-af01739c487d |  | note | Category - HP*
label | 1c932b2d-a6b7-5b1b-bb56-f22ac93114d1 |  | note | Responsibility - SE, NA
label | 86c676dd-4534-5203-8b6f-6149d9264544 |  | note | Verifying Documents - This ITP Signed-off
text | 423a13d0-ca67-5727-9392-ebc99af2295f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Backfill Installation (No Fines)
label | 74acda89-7936-5a8c-8fc4-23c756fc8add |  | note | Reference - Section 702.09 (g)
label | f6085be0-f146-54a6-af4e-54417cc92429 |  | note | Acceptance Criteria - All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing.
label | cea87425-1c26-544f-b900-673131d0b962 |  | note | • Attach Backfill Delivery Dockets
label | 2359108a-063c-5d17-924c-fd29799c5c52 |  | note | Method - Visual
label | 83759285-96ac-586c-85e2-4abd1b459878 |  | note | Frequency - Each lot
label | 4c972846-af50-55df-99e3-c358c9d69b0c |  | note | Category - HP*
label | c3624f7e-616a-590d-93c0-573c4789f896 |  | note | Responsibility - SE, NA
label | cc7dc6ec-a691-5c59-a28b-dfb78094c16a |  | note | Verifying Documents - This ITP Signed-off
text | 3b319340-47c3-5043-a165-aeacec418bed |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Install Pits and Flushouts
label | eb52c2d6-8ac5-5746-a0ec-2ee48969ea31 |  | note | Reference - Section 702.10
label | 6e148972-a161-5be8-814a-77252d24f099 |  | note | Acceptance Criteria - Subsurface drains shall have access points at the start and finish of each run.
label | f746ce8b-a7dc-5da9-9d4d-d63708011f3d |  | note | • Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings.
label | 5e596683-69fc-5fe1-b6ff-7e90f625dac9 |  | note | • Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
label | c6075ac1-ca70-51e1-9431-63fedb0ec56e |  | note | • Attach Pit and Flushout Delivery Dockets
label | 8047eb38-f5d9-5478-bf18-0b8b6094aee6 |  | note | Method - Visual
label | c540bead-2874-56c5-af4d-a235c932ca24 |  | note | Frequency - Each lot
label | 2ecc4d8d-6ca7-55df-afa6-01d776bbc20d |  | note | Category - WP
label | cc5351f2-b788-5e44-a7cf-e2cb752ebde8 |  | note | Responsibility - SE/Site Supervisor
label | a7517441-2bc1-5a16-9109-1600758d17d5 |  | note | Verifying Documents - This ITP Signed-off
text | de5d8165-62c3-5c35-af53-ad38fdb95981 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Marker Points
label | e047c081-f1dd-5f9e-8f7c-bb7934ed2ab3 |  | note | Reference - Section 702.11
label | 3d0cbebe-6d20-56d0-9acd-93af052b2166 |  | note | Acceptance Criteria - At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
label | d575821b-c29b-53dc-a2c1-a687e0205b76 |  | note | • Attach Marker Post Delivery Dockets
label | 502e7323-e708-5d20-b9ae-acbe1d09cef1 |  | note | Method - Visual
label | 187abe52-5a65-5c5f-b084-69762e84edf5 |  | note | Frequency - Each outlet
label | 70f4068d-661a-50d0-82a5-74c852be709f |  | note | Category - IP
label | 3329a9cf-c213-5e6a-b4b4-f27156365c76 |  | note | Responsibility - SE/Site Supervisor
label | cbac4167-5bfb-51c6-8557-2d520df43e35 |  | note | Verifying Documents - This ITP Signed-off
text | 715a474e-b1eb-5b53-be00-39cbf91a97f6 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As Built Information
label | 85c26b24-727b-50ee-8de6-3c6d8317d8c7 |  | note | Reference - Section 702.03
label | a786e809-50ea-55be-ad4c-319cc1c94348 |  | note | Acceptance Criteria - The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
label | 1f33915d-3d9a-5387-8ab4-5dd9ae08bff2 |  | note | • Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length.
label | 206579b8-6554-50d6-aa36-0d1531fac5b8 |  | note | • Attach Survey Conformance Report
label | 7a7793bb-6400-5b5f-86a9-fdcb46dd7e8d |  | note | Method - Document Review
label | f76e61d9-05f6-5af7-9e6b-ed385a2adf17 |  | note | Frequency - Each lot
label | db6f68f1-2e48-580a-8ddf-c81c515fee94 |  | note | Category - IP
label | 789dc594-c779-5589-ac3e-dc8f2b636c75 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 3df17ede-d5e5-5ebd-a7d2-b728465e1124 |  | note | Verifying Documents - This ITP Signed-off
text | 31cbdff4-8b28-5c4a-9967-4249661eb4e5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Flushing
label | 7fac7770-1824-5d53-9f6e-f6d169c0802b |  | note | Reference - Section 702.09 (h)
label | 89c741b8-2d9f-562b-9c3f-b3a545855ff0 |  | note | Acceptance Criteria - Flushing test shall be witnessed by the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
label | f77cf290-b9fc-57b0-ac44-d76ac248f0c6 |  | note | • Attach Flushing Tests Records
label | ad869ed9-8b52-58fb-b5e4-d5a42ad95a5f |  | note | Method - Document Review
label | b6510b1b-92d9-56dd-a004-f8aebec2c06e |  | note | Frequency - Each lot
label | 51b61388-5855-5f13-b92b-1688d13232e2 |  | note | Category - HP
label | c190dbdc-f065-58d9-bb39-b3590d45b102 |  | note | Responsibility - SE, NA
label | 9b4da817-4475-5425-b940-40e09253dbb8 |  | note | Verifying Documents - Conqa HP Release
text | 76cf8b12-05be-5cb8-8bc4-9f96688e2b8f |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3 - Inspection of Subsurface Drainage - CCTV
label | 50f09ae0-1760-54f4-ab9e-3833c970dbbd |  | note | Reference - Section 702.09 (i)
label | 15e991a3-07af-5e10-b6aa-9c6c6230535d |  | note | Acceptance Criteria - All subsurface drainage lines shall be inspected, after the flushing test as per clause 702.09(h), and prior to placement of asphalt by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is free from obstruction and to check for visible signs of defects.
label | 7cef991c-1b5a-5b41-ad05-5bcfeb64979d |  | note | • Attach CCTV Inspection Record
label | 72847521-4d11-5acd-aaf1-e224600441f8 |  | note | Method - Document Review
label | 23ca1eb0-1c8f-5155-bf22-43cbc5a3cda8 |  | note | Frequency - Each lot
label | d3998dc4-6389-5d01-b944-4c263846f273 |  | note | Category - HP
label | ff23ec9e-9d32-5c58-83f4-7afd16bada64 |  | note | Responsibility - SE, NA
label | ccf4b25b-7b8e-55b0-a858-6e14888220fd |  | note | Verifying Documents - Conqa HP Release
text | b4011a66-7aa9-5513-ae59-84f65eebad8f |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | 35fa8fb7-10d6-5a7c-9a8a-30f5f24da95a |  | note | Reference - MRPA Quality Management Plan
label | 8f6ffcdd-295d-5834-bc64-bc8fc44b9856 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed in CAMs.
label | e47a01ba-0c65-5d72-bd15-72c8a055a60b |  | note | Method - Document Review
label | 5ad6364a-8853-5592-a982-cd4ccb6ee130 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 40ecc591-f9fb-59a4-8dec-eb011bc621a3 |  | note | Category - HP*
label | 1b33d991-0b38-5b86-b47e-e8932df24bc2 |  | note | Responsibility - SE/PE/SPE
label | 45a4651e-2ddc-5cbb-8c88-1da11aa260cb |  | note | Verifying Documents - This ITP Signed-off
text | 39cee6ae-fb96-55d5-93d4-5dd3033dbd3b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1906eb47-6ddd-522d-8aac-61c67e65097e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | edd5b7dd-7068-53aa-9fa5-c796b85993d3 |  | textbox | Name:
text | 288f74df-e006-5904-846f-15d1971cee2b |  | textbox | Position:
text | 1942fac1-7484-583c-bf81-e53d5cdf2c73 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction | itp |  |  |  | Yes | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | b6ddc7f6-b6bd-404a-a002-1afc2d27a009
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | ef2320af-26dc-5cdb-8440-e1e8c78c3b3c |  | note | Document Title: ITP-CIV-CPD Unbound Flexible Pavement
label | 2cbeac5b-2b48-5450-8ea9-c52c6d8b1210 |  | note | ITP Description: Unbound Flexible Pavement
label | afdd6abf-7f1e-597f-a368-ed0ab3ce8453 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 3b6e9a75-fea6-52fc-806f-54e714466ffb |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | 7875f11f-5110-5baf-857b-b5ef577d07a6 |  | note | Revision Number: 0
label | 2038d4b2-271f-5dc3-9790-e406677c4285 |  | note | Revision Date: 14/08/2023
label | 63cb63d5-a56c-508c-a594-2fc0447af96c |  | note | ITP created by: Ethan Caruana-Smith
label | 35a8ba9b-bfeb-5080-ad7c-924698de66e3 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 9255c4c4-eae7-5f64-92e9-4b5440837f47 |  | note | Reference - IFC Drawings
checkpoint-status |  |  | checkpoint | 1.2
label | abc6407d-b876-57e2-bb82-867378991163 |  | note | Reference - VicRoads Section 173 (10/9/2008)
checkpoint-status |  |  | checkpoint | 1.3
label | 929e635c-bb1a-5fb4-9ee0-0f45b42d8276 |  | note | Reference - VicRoads Section 304 (13/8/13)
checkpoint-status |  |  | checkpoint | 1.4
label | 3b425cbc-612c-5694-8139-63d59b27156d |  | note | Reference - VicRoads Section 801 (19/07/18)
checkpoint-status |  |  | checkpoint | 1.5
label | dd274434-1e79-59a4-973a-e498e860c203 |  | note | Reference - VicRoads Section 812 (13/07/16)
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Crushed Rock Mix Design
label | cb7270e0-3687-537c-8e0b-c2089f472990 |  | note | Reference - Section 304.03, Section 304.05, Section 812.04 Table 812.121 IFC Drawings
label | 74f060ed-0c21-5058-aab6-21142e27edc3 |  | note | Acceptance Criteria - All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
text | 1e8b38d9-00d5-5fc6-b622-5623d2e8145f |  | textbox | Enter: Teambinder Material Approval number
label | 6421c17c-5f15-5ac8-9493-043e99e8de75 |  | note | Method - Document Review
label | 9423e754-7887-5b0d-8b91-d9f7677e2e19 |  | note | Frequency - Material conformance as per Table 812.121
label | 8c9bea69-1e3e-5e8a-840a-65b9ebf6d012 |  | note | Category - HP
label | 4c9a7e25-f2f2-5c2b-a001-0c81d51b9c31 |  | note | Responsibility - NA
label | 7719a719-dde4-50bc-99ae-3731de8b907c |  | note | Verifying Documents - TeamBinder Material Approval Number
text | 971649c9-92d1-53a7-a2b4-19c122ec4da1 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3. Preliminaries-Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Subgrade Preparation
label | 64302fc0-0c83-5f0b-95ef-02bfc2562a1c |  | note | Reference - 304.04
label | a5dc12f6-8494-503a-9d6c-071b45eacdc3 |  | note | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
label | 6cc7dfda-a294-530e-8a3a-d9fffd21c03f |  | note | Reference: Subgrade Preparation/Type fill Lot Number:
label | ce02167f-bbbf-5702-bd74-694ca167ae60 |  | note | Method - Document Review
label | 91b67b0f-8c05-56e1-a25c-75b88bf22d44 |  | note | Frequency - Each Lot
label | fddca177-850a-52ed-9fe4-12e7fb7e6910 |  | note | Category - HP*
label | 9fbd03f2-9838-53b5-a895-97caf6f82257 |  | note | Responsibility - PE
label | e242e0d6-b395-5eef-bbaa-e4f5d4d6fb46 |  | note | Verifying Documents - Underlying layer Lot number
text | 9b8f20d9-215e-5ed5-b438-99239b0c5d57 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Select Scale
label | 3fde8bc7-22bd-5946-a6aa-ef71e7133ce8 |  | note | Reference - Project Requirement Specifications IFC Drawings
label | d86a0587-ab72-5981-93db-b14ab9f556e0 |  | note | Acceptance Criteria - Specify site specific scale:
text | 8c782be8-d468-5003-be22-aa573e784814 |  | textbox | Enter: Site Specific Scale (A, B or C)
label | 1641f9e6-e798-5ffe-809e-1ca2a87987f8 |  | note | Method - Document Review
label | b577eba2-ad0e-51ef-b8bb-b08055150d0f |  | note | Frequency - Prior to Commencement Each lot
label | 5a32cc8f-41e1-5a94-8fbe-9bda50302ff0 |  | note | Category - HP*
label | 08f9b94e-282b-5ee6-95da-9553d8c25671 |  | note | Responsibility - PE
label | d625fedd-7b73-5b0f-bf0c-3ef8b85b6088 |  | note | Verifying Documents - Sign ITP
text | 30200f34-0a82-5dd1-be6a-20af53b1c63b |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out and Lot size
label | ed8f00ef-e837-5f41-b1ab-fc26f3daa444 |  | note | Reference - IFC Drawings Section 304.06
label | 8f8c696f-79dd-5b2f-b1a2-5c7295a51b83 |  | note | Acceptance Criteria - Lot size shall be the lesser of 4000sqm or a days production.
label | b31d0dd0-a009-5fe1-99a0-8ef3115b7a87 |  | note | ○ Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
label | 37ffdf15-a490-5bfd-bcb7-3d307bd041a0 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | 2b744394-5f69-524e-a441-f64e2ab007b0 |  | note | Method - Survey, Document Review, Measure
label | d45237eb-ad3d-567c-99f8-39409e602e41 |  | note | Frequency - Each lot
label | 4c4dbb3a-e436-5edf-be56-ea23d178efa4 |  | note | Category - IP
label | ceeaae3e-1daa-506e-8e92-aef482aed839 |  | note | Responsibility - Surveyor, SE
label | 63a9f3cb-0c9d-52c9-8cb2-6d5286b14270 |  | note | Verifying Documents - Sign ITP
text | 36fc3025-54a7-57a8-9415-41c21f87e568 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Crushed Rock Delivery Dockets
label | 12718882-db02-5606-a571-0666b70984cf |  | note | Reference - 304.04
label | c6fd7c0e-2dab-5ae3-a795-02d2e6ae82dc |  | note | Acceptance Criteria - A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
label | b6149cc5-d08d-5ed4-8bf7-969dfe54af95 |  | note | ATTACH: Delivery Docket(s)
label | 5adf6d2b-a0c9-5aba-ae31-64f268429cab |  | note | Method - Document Review
label | 40b60401-c4f3-5e1c-87af-9e948b3b65af |  | note | Frequency - Each Lot
label | 6847a6a1-3e62-5027-bb94-059d50afb645 |  | note | Category - IP
label | 9cd4855e-c5f1-5cd4-bc12-4ed167abcd16 |  | note | Responsibility - SE
label | 8796dfd3-112d-5e6a-9efa-f462e56c164b |  | note | Verifying Documents - Attached Docket, Sign ITP
text | cf1cf749-a11c-5cdb-a47b-a39c5dddd61d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Placement of Material
label | bcb1ba30-363f-5857-bd1d-a1ecd0c586e9 |  | note | Reference - Section 304.03, Section 304.06, Section 304.08
label | 2c66ba9a-a9d3-5c80-be73-0a397ae01705 |  | note | Acceptance Criteria - Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
label | 7f395a4f-604f-5a76-9403-c5d8998abd12 |  | note | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
label | 7c0b8a25-01f3-5dd3-b72e-022a807503d0 |  | note | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | 72266e1e-1033-583f-bcf4-5818a317c007 |  | note | ○ At no location shall water pond on the surface of any pavement layer.
label | 3a035549-0e3c-5170-9f6e-cb3327aa9a1e |  | note | Method - Visual and Measure
label | 1c6fb702-1fe2-5ac8-8a5e-40e5def1affa |  | note | Frequency - Each lot
label | 432f659d-933b-588e-8ee4-900cbbe02782 |  | note | Category - IP
label | c4fbee85-77e1-5034-a521-f2cd7c1340ef |  | note | Responsibility - SE/Site Supervisor
label | 636045f5-15fe-57e0-8cfa-7cdecc87e65e |  | note | Verifying Documents - Sign ITP
text | bbae402b-e9d6-530e-b742-8cefe5ed130c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Construction - Jointing
label | 8f728c6d-963b-5e34-8f97-2aca6616e75e |  | note | Reference - Section 304.07
label | acf792a6-fd49-5145-bb5b-59a2490daf52 |  | note | Acceptance Criteria - The layout of joints shall conform to the following requirements:
label | 7f65d51f-78ba-528a-a922-a374d0a8cdf2 |  | note | (a)material shall be spread in such a manner as to minimize the number of joints;
label | 6792e001-5f31-54f7-8f6a-d08697f60c72 |  | note | (b)for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | a655c747-815d-5a27-8f85-09528ababcc2 |  | note | (c)transverse joints shall be offset from one layer to the next by not less than 2 m;
label | 89d2f63d-2602-524c-a9a7-a83e7a1bf470 |  | note | (d)longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | a2208e64-d1e8-5345-94f2-ba9119ba8221 |  | note | (e)longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | d27a486e-bf12-51d3-83d9-9b9df3cfd012 |  | note | Method - Visual and Measure
label | 49977efe-6632-52e0-944c-7f4a03d22663 |  | note | Frequency - Each lot
label | 11a3c6cd-23ec-5827-9843-707129b0a921 |  | note | Category - IP
label | e0a10294-38d8-57d0-acfb-4ad558dddcd4 |  | note | Responsibility - SE/Site Supervisor
label | ae052435-06ae-5297-9e0b-b240a0c2e4e9 |  | note | Verifying Documents - Sign ITP
text | f9e22e9d-6b78-52bb-b8a0-712758eed998 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Compaction test (Frequency)
label | e5c1edb7-bed6-5983-ab57-d2a5f9be2e36 |  | note | Reference - 304 .11 (b)
label | 3a5c72e8-fbd9-5646-aa27-20290a21afe7 |  | note | Acceptance Criteria - The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
label | ba85afe3-76e8-56e9-a84d-2e6217681447 |  | note | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
label | 015d310c-0b1b-5a36-9590-adc818b57617 |  | note | ○ Scales A and B: 6 samples
label | 34f81167-ed4b-5172-8822-f430f7e2b8d3 |  | note | ○ Scale C: 3 Samples
label | 2f542fc9-ba3a-5027-a797-a3c4bcca31e1 |  | note | ○ Pass: Tested
label | 9d5e4c6a-f243-5ad9-b803-54f994846b2e |  | note | ○ NA: Not Tested
label | 9266e1fd-c224-5914-9886-f72d84d2fd8e |  | note | Method - Visual
label | f105a76f-1891-5063-8277-018b508f804d |  | note | Frequency - Each Lot Where applicxable
label | 55375623-073a-52b7-b5d3-04e7106bd588 |  | note | Category - IP
label | 3774f41d-c8ac-5881-8241-fafeb21e9622 |  | note | Responsibility - SE
label | c3391b2a-c9aa-5433-94e5-33c7bc86901e |  | note | Verifying Documents - Sign ITP
text | 40645c17-0428-56fa-8d44-7c143e802a40 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Post Compaction Materials Testing (Frequency)
label | 06d5a86f-2801-55b5-b77c-dc0b0a612f6f |  | note | Reference - 304.11 (c)
label | 8275823d-28c5-581c-91b3-48e320f8e898 |  | note | Acceptance Criteria - SCALE A:
label | df0a5516-796f-504f-bc54-5490228590f5 |  | note | ○ The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
label | 49e8bfb4-738b-5948-886c-b512c3b78ade |  | note | Compaction:
label | 845d3c40-9358-584f-a50d-95a9b3ad899d |  | note | ○ Lower Subbase: none
label | 721796a4-dc91-5cbe-8398-0ed5a83679f6 |  | note | ○ Upper Subbase: 1 in 4
label | b86ebbde-90f4-5539-9c91-1434778902ff |  | note | ○ Base: 1 in 2
label | 43fadb60-bb38-5f6b-bc70-7e9252c6779b |  | note | PI:
label | 9ec6b3bb-5cde-54dd-8bb0-ed1d1e5f79b7 |  | note | ○ Upper Subbase and Lower Base: 1 (two samples) in 8
label | 3a4aa8ef-f061-5535-a230-f348eae3de32 |  | note | ○ Upper Base: 1 (two samples) in 4
label | cf2dad95-d715-508b-a689-06d01a09e871 |  | note | SCALE B:
label | df249b67-9751-5f27-94e8-95fb90e714bb |  | note | ○ the first lot of each pavement course shall be tested for post-compaction grading and PI.
label | 163ed4b1-6d6f-5ab4-a69a-4b2ca5b4cb14 |  | note | SCALE C:
label | 495e157a-7355-57a7-a09e-c620d3cd7bce |  | note | ○ Post compaction grading and PI testing is not required (CHOOSE NA)
label | 074437bf-5ccf-5c1f-b6de-f59ebcb15784 |  | note | Method - Visual
label | 577df030-3595-5854-989d-4b4ac33eaa8e |  | note | Frequency - Each Lot Where applicxable
label | 7e75f971-a2e1-5c4f-9484-ce3a556eb707 |  | note | Category - IP
label | f646a15c-161a-5145-9c30-5fa1a49865f3 |  | note | Responsibility - SE
label | 2b030299-c6b9-5ef5-8065-66eea984e9d9 |  | note | Verifying Documents - Sign ITP
text | aa03fa7f-55e1-587c-91d2-090471f1e949 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Proof Roll
label | 4c670494-f690-5b50-810e-b494570a6bb1 |  | note | Reference - Section 304.08
label | 4fd0a818-401e-5e3e-aeb7-406ef6b362eb |  | note | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
label | 8c320614-1cce-5fcd-9686-b21ce9ad32f1 |  | note | Method - Visual
label | 9562dd5a-f4ec-5eba-8de4-2bde4a837d12 |  | note | Frequency - Each lot
label | a3592546-ce81-5d32-8c05-77f347e488d5 |  | note | Category - HP
label | 50451aa1-f26c-5901-bdd2-6facbe8a04a9 |  | note | Responsibility - Nominated Authority
label | cd5ec3b1-837d-545b-a085-b6d24852b0a3 |  | note | Verifying Documents - Sign ITP
text | 234bdd0f-6ce6-5392-ad0d-4789896643f6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.7 - Protection of compacted layer
label | 9de1387d-da9e-5443-8866-d2cf11176d33 |  | note | Reference - Section 304.09
label | adcd9f68-6b46-536c-85bf-7ad429565437 |  | note | Acceptance Criteria - The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
label | 1465141b-6e46-5801-96b2-6679fa90e68a |  | note | Method - Visual
label | 44f84631-9610-5022-96fa-789f1ee4da19 |  | note | Frequency - Each lot
label | ec0860e5-2b42-5f33-bccb-8c17271d442e |  | note | Category - IP
label | 57a07243-aa6d-5bf1-a019-6cc45bbb11a3 |  | note | Responsibility - SE/Site Supervisor
label | 27dfa74d-3c27-5935-bb06-661942abc55c |  | note | Verifying Documents - Sign ITP
text | 494d0f6e-c5ed-548f-bce6-34476297cec1 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - Compaction Testing (results)
label | 2242548d-40ec-5a75-a1c2-5ce801574c92 |  | note | Reference - Section 173, Section 304.08 Table 304.081
label | b20d74d0-e862-525d-8587-87cfeb821dfb |  | note | Acceptance Criteria - During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
label | 9d04de45-b2ec-5050-8536-04ede1937e2b |  | note | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
label | 5f56cb8b-14d7-587f-8cf9-75dbe6ad5d3b |  | note | Scale A:
label | 20835722-b854-5339-8cb4-ef3e51a79c00 |  | note | ○ Subbase Layer Characteristic Density Ratio (CDR) ≥ 98%
label | b27f285d-161f-581a-9ac2-ff1da6e298a8 |  | note | ○ Base Layer CDR ≥ 100%
label | eb177e72-a221-53db-8be1-5601cc512574 |  | note | Scale B:
label | 2c10a9d8-c7a0-53bc-b762-f36863dff1d5 |  | note | ○ Subbase Layer CDR ≥ 97%
label | 4bfd70ed-b4ec-5fa3-a291-c3335ce0fbbc |  | note | ○ Base Layer CDR ≥ 98%
label | 63042eec-cb6a-5b54-99e2-056b2996e1b2 |  | note | ○ 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
label | 9e7a3c9b-e687-5b20-bcaf-56f0d6665a21 |  | note | Scale C:
label | cc214577-2622-5d6e-ba15-94702ad8d3fa |  | note | ○ Mean Value of Density Ratio (3 tests):
label | 4cb065f7-a97e-5366-9ef8-552d0580d99a |  | note | ○ Subbase Layers >98%
label | b0e6fa51-0c88-51c1-9c21-82f03d00efc5 |  | note | ○ Base Layers >100%
label | 56c80dc4-1d4b-586c-988b-9afff67683a6 |  | note | ATTACH: Compaction Test Results
label | 63af89d5-6d7b-5107-b85d-95a4a45b09da |  | note | Method - Document Review
label | 561d7d45-92d8-5d24-8ce0-8782ea1dd555 |  | note | Frequency - Each Lot Where applicable
label | a0f3545d-4bde-53ab-95b9-1492b090b9ec |  | note | Category - IP
label | 276995be-006e-54f0-86eb-990c537d6548 |  | note | Responsibility - PE
label | f6477e74-934c-5ed4-b1b0-159de42d7881 |  | note | Verifying Documents - Compaction Test Rersults
text | 4239c8d9-0e22-5550-b373-b321fa78c676 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Post Compaction Materials Testing (Results)
label | 731d3ff7-2559-54c0-aad4-be2b0b89a328 |  | note | Reference - Section 304.10, Section 304.11 RC 500.02
label | 27189b99-b814-5755-aa37-e802bd3f6d3f |  | note | Acceptance Criteria - Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
label | edd68a6c-32fe-5d26-9ea7-50f8aa9e12b6 |  | note | 20mm Class 3:
label | 124262fd-5324-5bd1-879d-1a16f2fc246b |  | note | Grading
label | 0572fd0a-e62c-5d55-a135-c4701c683fa1 |  | note | ○ 26.5mm 100%
label | f6bea2c8-ec7e-54ea-b429-e7ffefe672f6 |  | note | ○ 19.0mm 95-100%
label | 399f3b38-5f14-51c0-813f-11c7d0e46e57 |  | note | ○ 13.2mm 75-95%
label | 491496be-136e-58d2-8302-aa0e4c21c0df |  | note | ○ 9.5mm 60-90%
label | 5780aad9-b3d1-58a7-a4fc-2030f778f9b2 |  | note | ○ 4.75mm 42-76%
label | 0b37b07a-c016-544b-9b4c-18f078808bd2 |  | note | ○ 2.36mm 28-61%
label | b78f1cf6-3527-5bba-870c-9ffed8683269 |  | note | ○ 0.425mm 14-29%
label | 7cf7dce7-d45d-5913-92a2-9c9e388b6655 |  | note | ○ 0.075mm 6-14%
label | e32a840b-9f12-516c-a624-a87791820b02 |  | note | ○ PI between 0 to 10
label | dad2a5fe-0af1-5d1b-9272-2e91f1f2d937 |  | note | 20mm Class 4:
label | 9753c4d7-b0d9-53e7-89f6-c5e8286e4fe9 |  | note | Grading
label | b6081ed9-499d-53b0-ae9c-3999cf4df452 |  | note | ○ 26.5mm 100%
label | 1c23d409-7a0a-5977-88bf-64ed8fc6b327 |  | note | ○ 4.75mm 42-76%
label | c2c8b3f6-63d8-5717-8468-10134b9d8d57 |  | note | ○ 0.425mm 10-28%
label | aabc78da-ed56-5718-855a-c7ef432490a0 |  | note | ○ 0.075mm 2-14%
label | 20d3958b-5a3c-5b71-a5ce-fbc1190bb98d |  | note | ○ PI between 0 to 20
label | 6dd20bde-d680-59b8-807d-448f861263c8 |  | note | ○ PI x % passing 0.425 mm sieve (max) 450
label | d0f04ea2-b903-59ae-a19c-1b2274dc3f74 |  | note | Scale C: Post compaction material testing is not required (Choose NA)
label | 56c0b8df-a95c-59b2-8320-7156be335e23 |  | note | Method - Document Review
label | 9b0694cd-569d-598c-b1ab-8048e9f9b41c |  | note | Frequency - Each Lot Where applicable
label | bdefee9c-c7a6-51d9-9ad0-2350efe46d90 |  | note | Category - IP
label | b2a3c4a2-70ba-53ad-a7f3-94ed4d9e57be |  | note | Responsibility - PE
label | f307566d-a017-56dd-819a-f8e6d484163a |  | note | Verifying Documents - Compaction Test Rersults
text | 91ae96d0-ab72-5b3a-986b-252f7dcbf82e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Survey As-Built - Surface Level
label | 2f177bd5-09e5-5cc2-9f73-a9b4944a6a28 |  | note | Reference - IFC Drawings Section 304.06 Table 304.061, Table 304.062
label | daac33a4-2505-5dc2-bac2-215948de096a |  | note | Acceptance Criteria - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
label | f713b0ed-011b-5dcc-91db-3aaef1714c1a |  | note | ○ Subbase course shall be not < the specified thickness by more than 15 mm.
label | 0c9f80a3-e46e-5888-a959-3ca7ca48eb42 |  | note | ○ Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
label | 9e30fc32-4606-5db2-9198-52170d3b71ca |  | note | ○ The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
label | 98a82767-7f60-52ca-a42c-5fa125ce0be5 |  | note | Scale A: A minimum of 80 measurements per lot
label | 73192754-d30e-54c2-bb01-2c9c6f256c11 |  | note | ○ Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm
label | 1ad6d947-d6d2-5e85-9f9d-693d8ac8eb72 |  | note | ○ Base: mean range ±5mm, maximum Standard Deviation of 8mm
label | 01a0161b-df65-515d-8d32-ac84bc31439d |  | note | Scale B: A minimum of 40 measurements per lot
label | fae784a6-f3a1-5266-83d6-391aebc9ab07 |  | note | ○ Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
label | 62fcef04-af3a-5f58-a603-7911a85c6ac0 |  | note | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
label | fc7113e9-698c-5381-a95b-98ca9320402e |  | note | Scale C:
label | 80fd02b2-a566-5015-8441-ea674e409f53 |  | note | ○ Lower Subbase (mm) +15/ -25
label | 677164f0-04c0-55fd-9e53-12cd8b1805a1 |  | note | ○ Upper Subbase (mm) +10/ -25
label | fd437000-87e0-5439-ad1b-089e245f1458 |  | note | ○ Base (mm) +/-15
label | 628a2dd0-6740-5b9e-8ec5-a2aa0bc33e87 |  | note | Method - Document Review
label | c39b8114-4091-5992-ac73-3aba3cbf351e |  | note | Frequency - Each lot
label | 16cdada0-abd7-57d3-a1ef-1b40206f7670 |  | note | Category - IP
label | afaef9cd-b082-5e2b-bf21-5b9cc91e940f |  | note | Responsibility - PE/Surveyor
label | 4888d8cd-d316-5b22-8d69-c5e60bc43a02 |  | note | Verifying Documents - Survey Conformance Report
text | 19522a1d-657a-5f6f-89b6-8b9945570eb9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 97701c0f-330d-56ba-a590-f042cb2a259c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 71328de3-80bb-5389-8ad2-f8e82e3425ac |  | textbox | Name:
text | e565f738-e0ef-5bf5-8937-eae0ef2cad8c |  | textbox | Position:
text | 2fc62b8c-0047-57b0-a093-084902d943a3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-055-CIV-CPD-Conduit & Pits-Rail (Supply & Install) | itp |  |  |  | Yes | ITP-055-CIV-CPD-Conduit & Pits-Rail (Supply & Install) - Rev 0 | ee98f55a-f499-409c-a25c-ac3c6a9d17f9
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | d574efd4-ae65-577c-8f36-b253727c2e98 |  | note | Document Title: ITP-055-CIV-CPD-Conduit & Pits-Rail (Supply & Install)
label | 0e346702-12a7-5fff-b8e1-8446c0b3b1c5 |  | note | ITP Description: Conduit & Pits - Rail (Supply and Install)
label | d215155f-81ff-52e8-b169-f142c50ba78a |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 3939086a-5226-54e2-95bb-ce728f55cc4f |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 3ce57144-ec29-57e5-ad0d-b28455374f10 |  | note | Revision Number: 0
label | 15de89f3-76c2-5184-87af-10d6a7b23638 |  | note | Revision Date: 4/08/2023
label | db21fc11-ca47-5c1f-8eb3-963ae41db11b |  | note | ITP created by: Andrew Carlini
label | 17e349c7-4521-52a7-a0cf-ec6a4974126e |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 700c534b-d66c-5720-b337-23bd8e85c2ee |  | note | Reference - IFC Drawings L1-CHE-STD-043 (VRIOGS 012.2.1) L1-CHE-SPE-070 Australian Standards MRPA Standards
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Conduits
label | adda807a-ac2c-5131-95df-260c5add916c |  | note | Reference - HV Conduit: AS 2053, HV Conduit (boring): AS 4130, Comms Conduit: AS/ACIF S008:2006, LV Conduit: AS/NZS 3000 - 2000. L1-CHE-STD-043, L1-CHE-SPE-070
label | 641e28d3-a4a6-5fa1-b3de-129b42980852 |  | note | Acceptance Criteria - LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
label | 2ad198a9-daf3-57a3-b6e7-94848db131f2 |  | note | ○ LV & COMMS CONDUITS TO HAVE A MIN 600mm BENDING RADIUS
label | fd55a62f-8c2b-5cc6-9f61-e59c79bf4925 |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | a414aed1-ee27-5902-8fe3-c955e274455d |  | note | Method - Visual, Document Review
label | 2dc4ce3b-6496-5123-a6cf-528a1feafce2 |  | note | Frequency - Each Material Type, Each Delivery
label | b1e6392e-0a69-5f54-911d-d68df12eec36 |  | note | Category - IP
label | f9fbfead-bc3e-50b2-8248-b531e1569ffb |  | note | Responsibility - SE/PE
label | ac4286c5-11cb-5c11-97dc-a3e2ff9c8035 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | 8ae9671f-ecfb-52d6-936e-6c6629e382f1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Pits and Pit Lids
label | 5a2b71e2-aeb4-5842-836d-e5c22f3db003 |  | note | Reference - IFC Drawings VRIOGS 012.2.1 Section 6.15-16, VRIOGS 012.2.1 Section 6.9, VRIOGS 012.2.1 Cl.6.7 (c) L1-CHE-SPE-070 Cl.10 AS1289
label | 8e0c8c84-808e-521d-b47b-20baa8abb5d8 |  | note | Acceptance Criteria - Pits:
label | 2ba34af4-eae6-5e7f-8564-fc1360054418 |  | note | ○ Pits located within 1.5m of nearest rail, pit to be 300LA Railway loading
label | 00d89f1f-ff61-5d12-a523-dcf5c908bee1 |  | note | ○ Pits 900x900mm or greater, multipart pits lids to be used.
label | 397b2ab5-52ac-52d0-a02a-99f1091d4004 |  | note | Pit Lids:
label | 6a7cb99d-b793-5063-8d62-b9fa3a16bbc5 |  | note | ○ Pit Covers shall comply with AS3996-2006
label | 5dfe8848-8465-5782-bf1b-9a17f5bd312e |  | note | ○ Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
label | 01ea0439-4a0c-5f4e-90de-51a1d95c6d9d |  | note | ○ LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
label | 228eb118-fe5b-5679-ab30-dfb17a518fa1 |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | 3e1cdd0f-f6ba-51bf-b195-5730b4e1b780 |  | note | Method - Visual, Document Review
label | 22003fba-5c13-5142-8fd2-e2d56322f224 |  | note | Frequency - Each Material Type, Each Delivery
label | 0ea1de73-44ad-5115-bf3c-e1463d998309 |  | note | Category - IP
label | f9b48deb-5708-593b-841e-471a76a1a888 |  | note | Responsibility - SE/PE
label | 9e49cac3-6eb9-52d6-9933-8c04b786a9c2 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | 23d54b23-4ef6-50e0-a002-63795f327098 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Warning/Marker Tape
label | 81322cb4-fb9b-566d-a1a5-23b2cc751a0d |  | note | Reference - IFC Drawings AS/NZ 2648.1 TS-SP-013 L1-CHE-STD-043 6.4
label | 177bcef4-9d12-5df8-ac98-952330e76d8c |  | note | Acceptance Criteria - Warning/Marker Tape:
label | e7a554ba-76fa-58b6-af2d-9fb5ceff60af |  | note | Above LV:
label | 068f767f-0fc1-5e8d-9e52-154ca2294b5d |  | note | ○ 150mm minimum wide orange coloured PVC
label | e5423953-b56c-538e-8cda-30cc2f27b69b |  | note | ○ ‘DANGER RAILWAY SIGNALLING CONDUITS’
label | 62c87c4d-caea-5e44-97a6-e2cc8696b950 |  | note | Above Comms:
label | 1aaa33f0-1ddb-50c8-ba9e-0cd1dc43a833 |  | note | ○ 75mm minimum wide white coloured PVC
label | 90bb46ae-0a50-537b-b900-481bf0a0e297 |  | note | ○ ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire to be laid directly above trenched VicTrack assets
label | e18c2a58-1b69-5405-bc5b-e02400443ea6 |  | note | Above HV:
label | 667b80b6-2b57-5bae-8d69-43d1a4a5f5d1 |  | note | ○ 300mm minium width orange coloured PVC 'Danger - Electrical Cable Below'
label | a13d5dad-11ed-5423-8d90-523db7729ffb |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | 8246514c-c6c3-5dc9-a6c1-1247a06e69f5 |  | note | Method - Visual, Document Review
label | 92e2f927-3749-52f8-b351-3e46f711ed51 |  | note | Frequency - Each Material Type, Each Delivery
label | 0b44d18b-032e-534c-991e-73089137eccf |  | note | Category - IP
label | 51b3c154-84a3-5557-98b4-1b5c2ef8185c |  | note | Responsibility - SE/PE
label | e3b7bf58-1770-5e93-ac66-73fe45488051 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | dbc7ad92-4ef6-5dbf-9fa7-b0bda4d41cb2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Protection Barriers
label | f3168ab3-1588-585c-b331-cca86a14873a |  | note | Reference - IFC Drawings L1-CHE-STD-070 10.3.3 AS4702
label | 088bdbf5-25fe-5f73-b445-3f9d03c21013 |  | note | Acceptance Criteria - Protection barriers shall be polymeric cable protection covers complying with AS4702 OR a min. 40mm thick concrete barriers (pavers) not less than 15MPa at 28 days
label | 95c43c6d-d061-53ea-99f6-97138cc812bd |  | note | ○ Inspect materials upon delivery and attached delivery dockets.
label | f3b9df6e-5228-501c-8e4c-5e52f7cf1cc3 |  | note | Method - Visual, Document Review
label | 3f526150-ac73-5840-b772-2a10433adc3e |  | note | Frequency - Each Material Type, Each Delivery
label | 5800ab40-e139-503c-8eba-7ce86b1ecae3 |  | note | Category - IP
label | bbbfbaba-abc0-5063-b81f-f96d843d495d |  | note | Responsibility - SE/PE
label | f0db990e-5907-5adb-8395-916e0f2fbeaf |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | 17516c59-4539-58b5-81f8-3c16e72e22b4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Backfill Material (stabilised sand)
label | a4095bee-1b38-5faa-8d65-3bab95828070 |  | note | Reference - IFC Drawings, L1-CHE-STD-043 Section 2 Table 1
label | 3d88d363-a112-5329-8d68-c20519686407 |  | note | Acceptance Criteria - Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could dmanage the conduits.
label | d40f9be1-1cb4-5efb-a5ed-b39e07a2410e |  | note | ○ Inspect backfill material.
label | 8990036b-a781-5223-b5f4-36e607b82d94 |  | note | ○ Attached delivery dockets (if applicable).
label | 288a02cd-f330-5062-b692-0088c2786dd6 |  | note | Method - Visual, Document Review
label | d567bd72-ac03-55ad-b563-90de126f2fc6 |  | note | Frequency - Each Material Type, Each Delivery
label | 436df35b-a50b-51d8-8944-0e4b9ea1660a |  | note | Category - IP
label | 4d8576a0-3d27-59a6-a8c6-23192ebee22a |  | note | Responsibility - SE/PE
label | ad07a356-62cf-5142-9db0-40e1be211b10 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | 62919031-e79c-5d11-a056-7a28a0a50896 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Bedding Sand
label | 5d2d8ad6-0283-5e6b-bf72-fe94f760e0c7 |  | note | Reference - IFC Drawings AS2758.1
label | 2b1dd650-d6e2-5e6a-829d-96eb9cdea7f8 |  | note | Acceptance Criteria - Bedding Sand shall be a clean sand that is an uncrushed fine aggregate to AS2758.1 and shall have a thermal resistivity ≤ 1.2 °Cm/W at 5% moisture content.
label | 1dcd8f0f-d9be-5339-88cc-8457094006dc |  | note | Method - Visual, Document Review
label | dad097f9-26a7-5c45-a254-30c811dab74e |  | note | Frequency - Each Material Type, Each Delivery
label | facdc3db-7b75-55a7-9fc1-c0ab9f341c92 |  | note | Category - IP
label | fb3f4156-cb40-5483-bc4d-729c3bde7653 |  | note | Responsibility - SE/PE
label | 2f252b55-8443-5185-99dd-9d1bbab1fb23 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | 8cdae23a-759f-5eec-b077-d5be044d8a65 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Draw Wires
label | 0f61742f-2d8a-5ff6-acd3-13d9feadf38c |  | note | Reference - TS-SP-013 AS 4142
label | 1732fa4e-2f8d-5120-8527-23dad8a2018f |  | note | Acceptance Criteria - 6 mm diameter polypropylene blue/yellow
label | d11d5b4a-e8a8-5727-b13c-141fbf112420 |  | note | Method - Document Review
label | 9985d47c-af0a-5ac1-aa94-ab13f61536e2 |  | note | Frequency - Each Material Type, Each Delivery
label | a2b44d4a-b56d-555e-9e76-f3b32e1010f2 |  | note | Category - IP
label | 309035bd-6091-5495-9a26-2a9988b9a287 |  | note | Responsibility - SE/PE
label | e4fd4868-6b84-5fb5-b632-bafbe11e82c9 |  | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
text | ae06fbdd-2580-5ce9-8ab9-4edf2a99c372 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Concrete Mix - Trench
label | f09cb20e-9e0c-5d09-a71c-8f616caac142 |  | note | Reference - L1-CHE-STD-043
label | c1758b37-f8f5-5579-bd5b-3f266fd70f48 |  | note | Acceptance Criteria - N/A
label | 352fc044-65f9-52c7-bd44-5e54040a3f4a |  | note | Method - N/A
label | b2e9fd7a-7a4d-5a01-8f62-32826ba23586 |  | note | Frequency - N/A
label | 249e00d4-2d5c-56b9-8518-8d9ee519afda |  | note | Category - N/A
label | 3939c5ea-1736-5823-9346-d7f9693172b9 |  | note | Responsibility - N/A
label | 120ece0a-ecf5-5d6a-ba78-1f28512e149c |  | note | Verifying Documents - N/A
text | cdd8c11f-2684-52b7-a3fe-8b8abbab728e |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3. Prelimnaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Services
label | 10592b48-0888-51f1-a807-1bfed85b1143 |  | note | Reference - Services CAD file
label | f04260c8-f036-5644-8316-05a0bcaa61d6 |  | note | Acceptance Criteria - All services within 5m of Excavation location have been identified and appropriate control in place (refer to MRPA Excavation Permit).
label | 1f91c915-cc1a-5226-932b-d2b31a10364d |  | note | ○ Survey to mark out existing services.
label | cbfb6c8b-a507-596c-bdc3-be7e784474f2 |  | note | Method - Visual
label | d4decad2-ca0d-54ea-a5f9-86b56725c039 |  | note | Frequency - Prior to commencement of works
label | 474aa9e9-30a6-5af3-aeb9-2e1eb12b9107 |  | note | Category - IP
label | 7160db47-3e2d-560c-a8e8-de0d193dd936 |  | note | Responsibility - SE/Site Supervisor
label | cc293ac5-9031-5254-bc62-36d93bce4e40 |  | note | Verifying Documents - This ITP
text | 6c4dff34-fc15-5b53-a688-5c461423c08c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - CSR Works Procedure
label | 3f780eb8-3bad-5bff-ac91-94761f1afc29 |  | note | Reference - WAP_CPD_254
label | 18db5f7f-3efe-5bd7-9713-fa52735f82f0 |  | note | Acceptance Criteria - WAP to be reviewed and signed by all relevant stakeholders along with Rail Safety highlighting works proedure with in the Rail Corridor
label | e145eee5-a827-5eac-8d1b-61c81743a18e |  | note | Method - Document Review
label | ef997b0c-9663-5265-957f-1855c48a13bf |  | note | Frequency - Prior to commencement of works
label | 8861eb41-a5b3-5bb1-aba8-2305181d43e7 |  | note | Category - HP*
label | cf353dbf-e1f6-53c8-a293-5356b683923e |  | note | Responsibility - SE/Site Supervisor
label | 08937bdd-eb45-50aa-a3e8-d9f9a6c94a81 |  | note | Verifying Documents - This ITP
text | 7bdef42d-8851-595d-a36b-edeaff63d926 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out
label | 280f7842-2107-557a-9099-3c8f7688f5b8 |  | note | Reference - IFC Drawings
label | 1ab1d630-2ff1-5297-8965-6c018fbeddc5 |  | note | Acceptance Criteria - Survey to set out trench alignment and pits, and establish construction control (alignment and level).
label | 97420f9c-eac0-53e4-b078-4a02e0c551fc |  | note | Method - Measure, Visual
label | c8fba9b8-1004-5af3-b25f-76131d46159d |  | note | Frequency - Each element
label | c9c95446-196f-5396-b79e-38461fe7afe8 |  | note | Category - IP
label | af43c15d-4ce3-583d-b328-9e8388647c93 |  | note | Responsibility - Surveyor, SE/Site Supervisor
label | d5ac35ad-87e6-5192-bb2b-62a74cb22731 |  | note | Verifying Documents - This ITP
text | 1aa5020d-3efb-5ccf-afef-dd10f3a19f24 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - IFC Drawings
label | c4f6c505-b815-57d1-8a80-e185aa0b0754 |  | note | Reference - IFC Drawings
label | d1263639-8a8c-56d9-a54b-302fa6a40597 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 24835c94-aa10-5192-9caf-4cc4aef3770b |  | note | Method - Document Review
label | 9d29eb8d-5e17-5760-8d8b-b0da9ebf1610 |  | note | Frequency - Prior to commencement of works and at regualr intervals
label | a4dfc6d9-6b14-513d-bcb8-fcdcf2889d45 |  | note | Category - IP
label | f461ecaf-c155-50a9-bdcd-d6cac30a22c0 |  | note | Responsibility - SE/Site Supervisor
label | c8ed7922-a6ff-5152-918d-6c33c3e4de27 |  | note | Verifying Documents - This ITP
text | 6456aa3a-ec76-57e5-9ca8-54757e1e8a10 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Trench Excavation
label | eafe2cec-edd8-5851-baaa-65984714dd1f |  | note | Reference - IFC Drawings L1-CHE-SPE-070 7.3 Table 2 L1-CHE-STD-043 L1-CHE-STD-070 7.1c
label | 49da775b-5a2c-54da-93e9-f5fe9e473888 |  | note | Acceptance Criteria - Trench profile and depth as per IFC drawings.
label | 26b6a76b-ce11-5280-b227-4172134cb1ef |  | note | ○ Edge of trenching to be a min. 2m from strucutres/pile foundation (unless it is mounting the structure) and a min. 4m from the rail for HV and 3m from the rail for LV & Comms
label | a0d4c894-6777-5133-90c5-d2d13161acb9 |  | note | ○ The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits.
label | e6acfa55-b7ec-5408-97b6-938162db8efc |  | note | ○ The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
label | 1d4e5e63-53be-5e06-b29c-c427696e1c85 |  | note | Method - Measure, Visual
label | 70443a86-d9ca-5db1-ac8f-c88e8fa21e34 |  | note | Frequency - Each lot
label | 02f91683-dcea-588f-a18a-c693fd031530 |  | note | Category - IP
label | 6f553e96-fdbc-521e-b453-7fb0e7bc4919 |  | note | Responsibility - SE/Site Supervisor
label | f426a83e-7956-5c83-b990-7b15e1cb3998 |  | note | Verifying Documents - This ITP
text | 707266e4-30d8-59ab-b6c1-0ed87694b3a2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Trench Stability
label | 7af6e120-bf32-5a2d-86dd-dc524cc3e33b |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings MRPA Standards
label | 3ed4fb2b-7dea-578f-aac2-e86d84841634 |  | note | Acceptance Criteria - Trench stability check:
label | 64119b42-f251-5901-8c1e-72c25702b036 |  | note | – Shoring,
label | 973cb3e1-5f45-5c93-916f-e22f04f6ac1a |  | note | – benching
label | 2f45c57b-32e4-5bee-96a7-07d6afc08643 |  | note | – geotech signoff
label | 5e019d02-7665-5a1e-ab68-68fd6cab0276 |  | note | ○ Attached Geotech Report
label | 0cad6040-798f-589e-8838-1a402002776b |  | note | Method - Visual, Document Review
label | ccbe28d7-2884-55ee-b5ea-ce2b92010380 |  | note | Frequency - Each lot
label | ab0fbaf2-e89a-5d5b-9995-dbe823b51196 |  | note | Category - IP
label | 6b7d5873-8b4b-549b-8aff-95670b773cf9 |  | note | Responsibility - SE/Site Supervisor
label | be4bd7df-2cf8-5fea-9d77-247259a15f60 |  | note | Verifying Documents - This ITP
text | c46005aa-52c8-5052-9409-e076baebd2a6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Placement of Bedding Sand for Conduits
label | 58215e33-3c32-5291-a656-975b486d8139 |  | note | Reference - IFC Drawings L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070
label | 3303d0ca-532c-5f38-96dc-1bd669541f42 |  | note | Acceptance Criteria - 100mm of bedding sand/crusher dust to be places at the base of trench.
label | de3b34a7-0c7d-56fb-bfb2-773517287700 |  | note | Method - Measure, Visual
label | c21dab29-fb23-559d-83b1-3c497b8f81e0 |  | note | Frequency - Each lot
label | e8249845-e3c1-5c6e-947b-0762469a6e22 |  | note | Category - IP
label | 3f65e296-0bfa-5261-8679-f5d44764cd29 |  | note | Responsibility - SE/Site Supervisor
label | 2a3cb03e-ea87-5798-87ff-19b15aa016c1 |  | note | Verifying Documents - This ITP
text | 8e674989-908a-5d29-8bc4-baeb9831bbb5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Conduit Placement & Configuration
label | 12f01c77-9dd5-5b2b-8d0a-e9e5c47b8b60 |  | note | Reference - IFC Drawings L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070, L1-CHE-STD-077
label | 7d5bb706-effe-5738-bee8-3a6d399bfa5d |  | note | Acceptance Criteria - Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
label | 6eaf6216-fbbb-53f2-99af-b88244e2f5df |  | note | Min Cover
label | c30331cc-26fd-509c-a1cb-70fbe221c371 |  | note | – HV: 1000mm
label | 694951ad-c1a0-5f74-a6f8-28db36e53f24 |  | note | – VicTrack: 650mm
label | 645642a8-f0f8-5b63-a991-8a3918f01464 |  | note | – Signalling: 800mm
label | 75429d5d-c8fc-5a75-a370-13540c127f0e |  | note | – LV: 800mm
label | c344a6bc-47ef-5f98-9639-d2f3805d6122 |  | note | – Electrolysis: 800mm
label | c34c4e1a-d20f-5054-a38e-8c3db6f2503e |  | note | – SCADA: 800mm
label | d3f76d18-d174-5a20-9bd6-0df0538854ba |  | note | – MTM Comms: 600mm
label | 28d37a54-6f77-5481-9d47-acec5f1492a3 |  | note | – 800mm below water coarses (stab sand encasement)
label | 52a236c1-6022-537f-a81d-d965c6ad98fe |  | note | – 1200mm Under VicRoads Roads & top of Rail
label | 354b1e05-9ecc-593f-bf73-5b0fdcb367c3 |  | note | – 900mm below council roads
label | e6076fdb-e220-567f-ac03-1abd806be704 |  | note | Method - Measure, Visual
label | 11370d73-1af8-5b8b-9510-8f6c0a0eb185 |  | note | Frequency - Each lot
label | 38681cc7-f1b1-5a70-966f-1030c61c16b2 |  | note | Category - IP
label | f9daada6-2b74-5cf8-b562-5ed416a9eec3 |  | note | Responsibility - SE/Site Supervisor
label | 8f377df5-6e8b-5008-b2aa-03b258c0063f |  | note | Verifying Documents - This ITP
text | cdce26f5-31aa-58e9-8ca1-c3b2b6b302a9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Separation of Services
label | 074698bf-7bca-54dd-82c2-5f8e735081a0 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070, L1-CHE-STD-077 IFC Drawings
label | 9c630784-ff45-5859-8d9d-a661d1df465f |  | note | Acceptance Criteria - Separation of services
label | 7a350678-4383-5844-8498-27ea4448964d |  | note | – HV: Min. seperation distance between HV conduits at least 50mm
label | 0a5c0bbf-4844-5247-8205-c25f8d57b397 |  | note | – VicTrack: fiber 300mm from HV
label | f155bdc6-dc87-5ccf-a29a-b3d739a9e47d |  | note | – Utility: 300mm to utilities
label | b91f18e7-77a4-56df-8037-16cf4f034a8f |  | note | – Rail: When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 8bb70b9a-71cd-5411-93b2-382c4a3d5eef |  | note | Method - Measure, Visual
label | c9ea7a7e-5892-59a2-888b-bd389eec7989 |  | note | Frequency - Each lot
label | c3716912-4c25-56cf-8258-16e8b1b504aa |  | note | Category - IP
label | a0a4d3c9-eb34-5104-be42-b0236146890d |  | note | Responsibility - SE/Site Supervisor
label | 898f7551-f6b5-5ef6-878d-f2ace6eadce4 |  | note | Verifying Documents - This ITP
text | fc57cdbe-62ee-56c8-b0b9-eee946127b24 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Joints
label | 3db65550-8b92-5c38-8cdf-068f02046324 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | db7abc2e-2f5c-5463-96a4-b8265ad52c6c |  | note | Acceptance Criteria - All conduit joints shall be made by utilising the spigot and socket ends.
label | 2fa5f6eb-df66-5d14-8eca-bbcf04875a26 |  | note | ○ Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer.
label | 076de0a0-d42e-54de-a842-2147d22fed78 |  | note | ○ The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer.
label | 3b3ff1a3-0c07-598a-b338-3fbd09fb722c |  | note | ○ Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
label | 3a6dcc2a-de49-503b-a855-dcc587b4fe32 |  | note | Method - Visual
label | f74c4c14-e29f-5621-ab09-6165e3d001f9 |  | note | Frequency - Each Joint in each trench
label | c670e2d4-9e7e-583e-aecd-35b462a9c783 |  | note | Category - IP
label | 96a5a622-7fba-586f-bed7-c20a37f53cfc |  | note | Responsibility - SE/Site Supervisor
label | b7d64d44-2120-5744-aeac-ea1693042f60 |  | note | Verifying Documents - This ITP
text | 420e5be8-0f38-56f2-9ded-8d22f9a43850 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Conduit Inspection
label | 58a8c196-2d73-5ff6-8911-4c142cd69418 |  | note | Reference - L1-CHE-STD-070 16
label | 3c6837d8-c79c-58ff-b652-f1489a88348f |  | note | Acceptance Criteria - Provision shall be made for inspection of cable routes by NA, MTM/VicTrack representatives prior to backfilling.
label | 39c9a83d-05dd-5c80-b502-cee0596e7fec |  | note | Method - Visual
label | 0cf29286-ad39-513d-bfbc-905329a628cc |  | note | Frequency - Each lot
label | 29b22df1-8f70-5c70-9bc5-540085ce9469 |  | note | Category - HP*
label | aaa8ec4f-5d95-54af-b904-cc67a8374a43 |  | note | Responsibility - SE/PE MTM / VicTrack Rep.
label | 1e896922-7d20-532f-9ad0-447705ead382 |  | note | Verifying Documents - This Itp
text | 32f728f1-699a-5828-9135-fa7d7cd37e8d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Bedding Sand Installation
label | ef9e6720-6fc3-5332-8862-41f1e4895814 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 CL13.1 IFC Drawings
label | 9076c4f9-845e-5ead-8887-fabc81fe88b2 |  | note | Acceptance Criteria - Bedding sand/crusher dust extends 50mm past edge of conduits.
label | c4d2992f-115d-507b-a1e4-c9014f805f25 |  | note | ○ Bedding sand/crusher dust extends 100mm above conduits.
label | cf0df211-2f73-524f-8667-b7c1a8073e55 |  | note | ○ Attach Delivery Dockets
label | 84a51892-c323-5cef-83e8-f056e128ef9c |  | note | Method - Visual
label | bca1b862-bf5a-5dbe-887b-46ccbf70b24c |  | note | Frequency - Each lot
label | 63804100-df35-5244-a25a-06f3df7bd53f |  | note | Category - IP
label | 1f41e38e-038f-5569-baab-6f720ca0eefe |  | note | Responsibility - SE/Site Supervisor
label | cf561779-1a21-52c5-8417-80c8c4c667ed |  | note | Verifying Documents - This ITP
text | 44f53d78-5ea3-5d15-aea2-87a864af9a6a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Marker Tape
label | cd41623d-2523-588e-a4fe-b90c9213011f |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-SPE-070 Cl10.3.3
label | 5cd38453-ca09-59bf-9fc7-cf1b21117ac9 |  | note | Acceptance Criteria - Warning Tape installed a min. 300mm above top conduit or a min. 300mm above HV protection barrers.
label | 09f494b4-a20b-587b-913f-36540c08526d |  | note | ○ Tape to be one continuous length.
label | 8a285ce1-fbea-55f1-8ce1-b200855b781c |  | note | ○ VicTrack to inspect the Marker Tape placement..
label | 85b211cd-0ef6-5449-861c-500aed2dbce0 |  | note | Method - Visual
label | 7c78e7fb-eed2-5280-92af-8d6bd1797b57 |  | note | Frequency - Each lot
label | e4a8e826-4f5b-52c3-bce3-7dabf858dd95 |  | note | Category - HP*
label | 4a9ef731-ac03-55f5-bac9-a0ddf2f39f8c |  | note | Responsibility - SE/PE, MTM / VicTrack Rep
label | 5120c505-f768-5844-ade4-ff7531728474 |  | note | Verifying Documents - This ITP
text | e17ee366-ce0f-54bb-b6be-117cab6ddf43 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Backfill Installation for Conduits
label | 309229fb-1770-511d-9d02-d1e4fe30c714 |  | note | Reference - IFC Drawings L1-CHE-STD-043 clauses 6.15 and 6.16
label | fa39071b-07aa-52bf-b872-154f9b0bb4e3 |  | note | Acceptance Criteria - Backfill per trench profile
label | 9b6e5712-8d68-52c5-bf7f-bcf65a7558b4 |  | note | – 150mm layers of 3% stabe sand
label | 38885896-f690-5a06-9198-ae87018dbc2f |  | note | – conduits under water ways to have 800mm cover from base of water way and backfilled with 3% stab sand
label | 4535510d-1ad1-5c6c-b1f4-7169bdfac958 |  | note | ○ The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
label | 9948f318-7ebe-5092-a08b-07690e522eae |  | note | ○ Trenches under road pavement - backfill to be same material as the road formation material.
label | 42a9ea04-373b-5aa6-baba-d9257c33676c |  | note | ○ Trenches immediately adjacent to footing shall be 3% stab sand. To be thoroughly placed to fill all voids without placing undue strain on or cause displacement of conduits.
label | ac8e80a6-1d6a-52ca-9e4d-aa1046b29db5 |  | note | ○ When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 21f0ae9e-1b44-5347-9a58-fefbd261fda3 |  | note | ○ VicTrack to be notified and witness the first layer of backfilling.
label | 2650814c-a180-5ae0-98cf-4dcec2d79619 |  | note | ○ Attached Delivery Dockets
label | 85bb2de2-e23a-5781-90b9-94df0ac25668 |  | note | Method - Visual
label | d8812673-1803-5f52-9e15-c1020001d7b2 |  | note | Frequency - Each lot
label | 4c6f81a3-3039-513c-9343-143e79c91960 |  | note | Category - HP*
label | 321d3578-d78c-5754-ad69-9c98e2d2ca52 |  | note | Responsibility - SE/PE, MTM / VicTrack Rep
label | 5e158dca-a361-5545-b04f-7585263be18a |  | note | Verifying Documents - This ITP
text | 29c721d9-d35d-5437-beb3-99c340ab58c0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Signalling Pits, LV Pits, Electrolysis Pits, SCADA Pits, MTM Comms Pits
label | e5a8adc3-c03b-5f2b-850a-8251b9fb8bd8 |  | note | Reference - L1-CHE-STD-043 Cl7.14.o, Cl7.14.g
label | 0b84102d-2880-518e-b673-f514e1509d83 |  | note | Acceptance Criteria - intervals no greater than 400m (electrolysis 190m)
label | 9755bc0f-988a-5c61-a508-492bdba1cca4 |  | note | – 3m from rail
label | 702ad092-ff4b-536e-b232-1d65d55e51b1 |  | note | – Access Roads, Class D lids
label | b1f33314-a101-5636-bfb2-41de0398d1fc |  | note | – Footpaths and non traffiacl areas, Class C Lids
label | 7ac5c2a1-c0e1-570c-b3e8-ef1b5d83c0ce |  | note | Method - Visual, Measure
label | 2b4e2c64-4b51-5257-9a47-5985ff87efde |  | note | Frequency - Each Pit
label | 99417a6c-a826-58e1-a193-055512ba4037 |  | note | Category - IP
label | 0f25147b-6957-57da-ac57-fee24b77d4c4 |  | note | Responsibility - SE/Site Supervisor
label | 927b5fb9-22ac-5527-b140-9a67c343157e |  | note | Verifying Documents - This ITP
text | c07001d1-40a3-5781-879a-d452edfd60be |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 - Additional Considerations
label | f6aaaa5f-309a-5d3f-8e6d-709ff5b0eb9c |  | note | Reference - IFC Drawings
label | af47d0a8-79c1-5689-bf5b-cebba95fb597 |  | note | Acceptance Criteria - Access tracks to pits
label | fd5888b6-4114-56a9-ac01-4e044623674c |  | note | ○ Safe access and egress (i.e. lid doesn't open up with workers back to the rail)
label | 917c4c9a-fe1d-555d-99da-01cc3636a20e |  | note | ○ Hand rail & retaining wall installed as required
label | abd696f1-43b3-575d-96f5-cb201c2d6737 |  | note | Method - Visual
label | 7eba5134-a139-5c4e-9c49-28714126a6e5 |  | note | Frequency - Each Pit
label | a932b828-c904-549e-9c6f-859a9cf0e852 |  | note | Category - IP
label | e426eb48-4028-5a26-b0bd-482b701c223a |  | note | Responsibility - SE/Site Supervisor
label | 21e28740-15c5-5e53-9ded-77f3b811d434 |  | note | Verifying Documents - This ITP
text | 4a89f8d3-e9f0-5084-8cc6-04cf1d51c348 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 - Bedding for Pit Installation
label | e6c529e8-c553-550f-ae53-317a76a425f8 |  | note | Reference - L1-CHE-STD-070 Cl 7.21.u L1-CHE-STD-043
label | 38a14659-045d-5455-b1f2-0ee310c02bd4 |  | note | Acceptance Criteria - 150mm of crushed rock under pit extending 500mm past the pit
label | 2d84c477-ede4-5b53-84d1-dd088d15bdd6 |  | note | ○ Drainage arrangements shall be provided at the base of each pit.
label | 83c6375c-11f3-56ce-865f-e931179c37ad |  | note | ○ Attach Delivery Dockets
label | 02a0ea38-aeeb-5fb6-a7bf-17d1888eed82 |  | note | Method - Visual, Measure
label | 76f70624-88ba-56f7-b201-8eabd84f7d94 |  | note | Frequency - Each Pit
label | 871556c0-dce9-5950-af1d-97d8153e5acb |  | note | Category - IP
label | d6a1118d-e36f-5f8a-a9cd-0a0d10906f14 |  | note | Responsibility - SE/Site Supervisor
label | 1f3e0a81-00ca-5b32-b7ea-fa173f58ce63 |  | note | Verifying Documents - This ITP
text | 45687674-a8c0-5d6e-abc3-ab731c923cea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 - Pit Orientation
label | 4095909a-a01d-5d75-a411-0dd9c1bc4143 |  | note | Reference - IFC Drawings
label | 0e800dc5-6ccd-5dc8-88ec-296957475509 |  | note | Acceptance Criteria - Pit to be parallel to track and parallel to conduit route.
label | 6e6295a5-cabc-5df2-be14-7b01d6156613 |  | note | Method - Visual
label | 255d3569-1447-5776-a29f-0732352aa9f6 |  | note | Frequency - Each Pit
label | 1a32b1d5-bca4-5760-9b73-79907ee0cbd7 |  | note | Category - IP
label | 26af59a4-1fe8-5c72-8c4d-648a7d21482d |  | note | Responsibility - SE/Site Supervisor
label | f1521a62-99c2-5c0a-8379-ec62b37d2cb8 |  | note | Verifying Documents - This ITP
text | fbd14b9f-58bf-5693-b72a-69c91f163126 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 - Pit Installation
label | 767baceb-d5f4-5c84-a7a6-665fa6353fb9 |  | note | Reference - IFC Drawings
label | 2fea99fa-570d-528d-946f-14963f7808bf |  | note | Acceptance Criteria - Pit installed to design specifications. Pit chamber floor to be 100mm lower than the underside of the lowest conduit.
label | 40b6d2b6-1dbd-53da-b432-a5e65a433505 |  | note | Method - Visual
label | 7aae198c-7f3b-5043-aa17-894d9e8089dd |  | note | Frequency - Each Pit
label | 743825cb-bd78-5b9a-ae5e-44e2e4dd6bd2 |  | note | Category - IP
label | 716681d5-38eb-5699-ab54-cf3804c90a91 |  | note | Responsibility - SE/Site Supervisor
label | bc2acf09-1d65-511e-a4dd-b85110ab4ec1 |  | note | Verifying Documents - This ITP
text | 088089ab-ac40-5a91-a9e5-fc96f9cdca90 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 - Conduit Entry onto Pits
label | ea4af1eb-01c7-5c1d-84c0-146b23bf77e2 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | b717a97f-4229-59ac-9e88-ffed48553ec5 |  | note | Acceptance Criteria - Lowest conduit 100mm from the pit chamber floor.
label | bc8d57c4-b2c7-5ade-8b50-b9aeaa31eb0d |  | note | Method - Visual, Measure
label | f612fe6c-ad8f-5ef8-bf42-ad08e7166ca2 |  | note | Frequency - Each Pit
label | 1e3126be-4798-5253-9bdb-1dad82a58be8 |  | note | Category - IP
label | c18330d4-0a04-5086-8df4-f0cad540a016 |  | note | Responsibility - SE/Site Supervisor
label | 679d6c1e-6767-5c35-9f6e-1e12dbeed974 |  | note | Verifying Documents - This ITP
text | b75ba114-400d-5cb1-8f10-0411b6e7b1a5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 - Tracer Wire
label | fa991a31-8af9-5351-b2f6-342b564d3ce8 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | f279d04f-fc97-56d2-8494-e282a6339468 |  | note | Acceptance Criteria - Warrning tracer wire for Vic Track routes to be drilled into pits and crimped off. If tracer wire broken needs to Crimped
label | bb4729e0-a0d3-5038-b9fb-7311e37177d1 |  | note | Method - Visual
label | 3e1b70cc-450b-51fb-9b5c-02c0938f86b6 |  | note | Frequency - Each VicTrack Pit
label | 3dd1a31a-4882-56c4-aabf-7f76f5c16cc3 |  | note | Category - HP*
label | 767cf503-623c-5c2c-afa8-ad41d9c37731 |  | note | Responsibility - SE/PE, MTM / Vic Track Rep
label | 5ba3acab-e38c-5549-8894-3aab6f5e6d36 |  | note | Verifying Documents - This ITP
text | 84567fe8-f43e-5462-9925-059c6a7d4200 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 - Spigots and Bell Mouths
label | 6c9ba6b0-40bd-5f4f-9863-8c9b8550b09c |  | note | Reference - L1-CHE-SPE-070_9.3.4
label | c40254c0-8726-5f68-a59a-6a8c86a26f1c |  | note | Acceptance Criteria - All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush with the pit wall and not touching any other spigots.
label | 047871a9-496d-5bf2-832c-a0c3d3e0a5c1 |  | note | ○ HV Conduit entering the pit shall extend a minimum of 150mm beyond the edge of the excavation and be fitted with Bell Mouths.
label | 5631a1f9-24a1-575d-9e07-f8ef4e417384 |  | note | Method - Visual, Measure
label | 0812f447-08c4-582f-b275-445e2cd3e71a |  | note | Frequency - Each Pit
label | ad7a28c6-d64d-5e5a-9b63-36cd1adca824 |  | note | Category - IP
label | 7565d39b-fdde-588a-984f-8e229a176803 |  | note | Responsibility - SE/Site Supervisor
label | 1b804370-3a92-553c-a790-a0a3a3cec32d |  | note | Verifying Documents - This ITP
text | 49211a3f-4b6a-53e3-90b9-623874e0daaf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 - Draw Ropes
label | fbdca9ef-7c41-59ab-af02-b06b4fe182bc |  | note | Reference - VRIOGS 012.2.1
label | 0096efee-b8b9-5474-ba62-bce62a249561 |  | note | Acceptance Criteria - The draw wire shall be continuous for the complete length of the conduit run.
label | d3afb3d3-05f9-59d0-8c6e-99bf73ae7490 |  | note | ○ The draw wire shall have a minimum of 2 metres of slack within every pit.
label | 24a72e33-0a42-5e4e-a125-1dbdb5b4c2fe |  | note | Method - Visual
label | 647079a6-7a33-59a6-a9cd-4caca6f63731 |  | note | Frequency - Each Pit
label | 3ddb0e2e-d185-55e6-9383-ea9aa5c3d23f |  | note | Category - IP
label | 5f059c2f-024f-5473-94bb-0ce5ae8f7da1 |  | note | Responsibility - SE/Site Supervisor
label | 10bfb173-f04f-5f5b-bd1b-75751d2e2f22 |  | note | Verifying Documents - This ITP
text | d883517e-2efc-5fc6-8d0a-6346372b79b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 - Backfill and Compaction Testing (if applicable) arouns Pits
label | d3dc11e4-fb0f-5b39-9c60-b3e43b4f8cb6 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | c10eecfb-8f64-5872-9009-67f96676270f |  | note | Acceptance Criteria - Backfill used around pit & pit lid to achieve 95% standard compaction in layers no more than 150mm layers
label | c0b42b7d-43d3-5d6e-96bc-41979ac8f9fb |  | note | ○ Sand within sand pits to be compacted in layers no more than 250mm layers
label | e3fd918a-8917-5ba0-aca0-6f2626e53be0 |  | note | ○ Backfill shall be compacted and level with the collar and surrounds for Trafficable Pits.
label | 6c5da9c4-0f32-5938-a3aa-ebc3f9b44301 |  | note | ○ Attach Test Report
label | 27af2d9b-f078-5ade-9066-a2610c3732d1 |  | note | Method - Document Review, Visual
label | 99fcb32d-c3a2-5564-bb26-405bc5fbb413 |  | note | Frequency - Each Pit
label | d3bfb12e-96c7-5f3d-8383-ae37b607bc9a |  | note | Category - IP
label | 31d880ab-318e-5f93-8324-5948b6ead153 |  | note | Responsibility - SE/Site Supervisor
label | 00678977-c135-5e41-87c4-4127b3f3d9ef |  | note | Verifying Documents - This ITP
text | 461944d6-dbb3-5917-aaab-04cfe24b14a5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.21 - Spare Conduits
label | 7198f4db-5b7b-570b-a1f1-3fb56104cb02 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | f9e07ac0-4542-55b4-a8a4-b34267630601 |  | note | Acceptance Criteria - Spare conduits to be sealed and to be included on survey report.
label | 17ac863b-f4e8-5e2a-938c-ee715ea69d9b |  | note | Method - Visual
label | ab8ff0b7-e019-5192-a5bd-0d3837f0da91 |  | note | Frequency - Each Pit
label | e9383298-dd2f-5452-86e3-2fbf54e2011b |  | note | Category - IP
label | d38579e2-5c7a-5ec4-901f-9374d988bdbc |  | note | Responsibility - SE/Site Supervisor
label | 70ab70a9-793d-5329-91b7-0fe8684388f0 |  | note | Verifying Documents - This ITP
text | 84d3e9cf-635e-5c8b-863b-25b610b60306 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.22 - Pit Lables
label | 8b2469d8-609e-5f00-b0fa-5088ab86608b |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | 5b15e083-257f-50fa-b595-758ec9ab2eb2 |  | note | Acceptance Criteria - Pit labels Brass Label (30mm x 150mm)
label | ff2c4770-d874-5461-83bc-fdce2cc6e4c4 |  | note | – HV: DANGER - Railway High Voltage
label | ce7bdc95-7fd3-53b3-8d54-0bc8db360a0a |  | note | – VicTrack: Victrack Comms
label | 65763f92-69f7-58bc-9fec-38b76ccfeb60 |  | note | – Signalling: Rail Sign Comms
label | 5e2edce3-a88d-53d0-bf62-01d6910270ab |  | note | – LV Pits: Electrical
label | 06ec0057-9e77-55c6-8d5d-d82c652a1f33 |  | note | – Electrolysis: Electrolysis
label | 98363d14-5df3-5bbb-80c3-5789a0de2289 |  | note | – SCADA: Rail Sign Comms
label | 199a783b-d4a3-55b2-9163-c50c0162fe51 |  | note | – MTM Comms: Rail Sign Comms
label | 38085be2-d7e4-57fa-9e1c-60c4dfa68df6 |  | note | Method - Visual
label | aff0a11d-f6e2-5892-bd78-6c8ffb652972 |  | note | Frequency - Each Pit Lid
label | 823c27cc-93e7-5eb5-a615-bd098be7eecc |  | note | Category - IP
label | 19b42533-ee3b-5017-9b8b-cdb9de7e191d |  | note | Responsibility - SE/Site Supervisor
label | 00882f4f-1703-51e3-a2e1-33c47b43665f |  | note | Verifying Documents - This ITP
text | 6f66be85-0084-5e78-9ee8-76d26f5b1a98 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.23 - Pit Numbers
label | 57ef8401-2bef-58e4-95f8-e546a9032d3a |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | 2a33ed09-48aa-54e5-a160-57cbc29eb625 |  | note | Acceptance Criteria - Pit Number Brass Label (30mm x 150mm)
label | 63690212-9fad-5d38-87c1-f4707d2a35ef |  | note | – HV (22kVV Feeders): ###HV
label | c0f2a534-82a8-598e-a35d-88814d5eea8e |  | note | – DC (HV Feeders for OHLE): ###DC
label | 218ea3fd-3708-5225-a2c4-291ff3d93fe3 |  | note | – VicTrack: ###C
label | 538569ad-7b93-5cf6-9279-e3dd5c06d950 |  | note | – MTM Comms: ###M
label | cbe824e2-7099-53dd-9dd1-92c9c050defc |  | note | – Signalling LV: ###SL
label | 07be26a5-329a-5bb8-a4cb-3bda1612cdcd |  | note | – Signalling HV (2.2 or 3.3kv): ###SH
label | 528dee8d-a4e1-5a24-bc20-5316099c9679 |  | note | – LV Pits: ###L
label | 8a24c374-843e-522b-a204-313fa5bf95bf |  | note | – Electrolysis: ###E
label | 0b5c6c83-c7ac-5b6f-9f64-fc18611bad71 |  | note | – SCADA: ###MS
label | 6a31ff1a-cf87-5e1c-a51e-c0562438c5e1 |  | note | Method - Visual
label | 6aaa054c-563f-56c4-b8a9-027445a94742 |  | note | Frequency - Each Pit Lid
label | 25ac117d-b851-5d0f-b96d-b5662fa889b4 |  | note | Category - IP
label | 33a8480d-b169-5976-bda0-46a55412dc09 |  | note | Responsibility - SE/Site Supervisor
label | 38099c11-dc29-5088-8f09-f33d88d5da5a |  | note | Verifying Documents - This ITP
text | 8f8a93b9-56f1-58f3-96fc-09154eeedf1e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.24 - Cable Route Markers
label | 1c316756-406a-576d-a4ef-fa15cdd852d7 |  | note | Reference - L1-CHE-SPE-070_13.2, STD_E0169 and STD_E0170, AS 4799, STD G0003 and STD G0004
label | ef3cc1bc-cfc0-502a-aa8a-8fd4f7b2dd32 |  | note | Acceptance Criteria - Cable Route Markers
label | 3a02f06b-1422-5cb0-b0ee-db8042e2badd |  | note | – points entering & leaving the rail corridor
label | edca459c-117b-5ca5-b23b-ab70b9e441ce |  | note | – no greater than 100m spacing
label | f80540f6-b852-581e-b636-eff54eb60409 |  | note | – Change of direction (more than 5 degrees)
label | 06fa92c2-025a-5e50-ae37-facacc42e258 |  | note | – White posts with marker plates for conduit runs
label | b7d09e33-fda0-56e7-8e49-584662f57331 |  | note | Method - Visual
label | 38b3656d-8e2f-515e-9d01-58337029eb14 |  | note | Frequency - Per Cable Route
label | 00bd0f77-8335-5221-8ab7-3403377ab11c |  | note | Category - IP
label | ad2815d8-db44-5225-be92-184b82028378 |  | note | Responsibility - SE/Site Supervisor
label | 2f94395e-c145-5fe8-9ed3-6ffa6f8e3aa7 |  | note | Verifying Documents - This ITP
text | 415afb5e-0fac-5ed3-8e8e-7f988ea60088 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.25 - Cable Pulling
label | e0740c34-d166-58e8-ab4c-b0c4292a3158 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | f12da0cf-59a4-5134-be7b-54a48bf69d93 |  | note | Acceptance Criteria - Cable pulling to be witnessed by MTM/Vic Track and to be signed off.
label | 8732c8b5-fa53-53f3-84ec-8cebed44ab64 |  | note | Method - Visual
label | 87c219c2-6112-5985-b033-ebbb52dc7630 |  | note | Frequency - Per Cable
label | b4e85ddd-b085-5915-a90d-c9df148007cf |  | note | Category - HP*
label | 1119c78b-fbae-5ca4-8ea9-6ced38748868 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | f45a34d3-f75f-51c9-80d7-43f4ed019697 |  | note | Verifying Documents - This ITP
text | d3827269-fe2d-5dd5-b2c4-d29cfff946ae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.26 - Cable Labels
label | bd18e5a6-f38f-57c6-b402-7c25863f6a36 |  | note | Reference - L1-CHE-SPE-070 Section 13.3
label | 2c09ddcd-9084-55bb-8bb9-e99937d4a8d9 |  | note | Acceptance Criteria - All installed High Voltage Cables shall be legibly and indelibly marked with an appropriate identifying label at each end of the cable, and at any cable joints.
label | 93e2e7e8-682d-5fc1-807b-b8c8c6f1184e |  | note | ○ The label shall state the destination points of the cable and the name of the cable relevant to appropriate drawings
label | 4314af9b-6159-53e7-ba7b-590e8072d39c |  | note | Method - Visual
label | bef2445f-605f-5913-8bc5-f48db783ec5a |  | note | Frequency - Per Cable
label | 897034a6-3750-518e-821b-b8226f3951a4 |  | note | Category - HP*
label | e107edca-571b-5f46-97b9-c7b74793cfc9 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | f200d832-f329-53f8-80b4-a720f6da7a12 |  | note | Verifying Documents - This ITP
text | 1ef0e06a-a75f-5be5-b2ad-859e4607142a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.27 - Cable Joints
label | 27358873-bc05-5137-9d81-7f04d3d273b6 |  | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
label | 6d3afe82-ce73-579e-be9b-84f22854d7c6 |  | note | Acceptance Criteria - Cable joints are installed correctly, with sufficient fault loops lengths & supported correctly in pits.
label | 61587ece-4611-5c14-8ed7-cd33e7c769f2 |  | note | Method - Visual
label | 00810287-ae5f-501f-b19e-3e849ac3f6d1 |  | note | Frequency - Per Joint / Termination
label | f7280edd-2119-5d72-8337-8ad007fecd77 |  | note | Category - HP*
label | e4488101-8738-5daa-b94e-9702177a8668 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | e93aa4f1-4c92-58b9-af3e-41828e2bc68f |  | note | Verifying Documents - This ITP
text | 16e2445a-77e6-5156-ac41-9e9a80ebbe98 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | 5010c438-01ea-5916-a091-e7cff0c23133 |  | note | Reference - IFC Drawings L1-CHE-SPE-070 Section 13.1
label | 8f70877c-a2e2-5ad1-9479-baf43f33fb89 |  | note | Acceptance Criteria - Survey report to include but not limited to:
label | 07581f97-bc09-5cf6-8009-85695454ac8f |  | note | – Cable joint locations.
label | 5e6eee6c-b335-52b3-a148-59e98b4330a1 |  | note | – Cable pit locations (Corners)
label | 574d1ccf-2992-563f-977c-dc2797c1fe26 |  | note | – Pit dimensions & pit lid type
label | 41802733-43a4-5950-b8ce-e0d3684c58c9 |  | note | – Under line crossings
label | 8bbbf653-2927-5476-93f6-0325a8fbcc49 |  | note | – Under road crossings
label | 17b441e3-f462-5a00-8401-af5258c8841a |  | note | – Changes of direction
label | c86c2ca3-576c-55ea-be4a-6af3ce98ec5e |  | note | – Spare Conduits
label | 5fb45484-975b-59bb-a1a0-6bcac21ccd1a |  | note | – Conduits labelled as per trench profile
label | 69d1f8ec-011f-5c2a-b3da-b073813b89c9 |  | note | – every 10m
label | fda627e0-f0c9-5a6a-93e0-b20391b251b9 |  | note | – Other significant points of the cable route
label | d6d03b8e-a0ed-55cf-9c52-8a13506b53ad |  | note | ○ Attached Survey Report
label | 20e9cb1c-b5f9-5b0c-888e-a4ebe4eb4140 |  | note | Method - Document Review
label | ff1245a2-1acb-52ae-8081-6dea999155a1 |  | note | Frequency - Each Lot
label | 8ef73a25-2dee-5a63-805a-4564f330f04b |  | note | Category - IP
label | 1932aaf6-2a6c-5f47-9d93-38b7b4ba8a8a |  | note | Responsibility - SE/PE
label | c7a7d7f1-517c-585b-88d0-567837b51bbc |  | note | Verifying Documents - This ITP
text | b6b38845-7056-54b6-9209-c99adc186c46 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Handover Check
label | 1d488719-bd0f-5139-b906-c79d2b181adf |  | note | Reference - IFC Drawings
label | 09883a1f-dfb8-5107-b3e5-a64b0140d14d |  | note | Acceptance Criteria - Handover check completed for Testing and Commisioning.
label | a81d3e37-c1a1-535e-ba67-3189a2355801 |  | note | ○ Attach MTM/Vic Track Check Sheet (Signed-off)
label | e4ba4984-868f-5a65-83e4-1f84bb96d5bd |  | note | Method - Document Review
label | 5e2ca7fe-cd7e-5584-8708-b112b132c65a |  | note | Frequency - Each Lot
label | dd429740-1468-5cdf-ad56-629ba69a00f1 |  | note | Category - HP*
label | 4a4b687b-0975-5e4c-b6d0-e33ea794463e |  | note | Responsibility - PE, MTM/VicTrack Rep
label | 6ccd5f93-d08c-598a-9cd1-44a869b7c514 |  | note | Verifying Documents - This ITP
text | 5a9b9141-e1e4-582e-9ac3-80d4a3cb71b6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Testing and Commissioning
label | af019a27-52af-5329-85fd-6e4b55746cd9 |  | note | Reference - IFC Drawings
label | de0abc0e-f493-561a-a05b-faa3f82092f9 |  | note | Acceptance Criteria - Testing and Comminsiong to be completed
label | af79657f-efb8-5799-8224-c99300cab46d |  | note | ○ Attach Testing and Comminsiong Report
label | c41cc4e9-0c9d-5898-ac6a-3296182059a2 |  | note | Method - Document Review
label | 0997c5c0-19b3-5fa2-999d-53754efd1875 |  | note | Frequency - Each Lot
label | cab6c9b5-d8df-5c42-90a1-3057d19def65 |  | note | Category - HP*
label | 73783d45-9e70-5d68-adaa-68467df20161 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | 4b591755-52d2-5db2-8e4f-eb54b233c200 |  | note | Verifying Documents - This ITP
text | eefa444b-c58e-5a09-a6f4-5713e806bd9a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | f5319cb6-11f7-5b30-ab23-af85159a1eb2 |  | note | Reference - MRPA Quality Management Plan
label | 3c4084dc-0e77-515f-a2f0-5e4e4f76efc6 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 1ce62661-6684-58f1-99ff-d42b77acd1a0 |  | note | Method - Document Review
label | 28db623d-fe29-5557-aa70-2855e4f3c3a0 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | e25f0eaf-e438-5072-9525-39ebecab4401 |  | note | Category - HP*
label | a54ae390-f890-536b-8023-ebe7c9ba4a1f |  | note | Responsibility - SE/PE/SPE
label | 3cd77f36-2b38-573b-8121-83de76430ec7 |  | note | Verifying Documents - This ITP
text | 27213cda-753a-5f6e-9846-bf2c68ba8972 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | ac07e7f9-467b-5be0-9d99-69a508a34d63 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 691b314f-2aa8-5cab-af7e-908f31fc9297 |  | textbox | Name:
text | 745b76df-e074-5503-bb42-33bff019e066 |  | textbox | Position:
text | 362b811d-0e4f-5d48-9a08-842ed50ade40 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-009-STR-Bored Piling |  |  |  |  | Yes | ITP-009-STR-Bored Piling - Rev 0 | f3d066a9-d57e-4e39-94c6-6e609efce0b3
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 70deff00-e4c2-5484-ae92-ce89f855f706 |  | note | Document Title: ITP-009-STR-Bored Piling
label | 6ef3d51e-9fe2-556a-8294-ab785c5c5ef3 |  | note | ITP Description: Bored Piling
label | bef5ddca-cda4-5034-803c-f21f973ef84f |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 639ee6a9-c63f-59c1-952b-9d135eea4666 |  | note | Discipline (e.g. CIV/STR/RAIL): 009-STR
label | 860a3bb4-6b87-5525-8dc7-bf3d68f15b2b |  | note | Revision Number: 0
label | 4f49a0fb-0218-59fd-afc2-d3df71a80909 |  | note | Revision Date: 11/10/2022
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 641b35d4-14be-5196-9ff2-697557431081 |  | note | Reference - VicRoads Section 606 July 2017
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 688df7bb-a8eb-5248-b79c-433c1ac166e0 |  | note | Reference - VicRoads Section 610 Feb 2020
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | d844f97e-6b2e-50a4-953b-79581650df4b |  | note | Reference - VicRoads Section 611 November 2018
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 6d361911-ccfb-5caf-b282-9738c4ec2344 |  | note | Reference - AS2159-2009
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 7e8c2ef8-8d3b-537e-a808-9adb584b8ff2 |  | note | Reference - AS3810.1 2018
checkpoint-status |  |  | checkpoint | 1.6 - Non Dependent
label | 2825e1fd-2eda-5103-8318-b27132c0dddf |  | note | Reference - AS5100.3-2017
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete Mix
label | c46bd9d7-05b0-508e-96b1-9ca3e995e7fe |  | note | Reference - 610.07 Table 610.071
label | 185f114c-5b6b-5bec-a0c6-061dd78339c6 |  | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
label | 164ddf8d-41d1-5961-a707-c3fab2c53837 |  | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
label | afb43345-92dc-580d-a184-6db0f897bbc2 |  | note | Enter: Teambinder Material Approval number
label | 933742c4-77c8-5fef-bd7e-90a47db67028 |  | note | Method - Document Review
label | 9db5dc46-e510-5161-b166-23ce1253f146 |  | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | c3f17396-fa57-5f6f-b603-aaf766e16b57 |  | note | Category - HP
label | c96a2fc7-df6c-56e8-959f-144173db2238 |  | note | Responsibility - Nominated Authority
label | 9695e915-0047-5bb2-9a8a-7c18f9f9e0d5 |  | note | Verifying Documents - ConQA Hold Point Release
text | a89b79c4-9756-5dda-9a87-cdef5f74787e |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | 4cc5f199-c03a-5e72-a8ef-352c00bd512d |  | note | Reference - 611.05 (a)
label | 94a8981b-4bf9-50e2-bae6-ff07e803187d |  | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
label | 011d8146-4fb6-51cc-bad2-d2ff81f2e864 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 0fb27cfd-0607-51b7-a607-b0ef4e127d85 |  | textbox | Enter: Teambinder Material Approval number
label | 938994a9-054f-5094-8726-6bbe98201695 |  | note | Method - Document Review
label | 1c31a660-6966-5344-9c4f-cba319bb014c |  | note | Frequency - Once for each supplier, 14 days of award of contract
label | 0e570fdd-4672-52d3-b407-3cb16acd2439 |  | note | Category - HP
label | a738ab58-d089-542d-b6fe-7fa8022305d8 |  | note | Responsibility - Nominated Authority
label | 61990dc4-580e-5172-b067-b1caf9b21a39 |  | note | Verifying Documents - This ITP
text | 7e53f986-a668-5c08-8c75-3939f230d273 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Bar Chairs/Aspros/wheels Certification
label | 4b4e101f-dd88-57f3-bf25-ba9a0a8b81b7 |  | note | Reference - 610.26 (a)
label | a9dab2f2-d03f-5aa4-9b65-29a5c206ca08 |  | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
label | 6f95c768-3e5b-5478-aa66-85c452a3f9a4 |  | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 015cc1d4-2424-5230-80b5-430111a6f273 |  | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | a8c2ac94-488c-5531-9527-da44b2d85ca0 |  | textbox | Enter: Teambinder Material Approval number
label | 5204e8ac-9d63-5dbb-bdf1-0fcb4a741237 |  | note | Method - Document Review
label | 4c038cca-5d51-595c-ab2e-78f821ee5ae2 |  | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | 5a1ae7af-5cad-5a6e-96cd-cd827393de5d |  | note | Category - HP
label | 6ce6ae7f-b307-5cf3-a6d7-8303a3d595ae |  | note | Responsibility - Nominated Authority
label | ac2a7554-1ed5-5e09-98f1-94e293d0cc98 |  | note | Verifying Documents - This ITP
text | 2108ce6f-1d9f-50e1-93ce-7d78dba01652 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Working Platform certification
label | 5e9eb1b0-511b-5d80-8e64-0ec00e5e4658 |  | note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement
label | 494d1fa2-fa0b-5ca1-88f0-9c935222cedf |  | note | Method - Document Review
label | 4f5c9553-289e-57a1-b8b7-3706ec7110bc |  | note | Frequency - Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | 22895676-31fe-5d9f-bf96-ec9c72c87330 |  | note | Category - HP
label | 33372c2a-3842-5baf-95a2-11de3bc87e1f |  | note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | 5a0f0ff1-d1c5-5510-ace5-94e24fc6ffcd |  | note | Verifying Documents - This ITP
text | a6b9ef00-968d-5a0f-8e19-43b7423f9eaf |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Piling Operations Work Procedure
label | 19a55fbc-dd2b-5e43-aad5-cb8286214c24 |  | note | Reference - 606.03 (a)
label | 5d33d674-711f-5b46-9fca-cdb73ff2f722 |  | note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
text | 4a84677a-2aeb-53a5-a9c4-fdc51470e70b |  | textbox | Enter: Teambinder Approval number
label | 866b9f2e-c337-5de2-857f-7dd9705b6c9f |  | note | Method - Document Review
label | a08d7c62-0f9c-5982-95f9-b7a5ceffd854 |  | note | Frequency - Once, 4 weeks prior to the commencement of piling
label | f2861df1-b38a-55f2-bc3e-d3e3128ae5fe |  | note | Category - HP
label | fdbbcb31-8dc9-521a-9eb8-3261bbbfdf2e |  | note | Responsibility - Nominated Authority
label | ceecfde2-b5c4-5f57-8128-74741d275694 |  | note | Verifying Documents - ConQA Hold Point Release
text | baf340be-13c1-50e6-b49b-fb6eddf4f679 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Temporary Steel Casings
label | 77d2711e-9d3e-5192-af59-d6179c19e73a |  | note | Reference - 606.03 (b)
label | 6440ac1a-e921-534d-abdc-a2146d66fc61 |  | note | Acceptance Criteria - Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
label | dbdfafff-e0dd-5d58-939e-01d242b467b3 |  | note | • Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
label | 22a2dc1d-4ddb-5a6f-9ae9-a137410c89d8 |  | note | • The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
text | 5fb88094-f5f8-5c32-a09d-5fa5167aed40 |  | textbox | Enter: Teambinder Approval number
label | 577d364d-c460-5819-94f2-8910f8732b25 |  | note | Method - Document Review
label | e299dbae-04ee-5664-9bf9-2c5b887ed961 |  | note | Frequency - Where applicable, once, prior to use
label | 5d0ac6da-bc19-512b-9089-c92ed9e09e89 |  | note | Category - HP
label | f9edf96a-0573-5651-8270-ee8513307f77 |  | note | Responsibility - Nominated Authority
label | ab9dc98c-4c75-5a4e-b937-606cede89cbe |  | note | Verifying Documents - This ITP
text | cfc155bc-89f9-54db-8532-9f758223ce3d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Casting Under Water Procedure
label | 852e7a91-dea2-5743-9462-418af568d3e8 |  | note | Reference - 606.06 (a)
label | 29bbb10c-7542-5463-9cea-0407c6bfcc54 |  | note | Acceptance Criteria - Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
text | 050db3af-735e-55f5-be20-908bf53978cf |  | textbox | Enter: Teambinder Approval number
label | 4edc7f83-d45d-55f1-a78c-3265d6768512 |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 2c872037-2fe0-5ffb-b145-182ee38a55b4 |  | note | Method - Document Review
label | bc553972-ecfa-55d0-8ae9-0ff524eb9605 |  | note | Frequency - Where applicable, once, prior to placement of concrete
label | 5161391c-98fb-5ed3-bac7-8c5103153287 |  | note | Category - HP
label | d80a3d1d-c769-5a30-bdac-84b2651b044a |  | note | Responsibility - Nominated Authority
label | 0094db76-fda0-56a6-877d-be25ec9fd212 |  | note | Verifying Documents - This ITP
text | a08ad46a-8b0e-553d-9edf-bda6a50edae7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Boring With Bentonite or Polymer Fluids
label | 5393e021-cd75-583e-a782-6b15e121a60f |  | note | Reference - 606.03 (c)
label | fc93b65d-002b-574d-93fa-3136837fdb7e |  | note | Acceptance Criteria - Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
text | bff898b9-ed74-5381-843f-8159e1fe39a1 |  | textbox | Enter: Teambinder Approval number
label | 82b07a35-6b70-5477-9b5f-358a870b4edb |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 78dd738f-5ef3-5da5-9d27-0e6878ec613b |  | note | Method - Document Review
label | 55eaf5ad-5db1-5bbe-8f1a-3b44437a67e9 |  | note | Frequency - Where applicable, once, prior to commencement of boring
label | 6467ca66-604d-58f8-bbcc-7496147a68b3 |  | note | Category - HP
label | b4a7ffdb-062a-50b3-a365-5f8aaec24f8f |  | note | Responsibility - Nominated Authority
label | 8bad09d6-6992-5793-a403-f6a01179f00e |  | note | Verifying Documents - This ITP
text | 1ee2689d-c5b2-53e9-8eea-287ecc10a9c2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Dynamic Pile Testing Procedure
label | 47d0d2dd-f141-50e9-893a-486d315f573e |  | note | Reference - 606.07 (c)
label | 86c4e241-a19d-5754-a1bc-8b727c439f1b |  | note | Acceptance Criteria - Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | 2e9891f3-0500-5ccc-94c3-77ff34e4ea2e |  | textbox | Enter: Teambinder Approval number
label | e5c65b1b-c547-5fe1-8dd8-c0cbb9e9a8ae |  | note | Method - Document Review
label | d48a7568-8dd1-51d0-9091-eadc43c55bff |  | note | Frequency - Once, prior to testing
label | 206b1981-f9f1-5a8b-b255-36de0579ecd9 |  | note | Category - HP
label | d41faa86-651c-5914-8d47-4a90819b78c1 |  | note | Responsibility - Nominated Authority
label | 634a2276-807a-5e49-972b-1d9aa9d59853 |  | note | Verifying Documents - This ITP
text | c9e65f2f-caee-59df-b466-d261f8c584d0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Pre-qualified Pile Testing Consultant
label | 41e19f97-beb6-56cf-8439-02cfa696181e |  | note | Reference - 606.07
label | 50586dc0-a8c8-5aae-8351-6ee554fc903a |  | note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | f30dee24-1fc1-55a6-960e-298b00715a59 |  | note | • Details of the consultant to be submitted for review to the Nominated Authority.
text | d3365d35-913c-572b-82ac-ee3f0b0c1696 |  | textbox | Enter: Teambinder Approval number
label | 3d253a86-0f84-53bb-9f2f-379e4c212136 |  | note | Method - Document Review
label | 41e0f3d7-f5f9-5824-85f3-c7dd51e1e355 |  | note | Frequency - Once, two weeks prior to testing
label | 5c1e1f2e-6674-5bb4-90b9-a67124d3149c |  | note | Category - HP
label | 394fa4c9-64c5-5880-a11f-cb15eaa8f22c |  | note | Responsibility - Nominated Authority
label | 895ba038-c9aa-575a-912e-6feebeebc3c4 |  | note | Verifying Documents - ConQA Hold Point Release
text | 29565947-b1d9-5ab1-a932-52f289942255 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
label | cb2c9e3b-1700-58be-a0f8-ceda08077c88 |  | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
label | 94182149-cf10-5286-a001-a167a2871ae2 |  | note | Acceptance Criteria - Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
text | ee91287b-88ea-5930-80d8-6eb5b764913f |  | textbox | Enter: Teambinder Approval number
label | c2ea2cc6-15f9-5c16-8ba7-5f204921e47e |  | note | Method - Document Review
label | 5979b1b9-0f14-5ffe-b3fb-507b72c2d038 |  | note | Frequency - Where applicable, once, prior to welding
label | 65b844cc-1d90-59e3-a6b6-1e1aefdf02a9 |  | note | Category - HP
label | 6c593126-2fd9-537b-ac35-0ce3bc981105 |  | note | Responsibility - Nominated Authority
label | 3154af69-03c7-5e1e-af72-d4cf823a8fd2 |  | note | Verifying Documents - ConQA Hold Point Release
text | 6674978b-4b73-5efb-96d6-bec603d11782 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | 5bddffc5-0d1f-5633-935f-483d48084536 |  | note | Reference - MRPA Quality Management Plan
label | e57f53bb-dba1-5cb9-a8fd-94cb03369afe |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 183688c3-b5e2-51b5-a1b1-9848113ceb91 |  | note | Method - Document Review
label | 29a7dbbc-0394-509b-b062-c10ab9b8f751 |  | note | Frequency - Prior to starting Works and at regular intervals
label | 1a8d4338-2622-5605-a6ec-b22b41159907 |  | note | Category - HP*
label | 679f47db-c605-599b-8063-7160b387eaa9 |  | note | Responsibility - All
label | c1f7601f-22d5-5f99-9427-6dfed845c4a7 |  | note | Verifying Documents - This ITP
text | 7dd0fa56-209a-5b32-972a-74dfc35403ae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Survey Set-out
label | dd1b7f7f-26fc-5034-b4db-cef8fc49d576 |  | note | Reference - IFC Drawings 606.08 (a - c)
label | b4a06923-68a5-5301-adbd-04ed86486c0c |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | ab482f12-f23a-5e36-9701-cfe4ea38fdbe |  | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | 90842512-57ca-5ee2-a8e5-506301e115a1 |  | note | Method - Measure, Visual
label | 7822bc61-0ca1-5efc-9f1a-1ac0daec2a91 |  | note | Frequency - Each pile
label | 0815d47a-3087-585e-9ed6-c4fcebced536 |  | note | Category - IP
label | 83edb9a1-d6c3-5744-993f-5593f684c40f |  | note | Responsibility - Surveyor, SE
label | 68aec104-2401-5567-af27-6fd7bac18ec6 |  | note | Verifying Documents - This ITP
text | 665d69ce-ba28-5078-82cc-c3a0a0ae7798 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Protection of Adjacent Piles
label | 787cfeaf-2ba3-5868-af07-83837ca91f1e |  | note | Reference - 606.04
label | 168813c7-0d42-51e5-af7c-a9530cd5b6df |  | note | Acceptance Criteria - Pile construction shall not:
label | e814fc41-5f5c-50ad-ab08-ce60988e6e8e |  | note | i. result in damage to adjacent newly cast piles due to ground vibration.
label | 09e24af0-9a2d-510b-92ef-82f8fc3c93bf |  | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
label | 702f700d-8128-59a6-81be-070636581710 |  | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | 4c777e02-8960-5f31-a13b-407c4a89ec01 |  | note | Method - Measure, Visual
label | 6d96d74f-777d-503e-960f-178e94bcbe8a |  | note | Frequency - Each pile
label | 7d6589a7-1981-5f76-ae41-99e2700b7230 |  | note | Category - HP*
label | e35a8016-ea0f-5b6b-83c8-08df39f3cbab |  | note | Responsibility - SPE/PE
label | 24bcb744-d085-5b84-aae6-38c61a371d77 |  | note | Verifying Documents - This ITP
text | 4e2e5597-d0b3-5506-b107-5c1efb7a0f8c |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Boring Operations
label | 2e0e66ae-c32c-50a2-9260-637225c508f1 |  | note | Reference - IFC Drawings 606.03 (a)
label | 19e7bed7-f446-5330-8abb-c97c6e810bd1 |  | note | Acceptance Criteria - Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | b52cd620-5e74-5166-b404-cd3297d5d3de |  | note | • Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
label | 3999ddb6-e160-5ed2-ac55-0fdee1019f58 |  | note | • Excavation clean and de-watered (where applicable) for inspection.
label | 869cc012-f33f-57b2-ba30-ad6b0b9792bc |  | note | • Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
label | 2e2646fe-8a7d-52e7-a31a-eb3089acf99c |  | note | • Excavated material to be disposed of as appropriate to maintain a clean site.
label | ff74b51f-39bf-52dc-b89c-ff990d2bd686 |  | note | Method - Measure, Visual
label | f4e9d4c3-6bfb-5f0d-83ca-5a4cdee92bc3 |  | note | Frequency - Each pile
label | ecd4d15f-a7ce-5d6b-8905-60951373b4b6 |  | note | Category - IP
label | ad9ce876-6f2c-5960-a267-f3edcdc416f8 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 4ecc093a-56a1-51e0-9911-5208d694b2a7 |  | note | Verifying Documents - This ITP
text | 4ccce1e1-f277-57d3-9f68-042ba7140e83 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Formwork Extension
label | 8bc3c99f-a4be-58bc-825a-d30f52db1633 |  | note | Reference - IFC Drawings
label | 5a2444e8-9cff-50c8-8e13-e9d2f94b43a1 |  | note | Acceptance Criteria - Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
label | 56843e52-2052-58eb-807f-3a3a2e546788 |  | note | Method - Measure, Visual
label | 671aa1a0-9623-5ee6-b3e5-a882f5e63a3c |  | note | Frequency - Where applicable, each pile
label | 6923fc64-35a9-5109-9a64-8f1aa261e634 |  | note | Category - IP
label | 995e5b4d-09e8-5410-9972-87d31c5719ac |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 27027c48-f2b0-5454-965a-1dcfef2e3b1e |  | note | Verifying Documents - This ITP
text | c1724e1c-1ee9-55bc-9809-fec4a5ebbfb4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Inspection of Pile Excavation
label | 6c86c6e8-85a8-5a5a-95b3-982af1ff16e5 |  | note | Reference - 606.05
label | 92bc4419-fef2-5e48-a1ef-5b7fffd3524c |  | note | Acceptance Criteria - Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | 50beec26-9707-5195-b9d7-918807941c84 |  | note | Attach: Geotechnical Field Sheet or Report
label | dc445c7c-26bb-53a0-aff0-549cd7a08960 |  | note | Method - Measure, Visual
label | 5e4d8257-be18-5544-ac47-4a6af400b582 |  | note | Frequency - Each pile
label | ee751d8b-4777-52df-b2dd-01b7436fc707 |  | note | Category - HP
label | 6b17c0a0-2bb0-53e4-84d9-3acbc92c9687 |  | note | Responsibility - Geotechnical Engineer
label | a7f1be9f-b758-5fa3-bdf0-1579c5ed739d |  | note | Verifying Documents - ConQA Hold Point Release
text | fddf5e1f-50dd-5dee-a133-2ec2d4fe7992 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Reinforcement - Placement
label | c0d5509f-4c0e-531a-a927-98dbb33d5f89 |  | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12, 606.06 (a)
label | 2b6f02f2-d59d-5539-9783-b265089ed39a |  | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 0c77b42d-05a8-51d4-a265-bc7b3883b143 |  | note | • Projecting reinforcement is the correct length and location.
label | 383015dc-0157-5ded-bfdd-39307502e1e1 |  | note | • Splice lengths achieve the minimum length and are in contact for this length.
label | cb8f452b-8007-5249-9ee6-caa3d548a142 |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | 8f0409b7-c1b2-5840-92e1-e305cc640c5c |  | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | a637e21a-5b15-5414-aad3-ae9fcc1ea38a |  | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | 4a1ce2f2-a6f5-5f51-9ea0-bfa1f238cc49 |  | note | Method - Measure, Visual
label | b9d48af2-cde8-58b0-90b8-949778b26041 |  | note | Frequency - Each pile
label | edc011a1-da90-5f57-9fda-4152e220188c |  | note | Category - IP
label | d7686d48-67b7-54eb-8b92-fa70c8999f15 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 7ab39a4c-15e9-510c-b9ce-5e2f3e01ce09 |  | note | Verifying Documents - This ITP
text | 23814118-bfbc-5b8d-937f-58ad6e70f9b8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Reinforcement - Electrical Continuity
label | 8f5e0c62-f8f8-5f5a-8ae8-6e023530a64d |  | note | Reference - IFC Drawings 610.29 (d), 610.43
label | b8773b64-bab6-5f8e-a7fa-2539cc80e44c |  | note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
label | ce190e68-f8c7-5648-bc21-64be9ede9d75 |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 45cde450-090f-5728-885b-c36a56742954 |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | d18e43c8-dceb-5512-8dd1-d5d9f70160f7 |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | 4d6d29e3-aa8e-57c4-8d40-5bb2cac575c6 |  | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | 56ef2b2d-13dc-57ff-9827-96b3bd1c06e5 |  | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | 11652ba8-4ccc-5fd7-a877-520b19693dfc |  | note | Method - Measure, Visual
label | 14167044-8b7c-59df-9635-a3041ceeff18 |  | note | Frequency - Where applicable, each pile
label | e76a2cf0-6667-54df-bcaa-460875c24d3a |  | note | Category - IP
label | 1ec6c1fa-5f1f-505a-af05-7bb51d3c509d |  | note | Responsibility - Earthing Engineer, SE/PE/SPE
label | 989b82f4-eae5-5a1a-9dfe-a93e01b6f259 |  | note | Verifying Documents - This ITP
text | 5f41aa10-3720-5cfb-94d2-8a69676507a0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Cast-in Items
label | 19f8fcde-a882-5eaf-b154-5a430baac213 |  | note | Reference - IFC Drawings 610.46 (a), Table 610.462 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
label | 5b735a64-8d4e-5786-af63-168b596f6655 |  | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | 21f9ca48-9872-5124-a6fb-2d368a4c856b |  | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | dcd7de38-1ba1-5b65-8ffc-da15a16d1b66 |  | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | f67d5f75-a150-5602-8fb1-3eb71cd54e37 |  | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 7d264d81-7d6d-5157-b6be-7ea9f59952bc |  | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 2d205eaa-e326-51e5-b6c8-2a65aebf73d6 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | fb88f485-72c6-5f5c-9f8a-8904948b9f15 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 8e26a7f8-8e77-5389-94f3-06cb41fae72c |  | note | iii. Ducts and conduit location = ±12mm
label | e472e455-b7f2-54ef-a3ec-504f10280c21 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 8efb410c-2531-5ec6-a9b8-2c988fc93014 |  | note | Method - Measure, Visual
label | 403cda94-2204-5db9-b482-94f481400f40 |  | note | Frequency - Where applicable, each pile
label | 513dbd4a-fef4-5d4f-8c58-931b67fbff50 |  | note | Category - IP
label | a1dcdd77-54f4-5636-8987-d7b37b89eef9 |  | note | Responsibility - Foreman, SE/PE/SPE
label | f8d710ed-8097-516d-9a21-7f3bdc51bd62 |  | note | Verifying Documents - This ITP
text | d26079d0-d158-5b26-b1eb-7e50c346cbf9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Pre-pour Inspection
label | 26a05ffb-c0d1-59a5-8234-ec521a909376 |  | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
label | b31d5516-867e-57f1-9e0e-a0619547e9ee |  | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 154049df-8f96-5e80-b398-68576561b0b8 |  | note | • All foreign material has been completely removed from the excavation.
label | ad23c896-9c1a-5c4b-a984-897e77d4d922 |  | note | Method - Measure, Visual
label | d13d6261-fcfc-5954-b4ae-e6f6781fcbaa |  | note | Frequency - Each pile
label | b2a6f744-3450-5403-9a2e-e969a9247d84 |  | note | Category - HP
label | ac8fd46f-5541-583d-ac63-46d9f7013710 |  | note | Responsibility - Nominated Authority
label | 7afe085d-1a52-56ff-9fef-5f6c40e3fd52 |  | note | Verifying Documents - ConQA Hold Point Release
text | 64d68c03-43eb-50f2-87cf-81af218a0c68 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 - Weather Conditions & Evaporation Limits
label | 01c37bf8-1a5a-5ac1-8b77-0bd744e0e3c4 |  | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | d455a339-9141-579b-95ba-029c5a5a11cc |  | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 7df65bd9-783a-5200-9181-2cacc8b19310 |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 841b0326-ba53-5167-a1ca-8489ac2871e6 |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 0d8c9813-1b1a-5f21-a70c-147aae31ac32 |  | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 57eabf29-3c98-5d7a-9bc8-4b3a2665db69 |  | note | Record: Required information on the Concrete Pour Record.
label | b0182d67-8a7e-5b27-aa05-49c40d409a3e |  | note | Method - Measure, Visual
label | 3af144a4-d2b7-5d75-8941-0ca826dfbe19 |  | note | Frequency - Each pile
label | addb3a1f-970b-5a4e-8801-cec383bf9347 |  | note | Category - IP
label | 2a572dfb-41f1-53be-b5c5-14e8fe2ad5d7 |  | note | Responsibility - Foreman, SE/PE/SPE
label | be616ec0-b313-5b9e-82f1-7e021247037b |  | note | Verifying Documents - This ITP
text | 5736ff18-b456-5dd8-a998-cf60bf5f83e0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Concrete Testing - Sampling Frequency
label | a8ac749e-48eb-5176-b330-80d8cfbaba0f |  | note | Reference - Site Sampling & Testing Procedure 610.16 (b) Table 610.161
label | a428b53c-a748-56ab-97da-8e710c088066 |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 01f9ecb5-16cd-57d9-bbbe-3652617482e3 |  | note | • 0m³ to 10m³ = 1 sample
label | 97489ab9-c01a-5629-8517-f1b6c27fc659 |  | note | • 10m³ to 25m³ = 2 samples
label | 40293a3c-ec10-52b1-8137-080e66348e8f |  | note | • 25m³ to 50m³ = 3 samples
label | 0c797d15-bb8b-5650-95ae-7898de01b38c |  | note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | ae5a7495-ac36-5427-bd47-ae625bca663d |  | note | ○ For each additional 50m³ and additional sample shall be taken.
label | 41c629b4-658b-5ebd-a19e-95d208d178bd |  | note | ○ where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | 3186641b-5786-5247-9f88-ec278a0eb7b3 |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 0d507ecc-5efb-5682-8c5e-de25d351f8c1 |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 5ab32254-0f39-5a55-b936-924da5a63a4b |  | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 224d93ee-e6a8-5d6f-84eb-8f5186430cb7 |  | note | Record: Required information on the Concrete Pour Record.
label | 1cc8f27b-8ce2-59f5-8e6d-80f15969bd59 |  | note | Method - Test
label | 564d1b74-88b4-5104-8105-4b00708d7727 |  | note | Frequency - Each pile
label | a0de3e8c-6078-5cf5-bb5d-221adf0f7899 |  | note | Category - IP
label | dc7ddb89-6456-56c9-bb4f-2729533af90a |  | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | 259aec42-9d3b-5f9e-9783-8a08079be40f |  | note | Verifying Documents - This ITP
text | e61c9fb5-3de0-5af6-bfe2-3d78396f4c37 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Concrete Testing - Spread, Passability & Viscosity
label | c50304c0-a508-58ea-8ae1-3e9bbc15a952 |  | note | Reference - 610.13 (b)
label | cea33701-f9cc-5a83-a318-f6b6319fbad5 |  | note | Acceptance Criteria - Spread range = 550mm to 750mm
label | 2395d27f-fdf2-59aa-b7f0-268cdc489bdc |  | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | a010b04c-6d28-53a8-aedd-732d9456fee7 |  | note | • Passability = ≤10mm (aggregate height differential)
label | d1d80c52-2a39-5002-adf6-b1b8552f7d21 |  | note | Record: Required information on the Concrete Pour Record.
label | 95f31521-72d0-5dfc-8642-746ede2eece3 |  | note | Method - Test
label | 72ce3045-7603-5aff-9d67-994c50c72e14 |  | note | Frequency - Each sample of Self-compacting Concrete
label | cd7d726c-512e-595a-aa99-397dadcadce5 |  | note | Category - IP
label | e8961b09-00ce-595c-b138-5b43aea05c27 |  | note | Responsibility - Concrete Tester
label | 19d7f9a1-792b-5736-b438-6349f70ca4d6 |  | note | Verifying Documents - This ITP
text | 91262c33-ef3c-5369-a36e-011909452a57 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Concrete Testing - Compressive Strength Cylinders
label | 498bf912-5031-56db-9f30-84b3e8aa9159 |  | note | Reference - Site Sampling & Testing Procedure 610.16
label | 77f92e38-7eb0-5f43-827c-8a64fe154fa4 |  | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | e8329f3c-2bdd-5df0-bd19-abe22904d7f4 |  | note | Record: Required information on the Concrete Pour Record.
label | 0c161da9-e06f-5820-ab19-58bb496af78f |  | note | Method - Test
label | 82114fe6-f2a6-52af-be59-246ff5f6bdd5 |  | note | Frequency - Each sample
label | a015c77e-120d-564e-8e69-6681ad252438 |  | note | Category - IP
label | beb8dbad-5c5e-5627-a0ca-39204eff4827 |  | note | Responsibility - Concrete Tester
label | 01f8c5e5-1441-5901-a779-a136b6a9fa90 |  | note | Verifying Documents - This ITP
text | 7d61cedb-3b32-5327-bce9-fc1c839fc7ea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 - Placement & Compaction (Dry or Wet Excavation Conditions)
label | 50f5461d-d33b-5b71-a034-93ddc144cf84 |  | note | Reference - Piling Quality Procedure 610.18 (a) & (b), 610.18 (d) (i), 606.06 (a & b)
label | 3495ec75-4557-5fff-899e-ae6c6b9975e5 |  | note | Acceptance Criteria - Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
label | 077d25b6-87f8-59eb-9795-0307f81f603c |  | note | • All concrete batches are traceable.
label | 392ca1c8-34d8-5133-9bbc-11fcadfbcf28 |  | note | • Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | 65a996e5-de5d-5ad6-b57e-c8c6d402d304 |  | note | • The initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 58906133-50e4-5599-9105-57012729efee |  | note | • the ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | 0f2e4f18-7f1b-535f-9e99-2bc59fbe65b5 |  | note | • Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | 789e32d2-2d4c-543b-802e-7981f162bf40 |  | note | • Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | 74f80b59-d3c0-5628-99ec-9cd4409060b0 |  | note | Record: Required information on the Concrete Pour Record.
label | 7f7bcfc0-5bca-5a70-80be-04bc3359df98 |  | note | Attach: Concrete Pour Record
label | 94cb4a78-3ef7-5875-804b-223b5738c198 |  | note | Attach: Concrete Dockets
label | 6856b66b-72c6-5a5f-8711-102abef51f5d |  | note | Method - Visual
label | 3467b85d-0218-54b8-bb71-c75933af15eb |  | note | Frequency - Each load
label | 7b632bab-0c58-517d-9900-b84c79e379a1 |  | note | Category - SP
label | 10e86cc3-6161-5a18-aa25-8b06ef280317 |  | note | Responsibility - Foreman, SE/PE/SPE
text | 65b00a6d-3526-5536-b70e-d0ed6d55825b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 - Surface Finishes
label | 8ab540c6-0549-5637-b0f7-5682b00e5430 |  | note | Reference - IFC Drawings 610.31, 610.20
label | 2a0fbe2e-f68f-5dfe-a548-9c915c1c9544 |  | note | Acceptance Criteria - Surface finish as per IFC drawings.
label | 34a068a4-827e-52c6-929f-b56877992595 |  | note | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | c5b3d4ce-f8fb-5652-b688-5632839514ed |  | note | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 524c2986-849e-5168-9399-edbc4f36399e |  | note | Method - Visual
label | 6dd14904-d372-50f7-8873-d7a51e762e3f |  | note | Frequency - Each pile
label | 2653eeaa-84e9-506a-96c5-2d6779fe4404 |  | note | Category - IP
label | d19c9d3a-4a35-5ced-9493-c4fc72011c96 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 65370567-7b84-50ba-8951-eb08e6b9cb79 |  | note | Verifying Documents - This ITP
text | 82112d01-7b66-565d-a3c4-e3c8f780e2c5 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Pile Trimming
label | 4af8e301-96f4-5c22-a06a-3597c3db0871 |  | note | Reference - IFC Drawings AS2159 Clause 7.2.2 - 3, 606.06 (a & b)
label | 57462bbf-fffd-548a-9080-e98f36b8f046 |  | note | Acceptance Criteria - Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | 513230ec-c76a-56f9-81c4-b9c6ab93800a |  | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | 6b35115c-5a41-5f63-9515-531a28e130fe |  | note | • Any weak or damaged concrete shall be removed back to sound concrete.
label | 8ad4fbd8-1819-5493-8bcb-ebaffaf5d8f6 |  | note | Method - Measure, Visual
label | 94a38309-3711-5b5a-a12f-d8b6e25eab1b |  | note | Frequency - Where applicable, each pile
label | 9eb4f118-a4a1-5146-845d-36d88458ab69 |  | note | Category - IP
label | 40b67f49-0dd2-54e8-aaee-2613484e895d |  | note | Responsibility - SE/PE/SPE
label | 21e3755c-36e4-5258-8565-78b009b927a2 |  | note | Verifying Documents - This ITP
text | ed0ed1b7-34c0-5bd3-a9cb-058ca5dfe7d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Compressive Strength Test Results
label | 00800f81-04d1-5b0e-a49c-f2fcb758883b |  | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
label | d9671c21-3380-5453-9498-d443acb6ae02 |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | e67d52e4-c612-5724-9af8-84b9fa246105 |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 1fd1bcb1-d2d8-504c-8044-b426f3364ee8 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | a4197524-ccd9-5064-8984-3bc408c19eb6 |  | note | Attach: Compressive Strength Test Results
label | 05802d91-48c8-5c04-9f8a-e0f05aa3ed7c |  | note | Method - Document Review
label | 131061ef-7b2e-5daf-b124-556df8f9cc89 |  | note | Frequency - Each cylinder
label | ef05b7f2-fe31-5745-b417-572f3a373606 |  | note | Category - IP
label | 89aea3b0-671e-5748-bc4e-76ca2381886f |  | note | Responsibility - SE/PE/SPE
label | 5b3700f9-cd24-52be-b3f3-bcb5585ef23f |  | note | Verifying Documents - This ITP
text | 27019cad-7c8d-5ab8-850b-72b9905f445b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Pile Integrity Testing
label | d08293cb-c9f7-5e84-8ca9-176a7c3037cd |  | note | Reference - 606.07 (a, d & e) AS2159 Clause 8.8
label | 2502d88e-6e25-5f40-b2ff-3a3594b95fef |  | note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | eed571e4-dc37-5ca4-a3b5-661746583a0d |  | note | • Cross-sectional area = ≥95%
label | e7b5bf39-1546-56b7-b662-386351fe4949 |  | note | • If any test fails, all piles shall be tested.
label | b32bf22b-8cb7-5389-94f3-d820ec4e6d2e |  | note | Attach: Pile Integrity Test Report
label | 481224b3-970b-5205-8cc6-54b151088e74 |  | note | Method - Document Review
label | ebc1ef1a-39b3-50fc-adb7-ec835c4e00f9 |  | note | Frequency - Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
label | bd57d94f-25ab-5bbb-b98e-6f412261de56 |  | note | Category - IP
label | 43c5efe2-6a68-525e-a8b7-fbe061f111bb |  | note | Responsibility - Testing Consultant, SE/PE/SPE
label | 51b75e46-79dd-5184-80e9-1cd5b9cc8c65 |  | note | Verifying Documents - This ITP
text | 0b5e482d-a0dc-5582-b750-caf8c25bc14d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 - Static Load Testing
label | bb3e1383-3fc9-5bf2-801a-8e8e8273f23f |  | note | Reference - IFC Drawings 606.07 (b, d & e) AS2159 Clause 8.4
label | c7ebcbc3-949d-50d7-a1b4-b7d58fd43b81 |  | note | Acceptance Criteria - Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
label | eb1655fe-e3b9-543a-8e87-c0422fad802d |  | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
label | 57dffeb7-c639-5b57-9603-5143dd28a2fb |  | note | ii. Creep rate = <2mm / log cycle of time at the test load
label | 6e615506-14e1-58f7-99d5-23d996442b2c |  | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
label | 2a02f7b3-2393-5efa-bf5f-6579a2179907 |  | note | Attach: Static Load Test Report
label | 582f95eb-89f6-52ed-a42c-359ee650c629 |  | note | Method - Document Review
label | 5bc9f1a0-de25-5ec5-8f2d-1499a692278a |  | note | Frequency - Where applicable, as shown on the IFC Drawings
label | 6131c4c6-6d58-5b75-ae28-caf3b8a90d3b |  | note | Category - IP
label | 53fcf8ee-5a0b-5a3e-af6a-2f62ad575f31 |  | note | Responsibility - Testing Consultant, SE/PE/SPE
label | 0955070d-08ab-5025-b845-25e3fc6d4175 |  | note | Verifying Documents - This ITP
text | 81883927-3da1-5755-aa7c-2ad8faf168b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 - Dynamic Pile Testing
label | 6e7800f9-ec5d-518b-afc4-e51dceb1b554 |  | note | Reference - 606.07 (c, d & e), AS2159 Clause 8.7
label | e7ee23fe-366b-58af-bc60-3c5054b05dd8 |  | note | Acceptance Criteria - Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | f2a32143-d929-5f9a-9eee-64619d12624f |  | note | • Measured Ultimate capacity = ≥ values on IFC drawings
label | f993cc28-a30a-52c6-ba17-83dfcf5068bd |  | note | Attach: Dynamic Pile Test Report
label | 4ca71fe8-6361-5cf0-9782-02f6a3a34c8a |  | note | Method - Document Review
label | 26c93876-4132-5aac-97ea-81474c292fe0 |  | note | Frequency - Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
label | 75cf3c85-4cbc-5a1b-9e26-c8e779e4316f |  | note | Category - IP
label | 1c5e918c-b0fd-58b4-a3cf-47f58edf26d6 |  | note | Responsibility - Testing Consultant, SE/PE/SPE
label | ad7a6b35-e228-5d59-981b-de9c4b4e90f3 |  | note | Verifying Documents - This ITP
text | 0bf1011f-b840-5f23-b9f9-3a9bfe9a1b37 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 - As-built Survey
label | e210b520-0d29-5adb-9bba-ed0ff3ffe4b6 |  | note | Reference - IFC Drawings 606.08 (a - c), AS2159 Clause 7.2.2
label | d9cc5fa4-2e41-5d59-ad78-59a2af6f192f |  | note | Acceptance Criteria - The following tolerances apply to piles:
label | 11b9fcf9-ddaf-5e07-a95c-40edfe180db3 |  | note | i. Pile head plan location = ±75mm
label | 13c164b7-9184-5afc-a4f2-796ef4186f11 |  | note | ii. Variance from vertical or rake = 1:100
label | 927d25e5-7fa6-5f41-ad37-37c8c5172536 |  | note | iii. Irregularities in straightness = 1:100
label | 881c4620-ba37-5b61-aa82-1b7735a81455 |  | note | iv. RL = ±25mm
label | 5c0ae95e-dda1-543e-94ac-f930da1e58c8 |  | note | Attach: Survey As-builts / Survey Report
label | fb9bd508-5768-5edd-ae9a-2de3bd11c7cc |  | note | Method - Document Review
label | 2025aadb-9b87-5af1-b424-f9a720d97c2d |  | note | Frequency - Each pile
label | 25839e40-57b8-5b79-9192-fd744cbdf541 |  | note | Category - IP
label | e4e0712d-66b9-5234-830e-d4eb3b55a3d8 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 5234d5b7-0bdf-52dd-af6e-bb5d7d0fe9b2 |  | note | Verifying Documents - This ITP
text | bb115e70-f532-5135-aaf4-2212c5170e81 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 - Non-conformance Report (NCR) Closure
label | 15bb5809-c770-53ae-a21d-6d42d1ec0132 |  | note | Reference - MRPA Quality Management Plan
label | 3634dacd-dee7-5df4-bccb-9b857df9b3c5 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 3748ef3c-af8d-5033-925f-7fe9fca118ee |  | note | Method - Document Review
label | 66a34beb-791f-5600-96e0-7a27cebe2f1f |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 0cd02d17-19bf-5562-bb81-efc65d17b789 |  | note | Category - HP*
label | d9039f95-6d2f-5ea5-9fd7-adea2711689d |  | note | Responsibility - SE/PE/SPE
label | abadb37b-ae2a-5d72-be92-561b79eb911c |  | note | Verifying Documents - This ITP
text | 4edb2188-9c84-5248-bfa5-ef7ec6ee42fd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 4b9eb61b-e649-5927-a92b-6f76a54f79cc |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 9501bf7f-0768-5dec-8503-7e148a57b4c2 |  | textbox | Name:
text | a1806edd-8307-58fa-bf09-403bfef965dc |  | textbox | Position:
text | aed64315-ebdd-59b6-b933-4e4a7140e9fe |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP