## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) | itp |  |  |  | Yes | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-CIV-CPD-Hot Mix Asphalt (Supply and Install)
label | ITP Description: Hot Mix Asphalt (Supply and Install)
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | Revision Number: 0
label | Revision Date: 22/08/2023
label | ITP created by: Ahmed ABDELSALAM
label | ITP approved for use by: Pradeep TALASILA
checkpoint | 1.1 - Non Dependent
label | Reference - IFC Drawings Vic Roads 407, Vic Roads 404, Vic Roads 417 AS2150
section | 2. Preliminary Works
checkpoint | 2.1 - Mix Design & Trackless Tack Coat Approval
label | Reference - 407.09, 407.08(d) Mix Design Registration
label | Acceptance Criteria - Mix design and trackless tack coat to be used has been approved by project superintendent, prior to use
label | Method - Approval Correspondance
label | Frequency - Prior to commencing paving
label | Category - HP
label | Responsibility - Project Engineer/ Supervisor
label | Verifying Documents - Completed ITP
date | Date Completed:
textbox | Team Binder Approval Number
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Asphalt Placement and Lot Plan
label | Reference - Section 407.17
label | Acceptance Criteria - Asphalt placement and Lot plan to be created prior to commencement of works.
label | ○ The location of all joints shall be planned before work commences to achieve the specified offsets between layers and the final position of joints in the wearing course.
label | ○ Plan to specify start/end chainage, offset/lane and layer.
label | Method - Verify
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Site Engineer/ Asphalt Supervisor
label | Verifying Documents - Daily Lot Record
date | Date Completed:
checkpoint | 2.3 - Site Inspection and Base Condition
label | Reference - 407.17 AS2150 10.1 AS2150 10.3
label | Acceptance Criteria - Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | Method - Visual Inspection
label | Frequency - Prior to commencing paving
label | Category - WP
label | Responsibility - Asphalt Supervisor
label | Verifying Documents - Completed ITP
date | Date Completed:
textbox | Team Binder Approval Number
checkpoint | 2.4 - Ambient Conditions for Placing
label | Reference - 407.17
label | Acceptance Criteria - The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | ○ Where the above temperatures cannot be achieved, asphalt must be laid under the "Fulton Hogan Cold Weather Paving Plan"
label | Method - Infrared Thermometer
label | Frequency - Prior to commencing Paving
label | Category - IP
label | Responsibility - Asphalt Supervisor
label | Verifying Documents - Completed ITP
date | Date Completed:
textbox | Team Binder Approval Number
checkpoint | 2.5 - Planning of Joints
label | Reference - 407.21
label | Acceptance Criteria - Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints for the final Wearing Course are located on lane lines
label | ○ Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines.Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
label | ○ At the wearing surface where the new and existing pavement join, a hot applied bituminous crack sealant shall be applied.
label | Method - Measure and mark out runs by tape measure or survey
label | Frequency - Prior to commencing paving
label | Category - WP
label | Responsibility - PE FHC
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 2.6 - Tack Coat
label | Reference - 407.19 AS2150 11
label | Acceptance Criteria - Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2. This rate is to be doubled on joints and chases.
label | ○ Tack coat must be allowed to fully cure.
label | NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces Photographical evidence must be obtained (with an identifiable landmark)
label | *from 1st July 2023, "trackless Tack Coat" must be used
label | Method - Spray area and inspect
label | Frequency - Prior to Commencing paving
label | Category - IP
label | Responsibility - Asphalt Foreman
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 2.7 - Submission of Primer Material documents (if applicable)
label | Reference - 408.08 c, e
label | Acceptance Criteria - The primer shall be cutback bitumen complying with the requirements of clause 408.08(c) and shall be water resistant, of uniform appearance and capable of providing a strong bond between the bituminous surfacing and the pavement.
label | Method - Document Review
label | Frequency - Prior to commencing works
label | Category - HP*
label | Responsibility - Site Engineer/Project Engineer
label | Verifying Documents - Conformance Certificate uploaded to TeamBinder
date | Date Completed:
textbox | Team Binder Approval Number
checkpoint | 2.8 - Application Rates for Primer (if applicable)
label | Reference - 408.13 a
label | Acceptance Criteria - At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent
label | Method - Document Review
label | Frequency - Prior to commencing works
label | Category - HP
label | Responsibility - Site Engineer, NA
label | Verifying Documents - Application Rates uploaded to TeamBinder
date | Date Completed:
textbox | Team Binder Approval Number
holdpoint | AUTHORITY HOLDPOINT
section | 3. Asphalt Placement Works
checkpoint | 3.1 - Commencement of placing
label | Reference - 407.23
label | Acceptance Criteria - The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority.
label | Method - Visual Inspection
label | Frequency - Prior to Commencing paving
label | Category - HP
label | Responsibility - Asphalt Supervisor / Superintendent
label | Verifying Documents - Completed ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Delivery of Mix
label | Reference - Pavement Design Details 407.20
label | Acceptance Criteria - The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & intermediate courses: 5ºC for conventional binders or 10ºC for PMBs & Class 600
label | ○ Wearing Course: 10ºC for conventional binders or 15ºC for PMBs
label | ○ Where the above temperatures cannot be achieved , asphalt must be laid under the "Fulton Hogan Cold Weather Placement Management Plan"
label | Method - Check aspahlt delivery docket
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Asphalt Foreman
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 3.3 - Delivery of Mix
label | Reference - 407.11 Table 407.111
label | Acceptance Criteria - Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | Method - Visual Inspection & Delivery Docket
label | Frequency - Each load
label | Category - WP
label | Responsibility - Asphalt Foreman
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 3.4 - Traceability
label | Reference - Fulton Hogan Quality Plan
label | Acceptance Criteria - Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | Method - Measure and Record on Daily Lot Record
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Fulton Hogan Foreman/ Engineer
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 3.5 - Layer Thickness and Level Control
label | Reference - Pavement Design Details 407.25(a),(b)
label | Acceptance Criteria - Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | Method - Dips using ruler or dip stick
label | Frequency - Regularly during paving
label | Category - WP
label | Responsibility - Asphalt Foreman
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 3.6 - Spreading and Paver Stoppages
label | Reference - 407.25 (c)
label | Acceptance Criteria - All asphalt shall be spread with a purpose designed asphalt paving machine to form a uniformly smooth asphalt mat complying with the requirements of Clause 407.29 without segregation, tearing or gouging. In areas that are not accessible by a paver placement of asphalt by other means is permitted.
label | ○ The width of a single paving run shall not exceed 6 metres unless paving in echelon is proposed or procedures are in place to ensure that a uniform asphalt layer free of segregation can be achieved.
label | ○ The Contractor shall conduct spreading operations to ensure that the paver speed matches the rate of supply so that stoppages are minimised.
label | ○ If the paver is required to stop and asphalt in front of the screed cools to below 120C, a transverse joint shall be constructed.
label | ○ For asphalt work carried out on a road to be opened for traffic at the completion of work each day, each layer of asphalt shall cover the full width of the trafficked area. The requirements of Clause 407.21(f) shall be followed in respect of the treatment required for exposed edges.
label | Method - Thermometer
label | Frequency - If paver stops
label | Category - WP
label | Responsibility - Asphalt Foreman
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 3.7 - Surface Finish of Wearing Course
label | Reference - 407.29 (a) (i)
label | Acceptance Criteria - The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | Method - Visual Inspection
label | Frequency - During paving and after final roll
label | Category - WP
label | Responsibility - Asphalt Foreman
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 3.8 - Kerb and Channel
label | Reference - 407.29 (a)(ii)
label | Acceptance Criteria - The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | Method - Visual Inspection & Measurement
label | Frequency - During paving and after final roll
label | Category - WP
label | Responsibility - Asphalt Foreman
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 3.9 - Shape
label | Reference - 407.29 (a)(iii)
label | Acceptance Criteria - No point on the finished surface of the wearing course shall lie more than 4 mm below a 3 m straight edge laid either parallel to the centreline of the pavement or, except on crowned sections, at right angles to the centreline. For intermediate and base course layers, the distance below the straight edge shall not exceed 6 mm and 10 mm respectively.
label | Method - Visual Inspection & Measurement
label | Frequency - During paving and after final roll
label | Category - WP
label | Responsibility - Asphalt Foreman
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 3.10 - Alignment
label | Reference - 407.29 (a)(iv)
label | Acceptance Criteria - Where asphalt pavement is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside, the designed offset from centreline or design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25 mm in 10 m.
label | Method - Visual Inspection & Measurement
label | Frequency - During paving and after final roll
label | Category - WP
label | Responsibility - Asphalt Foreman
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 3.11 - Width
label | Reference - 407.29 (a)(v)
label | Acceptance Criteria - Where asphalt pavement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50 mm or greater than the design or specified width by more than 100 mm. The average width over any 300 m shall not be less than the design or specified width.
label | Method - Visual Inspection & Measurement
label | Frequency - During paving and after final roll
label | Category - WP
label | Responsibility - Asphalt Foreman
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 3.12 - Trafficking pavement after placment
label | Reference - 407.28, 404.14
label | Acceptance Criteria - Trafficking or placement of asphalt over previously constructed layers is not permitted unless the majority of the previously constructed asphalt has a surface temperature of 50°C or less and Falling.
label | Method - Visual Inspection & Thermometert
label | Frequency - After final Roll
label | Category - HP
label | Responsibility - Asphalt Foreman
label | Verifying Documents - Completed ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Testing
checkpoint | 4.1 - Compaction Testing (Open Graded Apshalt)
label | Reference - 417.12
label | Acceptance Criteria - Accpetance of compaction shall be on a procedural basis
label | Method - OGA/SMA Compaction Procedure
label | Frequency - Per lot
label | Category - TP
label | Responsibility - Fulton Hogan Laboratory Technician
label | Verifying Documents - Completed ITP
date | Date Completed:
checkpoint | 4.2 - Compaction Testing (Stone Mastic Apshalt)
label | Reference - 404.15, 404.14 OGA/SMA Compaction Procedure
label | Acceptance Criteria - Per lot, the Characteristic Density Ratio must meet the minimum limit of 96.0%
label | ○ For layers thinner than 25mm, accpetance may be on a procedural basis
label | Method - Nuclear Density Test, OGA/SMA Compaction Procedure
label | Frequency - Per lot
label | Category - TP
label | Responsibility - Fulton Hogan Laboratory Technician
label | Verifying Documents - Completed ITP, Compaction reports
date | Date Completed:
checkpoint | 4.3 - Compaction Testing (Dense Graded Apshalt)
label | Reference - Section 407.27(a),(c.) 407, Section 173, Dense Graded Compaction Procedure
label | Acceptance Criteria - Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits:
label | >50mm layer depth = 96.0%
label | <50mm layer depth = 95.0%
label | ○ Additional Test must be undertaken on the longitudinal joints for wearing courses
label | ○ Test Lots 50m2-500m2, may be treated as a small area,in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0%
label | ○ Test Lots <50m2, compaction for all lots shall be accepted on a procedural basis
label | ○ Mix Types where total contract supply <300t, compaction for all lots shall be accepted on a procedural basis
label | Method - Nuclear Density Test, DGA Compaction Procedure
label | Frequency - Per Lot
label | Category - TP
label | Responsibility - Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer
label | Verifying Documents - Completed ITP, Compaction rerports
date | Date Completed:
checkpoint | 4.4 - Level Conformance
label | Reference - 407.30, 407.29
label | Acceptance Criteria - The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.30 (b)
label | Method - Survey Results
label | Frequency - Each Lot
label | Category - WP
label | Responsibility - Surveyor
label | Verifying Documents - Completed ITP, Survey Conformance Results
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP