## Sheet1
Enviro BSM
SECTION | BATCH DETAIL NUMBER OF PRODUCTS
Checkpoint | Enviro BSM
Label | Record Batch Number
Checkpoint | Enviro Epoxy Grout 100
Label | Record Batch Number
Checkpoint | Enviro 700X
Label | Record Batch Number
Checkpoint | Envro Flex FC/ Sika FC
Label | Record Batch Number
SECTION | PRE COMMENCEMENT
Checkpoint | Material Management & Storage - Witness Point
Label | Enviro BSM should be stored upright (not laying down) in dry, cool conditions out of direct UV and weather. Maximum storage temperature is 45°C. - Record by timestamped photograph.
Checkpoint | Acceptance of Substrate - Witness Point
Label | The substrate should be sound and even, thus preventing movement or subsidence during concrete placement. The substrate in which BSM is to be installed should have no protrusions, gaps or voids greater than 10mm. Penetrations such as plumbing and electrical pipes should be stabilized to prevent movement during membrane and concrete placement. For horizontal membrane placement, ensure that the substrate is sound, especially when installing over compacted fill so to avoid displacement from traffic or pouring of concrete. For vertical placement, ensure substrate is sound to provide required support for membrane during concrete placement. - Record by timestamped photograph.
Checkpoint | Sample Approval - Witness Point
Label | Has the sample been approved for the following area?
Checkpoint | First Type Inspection - Witness Point
Has the builder conducted an inspection to the area before commencing works?
Checkpoint | Builders Pre-commencement Sign Off
SIGNOFF | Witness Point Sign off
SECTION | APPLICATION
Checkpoint | Horizontal application - Witness Point
Label | For horizontal applications, Enviro BSM should be placed with the coloured protective layer facing upwards and the white HDPE layer facing the substrate. Stagger end laps of each run to avoid a build-up of layers. Overlap each previous sheet by 75mm ensuring membranes overlap edge is positioned correctly. Ensure the back of each subsequent roll is clean prior to overlapping and once in place remove the plastic film (on the overlap section) to bond the sheets together. Ensure a complete bond with no creases by using a heavy roller across overlap areas. Once overlap bond is complete the plastic film can be completely removed. -Record by timestamped photograph.
Checkpoint | Vertical application - Witness Point
Label | Enviro BSM should be mechanically fixed to the substrate using (substrate dependent) fixings with the coloured protective layer facing the concrete pour. These fixings should only be placed in the overlap section of the membrane and have a low-profile head so that the sheet overlaps can lay flat and rolled evenly for optimum adhesion. Overlapping in vertical applications should be done in the same manner as horizontal applications ensuring subsequent sheet is overlapped by 75mm, adhered, and mechanically fixed correctly before proceeding with the next. The plastic film can be removed immediately in vertical applications. All cut edges and roll ends should be overlapped by 75mm, be clean and dry and sealed with Enviro BSM SeamTape. -Record by timestamped photograph.
Checkpoint | Builders Application Sign Off
SIGNOFF | Witness Point Sign off
SECTION | DETAILING
Checkpoint | Reo Bars - Witness Point
Label | Ensure bars are chemset in prior to detailing. Bar to be detailed with Flex FC/ Sikaflex FC, membraned with 700X with a 50mm return. - Record by timestamped photograph.
Checkpoint | Pile Caps - Witness Point
Pile cap to be encapsulated with epoxy grout 50mm finished height -Record by timestamped photograph.
Checkpoint | Builders Detailing Sign Off
SIGNOFF | Witness Point Sign Off