## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Sika Sarnafil |  |  |  |  | Yes | Sika Sarnafil | 007c0fec-1d87-409b-9220-31a1a186f42c
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 9256c010-19e7-545a-8cfa-70b70f98d7d6 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | 5c3655fa-b93b-52a4-bcd1-25da61ea627b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | ebaf5bb9-bbf1-58a9-a0c0-d764de45c5fa |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply Sarnacol. Record atmospheric & substrate conditions & notate in QA Documents. Humidity <85%, Delta >3⁰, Air Temp 5-40⁰.
label | f6d89b5a-be39-5eaa-9895-d167770c9712 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply Sarnafil. Overlap as per manufacturers instructions,75mm, stagger cut joins where possible, detail strip to be installed at cut joins.
label | b1059fdc-2209-53fe-a0a9-0cc69bed94f9 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Weld all joins, Ensure PPE, Respirator, fire extinguisher within vicinity. Weld overlap in one direction to avoid ribbons --Ensure 75mm overlap
label | 35259709-fbdd-5710-9bda-94c81b351c9e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Install Pressure Bar, Install as instructed by builder to finish termination height. Install sealant is placed above pressure bar. Every second hole on pressure bar to be drilled. 1 hole overlap on edge of termination bar
label | eb03a3f5-055b-5695-967c-3a019c191841 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Check all welds with spatula/screwdriver for lifts. Use blunt pointed object to ensure all welds correctly sealed. Any lifts, circle to return to weld
label | bc1f0a15-60a7-5366-ba33-73370c6198ef |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | First signoff. Visually inspect and ensure adequately cured. Check for any potential defects. Sign-off from builder.
checkpoint-status |  |  | checkpoint | Inspection of welds. All Elements to be inspected. Corner terminations, overlaps, lifts, burns, joins, and pressure seal
checkpoint-status |  |  | checkpoint | Test Welds. All Elements to be reinspected. Corner terminations, overlaps, pile heads. ensure all action items from previous inspection have been resolved.
label | 804992e8-7ead-583f-9983-2fdac2e7e291 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff. Visually inspect and ensure adequately cured. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 200P Secondary |  |  |  |  | Yes | Enviro 200P Secondary | 018fd93e-9eb9-4312-8353-51670eadf076
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 549d03b3-b0bb-5f8e-82f8-98ef9b777b66 |  | note | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Screed (moisture test if required).
label | 5f97dc96-2e11-5bee-8c72-9115253afb95 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply Primer. Enviro Shield or Enviro Prime WB.
label | 0db3b8c3-743c-5620-9284-d815da822088 |  | note | Visual
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro 200P with a brush or roller.
label | 4fc5ea98-0581-55a7-9933-379c4a8b59cb |  | note | Visual
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro 200P with a brush or roller. Achieve 0.8mm WFT and 1.0mm DFT.
label | 5038255e-055e-5121-a909-b00e2584e4e0 |  | note | Attach Photo of WFT reading. Enter WFT reading on comment section.
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro Shield + 700X |  |  |  |  | Yes | Enviro Shield + 700X | 170e3049-c794-41ba-9c5d-2ba176cd6ca3
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 9800be6c-4194-56b5-9567-38030d7f7328 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate/Work Area, Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | f86abf42-2891-5631-839f-62faebcc04f4 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | 1b199b9b-c929-5d8b-823f-78fc1252d356 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer (Enviro Shield/Enviro prime P2 or Enviro Epoxy B-LV) by brush/roller
label | cbbd4dc1-78c1-5f42-baf1-3b8ebb4f3bc7 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking. Apply Enviro Flex FC junction fillets (where applicable)
label | 0c367a94-779d-5b27-a539-309bb00c30b1 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. Mix Enviro 700X thoroughly using mechanical mixer. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT.
label | 3ac017fa-c655-54c5-acca-c05895b077b5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Carry out Dry Film Thickness test & Holiday Testing & Pull Off Test, Repair any defects found using patch and repair method specified in procedures.
label | fd8d14dc-88a7-5916-8aff-7780064dcf84 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Patching and Handover to Bondek |  |  |  |  | Yes | Patching and Handover to Bondek | 17bdf886-e8ff-48d3-a834-c214f17df1c9
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | ab59faf2-da25-5cbf-a667-98996336c8d9 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check membrane - Check for damages to membrane.
label | b66e9200-0850-5afc-90b5-e47c3e7f8914 |  | note | Attach Photo of damages
checkpoint-status |  |  | checkpoint | Patching. Apply Enviro HP1200 using a spray gun. Achieve 1.5mm DFT. Or Apply Enviro 700X.
label | 21493281-ee61-5c9c-a0d9-eaca2d86dec5 |  | note | Attach photo of patching.
checkpoint-status |  |  | checkpoint | Lapping to blockwork prior to bondek being laid. Apply Enviro HP1200 using a spray gun. Achieve 1.5mm DFT. Or Apply Enviro 700X.
label | 5c4ef210-c8f0-5741-9387-fe7567668cee |  | note | Attach Photo of lap to blockwork.
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+900 |  |  |  |  | Yes | Enviro HP1200+900 | 295077b6-2500-445d-9c71-6c4e376ce86f
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 3d7e6c36-500a-5783-89df-d8de883a2149 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | 262d6c6c-9211-507b-9491-be1b78b680f6 |  | note | Attach Photo of substrate
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 1b755a1c-2ab0-5f53-9e69-ff9173a36c6e |  | note | Attach Photo.
checkpoint-status |  |  | checkpoint | Moisture Content Test.
label | 71bc7fb0-3550-5f65-aaa8-ff4c8abbd21e |  | note | Attach Photo of moisture reading or enter moisture reading in comment section
checkpoint-status |  |  | checkpoint | Check label on drum to ensure correct material is being used
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | a4425b78-fe06-55f7-a7b6-77b783ee6864 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | d2c8dd48-56aa-5af7-9699-08f6dd38745f |  | note | Visual inspection, ensure adequately cured.
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
checkpoint-status |  |  | checkpoint | Mixing. Mix HP 1200. Mixing by way of 1:1 mix ratio (by volume) in heated plural component spray equipment such as Graco E-10 or EXP-2. Both low and high pressure spray equipment can be used for the application of Enviro HP1200.
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun. Achieve 1.5mm DFT.
label | cc00aff9-8d42-5981-85f1-fffa6169cf77 |  | note | Attach photo.
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test.
label | ea59b7a2-9418-57d4-b0d4-5eb9dc2cbb47 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Wear Coat - Mix and Apply Enviro 900 with brush or new roller (spray application optional) Broadcast aggregate uniformly to the wet Enviro 900 within the timeframes specified
label | 35bc7b54-5473-5ec4-bc0f-1e4fa9a17296 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat Mix and Apply Enviro 850 with brush or new roller (second coat optional pending specification)
label | 7327aeea-7f49-5ef1-8d05-0966792924f3 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | DFT Testing
label | ee613b8c-9254-5782-aa39-566faf99f3f7 |  | note | Attach Photo. Enter DFT reading on comment section.
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 700X + 800TC |  |  |  |  | Yes | Enviro 700X + 800TC | 35b85b5d-1497-4b32-9b2e-e23d6e42bb15
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | a5fd7761-b4dc-50e4-a5b9-79f0e42e724e |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. The surface must be clean, dry and free from all loose particles including dust, laitance, grease, coatings, curing compounds and any other foreign matter. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns)
label | c8b9354d-1ecc-5240-8835-62ba687feea7 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Substrate Preparation and Caulking. Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris. Remove all sharp edges including screws, nails and concrete/mortar projections. Apply a suitable and approved joint sealant such as Enviro Flex Pro or Enviro Flex FC to all joints and connecting building parts prior to the application of Enviro 700X.
label | 86ab5893-de2b-5127-a2cd-ce6cc65dce87 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Priming. Apply primer (Enviro Epoxy B-LV / Enviro Prime P2 / Enviro Shield) using a brush or roller. Allow primer to fully cure before proceeding with the application of Enviro 700X.
label | 104196e0-2975-55f1-89c1-8e61995c1d5b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. Enviro 700X should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT. (2 coats).
label | 1c35482b-2ac7-56c9-8c31-fe0bfb9fe76e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Curing. Allow product to cure for 12 hours before recoating. Care should be taken when walking over newly installed Enviro 700X to ensure the membrane is not damaged.
checkpoint-status |  |  | checkpoint | Top Coat. Enviro 800 TC should be thoroughly mixed using a mechanical mixer at low speed prior to application.Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application. Allow to react for 15 minutes when thinning with Enviro Thinner No.8 before application. Do not apply in damp or wet conditions. Allow each coat to sufficiently dry before proceeding to the next coat.
label | c1d877c1-1114-5e59-a93a-8c3125464e99 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test.
label | 8d95df1d-0724-5bd1-b030-b148b8f216eb |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+Shield |  |  |  |  | Yes | Enviro HP1200+Shield | 37ba342f-e687-4b0e-978b-8c4b82a0a412
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | d7980de8-b2a3-5def-851d-cf5c97df6ac0 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | 9d422931-c88a-5a25-a4af-b085c8569051 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) and prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | 13e02a4a-fda2-5f45-aba7-3b61a2a617f3 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Check label on drum(s) to ensure correct material is being used
checkpoint-status |  |  | checkpoint | Apply primer (Enviro prime P2 or Enviro Epoxy B-LV) by brush/roller
label | 91e68348-78de-58c0-9804-46084465bf5f |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking/ Joints. Apply bondbreaker at junctions
label | a0acb6bf-e1a2-5c13-85b6-f11942ed1fe1 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing. Mix HP 1200. Mixing by way of 1:1 mix ratio (by volume) in heated plural component spray equipment such as Graco E-10 or EXP-2. Both low and high pressure spray equipment can be used for the application of Enviro HP1200.
label | 03b67da4-7634-577b-bea5-ccdfca0117f3 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Application. Spray on Enviro HP1200. Achieve 1.5mm DFT.
label | d53d328c-34bd-5bb2-9f49-6d47d3f77700 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test.
label | fad7b31d-ee55-52ce-9de8-d997f19ae30c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | First signoff. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over if applicable.
checkpoint-status |  |  | checkpoint | Check Screed (areas where applicable) moisture test if required, Enviro Shield is moisture tolerant.
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro Shield with a brush or roller.
label | 9cf0c320-894c-5bf4-a0b8-bd9c2de5e811 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply second coat of Enviro Shield with a brush or roller.
label | e24b5485-8068-53f3-a316-08f191e868cc |  | note | label
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro Epoxy RC |  |  |  |  | Yes | Enviro Epoxy RC | 3955c432-a8ac-4321-bddb-4ba82fd93011
checkpoint-status |  |  | checkpoint | Batch Number
label | 44866fdd-2ecf-54cd-89e7-5cf503a28f82 |  | note | Record batch number: Enviro Epoxy RC & Epoxy BL/V Primer
checkpoint-status |  |  | checkpoint | Confirm and ensure that the substrate complies with relevant substrate standards as per manufacturer data sheets and recommendations. Ensure that the substrate is structurally sound against movement and excessive deflection. Ensure that the surface to be repaired and/or coated is clean, and free from dust, dirt, oils or grease and have no projections of sharp protrusions.
label | 43c2333c-fc14-55c4-810b-8e7ded586ce9 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Ensure that all surfaces have been prepared by diamond grinding as necessary to a minimum 75 micron profile. Surface is to be clean and free of all debris. Make good any cracks with Enviro Epoxy B L/V. Any Large voids in the substrate should be filled with Envirosystems ExpoxyTuff HD Mortar and finished flush with the existing surface.
label | 74039034-dd35-59ab-b6c5-d21110fb0ee3 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | For priming of trafficable hardstand areas apply 1 coat of Enviro Epoxy B L/V to concrete allowing overnight cure between coats. Do not apply where rain or low temperatures are likely.
label | 9f51fa12-d177-5e52-afb8-bcacc2744874 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Sand plus Epoxy B according to the works' design specifications, to the uniformity needed to create a cove.
label | 1699725a-867f-5914-bb3e-d114368864cc |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Mix and Apply Enviro Epoxy RC high solids epoxy coating by roller at @ 6m2 / L over the prepared surface in to coats to a minimum dry film thickness of 250 um.
label | acc38dda-515a-5c1e-86de-997fd245f4e3 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Mix and Apply EnviroEnviro Epoxy RC high solids epoxy coating by roller at @ 6m2 / L over the prepared surface in to coats to a minimum dry film thickness of 250 um.
label | 1421f4a4-1af2-5754-bb27-456585eff5e4 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequate cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro P2 + HP1200 |  |  |  |  | Yes | Enviro P2 + HP1200 | 3cfb4514-6259-4078-9e96-07efd964fc8b
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 264e59b3-3a8b-5e15-80da-c79eb445d855 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. The surface must be clean, dry and free from all loose particles including dust, laitance, grease, coatings, curing compounds and any other foreign matter. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns)
label | 7e6e01eb-74d3-5a54-b9a4-af0244915f02 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Substrate Preparation and Caulking. Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris. Remove all sharp edges including screws, nails and concrete/mortar projections. Apply a suitable and approved joint sealant such as Enviro Flex Pro or Enviro Flex FC to all joints and connecting building parts prior to the application of Enviro 700X
label | b8ed0597-ce9c-512b-9825-53dc295d9a5e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Priming. Apply P2 using a brush or roller. Allow primer to fully cure before proceeding with the application of Enviro 700X
label | f8d515e4-b480-57a4-8edd-ec0dfdb266c9 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. HP1200 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application
label | 61e8d7eb-d252-50ea-8e34-c72854d8ebd9 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Curing. Allow product to cure for 12 hours before recoating. Care should be taken when walking over newly installed waterproofing system to ensure the membrane is not damaged
checkpoint-status |  |  | checkpoint | Top Coat. should be thoroughly mixed using a mechanical mixer at low speed prior to application.Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application. Allow to react for 15 minutes when thinning with Enviro Thinner No.8 before application. Do not apply in damp or wet conditions. Allow each coat to sufficiently dry before proceeding to the next coat
label | 5f1c80a6-0503-5c77-a504-23333cddc4d0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test
label | be7721aa-47d6-53a5-b4fc-dbb35977226a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro CSH |  |  |  |  | Yes | Enviro CSH | 487c2786-8276-47f7-abd8-b79d2be99f66
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | fd9d2c2b-5c83-5956-8694-a55b67bf95ca |  | note | Specification / Standard: Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate. (moisture test if concrete not fully cured) and prepare surface using a scraper or grinder and vacuum or sweep residual debris.
checkpoint-status |  |  | checkpoint | Check for cracks/defect in concrete.
label | c8925691-3d76-51db-b857-5d54a30546f2 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Perform mechanical profiling / shot blasting to concrete
label | 981a4136-242c-5ef4-8b27-a68dbc773c74 |  | note | Visual
checkpoint-status |  |  | checkpoint | Spray Enviro CSH concrete surface hardener and moisture barrier, first application
label | a1306418-f76c-5f10-ba22-2fd71a5ed896 |  | note | Visual
checkpoint-status |  |  | checkpoint | Spray Enviro CSH concrete surface hardener and moisture barrier, second application
label | 82f9bc58-9744-50fa-a913-e0fd18066188 |  | note | Visual
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
label | 1b734492-771d-5b4a-8a3d-fc674f6fd4fb |  | note | Attach Photo.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro BLV + HP1200 |  |  |  |  | Yes | Enviro BLV + HP1200 | 4b165f6b-f91e-4e13-bcf8-7373b6b8124e
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 01ccb077-0633-5672-bc0b-9ac6237c8f2e |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. The surface must be clean, dry and free from all loose particles including dust, laitance, grease, coatings, curing compounds and any other foreign matter. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns)
label | 4f53862c-f4a4-5fc7-8eca-71f075a0488a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Substrate Preparation and Caulking. Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris. Remove all sharp edges including screws, nails and concrete/mortar projections. Apply a suitable and approved joint sealant such as Enviro Flex Pro or Enviro Flex FC to all joints and connecting building parts prior to the application of Enviro 700X
label | 2aba1255-ace1-503c-a89b-868fa2812c7b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Priming. Apply BLV using a brush or roller. Allow primer to fully cure before proceeding with the application of HP1200
label | 79470907-4a31-5eb1-a7b3-0efb62038074 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. HP1200 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application
label | c982f77c-16fc-5ba1-9592-5cd1a48c9550 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Curing. Allow product to cure for 12 hours before recoating. Care should be taken when walking over newly installed waterproofing system to ensure the membrane is not damaged
checkpoint-status |  |  | checkpoint | Top Coat. should be thoroughly mixed using a mechanical mixer at low speed prior to application.Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application. Allow to react for 15 minutes when thinning with Enviro Thinner No.8 before application. Do not apply in damp or wet conditions. Allow each coat to sufficiently dry before proceeding to the next coat
label | 30dc9492-68ad-5e50-928d-3cad7968f159 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test
label | 59db354a-fc1a-5912-9983-c6adaee171cd |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 700X |  |  |  |  | Yes | Enviro 700X | 4cf5962d-b14f-419f-9c63-7b70bcbce3a9
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 14253787-4423-5a52-8a66-3e8f360a97d5 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
label | ec5c4c69-a2d5-532c-bdd8-5dd0f838f67b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | bd4d08fe-7c9c-5a78-b5f0-d3b7421c7b31 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 4dc45412-06f4-5ea0-89ac-60b4f3d5a27b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 38f52e1f-44b4-5629-820e-67dac276c392 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 5e7ba5a4-9707-5b88-80fd-1879b0f58780 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Apply Enviro 700X using a brush or roller
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Apply Enviro 700X using a brush or roller
checkpoint-status |  |  | checkpoint | Flood Testing (if required)
label | ced01d7d-496c-5274-b661-e35bfdbe59e0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+900+850TC |  |  |  |  | Yes | Enviro HP1200+900+850TC | 5c865e50-f165-461a-883d-68ea7b3169bc
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | be933cd3-b548-5f71-8551-7e26edc18f7d |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
label | 00834fd4-ae66-5611-a46a-732026daeab9 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 8fee6fe6-6e45-5731-b853-1c933e38f759 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 86a93a16-c949-524c-9d38-441893238916 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 3e0b39f8-a73a-5d01-96d0-bd04f6eac393 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 31caf7b3-3b35-5cf4-b301-b09ae7faeef4 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | ef05dcae-81ac-57ac-9618-c8283dd72830 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Wear Coat - Mix and Apply Enviro 900 with brush or new roller (spray application optional) Broadcast aggregate uniformly to the wet Enviro 900 within the timeframes specified
label | b3bba806-9d56-5e5f-b1f9-721ab307d6d5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat Mix and Apply Enviro 850 with brush or new roller (second coat optional pending specification)
label | e592ea2c-ffa4-55b9-a9f2-0a8e0a1a67b4 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Combiflex |  |  |  |  | Yes | Combiflex | 5d3a8ef7-3387-40f0-9f82-453918f3fe99
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 03d87780-7e4d-5e41-b21b-91caa6755f21 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | 4be2a629-3722-55cd-908d-a5cfa5341903 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | 023534f2-3373-5359-aa4e-1f0f1302e438 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Measure and Temporarily fix ElastoFlex or Combiflex
label | a3f9a0a5-a99c-5bac-9e40-72b368926871 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Install ElastoFlex or Combiflex to Movement Joint locations
label | a263351d-04c4-5660-ae5f-94c4949f1c1e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Remove Push Pins and Patch holes
label | 9355a8a3-fba6-58ca-ac5a-58f600724207 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Inspect Length of Combiflex material
label | caf02f03-6846-5996-b05e-9ed6f0983c6c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Inspect Length of epoxy anchor
label | 581e03f1-63eb-577c-b688-0837c00489bf |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Carry out sprinkler testing
label | 65f528f3-6ed3-5cdc-a6c7-287ff0590214 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Check Substrate & Repair defects
label | 247e64e2-474d-5a50-9a36-263e233721ec |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff. Visually inspect and ensure adequately cured. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 700X + 200P |  |  |  |  | Yes | Enviro 700X + 200P | 716f031e-6dab-4afd-accf-a0fc77286503
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 23cc606c-304b-5c5c-a438-d93f831b1b2b |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | 7cb25a48-69c9-55e7-b3ca-9b1dbb5f4385 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | 49076d98-daf5-5c59-8b01-041f3adfdc10 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer (Enviro Shield/Enviro prime P2 or Enviro Epoxy B-LV) by brush/roller
label | 94fd5558-0beb-5f6d-b280-0ab8e10e13f5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking. Apply Enviro Flex FC junction fillets (where applicable)
label | ca3f61e6-7246-50d8-9fc0-6bff21dc01da |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. Mix Enviro 700X thoroughly using mechanical mixer. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT.
label | 3126fbb1-ec81-5ecd-afb0-634baed6b5bb |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Flood test when applicable.
label | 5bdfb6bd-4bf8-5c5e-8a30-0846d18ecabe |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | First signoff. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder.
checkpoint-status |  |  | checkpoint | Check Screed (moisture test if required).
checkpoint-status |  |  | checkpoint | Apply primer (Enviro Shield/Enviro Shield or Prime WB by brush/roller
label | 5d3039e8-e00e-5e2b-8e12-e59685d6c02e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro 200P Ultra with a brush or roller.
label | 03291f55-a0d8-503d-93be-0b9409cc3d14 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply second coat of Enviro 200P Ultra with a brush or roller. Achieve 0.8mm WFT and 1.0mm DFT.
label | 8422a63d-bdb5-5033-bb9b-d066d86a523f |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff. Visually inspect and ensure adequately cured. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+850TC |  |  |  |  | Yes | Enviro HP1200+850TC | 7c8f06a5-683f-4d3a-85b0-82d13739ba1a
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 60824d8f-0928-5c6c-8c01-920e5c6ba6b2 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
label | 3f986938-9b40-594c-a030-4a962b6684b9 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 68947181-1a3c-51e2-ab42-ae269d68a780 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 779105fb-3774-59e5-b925-866d66385e1b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | cfb2ea93-7c61-5c62-94f7-6f28e601c9c8 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | f65a2da0-1201-5ef9-ab2e-16461ad23207 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat - Mix and Apply Enviro 850TC with brush or new roller (spray application optional) Re-apply as required or determined by the Specification
label | 58c6a4c1-368d-5683-a21f-0eb33c0eb8a6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | b129530f-ad3a-5181-a497-4a2345e27428 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro BSM |  |  |  |  | Yes | Enviro BSM | 81066c22-909f-458f-8d2d-f8958747d068
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 6f58704f-d512-5ce0-838a-e98d34e43724 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. Blinding sound and level, Trowel finished, no voids or leftover formwork or sharp edges. NCR any unacceptable items
label | 535bf69a-9c49-5ade-9705-117492a9bbbf |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Free substrate of Dirt and Debris where required.
label | 482c7747-95ba-5add-b761-6b1ae9da0e27 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Reinspect substrate. Polyseal applicator - Area clean and dry, ready to instal sheet membrane
label | ec113d4f-7809-5f87-9c04-3cd190d2e4c0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Lay BSM - Overlap as per manufacturers instructions, stagger cut joins where possible, detail strip to be installed at cut joins.
label | 919c76f8-7136-5fbd-866e-79ec94322b6c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply Hp 1600 to Dwall BEFORE bars ensure lap down onto BSM
label | f257d362-c419-5d21-ba8c-64ecd7239ad0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Following bar install, bar to be detailed with flex fc, 700x to be applied with a 50mm return on the bar, bars to be epoxied in by others (generous amount of epoxy required)
label | 8b463e33-eaf3-5c7b-9e7b-110ad5fcb82b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | epoxy incapulation to pipe penos, Pile cap to be encapsulated with epoxy grout 50mm finished height
label | 8c53a093-cba7-56dc-a061-8ee41308492c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Inspection of Membrane - Pre Reo (Polyseal & Client & Enviro systems )tion of Membrane, All Elements to be reinspected. Corner terminations, overlaps, pile heads
label | 76213bde-995a-595a-8083-83046cf86236 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | SikaRoof® MTC-12 UV (SIKA Sikalastic 100 EP + 488 +622) |  |  |  |  | Yes | SikaRoof® MTC-12 UV (SIKA Sikalastic 100 EP + 488 +622) | 8155760d-0c62-413c-8b3c-21334a7577c5
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | e099b1fa-27bd-5f3e-af5b-ede691815822 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | c33be733-c831-5d5b-b0f6-d399e535e00c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | 537c8854-00a9-54b0-8fbe-c7ed7e9d734e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | PRIMER: 2:1 mix ratio (Part A: Part B) mixed for a minimum of 2 minutes - Prior the application of SikaRoof® MTC-12 UV the priming coat if used must have cured tack-free.. For the Waiting Time / Overcoating please refer to the PDS of the appropriate primer. Damageable areas (handrails etc.) have to be protected with tape or plastic wrapping. Please note, always begin with details prior to the installation of the horizontal surface
label | 7e9917a7-e105-538c-9c65-bbd3f95de184 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | 1. Apply first coat of Sikalastic®-488. Please refer to the Sikalastic®-488 product data sheet for application rates and drying times; 2 coats will be required to achieve the DFT of 1.2mm
label | a6ba5bea-7c69-5d56-ad15-7f695b4426a2 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | 2. Apply the top coat of Sikalastic®-622 Excel Top PLUS. If a non-slip finish is required, two coats will need be installed with the non-slip finish being broadcast into the first coat of Sikalastic®-622 Excel Top PLUS. Once first coat is cured, the coating should be broomed/vacuumed of excess material and the subsequent top coat applied within 24 hours.
label | b025c475-f6e8-5539-8eba-b56b9c7a9f7c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | First signoff. Visually inspect and ensure adequately cured. Check for any potential defects. Sign-off from builder.
checkpoint-status |  |  | checkpoint | Inspection of welds. All Elements to be inspected. Corner terminations, overlaps, lifts, burns, joins, and pressure seal
checkpoint-status |  |  | checkpoint | Test Welds. All Elements to be reinspected. Corner terminations, overlaps, pile heads. ensure all action items from previous inspection have been resolved.
label | 9e04e7c1-2d4e-5f28-aedf-23e1316ce1ce |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff. Visually inspect and ensure adequately cured. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-sectioned |  |  | checklist | Polyseal SWMS - Roller & Spray Application |  |  |  |  | Yes | Polyseal SWMS - Roller & Spray Application | 8f945403-eaea-4310-aa57-34b15815fe5a
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | e350832d-ba91-5b17-893d-dccbaba3eca1 |  | note | Occupational Health and Safety Act 1984
label | fac492df-841f-583f-8421-d622fd115c00 |  | note | Occupational Health and Safety Regulation 1996
label | 3bf81f94-2325-519a-8265-005b128b816d |  | note | NOHS Standard-Manual Handling
label | 421d29d7-0473-5b14-9a7b-6e2d296614ac |  | note | NOHS Standard-Hazardous Substances
label | 60489275-08ce-5e5d-b8f1-04cf6438e0ac |  | note | AS/NZS 4654.1:2009, AS/NZS 4654.2:2009, AS1337 Eye Protection
checkpoint-status |  |  | checkpoint | This SWMS was prepared and approved and details are entered correctly below
text | 165aebe6-d6c7-5754-81f4-311c7faebb1a |  | textbox | Name:
text | 1d577e52-1e03-5a76-8368-60ffce09c8a4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | The names and positions of personnel assigned the responsibility for supervising this work and their qualifications entered correctly below
text | ca5748a6-c049-5fe4-b7a6-08931d1343ad |  | textbox | Name:
text | 76b05281-1925-54ac-9dd8-4cc040c53df1 |  | textbox | Position
text | 2279cb0d-8f05-591d-bca6-7be52146fa0c |  | textbox | Qualification
text | 7f747cf5-27fc-5f08-b179-9b97bba01b68 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | The names of workers or their nominated safety representatives who were consulted and involved in the development of this SWMS are as follows:
text | 9c552645-308b-578a-b00d-7bb49a4cdb23 |  | textbox | Workers / safety reps names
checkpoint-group |  |  | section | Item no. 1 Material delivery & unloading
checkpoint-status |  |  | checkpoint | Hazard and Risk : Manual handling injuries, Spills, Moving plant
label | 32bdedd3-5836-55cc-a55b-a5e8914d8406 |  | note | Use of lift for vertical delivery of materials & equipment
label | c95c93d1-ab88-5bce-b520-cebc62c93c47 |  | note | Use proper lifting techniques. Code of practice for manual handling
label | 1e4319b5-f23d-5c0e-ba5d-1ccf8b78af0c |  | note | Use of trolleys for horizontal delivery of materials.
label | 3898e910-ad59-5383-ac4d-07a6b6588dca |  | note | Drums to be secured.
label | 455be5e3-f36d-51b7-ba13-78e7cad78e43 |  | note | Use absorbent (soil sand, vermiculite or other inert material) to collect and seal in properly labelled containers for disposal
label | 0bdaa210-3b61-5479-aadc-4de00c39496d |  | note | Make sure pathways are clear and free of loose materials
label | 4a922cf5-d610-551b-aa71-d8cad1bfffa3 |  | note | Be aware of surroundings and moving plants.
label | 41ea00be-05b6-5b8d-9c03-4464f3f5847b |  | note | High visibility vest, safety boots, long sleeve shirts and pants to be worn at all times.
label | eb542cce-c531-5edb-b44d-00578443d378 |  | note | Be aware of other workers.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | Item no. 2 Transport/Carry materials to workface or storage
checkpoint-status |  |  | checkpoint | Hazard and Risk : Manual handling injuries, Slips, Roof Access, Working at Height
label | be78632e-f1ba-5dc2-9100-c607374be899 |  | note | Limit manual lifting weight to 20kgs.
label | 6ef4769e-e851-56d6-9f5c-ae544961f321 |  | note | Use of lift for vertical delivery of materials & equipment
label | deaee3c4-632e-55fc-b189-213789a6633d |  | note | Use proper lifting techniques. Code of practice for manual handling.
label | 6af7c80e-490d-551a-bbf2-46b7511d7263 |  | note | Use of trolleys for horizontal delivery of materials
label | bf6f7b33-50b3-5826-bc73-bd85688aab76 |  | note | Drums to be secured.
label | dfaa89c7-4702-53ba-8355-6726c15a894d |  | note | Make sure pathways are clear and free of loose materials
label | f068a491-445a-5de9-9468-a7d1619a6c25 |  | note | Be aware of surroundings and moving plants.
label | d9063ac7-05cd-5c23-9493-54206aa239f6 |  | note | All personnel provided with appropriate PPE : masks, hard hats, safety boots, high vis vest, safety glasses, gloves, long sleeve shirts and pants
label | 84d340c6-502f-53a5-b912-cfe4e418043a |  | note | Be aware of other workers.
label | 0942f468-e978-599d-ac22-ee59fc3c0398 |  | note | Roof access permit required prior to accessing roof, working at heights certificate and harness/fall restraint to be worn if working within 3m of a live edge.
label | 73032f19-6f32-5a97-a174-806202bfbd03 |  | note | Roof access hatch to be closed and locked when operatives no longer working on the roof (end of day or during breaks)
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | Item no. 3 Safe storage of chemicals in agreed designated area approved by the builder
checkpoint-status |  |  | checkpoint | Hazard and Risk : Spillage, Exposure
label | 4f6f6429-04b1-57a2-899c-5d82e65798e6 |  | note | Drums to be secured. Use absorbent soil sand, vermiculite or other inert material to collect and seal in properly labeled containers for disposal.
label | 04a26bad-9b52-52ea-98c9-f2b1150cb0de |  | note | All personnel provided with appropriate PPE : masks, hard hats, safety boots, high vis vest, safety glasses, gloves, long sleeve shirts and pants
label | 95671092-6d55-5dd9-ae28-23f23cf8086e |  | note | All employees in house and supplier trained in MSDS requirements (refer to MSDS for appropriate handling of product). All storage to be in line with SDS attached
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | Item no. 4 Floor grinding to prepare surface to be membraned / coated
checkpoint-status |  |  | checkpoint | Hazard and Risk : Manual handling injuries. Contact with faulty electrical equipment. Running over obstacles and debris.
label | d9949492-877f-5f90-a59f-161c4c8b6fcd |  | note | Prior to using tools, ensure Polyseal risk assessment is completed with FM for the use of electrical leads and non battery tools. Ensure that person operating the machinery is suitably qualified.
label | d2f42a0e-c072-5981-b9b9-07294cb893a6 |  | note | Ensure permits for floor grinding are obtained and current for duration of the work.
label | 3f00dbbf-d641-52ec-a340-509d301016e2 |  | note | Ensure a p2 filter mask is worn during the grinding works to prevent inhalation of silica dust
label | 12400c84-2a11-5182-9a3c-bb16e10a7c6d |  | note | Ensure vacuum extraction with HEPA filter is in use and all fittings are adequate
label | 922685b2-7df7-5da5-a697-2643bc278486 |  | note | Check leads and connections daily.
label | 1a0b66bc-2735-5947-8f5b-4d57780cfe13 |  | note | Set up exclusion zones where work is to be undertaken.
label | 4e7b7a32-a6b1-5672-bba6-816abe042f08 |  | note | Ensure Polyseal provides provisions (e.g. tape off area) to prevent access from any other trades.
label | 42ba89e5-8e21-5750-80d2-db6c7aca1fe5 |  | note | All personnel provided with appropriate PPE: masks, hard hats, safety boots, high vis vest, safety glasses, gloves, long sleeve shirts, pants and ear protection.
label | 8f9512b0-79df-5672-8167-e7c8c72054a6 |  | note | Ensure hand grinder is currently tagged and frequently inspected & service monthly / serviced by licensed electrician. Check leads and connections daily.
label | 8b2cb14c-9e67-5117-a1b6-0dcf0e7904f3 |  | note | Ensure experienced operators use the machines as per personnel competency & training.
label | 6614deb6-bf06-5396-8ef8-602b8ad02e71 |  | note | Dust to be placed in plastic bags and secured and placed in bins provided.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | Item no. 5 Barricade work areas and clean work area and apply primer with brush or roller
checkpoint-status |  |  | checkpoint | Hazard and Risk : Dust, Inhalation/Health Risk
label | 9e4362e2-7b81-5ed6-abf9-1d4accb3816d |  | note | All personnel provided with appropriate PPE: Respirators, hard hats, safety boots, high vis vest, safety glasses, gloves, long sleeve shirts, pants and ear protection.
label | 6aeb55a2-57aa-5586-bf75-ce79863df667 |  | note | Provide fire extinguisher - refer MSDS for spillage etc.
label | 16abbc43-0048-536a-993c-46bd4d5c89b0 |  | note | Make sure pathways are clear and free of loose materials.
label | f03ea0e7-7564-5c4c-b2a2-71a7a84db4d2 |  | note | Set-up barricades and/or signage where and if required.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | Item no. 6 Apply membranes:
checkpoint-status |  |  | checkpoint | Hazard and Risk : Contact with chemicals- exposure, skin contact, eye contact, dust and burns Manual handling injuries with lifting pails Using hazardous substances and flammable chemicals e.g. (xylene, toluene). Ignition of chemicals and fire come into contact with body. Using faulty electrical equipment. Protection of existing surface finishes Working around peno’s , slab edges, voids. Risk of fall
label | 571661e9-c2f1-5f4c-8955-7555ccf53fe4 |  | note | All personnel provided with appropriate PPE : respirators, hard hats, safety boots, high vis vest, safety glasses, gloves, long sleeve shirts, pants and ear protection.
label | d9611be8-df26-59af-aa77-0cb04dc612e7 |  | note | All employees in house and supplier trained in MSDS requirements (Refer to product MSDS for appropriate handling of product).
label | 0388c8b5-ac6d-5ca0-a17e-d601f183f222 |  | note | All leads to be suspended off the ground.
label | abdeaf27-eb5f-5412-ae86-13d6805e1ece |  | note | Tools and leads inspected and tagged by licensed electrician on a monthly basis.Trained and qualified personnel use machine refer skills and competencies register.
label | 9001c939-9ff8-5bb2-869c-e221a3c3a438 |  | note | Proper lifting and handling techniques to be adopted.
label | 32ce679c-9ecc-5a05-b3d6-7ead68b2bd5e |  | note | Barricade & exclusion zone to work areas including signage.
label | f558c47e-c488-5d02-94a6-01c7c92a48d5 |  | note | Ensure work area is clear & safe to work in.
label | 7715b35f-4a1b-5181-9b5a-454ced0565c7 |  | note | Ensure all staff have been inducted & read, signed SWMS, MSDS, and Hazards Register for new products to be used. Follow recommended controls stated in SDS attached
label | 00421002-4153-5dfc-b618-7585f6df90fd |  | note | Spill kits to be used on site at all times.
label | 2f339f25-7264-5ddf-aa4d-ae0a8e33cb2c |  | note | No smoking in work area. Ensuring that any sources of ignition are kept away from area.
label | 670dbbc1-e4ba-54f0-ac91-aa980b32d8fa |  | note | Appropriate warning signs displayed around perimeter of work.
label | cff7cd7b-d110-5f19-8cbb-83acd65d0cf8 |  | note | Ensure that person operating the machinery is suitably qualified.
label | 3df31dac-3a43-58ff-acf1-0367d96c68ad |  | note | Ensure electrical equipment is inspected/tagged and checked regularly.
label | 1126a6a3-7757-57dc-b65b-ff4f196df5c5 |  | note | Advise builder should anything not be barricaded or closed up.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | Item no. 7 Rubbish disposal
checkpoint-status |  |  | checkpoint | Hazard and Risk : Environmental problem, Contamination
label | 364d8e03-a2c2-5b2f-894f-9dfdbd45961e |  | note | Daily clean of work site and storage areas
label | 37590c09-c378-512c-b304-020e744d7ad3 |  | note | Removal of debris to designated areas/bins etc.
label | ad5644f7-6247-5450-b8de-b441faabef85 |  | note | Polyseal to remove empty drums from the workplace and place in bins provided by builder
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | SWMS Induction Statement
checkpoint-status |  |  | checkpoint | SWMS Induction Statement - The following persons have been inducted into the work activities described in this SWMS.
text | 07cf93f4-e7af-5bd5-9249-8c00304e3633 |  | textbox | Persons
checkpoint-status |  |  | checkpoint | I have read and understood the content of this SWMS.
checkpoint-status |  |  | checkpoint | I will work in accordance with this SWMS.
checkpoint-status |  |  | checkpoint | If deemed necessary to amend this SWMS I will consult with my immediate supervisor and assist where required in reviewing this SWMS.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+800TC |  |  |  |  | Yes | Enviro HP1200+800TC | 94691c36-dff7-472e-a2d2-fde7132f7740
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 813defa4-809c-5e58-9ec9-26e2e6cb62e1 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 4aef7949-0e2a-577e-b72b-d8ddc701b3d4 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 2a421a04-dab4-565e-8203-67eda3241173 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 8c4791e9-232d-5856-a05c-4556a9f2ee17 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 8c001f6b-cda9-5cb9-a07a-3f2c5ac948bf |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | 208be48e-b61a-5e9f-b4fc-b80dbe4c3c76 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat - Mix and Apply Enviro 800TC with brush or new roller (spray application optional) Re-apply as required or determined by the Specification
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | 93cf1d61-c7cb-5c8b-bf66-970780575f3c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro Hydrostatic 1 |  |  |  |  | Yes | Enviro Hydrostatic 1 | 9a1d45df-37c4-4b23-807a-b7ca772dc7f2
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | bb04914e-901e-5788-91a2-58c9507abfc6 |  | note | Specification / Standard: AS4654.2-2012, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | 7e48cb8b-c6e0-5543-b198-9fc747e5606f |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 7e922158-6055-59b4-aa65-8b59bdbf7650 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Primer application - Lightly Spray areas to receive Hydrostatic 1
label | 73d0282d-b775-5c9b-879e-4ae8bef97dc5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Mix Enviro Hydrostatic 1 thoroughly using a mechanical mixer. Apply first coat of Enviro Hydrostatic 1 by brush or roller Use Enviro Joint Band in floor-wall junctions and general movement joints
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Mix Enviro Hydrostatic 1 thoroughly using a mechanical mixer. Apply second coat of Enviro Hydrostatic 1 by brush or roller
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200 |  |  |  |  | Yes | Enviro HP1200 | 9c6fda21-3724-4a69-a59b-4a7a5443b228
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | cc5315ba-0ca8-5ce1-9475-16d007f77a95 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | e9617116-3277-58a6-9505-e8e38f0ba1f2 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | f935bc86-ff01-5d5e-b9cf-7bd12f6a6492 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | e0ce13ec-3af0-5c81-ab03-185b3afac525 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | f128a9b0-a1a9-5dfe-8309-661c33ba89d1 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | f106771e-df74-5292-913f-570a1f98f055 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro Epoxy RC / Ultra Tuff |  |  |  |  | Yes | Enviro Epoxy RC / Ultra Tuff | a59a7c58-47ff-4486-8a34-fef8b5314ed9
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | c09f6772-5786-5db6-884a-718aa6b6875b |  | note | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | b0d63d1f-1985-552e-bbee-e9e16a7e0d3f |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 53cc98f1-3121-5e6b-b2a9-261f00720a7b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Cutting - Make sure that adjoining ends of intersecting waterstop segments are cut extremely straight
label | bbf8deed-0ff8-5934-b44b-f7076fe68a35 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 5b996799-3714-5eef-92f5-6943395b3592 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Epoxy Application (1st coat) - Apply Enviro Epoxy RC / Enviro Ultra Tuff with a brush, roller or spray
label | cc11abe9-0166-5569-bca6-12ea23b73dd1 |  | note | (If no aggregate is required, 1st coat of epoxy can be diluted with 10% xylene
label | 36eb1f31-ce4b-5cee-8195-d0c4254848fe |  | note | If aggregate is required, broadcast at correct coverage while 1st coat has been applied and is in it's wet state prior to curing
checkpoint-status |  |  | checkpoint | Epoxy Application (2nd Coat) - Apply Enviro Epoxy RC / Enviro Ultra Tuff with a brush, roller or spray
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured.
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 200P |  |  |  |  | Yes | Enviro 200P | a7e552da-0827-44dc-b6a6-60f6f90d31aa
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | d25b2224-26c7-52c6-b224-9eff36ea6291 |  | note | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | 5789b482-0837-5d25-90fb-ccf660051f2e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 668b06b0-2e5a-5e04-94ae-ceedf830c046 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 44b2bc8b-9192-5338-8b8a-c3004a274c80 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 9f19e206-8818-57e1-ad95-302356b275e1 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Apply Enviro 200P using a brush or roller
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Apply Enviro 200P using a brush or roller
checkpoint-status |  |  | checkpoint | Flood Testing (if required)
label | b762870b-5832-5c3c-a661-82225cc26a1d |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+900+800TC |  |  |  |  | Yes | Enviro HP1200+900+800TC | ad7b620c-f062-44bd-b775-cef2f4a950a9
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 968931c7-02f3-5779-a941-6f76383774e9 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
label | b734e95d-cfc7-5789-b741-e8f7773d38fd |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | a54c5739-dee3-52e1-a7a9-335cee0c737b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 3ccdac6c-7f20-574c-8149-92fe2ba2211c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 03ad384b-0242-5bbb-96bf-d6c372f8ee51 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 2e4aedb6-d376-5f55-b1a3-ccad01fb2d8f |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | 082d361b-2942-5619-9365-cc2fe37969fb |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Wear Coat - Mix and Apply Enviro 900 with brush or new roller (spray application optional) Broadcast aggregate uniformly to the wet Enviro 900 within the timeframes specified
label | 3897038d-fe5b-55ab-bc83-2021723b98f5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat - Mix and Apply Enviro 850 with brush or new roller (second coat optional pending specification)
label | 9d7c12aa-2748-5842-9da7-7dbad8185987 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro Clad |  |  |  |  | Yes | Enviro Clad | bc8d74b3-5c2b-4553-9eb5-49cf6e48aab0
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 86e033df-61ef-5f12-89e9-fb888be99ed2 |  | note | Specification / Standard: AS4654.2-2012, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | 677fe64c-3db0-5111-8d6b-3078223c34e6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Primer Application - Pending Substrate Condition, Apply Enviro Prime WB using a brush or roller
label | dabac5dc-74f6-5a09-874e-8cd00b904e05 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | e8dba662-76f5-5af7-ae26-a67e7e17b7c2 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Mix and Apply Enviro Clad as a first coat to the thicknesses prescribed by the specifications
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Mix and Apply Enviro Clad as a second coat to the thicknesses prescribed by the specifications
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Document Upload Checklist |  |  |  |  | Yes | Document Upload Checklist | c0af1764-879f-4fdb-b81e-39c19c03f692
checkpoint-status |  |  | checkpoint | Documents attached below - details entered in comments
checklist-flat |  |  | checklist | Enviro HP1200 + 700X |  |  |  |  | Yes | Enviro HP1200 + 700X | cbdcd905-e0b6-47ed-acef-96bbfda381ed
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 6cfd6274-c9c4-5e6d-853c-b24992b2a1a2 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. The surface must be clean, dry and free from all loose particles including dust, laitance, grease, coatings, curing compounds and any other foreign matter. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns)
label | 028f5687-e85e-569c-9331-2b0fe22086ad |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Substrate Preparation and Caulking. Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris. Remove all sharp edges including screws, nails and concrete/mortar projections. Apply a suitable and approved joint sealant such as Enviro Flex Pro or Enviro Flex FC to all joints and connecting building parts prior to the application of Enviro 700X
label | 31f5fb80-0935-5aa7-b4c5-3cd6362c9c1f |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Priming. Apply primer (Enviro Epoxy B-LV / Enviro Prime P2 / Enviro Shield) using a brush or roller. Allow primer to fully cure before proceeding with the application of Enviro 700X
label | 0f1e8ff8-e055-5e4d-aef5-16f6bf0b4701 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. HP1200 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT. (2 coats)
label | a8697fa3-1ee3-50b3-8a58-71a9bd625b64 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Curing. Allow product to cure for 12 hours before recoating. Care should be taken when walking over newly installed Enviro 700X to ensure the membrane is not damaged
checkpoint-status |  |  | checkpoint | Top Coat. Enviro 700X should be thoroughly mixed using a mechanical mixer at low speed prior to application.Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application. Allow to react for 15 minutes when thinning with Enviro Thinner No.8 before application. Do not apply in damp or wet conditions. Allow each coat to sufficiently dry before proceeding to the next coat
label | c2780e00-a6dd-5257-9cf6-f7097fbe3995 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test
label | 80bb2e89-a4c7-5d97-8d22-0127958c14e6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1600 |  |  |  |  | Yes | Enviro HP1600 | d09375dc-ae54-4aa4-a913-3194b7c7726c
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 4713256a-1cec-5477-b2ac-c08b6aff594c |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 46989deb-b5c2-5e67-97f3-2af4c85ee7ed |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 81d8f6d6-f76e-5dd4-9337-16506597c18d |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 160b10ae-76fc-5898-86de-a5ba88d1e841 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 0eccc29a-c64e-52a8-9f4d-26e0c8318c51 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1600 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | e2ce612e-1e75-5b69-aa78-aca71054b6e8 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro Flex 2 Part |  |  |  |  | Yes | Enviro Flex 2 Part | d6aed116-2745-4e81-9ac1-c103af2fdede
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 460ade2e-bc6e-58dc-a9b2-459ddd1d5b6a |  | note | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | 3d6dfad5-459c-5512-a7ed-ff13aace8c17 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 13093cd5-efc7-5b38-8bfd-4ed9839fdcc6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | df70b1d6-b075-5aef-94c6-467609b72a37 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 148619ff-418a-5707-986f-46f9a532dc2c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Apply Enviro Flex 2 Part using a brush or roller
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Apply Enviro Flex 2 Part using a brush or roller
checkpoint-status |  |  | checkpoint | Flood Testing (if required)
label | 897ad195-06ec-5479-9f31-4c10f6d09fbe |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro Shield / Prime P2 / Epoxy B-LV |  |  |  |  | Yes | Enviro Shield / Prime P2 / Epoxy B-LV | daa221a8-1aad-4a87-b41b-894e9465e086
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 99dcaa10-03d4-510b-9df8-845166ba13d8 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Screed (moisture test if required, Enviro Shield is moisture tolerant.)
label | 7df25a40-363f-560a-b8fc-2ba5a74d76aa |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro Shield with a brush or roller.
label | df267a8f-21f7-5cad-a339-c65ce86a95df |  | note | Visual
checkpoint-status |  |  | checkpoint | Apply second coat of Enviro Shield with a brush or roller.
label | e06d722f-907a-5a13-a805-368686877e95 |  | note | Attach photo
checkpoint-status |  |  | checkpoint | Protection board. Install Elmich Versidrain 8 Geo. Applicable to planters only
label | 9b9cb41e-b8fb-5849-aead-c4436b74954f |  | note | Attach photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 700X + 250NS |  |  |  |  | Yes | Enviro 700X + 250NS | de4bd4da-f648-4309-a289-65b9de4104dd
checkpoint-status |  |  | checkpoint | Specification / Standard Manufacturer's Technical Data Sheet / AS4654.1 - 2012
checkpoint-status |  |  | checkpoint | Batch Number
label | e3e8c07f-ce47-5106-8b21-58fd67146ccc |  | note | Record batch number
checkpoint-status |  |  | checkpoint | Substrate crack and falls inspection
label | 63b5b964-711d-547d-b3da-ded3d664854a |  | note | Obtain clearance for work to commence. Clean substrate so that is free of mould, paint, sealers, coatings, curing agents, loose particles, and other contamination or foreign matter that may interfere with the adhesion. for non metal surfaces: ICRI CSP-4 to CSP-6 for metal surfaces: ICRI CSP-1 to CSP-2.
checkpoint-status |  |  | checkpoint | Substrate crack and falls inspection
label | dbfb41e4-cea0-5f18-928a-036a651584b4 |  | note | Fill cracks less than 1.6mm with filler compatible (Enviro-Flex Pro) with the membrane system.Live cracks to be referred to engineers for treatment methodology. Builder to approve falls on substrate(Min 1:100) prior to application of membrane.
checkpoint-status |  |  | checkpoint | Moisture Content
label | 9a462eed-5003-5750-986d-c5419d9d9281 |  | note | Note. min. 3 tests per 15m2 Enviro Epoxy B-LV up to 6.9% Enviro Prime P2 up to 5%
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Ambient temperature and RH
label | fc8de219-b8a5-5071-ade8-3fd3859fc509 |  | note | Reading twice a day- every 4 hours Mirvac to confirm temperature between the ranges of 5-35 degrees celsius prior to application of membrane. RH must be greater than 50%
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Mechanical Mixing
label | 1975c4dc-d79c-5339-adb4-8f63ce8ad35b |  | note | If applying Enviro Epoxy B-LV: Mix Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Thoroughly mix with a mechanical mixer at low speed for not less than 5 minutes and until uniform.
checkpoint-status |  |  | checkpoint | Applying primer
label | 96b42542-7cf7-5a7c-a207-3778e346dda0 |  | note | Using a brush or roller apply the chosen primer. Allow to cure prior to over coating with sealants and/or membrane coats."Primer should be dry to touch and not be tacky when applying pressure to it. Enviro-Epoxy B-LV will take around 16-48 hrs @ 25 degrees C to dry (but could be longer depending on ambient temp and RH)
checkpoint-status |  |  | checkpoint | Seal/apply bondbreaker at junctions hob/floor
label | 7d4bda32-409d-5de2-9d77-8bccd1063969 |  | note | Apply Enviro Flex Pro to form smooth 15mm flexible cove to all internal corners, penetrations and joints.
checkpoint-status |  |  | checkpoint | Application of Enviro-700X
label | 13892e2e-3e43-5620-9265-6fb5567e3924 |  | note | Mix Bucket at low speed( 400RPM) until thoroughly mixed. Apply two coats of 700X. Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint-status |  |  | checkpoint | QA Testing
label | d7ca1e0e-bb4a-5732-a202-f5f88712fb75 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. 5 tests per 15m2 Holiday/ spark testing of area.
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Application of 250N-S Top Coat
label | 42711146-8ec1-5edb-9ec8-2d91633642d1 |  | note | Mix Bucket at low speed( 400RPM) until thoroughly mixed. Apply 1 coats of 250N-S Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint-status |  |  | checkpoint | Protection of membrane edge
label | 21e432e6-92fb-509a-9b58-f291ba5b47af |  | note | Ensure vertical terminations of membranes on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge. Ensure vertical membrane termination junctions are caulked with Enviro FC pro.
holdpoint |  |  | signoff | Completion of Work Element
checklist-flat |  |  | checklist | Envirosystems 200P - Internal Wet Areas |  |  |  |  | Yes | Envirosystems 200P - Internal Wet Areas | e869684a-0b30-44fc-953b-b201015f8c22
checkpoint-status |  |  | checkpoint | Batch Number
label | bdf22678-1c9b-58a4-b0f0-e3de2976be84 |  | note | Record batch number Min 1 photo
checkpoint-status |  |  | checkpoint | Floor Substrate
label | 0b7f6373-001d-5ef8-aac8-24c8d702b0ff |  | note | Surfaces must be clean, dry and free from all loose particles including dust, laitance, grease, or any foreign matter. All loose particles including dust, laitance, grease and other contaminants such as spray paint, coatings and curing compounds and the like should be removed by grinding or similar. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary. Cracks bigger than 1mm to be reffered to engineers for treatment methodolgy. Min 2 photos
checkpoint-status |  |  | checkpoint | Puddle Flanges
label | 8111647b-9995-5860-b177-421223a15168 |  | note | PVC Puddle flanges to be recessed into substrate so that they finish flush with the substrate. Min 2 photos
checkpoint-status |  |  | checkpoint | Wall Substrate
label | b2caea72-23de-5ac4-a21b-c30fedf76174 |  | note | FC sheeting to be installed to manufacturers specifications (i.e. maximum 6mm gap at floor / wall junctions) FC sheet and nails to be set with manufacturers base coat. Masonry substrates must be rendered /skimmed. Min 2 photos
checkpoint-status |  |  | checkpoint | SFL
label | d6d65e13-bb56-5d1c-9078-47697d91f258 |  | note | Falls in the substrate to drains to prevent ponding water outside of shower (1:100). Falls in the substrate to drains to prevent ponding water inside of shower (1:80). Falls in the substrate to drains to prevent ponding water in a bathroom designed as an unenclosed shower (1:80).
checkpoint-status |  |  | checkpoint | Holdpoint
label | 7b2d4e69-b542-5922-864d-62ea82f08809 |  | note | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Moisture Content-Tramex Moisture Reader
label | d9c0ee43-c08b-5888-86f6-0ac9546e1721 |  | note | Enviro Shield -Max 6.9% Enviro Prime WB - Max 4.5% Record and mark reading on tested area ( min 3 tests ) 3 photo of Markings on tested area and Tramex reading.
checkpoint-status |  |  | checkpoint | Primer Application
label | 22d67144-be41-561b-9299-0c9a3d87fd06 |  | note | Add Enviro Shield Part B (grey liquid hardener) to the Enviro Shield Part A (base). Mix using slow speed (max 400 rpm) mechanical mixing equipment with a suitable paste type mixing paddle attached. Mix for 5 minutes or until uniform. Allow to stand 5 minutes after mixing and then mix again for a minute. Apply 1 coat of Enviro Shield between temperatures of 5-35C with a brush and roller. Visually check product is cured before proceeding to the next step. Same applies for Enviro Prime WB above. Min 2 photos of primer applied. Min 1 photo of temperature reading prior to application.
checkpoint-status |  |  | checkpoint | Fillet and Bondbreaker
label | f7be5b94-8749-5bc0-b3cc-be43ab51f1c8 |  | note | Surfaces must be clean and dry. Apply the sealant firmly into the internal corner or joint and tool to the required cove size as per the relevant Australian Standard. This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal. Allow to be track free before proceeding with membrane application. Visually check product is cured before proceeding to the next step. Min 2 photos. Min 1 photo with coving testing tool.
checkpoint-status |  |  | checkpoint | Wall Membrane Application
label | c0ff7ed2-a0e3-558f-a4a3-9a17a09ef047 |  | note | Enviro 200P Ultra can be applied using a brush or roller in temperatures of 5-35C. Apply Enviro 200P Ultra to achieve the minimum Dry Film Thickness (DFT) of 0.6mm. Prefabricated waterproof collars to be installed and incorporated into waterproofing membrane around all plumbing penetrations. Visually check product is cured before proceeding to the next step. Min 2 Photos Min 1 photo of temperature reading
checkpoint-status |  |  | checkpoint | Floor Membrane 1st Coat
label | f00e0334-fd72-5a81-b0cf-354602cc3a36 |  | note | Mix using slow speed (max 400 rpm) mechanical mixing equipment with a suitable paste type mixing paddle attached. Enviro 200P Ultra can be applied using a brush or roller in temperatures of 5-35C. Apply Enviro 200P Ultra to achieve the minimum Dry Film Thickness (DFT) of 0.5mm. Visually check product is cured before proceeding to the next step. Min 2 photos Min 1 photo of temperature reading
checkpoint-status |  |  | checkpoint | Floor Membrane 2nd Coat
label | f01f8165-005b-5478-ace3-a82476d33472 |  | note | Mix using slow speed (max 400 rpm) mechanical mixing equipment with a suitable paste type mixing paddle attached. Enviro 200P Ultra can be applied using a brush (Min 150mm upturns) or roller in temperatures between 5-35C. Apply Enviro 200P Ultra to achieve the minimum Dry Film Thickness (DFT) of 0.5mm. Visually check product is cured before proceeding to the next step. Min 2 photos Min 1 photo of temperature reading
checkpoint-status |  |  | checkpoint | QA Testing
label | d0471d8b-4c83-5d15-8be7-1feb39087852 |  | note | Thickness testing of application to the recommended DFT to manufacturers instructions( 0.6mm walls 1.0mm floors 3 tests on floor/ 3 tests on walls.) 24 hour Flood testing. 6 photo of markings of testing on susbtrate and Positector reading Min 1 photo of Flood testing
checkpoint-status |  |  | checkpoint | Holdpoint
label | 37d01cb8-1056-597e-b157-63de231ef6aa |  | note | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | Delivery Checklist |  |  |  |  | Yes | Delivery Checklist | f58efb6e-753b-48eb-b6a4-5dd61c12f50e
checkpoint-status |  |  | checkpoint | Check correct materials are received at least 24 hours prior to commencing work on site
text | 848e23e0-4589-5955-8294-ced723f7ece3 |  | textbox | Batch No.
label | df14911b-3144-5ad1-9a3e-8cd44d2d3f16 |  | note | Specification / Standard: AS4654.1-2012; Manufacturer’s Technical Data Sheet
label | 0b086bdb-76c3-53a2-8886-5218851bf809 |  | note | Attach Delivery Docket
checklist-sectioned |  |  | checklist | Pre-Inspection Checklist |  |  |  |  | Yes | Pre-Inspection Checklist | fb3f412a-a94c-4e02-89dc-c653a53a98f3
checkpoint-group |  |  | section | General Area
checkpoint-status |  |  | checkpoint | Has the builder provided a marked up plan on each area to be waterproofed?
label | bfe6f37e-3538-5d73-a6e4-8144007a127c |  | note | Marked up plan has to be numbered if more than one area at a time is to be completed
checkpoint-status |  |  | checkpoint | Has the concrete been cured for 28 days, date of pour to be provided?
checkpoint-status |  |  | checkpoint | Has concrete moisture test been carried out and the result was provided for the locations on a marked up plan?
label | 2eb6a3cd-0e2b-58d3-8973-f89e739e3cbd |  | note | The moisture level should be around 7%
checkpoint-status |  |  | checkpoint | Is the concrete finished to an acceptable steel trowel class finish?
checkpoint-status |  |  | checkpoint | Have all tape, steel wire, nails, plywood or formwork, bracing, dyna bolt and/or steel brackets been removed and patched?
checkpoint-status |  |  | checkpoint | Is there any cracking in the substrate? If yes, an engineer’s report will need to be provided or the builder must sign off prior to commencement of works
checkpoint-status |  |  | checkpoint | Has any chemicals been used in the concrete process that may affect the membrane adhesion?
checkpoint-group |  |  | section | Hobbs
checkpoint-status |  |  | checkpoint | Spalling
checkpoint-status |  |  | checkpoint | Laitance
checkpoint-status |  |  | checkpoint | Boney Concrete
checkpoint-status |  |  | checkpoint | Prework was under standard
checkpoint-status |  |  | checkpoint | Form Ply Ridges
checkpoint-group |  |  | section | Wall
checkpoint-status |  |  | checkpoint | Spalling
checkpoint-status |  |  | checkpoint | Laitance
checkpoint-status |  |  | checkpoint | Boney Concrete
checkpoint-status |  |  | checkpoint | Prework was under standard
checkpoint-status |  |  | checkpoint | Form Ply Ridges
checkpoint-group |  |  | section | Floor
checkpoint-status |  |  | checkpoint | Spalling
checkpoint-status |  |  | checkpoint | Laitance
checkpoint-status |  |  | checkpoint | Boney Concrete
checkpoint-status |  |  | checkpoint | Prework was under standard
checkpoint-status |  |  | checkpoint | Form Ply Ridges
checkpoint-group |  |  | section | Access
checkpoint-status |  |  | checkpoint | Puddle flanges used or installed must be recessed flush to the top of the concrete surface
holdpoint |  |  | signoff | Builder to check correct falls to drains
checkpoint-status |  |  | checkpoint | Patching to be completed 3 days prior to waterproofing proposed start date and/or second inspection required
checkpoint-status |  |  | checkpoint | Adequate spacing to seal around each one for Cast in items (conduit, water pipes etc). No flexible conduits permitted
checkpoint-status |  |  | checkpoint | Would recommend using Enviro mortar 45 for all pin holes, overfilled then stoned back when dry