## Sheet1
Enviro Systems Checklist - Enviro B-LV+HP1200+900PUR+800TC
SECTION | BATCH DETAIL NUMBER OF PRODUCTS
Checkpoint | Enviro B-LV
Label | Record Batch Number
Checkpoint | Sika Flex FC/ Enviro Flex FC
Label | Record Batch Number
Checkpoint | Enviro HP1200
Label | Record Batch Number
Checkpoint | Enviro 900 PUR
Label | Record Batch Number
Checkpoint | Enviro 800TC
Label | Record Batch Number
SECTION | PRE COMMENCEMENT
Checkpoint | Material Management & Storage - Witness Point
Label | Store materials in a dry, clean place away from direct sunlight. - Record by timestamped photograph.
Checkpoint | Acceptance of Substrate - Witness Point
Label | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per PDS before applying the membrane. - Record by timestamped photograph.
Checkpoint | Acceptance of Puddle Flanges - Witness Point
Label | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing. - Record by timestamped photograph.
Checkpoint | Falls in Substrate - Hold Point
Label | Builder to confirm compliant falls; minimum 1-100 falls.
SIGNOFF | Foreman to confirm falls - Signature
Checkpoint | Cracks in Substrate - Witness Point
Label | Ensure no substrate cracks greater than 1.6mm. Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology. - Record by timestamped photograph.
Checkpoint | Builders Pre-commencement Sign Off
SIGNOFF | Witness Point Sign off
SECTION | SUBSTRATE PREPERATION: AS 4654.2-2012
Checkpoint | Substrate Preperation - Witness Point
Label | Ensure Surface is prepared to receive primer application. Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion. Achieve CSP2 and CSP3 Concrete finish. Remove all sharp edges including screws, nails and concrete/mortar projection. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary. - Record by timestamped photograph.
Checkpoint | Builders Substrate Preperation Sign Off
SIGNOFF | Witness Point Sign off
SECTION | EPOXY B-LV - PRIME COAT
Checkpoint | Moisture Content - Witness Point
Label | Check Moisture content of substrate, not to exceed 6% ( Min.1 test per 10m2.) - Record with Tramex Moisture Reader - Provide timestamped photograph
Checkpoint | Weather/RH - Witness Point
Label | Apply within 5-35°C RH must be 0-85% - Provide screenshot of weather reading.
Checkpoint | Product Mixing - Witness Point
Label | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Checkpoint | Primer Application - Witness Point
Label | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface. Apply one coat of Enviro Epoxy B to achieve a minimum Dry Film Thickness (DFT) of 75 microns. Ensure Primer is dry and tack free (within 24 hours) prior to next coat. - Record by timestamped photograph.
Checkpoint | Builders Prime Coat Sign Off
SIGNOFF | Witness Point Sign off
SECTION | BOND BREAKER
Checkpoint | Primer Application - Witness Point
Label | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints. This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas. Bond breaker to be tack free prior to coating. - Record thickness with a fillet gauge. - Provide timestamped photograph.
Checkpoint | Builders Bond Breaker Sign Off
SIGNOFF | Witness Point Sign off
SECTION | ENVIRO HP1200- BASE COAT
Checkpoint | Weather/RH - Witness Point
Label | Apply within 5-35°C RH must be 0-85% - Provide screenshot of weather reading.
Checkpoint | Product mixing - Witness Point
Label | Mixing by way of 1:1 mix ratio (by volume) in heated plural component.
Checkpoint | HP1200 Application - Witness Point
Label | HP1200 must be sprayed using high pressue plural component dispensing equipment - Drums of component must be pre-heated to at least 25C prior to mixing or dispensing. Mix Part B thoroughly with a mechanical power mixer before use. - Provide timestamped photographs.
CheckPoint | QA TESTING - Hold Point
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions.( 1 test per 10m2) - Conduct Electronic Leak Testing ( ELT) and rectify as required. - Record DFT with Positector. - Provide timestamped photograph.
Checkpoint | Builders Base Coat Sign Off
SIGNOFF | Witness point sign off.
SECTION | ENVIRO 900 PUR- WEAR COAT
Checkpoint | Weather/RH - Witness Point
Label | Apply within 5-35°C RH must be 0-85% - Provide screenshot of weather reading.
Checkpoint | Mixing of Product - Witness Point
Label | Enviro 900 has a mix ratio of 2.2:1 (A:B). Mix Part A and Part B separately, before combining. Enviro 900 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for a minimum of thirty seconds prior to application.
Checkpoint | Application - Witness Point
Label | Enviro 900 to be applied by squeegee, roller or brush to finished membrane. Aggregate should be uniformly broadcasted to the wet Enviro 900 within 10 minutes. - Provide timestamped photograph.
Checkpoint | Builders Wear Coat Sign Off
SIGNOFF | Witness point sign off.
SECTION | ENVIRO 800 TC
Checkpoint | Weather/RH - Witness Point
Label | Apply within 10-35°C RH must be 0-85% - Provide screenshot of weather reading.
Checkpoint | Mixing of Product - Witness Point
Label | Mixing by way of 4:1 mix ratio (A:B) by volume. Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
Checkpoint | Application - Witness Point
Label | Enviro 800TC to be applied by roller or brush to finished membrane. Allow coat to sufficiently dry before proceeding to the next coat. - Provide timestamped photograph.
Checkpoint | Builders First Coat Sign Off
SIGNOFF | Witness point sign off.
SECTION | ENVIRO 800 TC - 2ND COAT
Checkpoint | Weather/RH - Witness Point
Label | Apply within 10-35°C RH must be 0-85% - Provide screenshot of weather reading.
Checkpoint | Mixing of Product - Witness Point
Label | Mixing by way of 4:1 mix ratio (A:B) by volume. Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
Checkpoint | Application - Witness Point
Label | Enviro 800TC to be applied by roller or brush to finished membrane. Allow coat to sufficiently dry before proceeding to the next coat. - Provide timestamped photograph.
Checkpoint | Builders Second Coat Sign Off
SIGNOFF | Witness point sign off. | `
SECTION | DETAILING
CHECKPOINT | Vertical Termination Detailing - Witness Point
Label | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge. - Provide timestamped photograph.
Checkpoint | Builders Detailing Sign Off
SIGNOFF | Witness point sign off.