## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | Floor Finishes ITP |  |  |  |  | Yes | Floor Finishes ITP | 947f73c1-18bf-4e5a-bdd3-87a7c19e5a52
checkpoint-group | Subfloor, Floor Preparation, Adhesive
checkpoint-status | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status | Subfloor mechanically diamond ground
checkpoint-status | Floor preparation product installed in accordance with manufacturer's instructions
checkpoint-status | Floor transitions installed as per instructions from builder
checkpoint-status | Waterproof tested for falls, and water test completed by waterproofers
checkpoint-status | Mediseal installed to carpet areas as per plans - min 24 hours curing time observed
select | Product: | MAPEI PLANIPREP SC, 3-4 Mapei Floor Leveller
text | Average thickness: |  |  | mm
checkpoint-status | Correct adhesive used
select | Adhesive: | V4 Evolution Vinyl Adhesive, Monstertack PS Carpet Adhesive, G19 WET AREA ADHESIVE, Capitol PS Adhesive
checkpoint-group | Carpet / Vinyl
checkpoint-status | Confirm area of work is accessible & acceptable to commence (If not comment below)
text | Drawing & revision number(s)
checkpoint-status | Vinyl installed as per plan
select | Material: | RF01 - ARMSTRONG ACCOLADE FOOTHOLD CAMDEN GREY, RF02 - ARMSTRONG ACCOLADE PLUS MINTARO SLATE, RF02A - ARMSTRONG ACCOLADE FOOTHOLD MINTARO SLATE, RF03 - ARMSTRONG SAFEGUARD R12 STORM GREY, RF04 - INSPIRED GRANIT
checkpoint-status | Carpet installed as per plan
select | Material: | CPT01 - Inspired Carpet Tiles - Mist
text | Other colour:
checkpoint-status | Joints sealed with heat welded seams and mitres as per AS 1884-2012
checkpoint-status | Vinyl skirt and coving used as per finishes markup - 150mm height
text | Custom height:
checkpoint-status | Installer Sign Off: Carpet / Vinyl installed as per manufacturer's instructions
checkpoint-status | Add-Floors Sign Off
checkpoint-status | Foreman installation sign off
checkpoint-group | Wall Finish
checkpoint-status | Wall Finish installed as per plan
select | Material: | WV - ARMSTRONG WALLFLEX ALABASTER
checkpoint-group | Protection and Handover
checkpoint-status | Installation complete, checked and reviewed - as per specification
text | General comments / observations
checkpoint-status | Floor protected with bubbleweave floor protection or polyweave
checkpoint-status | Installer Sign Off: Protection installed as per manufacturer's instructions