## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Warrior Shutters - Installation |  |  |  |  | Yes | Warrior Shutters - Installation | 4c69ce83-b7f7-4bf4-83bf-d9a63cf9e65d
checkpoint-group |  |  | section | Installation of Warrior Bushfire Shutters
checkpoint-status |  |  | checkpoint | D1 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | D1 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | D1 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | D2 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | D2 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | D2 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | D3 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | D3 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | D3 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | D4 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | D4 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | D4 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | D5 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | D5 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | D5 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | D6 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | D6 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | D6 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W1 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W1 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W1 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W2 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W2 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W2 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W3 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W3 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W3 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W4 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W4 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W4 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W5 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W5 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W5 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W6 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W6 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W6 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W7 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W7 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W7 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W8 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W8 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W8 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W9 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W9 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W9 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W10 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W10 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W10 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W11 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W11 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W11 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W12 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W12 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W12 - Fit plugs, tags, and signage (shutter deployed)- Photo required
checkpoint-status |  |  | checkpoint | W13 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W13 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W13 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W14 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W14 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W14 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W15 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W15 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W15 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W16 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W16 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W16 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W17 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W17 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W17 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W18 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W18 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W18 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W19 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W19 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W19 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-status |  |  | checkpoint | W20 - Fire shutter installed in accordance with the shop drawing
checkpoint-status |  |  | checkpoint | W20 - Fire shutter operational check
checkpoint-status |  |  | checkpoint | W20 - Fit plugs, tags, and signage (shutter deployed) - Photo required
checkpoint-group |  |  | section | Other relevant comments / photos
checkpoint-status |  |  | checkpoint | Other 1
checkpoint-status |  |  | checkpoint | Other 2
checkpoint-status |  |  | checkpoint | Other 3
checklist-flat |  |  | checklist | Warrior Shutters - Commissioning |  |  |  |  | Yes | Warrior Shutters - Commissioning | 56809ee1-f929-4527-8348-399d0e3b0be6
checkpoint-status |  |  | checkpoint | No gaps greater than 3mm on all Warrior shutters
checkpoint-status |  |  | checkpoint | All Warrior controllers are connected to 240v power
checkpoint-status |  |  | checkpoint | All Warrior control box lids are fixed in place
checkpoint-status |  |  | checkpoint | All Warrior controllers are connected to the operation switch
checkpoint-status |  |  | checkpoint | All Warrior shutters deploy on activation
checkpoint-status |  |  | checkpoint | All Warrior shutters rewind into position on reset
checkpoint-status |  |  | checkpoint | Photos taken of completed install and commissioning
checklist-flat |  |  | checklist | Warrior Shutters - Closing Out |  |  |  |  | Yes | Warrior Shutters - Closing Out | 98c79c5f-f713-48db-89d7-2cde5ed2a501
checkpoint-status |  |  | checkpoint | Final documents drafted
checkpoint-status |  |  | checkpoint | Final payment received
checkpoint-status |  |  | checkpoint | Reports signed by builder / supervisor
checkpoint-status |  |  | checkpoint | Final documents issued
checklist-sectioned |  |  | checklist | Warrior Shutters - Daily Site Safety |  |  |  |  | Yes | Warrior Shutters - Daily Site Safety | 3e18d48c-9172-4759-a0e8-fa0e83619df2
checkpoint-group |  |  | section | Daily toolbox talk
checkpoint-status |  |  | checkpoint | Working at heights
checkpoint-status |  |  | checkpoint | Working near mobile plant and equipment
checkpoint-status |  |  | checkpoint | Working on scaffolding
checkpoint-status |  |  | checkpoint | Materials handling
checkpoint-status |  |  | checkpoint | Working near energised electrical equipment
checkpoint-status |  |  | checkpoint | Tagging and testing of all electrical equipment
checkpoint-status |  |  | checkpoint | Guarding on machinery
checkpoint-status |  |  | checkpoint | PPE
checkpoint-status |  |  | checkpoint | Toolbox Talk has been completed and attached
checkpoint-group |  |  | section | Site housekeeping and materials storage
checkpoint-status |  |  | checkpoint | All materials are stored neatly in a safe and secure area
checkpoint-status |  |  | checkpoint | All materials are protected from elements
checkpoint-status |  |  | checkpoint | All materials are out of the way of other trades
checkpoint-status |  |  | checkpoint | Work area left neat and tidy with material waste disposed of correctly
checkpoint-group |  |  | section | Incident report
checkpoint-status |  |  | checkpoint | Minor, major, or fatal
checkpoint-status |  |  | checkpoint | Who, when, and what
checkpoint-status |  |  | checkpoint | Report attached
checklist-sectioned |  |  | checklist | Warrior Shutters - Site Survey & Site Safety |  |  |  |  | Yes | Warrior Shutters - Site Survey & Site Safety | a1eb45fb-7d03-45f6-b1e3-c20519d2e933
checkpoint-group |  |  | section | Site survey prior to installation
checkpoint-status |  |  | checkpoint | Ensure site access is adequate and safe
checkpoint-status |  |  | checkpoint | Ensure the openings have been suitably prepared for installation
checkpoint-status |  |  | checkpoint | Progress claim is paid up to date
checkpoint-group |  |  | section | Site pre-start
checkpoint-status |  |  | checkpoint | Site walk and identify any potential hazards (update SWMS as required)
checkpoint-status |  |  | checkpoint | Check plant equipment and fill out log book
checkpoint-status |  |  | checkpoint | Ensure scaffolding is tagged and signed (do NOT use if not compliant, advise PC immediately)
checkpoint-status |  |  | checkpoint | SWMS have been read and understood
checkpoint-status |  |  | checkpoint | SWMS signed off
checkpoint-status |  |  | checkpoint | Ensure all materials are on site including appropriate fixings
checklist-flat |  |  | checklist | Warrior Shutters - Defects |  |  |  |  | Yes | Warrior Shutters - Defects | fa3a81e6-cbbc-4bbd-b3ba-dc414cf46716
checkpoint-status |  |  | checkpoint | No paint touch ups required
checkpoint-status |  |  | checkpoint | No damage by others
checkpoint-status |  |  | checkpoint | No materials damaged
checkpoint-status |  |  | checkpoint | No gaps greater than 3mm
checkpoint-status |  |  | checkpoint | All materials stored correctly
checkpoint-status |  |  | checkpoint | All required materials installed
checkpoint-status |  |  | checkpoint | All Warrior shutters operational
checkpoint-status |  |  | checkpoint | All products correctly ordered (dimensions, finishes, etc.)