## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Pipe Flushing & Cleaning - Floors, Plant, Risers |  |  |  |  | Yes | NFH-ITP-04 - Pipe Flushing & Cleaning - Floors, Plant, Risers | 4d001938-f25a-49b3-9f2b-02305c583a32
checkpoint-status |  |  | checkpoint | Paper ITP Uploaded below
checklist-flat |  |  | checklist | HVCA DW143/DW144 Duct Leakage Test |  |  |  |  | Yes | NFH-ITP-05 - HVCA DW143/DW144 Duct Leakage Test | 61467c7c-9dfa-4f13-9802-8073a05b3a98
checkpoint-status |  |  | checkpoint | Paper ITP Uploaded below
checklist-flat |  |  | checklist | Piping Pressure Test |  |  |  |  | Yes | NFH-ITP-02 - Piping Pressure Test | 79cca176-3498-4b02-9cc9-929fad95c499
checkpoint-status |  |  | checkpoint | Copper pipe used meets AS1432
label | 5e8b45aa-2a38-5fba-8ba1-155fc18b1b5c |  | note | (Type A, B and C Copper Tube from DN15 to DN100)
checkpoint-status |  |  | checkpoint | All Viega Press fittings have been marked and crimped
checkpoint-status |  |  | checkpoint | All welded/brazed joints [steel or copper] have been visually inspected
checkpoint-status |  |  | checkpoint | Details
text | 7813ef98-d57b-5391-82af-f3c62dc50fe8 |  | textbox | Test Date
text | 18d012ad-ec44-5707-a616-c6577861be80 |  | textbox | Test No.
text | 9fe521b0-98c7-5d1e-9121-1acc24bcb4ef |  | textbox | Pipe system under test
text | fee766ed-ab4f-5e80-89d2-9c9a788c8360 |  | textbox | Area/Section under test
text | 47dd69ce-c2b6-51c4-b50a-e39e942c1470 |  | textbox | From
text | cc7cec26-a3f5-521c-b92f-6b292d10dc36 |  | textbox | To
text | be7a13e4-94eb-5165-82dc-d441b623a226 |  | textbox | System Working Pressure
text | eff25227-b369-5f69-980f-2f87c03beb08 |  | textbox | System Test pressure (as per Specifications)
checkpoint-status |  |  | checkpoint | First Reading
text | 7d3ddc14-5dfd-5ffb-a71a-13697ab9b323 |  | textbox | Pressure (KPa)
text | c8bc9f3a-30fa-5b0e-929b-a09d8316dffe |  | textbox | Time
text | 436b53c8-785a-5428-a6da-913c798a8d6b |  | textbox | Ambient Temp (Deg Cels.)
checkpoint-status |  |  | checkpoint | Second Reading
text | 247deb09-34ca-56cc-b00a-4f94aaa33831 |  | textbox | Pressure (KPa)
text | 5ed58343-2e40-5cfa-a191-2e4634f8f97b |  | textbox | Time
text | 3b9e22a4-1481-5b91-8e7c-cc8edb9c08a5 |  | textbox | Ambient Temp (Deg Cels.)
checklist-sectioned |  |  | checklist | Mechanical Installation Rough In & Fit Off |  |  |  |  | Yes | NFH-ITP-01 - Mechanical Installation Rough In & Fit Off | b570f47b-2bd3-4f7e-afb0-92e7a8cbd6f4
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Equipment
label | fd734c87-4335-5a0f-9a48-ad667768ba0c |  | note | Ductwork and Pipework installed in accordance with approved IFC Drawings
label | 3d1c8e81-7598-5f54-87de-8bb9f1873804 |  | note | Photos of all title block/(s) required
checkpoint-status |  |  | checkpoint | Equipment Installed
label | 1b71c90c-9f91-53fe-9bb8-789ebe5a639f |  | note | Photo of equipment schedule on drawing required
checkpoint-status |  |  | checkpoint | Duct Pressure Tested (Refer NFH-ITP-05)
checkpoint-status |  |  | checkpoint | Pipework Pressure Tested (Refer NFH-ITP-04)
checkpoint-group |  |  | section | Fit Off
checkpoint-status |  |  | checkpoint | Registers installed in accordance with approved IFC drawings
checkpoint-group |  |  | section | Subcontractors
checkpoint-status |  |  | checkpoint | Subcontractor ITPs submitted
label | 96199b07-7376-5742-b69f-63232de541f3 |  | note | DO NOT PASS UNTIL ALL SUBCONTRACTOR ITPs SUBMITTED
label | db62e2b8-ceba-5138-a853-42b367d6892b |  | note | Comment subcontractor names below as checked ITPs submitted
label | ef056ebe-b917-5975-b33a-80082b374043 |  | note | Pass once all subcontractor ITPs submitted