## Table 1
SECTION 1 – GENERAL DETAILS
Project Name: | [6 empty] | Infrastructure Alliance | [11 empty] | Inspection Key Use in sections 3, 4 and 5. |  |  |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | [6 empty] | 94 | [11 empty] | A | Action |  |  | Role Key |  | Name |  |  | Signature/ Initial
Customer: | [6 empty] | Hamilton City Council | [11 empty] | B | Report by Breach |  |  | FP Foreperson
Contract Number: | [6 empty] | 550580 | [11 empty] | C | Check |  |  | SV Supervisor |  | Conrad Ferreira
Area/ Sub-System: | [10 empty] | Lot ID Number: | [7 empty] | D | Dimension Inspection |  |  | MM Maintenance manager |  | Darrin Williams
[19 empty] | E | Examine |  |  | QE Quality engineer |  | Gurjiwan Brar
ITP Number: | [10 empty] | Version: | [7 empty] | H | Hold Point |  |  | OM Operations manager |  | Wayne Bowden
ITP Description: | [6 empty] | Asphalt Footpath Renewals | [11 empty] | I | Inspection |  |  | RM Renewals manager
Discipline: | [18 empty] | M | Monitor on Random Basis |  |  | AM Alliance manager
Specification: | [6 empty] | Refer to relative RITS and SWMS | [11 empty] | O | Operation |  |  | PM Project manager
Drawings: | [6 empty] | Refer to relative RITS and SWMS | [11 empty] | R | Review |  |  | PE Project engineer
[19 empty] | S | Subcontractor
[19 empty] | V | Visual Verification
Prepared By: (Name) | [10 empty] | Date:
Quality Specified: | [18 empty] | W | Witness Point
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer | [8 empty] | Name: | [9 empty] | Signature: | [5 empty] | Date:
Downer Approval | [8 empty] | Name: | [9 empty] | Signature: | [5 empty] | Date:
Customer Approval | [8 empty] | Name: | [9 empty] | Signature: | [5 empty] | Date:
SECTION 3 - Notifications
Item No. |  | Activity/ Task Description | [5 empty] | Inspection Point: Quality Control Activity. |  |  |  |  | Acceptance Criteria | [7 empty] | Verifying Document | Frequency |  | Inspection /Test Key |  | Role key | Authoriser signature & Date
3.1 |  | Site inspection | [5 empty] | Walk over with maintenance supervisor and foreperson |  |  |  |  | Visual inspection | [7 empty] | ITP | Once |  | V |  | SV FP
3.2 |  | Service location and permits issued | [5 empty] | All services located and marked. Permits issued |  |  |  |  | Permits issued and received by qualified staff only | [7 empty] | Relative permits to be kept in work pack | As permits expire |  | V |  | FP
3.3 |  | Work pack Checklist | [5 empty] | Check the work pack checklist |  |  |  |  | Copy of work pack with all documents | [7 empty] | As per site meeting | Once |  | V |  | FP
SECTION 4 - Construction
4.1 |  | Environmental controls | [5 empty] | Apply environmental controls to site. Witches hats, silt socks, water for concrete saw |  |  |  |  | Consider drainage, noise, dust, weather. | [7 empty] | Refer to DN- ZH-FM028.2 | Once |  | V |  | FP
4.2 |  | Saw Cutting | [5 empty] | Cut the existing footpath to the full depth of asphalt |  |  |  |  | Cut in straight line and regular shape | [7 empty] | RITS 3.4.9.2 | As required |  | V |  | FP
4.3 |  | Excavation | [5 empty] | Dig out the existing footpath to the pavement depth. |  |  |  |  | Visual subgrade inspection by site Foreperson | [7 empty] | Refer RITS 3.4.9.3 & Drawing D3.3.5 | Once |  | V |  | FP
4.4 |  | Preparing subgrade(If Subgrade fails Visual inspection) | [5 empty] | Subgrade shall be further compacted and replaced with Suitable material. |  |  |  |  | Visual inspection | [7 empty] | Refer to RITS 3.4.9.4 | Once |  | V |  | FP SV
4.5 |  | Timber Edging | [5 empty] | Pegs spaced every 750 max from centre to centre and edge boards shall be 75 x 25. |  |  |  |  | Visual inspection | [7 empty] | Refer to RITS D3.6.1 | As required |  | V |  | FP
4.6 |  |  | Pavement base course |  |  |  |  | Make up existing base preparation where required. It will change on as per suitable vehicle crossing. |  |  |  |  | Clegg hammer value shall not less than 12 after 4 blows | [7 empty] | Refer to RITS D3.3.5 | Throughout the activity Clegg Every 10m |  | H |  | FP SV
4.7 |  |  | Asphalt surfacing |  |  |  |  | Asphalt layer 25mm. 40mm for vehicle crossings. |  |  |  |  | String line from top of both sides of boxing. | [7 empty] | Refer to RITS D3.3.5 & RITS 3.4.9.8 | Every 10m for the duration of the project |  | V |  | FP
4.8 |  |  | Site reinstatement |  |  |  |  | Berms reinstated with top soil and grass seeded. Site to be swept |  |  |  |  | Minimum of 100mm of topsoil and a good amount of grass seed applied. | [7 empty] | Refer to RITS 2.2.4.6 | As required |  | V |  | FP
SECTION 5 – Post Construction Audit
5.1 |  |  | Post Completion Audit |  |  |  |  | Area measured? Any visual crack observed? Photos taken? As-built updated? |  |  |  |  | Refer to RITS | [7 empty] | Post completion Report | After the completion of job |  | W |  | SV
COMMENTS
Berms are to be mown during the defects liability period as well as prior to take over by Council. 3.4.9 Footpaths, Cycle Paths and Vehicle Crossings This section outlines the work required to construct, reinstate or repair footpaths, vehicle crossings and away-from-road cycle paths. 3.4.9.1 Alignments, Lines and Levels The edge lines of kerbs, footpaths, shared paths and vehicle crossings shall be perfectly straight between tangent points, and on curves shall sweep round without kinks, flats or angles in a smooth, true arc to the radius shown or directed. Design levels and alignments shall be strictly adhered to and the grade from level peg to level peg shall be even, provided always that at changes of grade the angle between the grades shall be eased so as to form a vertical curve or other form of smooth transition. The entire berm area shall fall, at an even grade where possible, from the property boundaries to the kerb and channel. 3.4.9.2 Break out, Removal and Disposal of Existing Berm Features All existing berm features that are to be removed shall be broken up and lifted out to reduce damage to the surrounding features. The outer limits of these features shall be saw cut, except in the case of paving blocks or grass verges, before removing to provide a tidy interface between existing and replacement work. Where salvaging of materials (e.g. catchpits, gratings, frames, stormwater piping) is specified, care shall be taken to ensure that as little damage as possible is done to materials. Such units shall be neatly stacked on the site such that they do not obstruct any footpath, vehicle crossing or roadway until they are taken off site. All materials not for reuse shall be removed from site and appropriately disposed of. 3.4.9.3 Excavation to Pavement Depth
Excavation shall be to the pavement depth as shown on Drawing D3.3.5. The width of all excavation shall be no wider than necessary to construct or reinstate the various berm features. Where excavation adjoins existing berm features or carriageways, care shall be taken not to undermine the existing surfacing while material is being removed. The sides of the excavated area shall be trimmed to as vertical as possible without being unstable or causing undermining.
3.4.9.4 Subgrade Preparation The exposed subgrade (excavated to trial subgrade level or pavement depth) shall be tested by using a Scala Penetrometer for compliance with the following CBR values a) In footpath, cycle paths and traffic island infill CBR value >10 (4 blows per 100mm) b) In vehicle crossing and kerb and channel areas CBR value >10 (4 blows per 100mm)
Regional Infrastructure Technical Specifications | [5 empty] | Waikato Local Authority SHARED SERVICES Page 137 of 601
l i J ..:,,., ! P1•·emenI DeiHtl = 175mm I P1vem.,nt =200mm I Pa..emenl De9CII 250mm I P.wemfflt Oepth • 300mm
.. S0/60mm Pi!vil1_BBlock 81)nm Pavl11&_llloct 80mm Pavina.lllodt 80mm Pwtna8lodt i
f CBR > 10 2.Smn, lleddlnc sattd C811> 10J J I 25mm tlciddln1 d Pa•eMem Depm = 175mm I Pave111er,1Depth= 195mm I Pavement Df!plt, = 250mm I Pavemenl Depth• 300mm
f'@destr1an cro lng
" C- i 1-I J1.!S CB11> 10 P4vcmem Dcptll =200mm J P•..,mcnl Dq,lh= 200mm J Pltvcmenl Dq,lh =300mm I P | [17 empty] | r:... r,. -ment Depth = 350mm
NOTIS; 1. Cor1aete - 28Day In pl- mlnlmllffl s11ell(lh or 20Ml'll. J 1. aasecoor,e depth c.n be amended t,y us.nc steel nwsh relnford111 In concrete vehiclecrossings(spedfkdeslg,,,equlred). I I [ . ·· • ·..' · l Depth or s;ind / GAP m;ilerl;il to beincreased where the C8II i< .... t •• not ;ithivvablc. t I • . .._ MACHINE EXTRUDED CROSSING P.rllt<nent Depth • 42SrM1 C6R > 10
1 w,iuto Lot,l Avthonty SHAREO SERVICES CROSS SECTION DETAILS FOR FOOTPATH, VEHICLE CROSSINGS AND DEPRESSED D3.3.5 KERB AND CHANNEL RC.GIOHAL llil'IIASTIWCTUltf TECHNICAi. SPECIACAJION Version: AUGUST1016
|  |  |  | Pedestrian Footpath ISlnafc Re cnri I OwellinaJ | [5 empty] | Resldent1al Strength Vehicle Crossing (Mulalllnes2-6) |  | Commercial Strength Vehlde Crossing (Multi Owelllncs 7•1 |  |  |  | Industrial Strength Vehicle c.-ossings
|  |  |  | 25m.tn Mlil 10 Asph•lt | [5 empty] | 25mm Mix 10phillt |  | 2Smm Ml 10l\sph;ilt |  |  |  | 50mm MIK 20 AspNlt
PAlll.'menl Dq,U, =175mm | [9 empty] | I Pavl,ment Do,pth = 200mm I |  | CBR > 10 Pavement Dq,lh =250mm |  |  |  |  | C811>10 J me111DepI11= 300mm
100mm Conaete ·"a' | [9 empty] | 1251nm <:oncrete |  | 150mm Cooaete 1 |  |  |  |  | 175mmConctete
i
Drawing 3-17: Cross section details for footpath, vehicle crossings and depressed kerb and channel
Page 208 of 601 Waikato local Authority SHARED SERVICES | [18 empty] | Regional Infrastructure Technical Specifications
|  | 75 • 25 Jc,ln,n st.w n•lled plvaMed fla ! N | [11 empty] | g board jo, rrom both thead nails | ed board oNcut) ode$ with 50mm 100• 25 amber edg,eboards
f 100 ◄ m•"- SOx 25 x22S m,n.peasor l batons Nailedfrom e;idl side [min. 2 nails per pq) with 750mmmllX. adja nt to joining bo td, SO!nmgal\,anl ed fLlthead na,ls.. 1000mm m;i,ic. pea spatlng flsewlteA! A ct,lp seal surfKAflC M J!J.----1!! M T oll 75mmGAP20 SubirM •Pit i;ond '-- -- wt,,:r,:,re,.q,u,,i.m_! / 1s • 25 Jololna board 50 x 25 or balor,s.. Pltnnd SUb8111d to Minimum lencth 22.5mm 4:Xlond100mm p;nt edll'Gbo rd5. SECTION A •A hlcle cro!.Slll1/ footpath 2 • 50mm phr.M,lscd 200 100• 25timber edpbo.lfds llitheid nalls ,nax ijli .\ M M \r Ii'{ - SO • 25xUS min, pqs or batons M 1¼. M. M V.: oowting I Ni. :.'-6. M .M. M M CORNER DETAIL NOTES,: All llrnber components shaa be H ground .rted
Iw.,1;,10 Lcx,tA tt,ci,ity SHAREO SERVICES TIMBER EDGING DETAILS FOR CHIP SEAL, ASPHALT AND BLOCK PAVING D3.6.1 RI.G'IOHAL INnlAS'TlltlfTURf_T[O\NICAl SPECIFICATION V..,r1ion: M.IGUST 2016
Drawing 3-24: Timber edging details for chip seal, asphalt and block paving
Regional Infrastructure |  |  |  |  | Waikato Local Authority
2.2.4.3 End Product Specification Where an end product specification is required, the desired compaction criteria of the placed and compacted fill are specified and the earthworks contractor is free to choose whatever method of compaction they wish to achieve the targets specified. 2.2.4.4 Frequency of Tests During the earthworks, soil tests need to be undertaken on the placed fill to ensure the necessary degree of compaction is being achieved. The methods of testing and frequency of tests shall be specified and included in the Fill Design Report. 2.2.4.5 Cuttings and Embankments For cuttings and embankments formed as part of the earthworks, details of analytical methods used to determine slope stability are to be included. As part of this, the engineering properties and relevant ground investigation information is required. As these earthwork features can affect the groundwater and surface run off, or need drainage measures to ensure stability, details of the drainage must be included. If embankments form part of the proposed site works, settlement calculations must be included and justified from ground investigation data. Details of any special measures to analyse slope or control settlements shall be included. 2.2.4.6 Topsoil Top soiled surfaces shall be between 150-300mm consolidated depth, and shall consist of the outermost layer of natural soil with the highest concentration of organic matter and microorganisms, and generally be free of vegetation, large clumps, excessive and large stones, and be suitable for easy spreading in an even layer. This topsoiling should endeavour to mimic the pre-existing conditions. 2.3 CONSTRUCTION AND FINAL DOCUMENTATION 2.3.1 Construction During construction, site inspection and or testing shall be undertaken by a suitability qualified geo-professional with the requirements outlined in the geotechnical assessment report. If any archaeological site or waahi tapu is discovered or disturbed during the works, lwi and the Council shall be notified immediately 2.3.2 Dust Management Reference should be made to MfE's Good Practice Guide for Assessing and Managing Dust. During dry weather, where there is more than 400 m2 of bare soil exposed on a development, one or more of the measures below is to be employed to reduce wind erosion and the amount of airborne dust emanating from the site:
Regional Infrastructure |  |  |  |  | . Waikato Local Authority
!Notis>)