## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - 09.1 Full ITP AC Footpath | itp |  |  |  |  | ITP - 09.1 Full ITP AC Footpath
section | SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
checkpoint | ITP Close-Out by Downer
text | Name:
text | Date:
checkpoint | Downer Approval
text | Name:
text | Date:
checkpoint | Customer Approval
text | Name:
text | Date:
section | SECTION 3 - Notifications
checkpoint | 3.1 - Site inspection
label | Inspection Point: Quality Control Activity - Walk over with maintenance supervisor and foreperson
label | Acceptance Criteria - Visual inspection
label | Verifying Document - ITP
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - SV FP
checkpoint | 3.2 - Service location and permits issued
label | Inspection Point: Quality Control Activity - All services located and marked. Permits issued
label | Acceptance Criteria - Permits issued and received by qualified staff only
label | Verifying Document - Relative permits to be kept in work pack
label | Frequency - As permits expire
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 3.3 - Work pack Checklist
label | Inspection Point: Quality Control Activity - Check the work pack checklist
label | Acceptance Criteria - Copy of work pack with all documents
label | Verifying Document - As per site meeting
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
section | SECTION 4 - Construction
checkpoint | 4.1 - Environmental controls
label | Inspection Point: Quality Control Activity - Apply environmental controls to site. Witches hats, silt socks, water for concrete saw
label | Acceptance Criteria - Consider drainage, noise, dust, weather.
label | Verifying Document - Refer to DN- ZH-FM028.2
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.2 - Saw Cutting
label | Inspection Point: Quality Control Activity - Cut the existing footpath to the full depth of asphalt
label | Acceptance Criteria - Cut in straight line and regular shape
label | Verifying Document - RITS 3.4.9.2
label | Frequency - As required
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.3 - Excavation
label | Inspection Point: Quality Control Activity - Dig out the existing footpath to the pavement depth.
label | Acceptance Criteria - Visual subgrade inspection by site Foreperson
label | Verifying Document - Refer RITS 3.4.9.3 & Drawing D3.3.5
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.4 - Preparing subgrade(If Subgrade fails Visual inspection)
label | Inspection Point: Quality Control Activity - Subgrade shall be further compacted and replaced with Suitable material.
label | Acceptance Criteria - Visual inspection
label | Verifying Document - Refer to RITS 3.4.9.4
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP SV
checkpoint | 4.5 - Timber Edging
label | Inspection Point: Quality Control Activity - Pegs spaced every 750 max from centre to centre and edge boards shall be 75 x 25.
label | Acceptance Criteria - Visual inspection
label | Verifying Document - Refer to RITS D3.6.1
label | Frequency - As required
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.6 - Pavement base course
label | Inspection Point: Quality Control Activity - Make up existing base preparation where required. It will change on as per suitable vehicle crossing.
label | Acceptance Criteria - Clegg hammer value shall not less than 12 after 4 blows
label | Verifying Document - Refer to RITS D3.3.5
label | Frequency - Throughout the activity Clegg Every 10m
label | Inspection/Test Key - H
label | Role key - FP SV
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Asphalt surfacing
label | Inspection Point: Quality Control Activity - Asphalt layer 25mm. 40mm for vehicle crossings.
label | Acceptance Criteria - String line from top of both sides of boxing.
label | Verifying Document - Refer to RITS D3.3.5 & RITS 3.4.9.8
label | Frequency - Every 10m for the duration of the project
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.8 - Site reinstatement
label | Inspection Point: Quality Control Activity - Berms reinstated with top soil and grass seeded. Site to be swept
label | Acceptance Criteria - Minimum of 100mm of topsoil and a good amount of grass seed applied.
label | Verifying Document - Refer to RITS 2.2.4.6
label | Frequency - As required
label | Inspection/Test Key - V
label | Role key - FP
section | SECTION 5 – Post Construction Audit
checkpoint | 5.1 - Post Completion Audit
label | Inspection Point: Quality Control Activity - Area measured? Any visual crack observed? Photos taken? As-built updated?
label | Acceptance Criteria - Refer to RITS
label | Verifying Document - Post completion Report
label | Frequency - After the completion of job
label | Inspection/Test Key - W
label | Role key - SV