## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - 09.2 Full ITP Kerb and Channel | itp |  |  |  |  | ITP - 09.2 Full ITP Kerb and Channel
section | SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
checkpoint | ITP Close-Out by Downer
text | Name:
text | Date:
checkpoint | Downer Approval
text | Name:
text | Date:
checkpoint | Customer Approval
text | Name:
text | Date:
section | SECTION 3 - Notifications
checkpoint | 3.1 - Site inspection
label | Inspection Point: Quality Control Activity - Site walk over with supervisor and foreperson
label | Acceptance Criteria - Visual inspection
label | Verifying Document - ITP
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - SV FP
checkpoint | 3.2 - Service location and permits issued
label | Inspection Point: Quality Control Activity - All services located and marked. Permits issued
label | Acceptance Criteria - Permits issued and received by qualified staff only
label | Verifying Document - Relative permits
label | Frequency - As permits expire
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 3.3 - Work pack checklist
label | Inspection Point: Quality Control Activity - Check the work pack checklist
label | Acceptance Criteria - Copy of work pack with all documents
label | Verifying Document - Work pack
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
section | SECTION 4 - Construction
checkpoint | 4.1 - Environmental controls
label | Inspection Point: Quality Control Activity - Apply environmental controls to site.
label | Acceptance Criteria - Consider drainage, noise, dust, weather.
label | Verifying Document - Work pack
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.2 - Saw cutting
label | Inspection Point: Quality Control Activity - Kerb and channel cut twice, vertically and at a right angle to the kerb.
label | Acceptance Criteria - Existing sealed surface cut parallel to kerb and at a distance of 500mm
label | Verifying Document - Refer to DN- ZH-SWMS026
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.3 - Excavation
label | Inspection Point: Quality Control Activity - Remove existing kerb. Pot hole. Excavation no deeper than 300mm
label | Acceptance Criteria - Visual subgrade inspection
label | Verifying Document - Refer to RITS D3.3.6
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.4 - Preparing subgrade if inspection fails
label | Inspection Point: Quality Control Activity - Subgrade further compacted or excavate the unsuitable material and replace
label | Acceptance Criteria - Visual inspection
label | Verifying Document - Refer to RITS D3.3.6
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.5 - Pavement Material
label | Inspection Point: Quality Control Activity - Compacted layer of GAP40 75mm deep shall be placed over subgrade.
label | Acceptance Criteria - Clegg test every 10m shall not be less than 12 CIV after 4 blows.
label | Verifying Document - Refer to RITS D3.3.6
label | Frequency - Every 10m, surface of GAP40
label | Inspection/Test Key - H
label | Role key - SV QE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Concrete Works
label | Inspection Point: Quality Control Activity - Damp the prepared surface and check the weather conditions, Use concrete from certified plant
label | Acceptance Criteria - Machine not be used to pour curves less than 5m radii.
label | Verifying Document - Refer to DN- ZH- SWMS026
label | Frequency - Throughout the activity.
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.7 - Contraction/Expansion joints
label | Inspection Point: Quality Control Activity - Maximum spacing of 3m and minimum 50mm deep
label | Acceptance Criteria - Concrete paths provide smooth and even surface after finishing.
label | Verifying Document - Refer to DN- ZH- SWMS026
label | Frequency - Throughout the activity
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.8 - Curing of concrete
label | Inspection Point: Quality Control Activity - Curing period shall not be less than 1 day OR 36 hours?
label | Acceptance Criteria - Visual inspection
label | Verifying Document - Refer to DN- ZH- SWMS026
label | Frequency - Throughout the activity
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.9 - Backfilling
label | Inspection Point: Quality Control Activity - GAP40 compacted 40mm below lip of kerb. Pit sand behind kerb in berm 100mm below top of kerb.
label | Acceptance Criteria - Clegg test shall not be less than 40 CIV.
label | Verifying Document - Refer to RITS 3.4.6.7
label | Frequency - Every 10m, surface of GAP40
label | Inspection/Test Key - H
label | Role key - SV FP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.10 - Joining the carriageway
label | Inspection Point: Quality Control Activity - The carriageway to be married into the existing carriageway and new kerb lip.
label | Acceptance Criteria - concrete must have reached sufficient strength before applying any AC or Chip seal layer
label | Verifying Document - Refer to RITS 3.4.6.7
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.11 - Site reinstatement
label | Inspection Point: Quality Control Activity - Berms reinstated with top soil and grass seeded.
label | Acceptance Criteria - Minimum of 100mm of topsoil and grass seed applied.
label | Verifying Document - Refer to RITS 2.2.4.6
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
section | SECTION 5 – Post Construction Audit
checkpoint | 5.1 - Post Completion Audit
label | Inspection Point: Quality Control Activity - Have kerb adaptors been installed? Any visual crack observed? Photos taken? As-built updated?
label | Acceptance Criteria - Refer to RITS
label | Verifying Document - Post completion Report
label | Frequency - After the completion of job
label | Inspection/Test Key - W
label | Role key - SV