## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - 09.3 Full ITP Concrete Footpath | itp |  |  |  |  | ITP - 09.3 Full ITP Concrete Footpath
section | SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
checkpoint | ITP Close-Out by Downer
text | Name:
text | Date:
checkpoint | Downer Approval
text | Name:
text | Date:
checkpoint | Customer Approval
text | Name:
text | Date:
section | SECTION 3 - Notifications
checkpoint | 3.1 - Site inspection
label | Inspection Point: Quality Control Activity - Site walk over with supervisor and foreperson
label | Acceptance Criteria - Visual inspection
label | Verifying Document - ITP
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - SV FP
checkpoint | 3.2 - Service location and permits issued
label | Inspection Point: Quality Control Activity - All services located and marked. Permits issued
label | Acceptance Criteria - Permits issued and received by qualified staff only
label | Verifying Document - Relative permits
label | Frequency - As permits expire
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 3.3 - Work pack checklist
label | Inspection Point: Quality Control Activity - Check the work pack checklist
label | Acceptance Criteria - Copy of work pack with all documents
label | Verifying Document - Work pack
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
section | SECTION 4 - Construction
checkpoint | 4.1 - Environmental controls
label | Inspection Point: Quality Control Activity - Apply environmental controls to site.
label | Acceptance Criteria - Consider drainage, noise, dust, weather.
label | Verifying Document - Work pack
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.2 - Saw Cutting
label | Inspection Point: Quality Control Activity - Cut the existing footpath to the full depth of concrete
label | Acceptance Criteria - Cut in straight line and regular shape
label | Verifying Document - Refer to DN- GD-GP145
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.3 - Excavation
label | Inspection Point: Quality Control Activity - Dig out the existing footpath to the required width and make good basecourse. Add 100-200mm either side for boxing.
label | Acceptance Criteria - Visual subgrade inspection
label | Verifying Document - Refer to RITS 3.3.5
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.4 - Preparing subgrade(If inspection fails)
label | Inspection Point: Quality Control Activity - Subgrade further compacted or excavate the unstable material and replace
label | Acceptance Criteria - Visual inspection
label | Verifying Document - Refer to DN- ZH-FM028.2
label | Frequency - Once
label | Inspection/Test Key - V
label | Role key - SV FP
checkpoint | 4.5 - Timber Edging
label | Inspection Point: Quality Control Activity - Pegs spaced and timber edging as required.
label | Acceptance Criteria - Visual inspection
label | Verifying Document - RITS Drawing 3.6.1
label | Frequency - As required
label | Inspection/Test Key - V
label | Role key - SV QE
checkpoint | 4.6 - Base preparation
label | Inspection Point: Quality Control Activity - Use Gap 20 or Sand when preparing the base for concrete Footpaths
label | Acceptance Criteria - Clegg Hammer value shall not be less than 12 after 4 blows
label | Verifying Document - RITS D3.3.5
label | Frequency - Every 10m
label | Inspection/Test Key - H
label | Role key - SV QE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Concrete Testing
label | Inspection Point: Quality Control Activity - QA results needs to be supplied by supplier
label | Acceptance Criteria - Minimum Strength of concrete needs to be more than 20MPa
label | Verifying Document - Refer to RITS 3.4.5.2
label | Frequency - Every 6 Months
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.8 - Placing Concrete
label | Inspection Point: Quality Control Activity - Check the weather condition, Surface condition before placing concrete , Lightly damped the surface before placing concrete
label | Acceptance Criteria - Temperature shall not less than 5 degrees Celsius or concrete shall not place in frozen or wet conditions
label | Verifying Document - Refer to RITS 3.4.5.3
label | Frequency - Every Time
label | Inspection/Test Key - V
label | Role key - FP
checkpoint | 4.9 - Curing Concrete
label | Inspection Point: Quality Control Activity - Curing period shall not be less than 36 hours
label | Acceptance Criteria - Visual inspection
label | Verifying Document - Refer to RITS 3.4.5.9
label | Frequency - Throughout the activity
label | Inspection/Test Key - V
label | Role key - SV FP
checkpoint | 4.10 - Site reinstatement
label | Inspection Point: Quality Control Activity - Berms reinstated with top soil and grass seeded.
label | Acceptance Criteria - Minimum of 100mm of topsoil and grass seed applied.
label | Verifying Document - Refer to RITS 2.2.4.6
label | Frequency - As required
label | Inspection/Test Key - V
label | Role key - FP
section | SECTION 5 – Post Construction Audit
checkpoint | 5.1 - Post Completion Audit
label | Inspection Point: Quality Control Activity - Area measured? Water pooling? Any visual crack observed? Photos taken? As-built updated?
label | Acceptance Criteria - Refer to RITS
label | Verifying Document - Post completion Report
label | Frequency - After the completion of job
label | Inspection/Test Key - W
label | Role key - SV