## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-050-CPD-RAIL-Calder Park-OHLE Installation | itp |  |  |  | Yes | ITP-050-CPD-RAIL-Calder Park-OHLE Installation - Rev 1 | 0d16b7a4-af42-4318-ab53-e8c45b46cb72
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | b7df6a49-54d7-57cf-921e-fb4555682e76 |  | note | Document Title: ITP-CPD-RAIL-Calder Park-OHLE Installation
label | 7fe286bd-4b9c-5eed-b7d2-ddf3c07f550e |  | note | ITP Description: OHLE Installation
label | bbab5c57-2d08-5c1f-828e-0366de5e1730 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 1dcd54fc-d22b-5a20-85ad-abb2ffeadd4b |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | 7926b4ef-e200-52d4-9c92-3845f9bb1ae8 |  | note | Revision Number: 1
label | d90ed7af-faed-5a1e-810c-ce1c3f61f380 |  | note | Revision Date: 24/07/2023
label | 2f11af77-9018-55f6-b9f5-8f2491537e2c |  | note | ITP created by: Kevin Liang
checkpoint-status |  |  | checkpoint | 1.1 - Overhead Line Electrification
label | 775a0b1e-c92a-513d-9a77-f92d7b520c11 |  | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
checkpoint-status |  |  | checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | e7953282-822e-5327-9fbd-3c2884ce06a7 |  | note | Reference - VRIOGS 001 AS 4100
checkpoint-status |  |  | checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
label | b705f63d-129d-5cad-8efb-461cd91b2213 |  | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1
checkpoint-status |  |  | checkpoint | 1.4 - Fabrication of Steelwork
label | 5c16f59e-2a3b-5d51-873f-cf6afd16d0bc |  | note | Reference - VicRoads Section 630 January 2023
checkpoint-status |  |  | checkpoint | 1.5 - Electrical Networks Standard Electrical Networks Principles and Performance
label | 08177b38-c8cf-564c-892c-bd6d722802ea |  | note | Reference - Structural Steel Work - Fabrication and Erection
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Structural Steel Components and Fasteners
label | 029dfd34-b50a-569f-a7cd-05f7c012e070 |  | note | Reference - IFC Drawings
label | 5632fa21-5519-5876-998d-8751084f31b6 |  | note | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | ab2345a8-6516-54e6-927f-7934525af411 |  | note | • Typically this consists of but not limited to:
label | 635ba4f0-5ea2-5762-a404-ab1e43c40894 |  | note | i. Completed fabrication ITP
label | 5e5ca6e7-c2eb-5bb9-9ecb-319799692cee |  | note | ii. Weld Procedure Specifications
label | 0a69420e-903a-51f9-9178-36c66a3e19d4 |  | note | iii. Weld Procedure Qualifications
label | 9ecffd6c-7482-5b95-b1fe-28a0b367cd9b |  | note | iv. Welder Qualifications
label | f946d9d7-1ec7-597f-87f5-9eac157dae47 |  | note | v. Material Certificates
label | e01955a7-113e-5b4f-a2c4-291b7bf8d187 |  | note | vi. Coating certificate(s)
label | 0dad601c-c8f7-5d83-8421-091e4e82ce80 |  | note | vii. Non-destructive Testing (NDT) Reports (if any)
label | 9d0c5e70-dde3-56d2-90bb-f5c85dd3a178 |  | note | viii. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | 749f4d78-0637-5bb4-963b-bf4857d9a10e |  | note | • Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
label | 8d4ebc6c-440e-5fb9-b3db-b63033213f51 |  | note | • Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252.
label | 20560b8d-5917-5ca1-814e-88d6f183e0ad |  | note | • All bolts nuts and washers are hot-dipped galvanized.
label | c8a61a7e-4572-5ff6-a50a-133136a4be54 |  | note | Collate: Structural Steel Quality Assurance Documentation.
label | 8a7df7f4-f2a1-57fe-a976-9a46b57545e4 |  | note | Attach: Collated QA documents in ConQA
label | 05f6388b-487f-5e03-a925-85fb9d5cc326 |  | note | Method - Document review
label | dfbcf741-d246-529e-8a59-0380af6f5546 |  | note | Frequency - Where applicable/ Each element
label | faf9a59f-2fce-54a9-9522-9adafb711d4b |  | note | Category - HP
label | 133b2be5-8601-5b00-8896-3244d9565109 |  | note | Responsibility - PE
label | ee4ef774-5114-53de-a293-a92c6e939b68 |  | note | Responsible person - MRPA Engineer
label | a673634f-12f3-57f7-aee0-baf4dd58a2fc |  | note | Verifying Documents - This ITP Signed Off
text | 21797d05-10e4-56c3-b344-a68dde6480e0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Bolted Connections Using Direct Tension Indicators (DTIs)
label | 698738ba-468a-5f98-9679-f91e263f6116 |  | note | Reference - AS4100 Clause 15.2.5.3 (a), AS5131 Clause 8.5.7 (a)
label | 5e8fdc3a-377a-50ea-8157-0db5c8c753d9 |  | note | Acceptance Criteria - Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
label | 0c423b1e-6833-500d-a588-0d17bef07db7 |  | note | i. technical data sheet or information on the product
label | acd47a5e-a2f0-513e-b729-ff4a033bde82 |  | note | Method - Document Review
label | f2f07875-8fb1-531f-a95b-ae21b656d50d |  | note | Frequency - Where applicable/ Each element
label | 47e25988-cd98-57a2-b86e-48ef806931dd |  | note | Category - HP
label | 1227b6f1-fad6-5d05-ae58-c2547960b6c7 |  | note | Responsibility - PE
label | 5300020b-6bec-5ce4-89b3-78238718ec4f |  | note | Responsible person - MRPA Engineer
label | d795bd97-50e2-5afc-8636-77e048c4e6cf |  | note | Verifying Documents - This ITP Signed Off
text | f2fc33fd-12f0-514c-b017-98cfec7cce33 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Overhead Wiring Small Parts Steel and conductor wires
label | 16162b97-9eac-5ebd-8b10-8d8db1f30b51 |  | note | Reference - Relevant MTM Standard Drawings
label | f38b1f7b-8983-5daa-a886-8ffe59c0d1b3 |  | note | Acceptance Criteria - Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings.
label | 12368912-23c3-58fd-878e-7137edfb4868 |  | note | • Deliveries are to be inspected to match the purchase order
label | 91f21825-3a45-5a2c-b9c3-8e9ff3a684da |  | note | Attach: Purchase order/Delivery dockets/Certificate of conformity
label | b51576b3-0083-57d3-a4da-f1a0f37b67c4 |  | note | Method - Visual Inspection and measurement
label | 6f2fe054-11a6-5da6-8f05-c271329b8ddc |  | note | Frequency - Upon delivery
label | 9a9ae8cf-589b-527f-9f82-463adc2b871a |  | note | Category - IP
label | 3b5d102a-2a2d-550c-89b5-c9d88bc5d296 |  | note | Responsibility - PE
label | d2b4931d-222f-5c52-9b6a-52185b512e35 |  | note | Responsible person - MRPA
label | 5f9347ac-56b2-541f-989b-490e654de5d7 |  | note | Verifying Documents - This ITP Signed Off
text | ed8f0551-649b-510d-85a0-4a0477377ce9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Grout
label | 16af3265-c4ba-5307-8917-132b741b0650 |  | note | Reference - IFC drawings
label | 63fef92b-a720-5223-ba1e-24d604d9459c |  | note | Acceptance Criteria - All grout under base plates shall be CONBEXTRA C or equivalent as approved. Approved grout to be Flowable shrinkage compensated with minimum 50 Mpa compressive strength.
text | 736c1915-f532-50df-bace-8e911ed4e1b1 |  | textbox | Enter: Teambinder Material Approval number
label | 80c87a6b-04aa-5906-bb55-0e4dd31f45fb |  | note | Method - Document Review
label | 4e488029-e58f-511c-bc6d-9ce332d0a827 |  | note | Frequency - Where applicable/ Each element
label | e904aa7f-86e1-5c81-af4e-c2b3a4e92814 |  | note | Category - HP
label | 79af41c1-3775-575d-9146-48753e39c0ea |  | note | Responsibility - PE
label | 5bd590e0-a147-5589-8269-588e9d8d9187 |  | note | Responsible person - MRPA
label | 9cff3a7f-18d9-51b3-bad7-9fa4afaefd4c |  | note | Verifying Documents - This ITP/Material Approval
text | 5349b714-ce56-5515-a8c6-38c47f49cf75 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Installation Methodology & Works Method Statement
label | c6587f6a-a357-5edf-bde9-03b72fe60ccf |  | note | Reference - AS5131 Clause 11.2.3
label | 8df0a5dc-e910-5e44-a3f4-ce954288e1e6 |  | note | Acceptance Criteria - Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
label | 226c4203-33a4-5c22-875c-72287ce67144 |  | note | – Transported to site;
label | 035476c6-c2c0-5c61-a1ec-9294a0c7b031 |  | note | – Handled on site;
label | bfebf7ee-1afe-56cb-866e-a4a3a8aa94d2 |  | note | – Installation Procedure (subcontracor ITP's);
label | 87fb6b1a-d92c-5a3d-ab47-96a69d25180d |  | note | Submission of Work Package Plan and MRPA approval and acceptance.
text | bb7ce7a4-5cb9-580e-a381-3e0c0969a9d5 |  | textbox | Enter: WAP number
label | 67879b4c-cc69-51ef-b074-21e640d73b84 |  | note | Method - Document Review
label | fe395e54-c5cb-5e85-ab45-dc862e65cd87 |  | note | Frequency - Prior to Works Start
label | 06bb3c0d-0308-506b-88b1-f70b645b233b |  | note | Category - HP
label | 03578780-31fd-523c-9d11-3f9c16e4d1e5 |  | note | Responsibility - MRPA/CAT5
label | afe8ccae-6cb9-5bc8-a904-ee1905908194 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 3500f4d0-88ed-5646-936a-5daa2484e8c0 |  | note | Verifying Documents - This ITP Signed Off
text | c8c4e938-babd-5ad7-b897-66c4bd018026 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Approval of IFC drawings
label | 368e71de-5229-5aac-9a5d-dff973d76941 |  | note | Reference - Contractor Design Management procedure.
label | 7455b354-e835-57d9-8785-a417392ab4dd |  | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
label | 9d83171d-72ba-51bf-80ad-71c1a3479543 |  | note | Method - Document/Drawings Review
label | c8117857-4586-536a-b053-7499a310d477 |  | note | Frequency - Prior to Works and at regular intervals.
label | 6606ad9b-2ba4-5d58-a610-c60c577db098 |  | note | Category - HP
label | 8900b961-9aa2-5f2a-9ad4-34a0d13e74ae |  | note | Responsibility - MRPA/CAT5
label | 3bdf8cd2-edcf-5538-81c2-7889f14f4cd7 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 8e5d91ff-6f63-5be4-adfc-457d932b6f3d |  | note | Verifying Documents - This ITP Signed Off
text | 880c9916-b058-5360-a555-0431c8be69c4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Cantilever assembled.
label | b850281a-3bc0-54a2-8a57-5e8c4546fb6b |  | note | Reference - Cantilever assembled as per IFC design.
label | 0618ae21-d518-56d9-8955-1b2a1b8b1ec1 |  | note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | 4a1f8606-369c-52a3-9f59-208154f61410 |  | note | Method - Visual, Document Review
label | 68669a8b-cee3-5b90-9d21-7f142c2b6857 |  | note | Frequency - Each Task prior to works start.
label | 6a92ed3f-c499-583e-8d0d-5d3a4f3453e5 |  | note | Category - IP
label | d3fad57c-002a-522c-b4c4-3e028e709cfa |  | note | Responsibility - CAT5/MRPA
label | 699579d4-0032-555f-8f81-2b8dcd88b034 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 003bc675-31a9-5700-b3ea-13ad08a6ce08 |  | note | Verifying Documents - This ITP Signed Off
text | 1925b685-0a9a-5940-8e82-12e40e52d9dd |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Mast Installation
label | d7fa4e75-f469-5ebc-81f4-87706b0cc63e |  | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | 4bd483c3-e3c9-5aca-b9d8-be3ce2ec148b |  | note | Acceptance Criteria - Work instructions in accordance to IFC design
label | 164f2b7b-93c7-56eb-b74c-aae44483a219 |  | note | Method - Measure, Visual
label | 55954879-c213-5dc8-8484-8997d9c968bf |  | note | Frequency - Each OHLE Structure
label | e5c5d5e6-12cd-50e0-b9aa-dae80c849b46 |  | note | Category - IP
label | 90803712-af54-5e9a-9960-b619c0bafdb0 |  | note | Responsibility - CAT5/MRPA
label | bae94ef2-b026-5f87-b2c8-709d4f3d0e58 |  | note | Responsible person - MRPA/CAT5 Engineer
label | e3944dd8-bddc-5fba-80ad-a08a8389b0bb |  | note | Verifying Documents - This ITP Signed Off
text | 185e3853-3b16-5fd8-8036-33e82070735c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Cantilever installed.
label | 72916c76-b4c0-5610-a03e-d6a497b0b3db |  | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | 2937d25a-6369-5345-a242-76e5efca9317 |  | note | Acceptance Criteria - Work instructions in accordance to IFC design
label | ae493b9b-a16c-5eeb-b0ec-f310510fd231 |  | note | Method - Measure, Visual
label | 8da15e91-9ceb-5b6c-9b7a-ffd9363377b1 |  | note | Frequency - Each OHLE Structure
label | 270fe969-e7d3-52be-99f0-ae19c188da46 |  | note | Category - IP
label | 1191c96f-1b99-59b5-90b9-72d440521b2e |  | note | Responsibility - CAT5/MRPA
label | 1a171ecb-2900-52a9-b704-33364a87b3cc |  | note | Responsible person - MRPA/CAT5 Engineer
label | a4619230-92ba-56a6-b7c6-2ee082f5dd14 |  | note | Verifying Documents - This ITP Signed Off
text | e876fabf-0620-57d8-b177-a3d4ef33efc5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Bearing type Joints TB Friction type joints TF
label | 5423b22f-52ba-53d2-855f-ac5ee8aaa96a |  | note | Reference - IFC Drawings
label | 573fad50-0d61-5bd4-8258-b4262d7dbe57 |  | note | Acceptance Criteria - BOLTS DESIGNATED TB & TF ARE TENSIONED AS PER AS 5131 and Table 8.5.6
label | 9fa1d3e7-495f-5740-a080-a6deff8bcd6c |  | note | – Bolt mark ups (in case of partial tensionening) should be visible for inspection
label | 6addbb4c-2134-58ac-928c-3d5aebcafda8 |  | note | – DTI squirts are to be visible for inspection
label | 6f02c5d0-2904-58ad-b685-2f8427d4d845 |  | note | Method - Visual
label | 8c6997de-b5dc-54e1-ab9f-968e9aeedf3c |  | note | Frequency - Where applicable/Each element
label | 93083ea4-055a-5c8f-90a3-f64fd557388b |  | note | Category - IP
label | 6ab03fce-e0d3-5242-848d-0cae03130dd4 |  | note | Responsibility - PE
label | 43fc32e5-896d-5442-a921-a59c2152e505 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 882665a2-68be-5e5c-9925-f66895636292 |  | note | Verifying Documents - This ITP Signed Off
text | 289b128e-cc79-5baf-9560-c4dbd08ea339 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Install SPS to correct height / position relative to track
label | 98eeb97b-55c3-5e5d-a63d-6f74b05346de |  | note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | d49bc80d-a8fa-5fc6-b0a3-891f4f7cc8ea |  | note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
label | ffc8eb28-0fe8-5436-938a-16daafa0a6ce |  | note | Method - Measure, Visual
label | a0e53f07-4bc6-56f8-82d8-38d6cea891c1 |  | note | Frequency - Each OHLE Structure
label | 89afd2e7-b989-53bd-822b-ae8eb97c176b |  | note | Category - IP
label | 4142806a-586a-553d-aa0c-3817ec479052 |  | note | Responsibility - CAT5/MRPA
label | 5342fb19-ee01-5b87-b0e5-ecf2b262b8c1 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 12cdb7dc-6e9d-5c57-a4f4-f747226f1b76 |  | note | Verifying Documents - This ITP Signed Off
text | caf7854a-3ef9-5e58-a8b0-cb96905f317e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Cantilever checked once installed.
label | 1d1e9baf-cf72-5ac7-acf9-689f4fffc6f4 |  | note | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet. CAT5/OHLE/CHK002
label | 60910551-84f1-5a67-a641-fbfd061eeb36 |  | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
label | aa35198b-efd7-508a-9532-0bb25081ff9f |  | note | Method - Measure, Visual
label | 5e068f40-e647-5429-a91a-afee2528e43c |  | note | Frequency - Each OHLE Structure
label | 175d8d21-7874-5005-b2f4-5907c7e057b1 |  | note | Category - IP
label | 5753d68e-1701-5c40-9c46-9660f5652712 |  | note | Responsibility - CAT5/MRPA
label | 072c91cc-ca8f-5d0d-b286-5216c49eafbf |  | note | Responsible person - MRPA/CAT5 Engineer
label | 8793ebca-4e73-544b-b07b-cf2a834632ba |  | note | Verifying Documents - This ITP Signed Off
text | 63ab84da-706f-55f9-91cf-a26a1003da38 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Base Plate Grout
label | 03cede83-307e-56ad-8ccf-75b63c65f8c2 |  | note | Reference - IFC Drawings
label | 9e171f96-5e9b-52a7-9b63-eb78f777b9a7 |  | note | Acceptance Criteria - Grout to be mixed as per manufacturer TDS.
label | aaf273a0-14bf-5430-8ddb-307cdbc70e28 |  | note | • Grout to be poured under base plate as per IFC drawings. Grout over pour is to be 6mm and cover area with Nom 50mm offset around the base plate.
label | c97fb2f9-f1df-5eb1-9535-cc73fd2225bf |  | note | Method - Visual
label | 8acb541d-f163-5920-88c8-7a8805e98d69 |  | note | Frequency - Where applicable/ Each element
label | e39559b0-e518-5720-b2c4-ef1288522170 |  | note | Category - IP
label | 7e36eb3f-15f3-5eda-9284-b2aa411ca2b9 |  | note | Responsibility - PE
label | 16d8ecfa-b5c2-5654-af1c-891dca27e6dd |  | note | Responsible person - MRPA/CAT5 Engineer
label | 4c091ce7-10b6-5890-be1e-a8c42a0232ce |  | note | Verifying Documents - This ITP Signed Off
text | 493d12cd-88c9-5e3d-9fce-7add77cfe733 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Installation of wire supports at the correct height and stagger
label | 539adbc3-dcf4-55ee-be2a-325571885060 |  | note | Reference - Install as per design
label | f69c7e4a-89e9-5854-ab64-106f8e7445fa |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | e99b72a1-7ad6-549f-b16f-04a4876f67a6 |  | note | Method - Visual
label | 36980f2f-bc58-5250-8346-3504777c7855 |  | note | Frequency - Each OHLE BWA Structure
label | d94c9af4-dddd-5192-b51a-c0dda5f3283b |  | note | Category - IP
label | 6845e37e-314d-563a-8c8f-5f225055964c |  | note | Responsibility - CAT5/MRPA
label | f6ed7c85-c1e6-5534-b7fb-cf5e6abc171f |  | note | Responsible person - MRPA/CAT5 Engineer
label | 7459bd7c-eabb-575a-85ca-b5fac33eac47 |  | note | Verifying Documents - This ITP Signed Off
text | cf0923e4-7127-5b39-9d22-5097963929dc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Install to correct tension
label | 782f3c8c-be77-5b78-9018-6e8e58a79fe2 |  | note | Reference - Install as per design
label | 7669bb2b-579d-580c-a199-73394edd8584 |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | 98b9bbde-42c8-52a4-9dea-ac8ce0e49df3 |  | note | Method - Visual
label | 34e054d9-fb74-5655-a983-e1f4d20bfc62 |  | note | Frequency - Prior termination
label | 113a1880-5aaa-58e0-90ee-c47659cf4bdb |  | note | Category - IP
label | ad11b4f3-8db6-5730-8b1e-3d67c693489b |  | note | Responsibility - CAT5/MRPA
label | 26b458b2-78e9-5eb0-bf17-88fdfcf6f51d |  | note | Responsible person - MRPA/CAT5 Engineer
label | da636222-c2a3-57bb-ad69-2fd8c2f56435 |  | note | Verifying Documents - This ITP Signed Off
text | 6570bee7-7c2e-5dc3-9ef9-186528384b97 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Defects/Temporary Works
label | b7fdcbb1-c935-54f3-9e03-139089ec12bc |  | note | Reference - IFC wiring layouts, cross sections and design drawings.
label | a331a43b-777a-5c6f-9fa7-0d269661b744 |  | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
label | 71d61591-7fe3-552f-9bc5-f2414166c90a |  | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
label | 7a67192f-51df-512a-a193-dd0c62120e27 |  | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | 8a1da561-485a-532b-a3ce-0ea94ea5000a |  | note | Method - Document Review, Visual
label | a9eca315-b848-5ef5-af84-69891bc8424e |  | note | Frequency - Each OHLE Structure
label | 4a478cd6-a6ab-5d50-b011-52df20e93f48 |  | note | Category - IP
label | 82272085-0e5c-5298-b092-111f410bc0d1 |  | note | Responsibility - CAT5/MRPA
label | bb855b39-aee0-59ad-841f-ef4a5e4f0924 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 1c15292f-aa0f-5156-b2e6-a69ec820e23c |  | note | Verifying Documents - This ITP Signed Off
text | d99ccbce-7b98-5cf4-903f-72a867c542a4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
label | a67cccf8-2a0d-5571-bd79-8cbf5c1980f8 |  | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
label | eb4f5970-6170-542c-be3b-03bfd0571f48 |  | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
label | 21dd5b86-030d-5d7e-926c-fe2a023f4d73 |  | note | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
label | a3c24381-e773-5a9f-89e3-7135dd09e59d |  | note | Method - Document Review, Visual
label | 12870edc-9409-5622-a011-eec68ce26af3 |  | note | Frequency - Each OHLE Structure
label | 1a3336ce-fb6f-5921-a6a9-ca628ac26423 |  | note | Category - IP
label | 41378d87-fec4-52bd-9b0f-47dc5501dff3 |  | note | Responsibility - CAT5/MRPA
label | 11adcea8-0168-568f-9074-00f930ead2b7 |  | note | Responsible person - MRPA/CAT5 Engineer
label | f0f70156-0135-5099-a9f5-c407ef1af77c |  | note | Verifying Documents - This ITP Signed Off
text | 0927b0a2-775a-5e13-91e3-c79ea5f94406 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | e55c9aba-0ac2-5905-9535-e7e494f72dbe |  | note | Reference - MTM Quality Management Plan
label | 208b0531-628b-532b-b163-79daa7369fd7 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | e091dedd-d16b-585a-9122-05ae465f02c3 |  | note | Method - Document Review
label | 85031bd7-60d9-5ae9-92ea-6eb70c964bff |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 4552a864-685b-546a-8df6-0e34156576c4 |  | note | Category - HP
label | 8ca1cd12-9e96-558b-a39c-f36f5f68b8ce |  | note | Responsibility - CAT5/MRPA
label | 7e7f0af0-24f5-5303-9d15-2cba98f82752 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 5fad917a-8b9f-56eb-b182-59cd7ce74386 |  | note | Verifying Documents - This ITP Signed Off
text | aadf3dfc-60a4-545a-b43b-9fb73f545a9b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | a8f47ae1-9e40-58c8-9e85-fffeff467ee2 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 2230d07b-e89a-59a5-a6b2-64156b49655c |  | textbox | Name:
text | 8a49cbd4-0edf-5503-9a02-a05e2b7fe0da |  | textbox | Position:
text | 34f1fedc-b615-5efb-b162-42491ff8e638 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-048-CIV-Calder - Stormwater Drainage Supply & Installation | itp |  |  |  | Yes | ITP-048-CIV-Calder - Stormwater Drainage Supply & Installation - Rev 0 | 1c13b79f-05b4-4abd-b61f-9be7a4ee36b9
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 54cbbd25-0217-5f93-8c04-32ab25705d02 |  | note | Document Title: ITP-048-CIV-Calder - Stormwater Drainage Supply & Installation
label | 42c73e1f-b4fe-5e17-a4e6-fe786d9930e6 |  | note | ITP Description: Stormwater Drainage Supply & Installation
label | 1072443b-4ce6-5d29-99dd-1e5558e3eec9 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 97538d00-08c4-5a58-9b5e-371d88c3ab2b |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 0b1049cc-c86a-56cf-a523-601b79eabb9d |  | note | Revision Number: 0
label | c5684dc8-88cd-5f91-a657-01aa964aac1f |  | note | Revision Date: 19/07/2023
label | 2c42a650-f171-5637-9c8a-f3c8221f848a |  | note | ITP created by: Ethan Caruana Smith
label | 3a4fd5a2-f344-530b-8cff-3ad6650804a5 |  | note | ITP approved for use by: Pradeep Talasila
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 049d257f-d67a-5254-9e87-432b7942d94f |  | note | Reference - VicRoads Section 701 (May 2020)
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 1373b251-3ace-5e65-b601-89dd12746253 |  | note | Reference - VicRoads Section 705 (June 2021)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 290abb78-b920-58d1-882c-07f26b057f92 |  | note | Reference - IFC Drawings - package 13
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Drainage Reinforced Concrete Pipes (RCP)
label | 5133ef34-9f0e-5f1c-a55a-73ea66b52c6f |  | note | Reference - Section 701.04, Section 701.05, Section 701.09
label | 60fa969a-ef98-52e5-badc-796c6863f8f3 |  | note | Acceptance Criteria - Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and Sections 701.05 & 701.09
label | 1d9b6d4d-27f2-5f39-b007-284f3632a292 |  | note | • Precast reinforced concrete box culverts shall comply with the requirements of Section 701.04
label | 04545dc0-1ab0-591f-8f08-70a29a845bb5 |  | note | • Rubber ring joints shall comply with the requirements of AS 1646
text | 38bbd1f4-2d65-5143-a9b1-6247293e3f6f |  | textbox | Enter: Teambinder Material Approval number
label | 93b9fe18-2b6f-5666-a865-555cefa2e92c |  | note | Method - Document Review
label | d79391aa-d611-5d18-aaa6-c67571466739 |  | note | Frequency - Each lot
label | 594117ee-77f5-5ab2-bb85-e26d59148d12 |  | note | Category - HP
label | bf3f0b6e-d05d-5464-8cf9-3c441e8eaa6e |  | note | Responsibility - Nominated Authority
label | 4878f0ce-de8f-51a7-82a5-2415a004563d |  | note | Verifying Documents - Teambinder Material Approval
text | 769d6910-4e6b-5e3d-a923-aa280010a925 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Drainage Flexible Pipes
label | 2719ec57-48eb-52f2-bf32-78fbf41e4fec |  | note | Reference - Section 701.08
label | 54afc51d-7959-5eca-a6ca-cee0aada02ec |  | note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
text | 1893723f-e63d-5060-b679-921de47f50ee |  | textbox | Enter: Teambinder Material Approval number
label | 5ad4e039-2896-55b3-8b69-ba5ce5ccb4d8 |  | note | Method - Document Review
label | 28c02fcd-976e-5151-b77e-bc0f9325dffb |  | note | Frequency - Each lot
label | a488a7ae-65cf-59ac-aa33-b0dcf57394c9 |  | note | Category - HP
label | cf212d1a-bc40-53da-b07b-9a464ca7db40 |  | note | Responsibility - Nominated Authority
label | 50a55385-8b8e-5017-90fc-cc6b36b4393b |  | note | Verifying Documents - Teambinder Material Approval
text | dfe786c1-a388-5026-97c3-63068e294d77 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Precast Drainage Pit
label | f0d33795-6cf4-5e2c-89b2-cb962804e517 |  | note | Reference - Section 705.07, Section 705.04, Section 705.09
label | 4259a9fd-ffa0-506a-b45d-85fb802bb345 |  | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
label | 0fbdbc27-1134-5b87-83d7-3d91964e65f6 |  | note | • All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
text | 5ff9ae96-528a-53c9-8c59-720be22cbb93 |  | textbox | Enter: Teambinder Material Approval number
label | 83dae22d-3dd4-539c-8ad9-b87f915e213b |  | note | Method - Document Review
label | b05605b5-c370-548e-a9bd-8a5b67ae4d42 |  | note | Frequency - Each lot
label | 9862f83a-a3a7-5540-ad14-a1b7d1b9ce5b |  | note | Category - HP
label | ce3276fb-1124-57dc-973d-69937c3ceade |  | note | Responsibility - Nominated Authority
label | 254f27fc-ce7e-51b3-b351-efb9371d71a8 |  | note | Verifying Documents - Teambinder Material Approval
text | 6deee45d-38ca-55a0-9dd0-bafda30155c6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Cast in Place Drainage Pit
label | b0c6263a-4906-5eeb-bed0-6a05159afefb |  | note | Reference - Section 705.06 IFC Drawings
label | 4c574fbf-66de-5d27-adc5-9762d785a5ce |  | note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | 7356e754-fcfb-5158-b07d-ab82d4f69446 |  | note | Method - Document Review
label | c8012b05-25d5-55fc-a331-524090c05bca |  | note | Frequency - Each lot
label | 2cd6f092-3b20-573f-8a36-6f31eb417ee7 |  | note | Category - HP
label | 1552e327-2f0f-5c95-8180-dd0104a1610f |  | note | Responsibility - Nominated Authority
label | 8583b9f9-0559-5e0c-9103-743cc4278ea2 |  | note | Verifying Documents - Teambinder Material Approval
text | adb3fb5f-7143-5e51-a951-971fe87f493f |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Drainage Pit - Step Irons
label | de1765f1-a411-599f-ab5a-14b9678c3e3a |  | note | Reference - Section 705.04, Section 705.12
label | 3e26662e-84bf-510e-b3f6-d42424d71596 |  | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | bee12f83-908c-5b48-82cd-93c14abc4787 |  | note | • Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
text | ba8abbd4-9dc4-55f9-80ee-e47b2f3f5d49 |  | textbox | Enter: Teambinder Material Approval number
label | 99b5df9e-9c16-547b-8db6-0e7acb88655f |  | note | Method - Document Review
label | 6272a703-8f4d-5f92-a46f-463b35b49417 |  | note | Frequency - Each lot
label | df43af24-e5f9-578b-a8d3-ea92460ea8a4 |  | note | Category - HP
label | 022e485b-8cd8-5a48-bfcd-facc399c0a54 |  | note | Responsibility - Nominated Authority
label | 0177011a-dcb4-5593-9ecf-79e631c2132f |  | note | Verifying Documents - Teambinder Material Approval
text | e7f9e350-cb0a-507b-870f-3d7359d1e940 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Drainage Bedding Material
label | 92e4115c-4958-5781-b554-bf6a0f20ebc2 |  | note | Reference - Section 701.09
label | 424a6ae9-cf56-542a-a746-425541df9ac4 |  | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | b7242711-1be5-5a69-a5ac-d51aae795379 |  | textbox | Enter: Teambinder Material Approval number
label | 8d2e688d-6ca9-52a8-88f4-53fe73f2d64f |  | note | Method - Document Review
label | a0500e5d-b26a-544a-99ad-58f9d349ad7c |  | note | Frequency - Each lot
label | a2331930-1dea-5021-a18b-54000a2ea669 |  | note | Category - HP
label | 8d52516d-7bc1-5423-9d05-8301e55b1d82 |  | note | Responsibility - Nominated Authority
label | 66026fc8-7e6c-56ba-be5c-c1ebfc74f4e0 |  | note | Verifying Documents - Teambinder Material Approval
text | df192745-9d6d-55fc-a48f-006c81689cff |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Drainage Backfill Material
label | a5660455-5648-51f1-b7fb-301f2a5deba1 |  | note | Reference - Section 701.09, Section 701.19
label | eb8c7bb1-a2ea-5db9-a7ec-0c8b9eaecb67 |  | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
label | e757e716-dab5-5cd7-895a-67df1ae343c8 |  | note | • Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
text | 61bf1fb8-75bd-5da6-8e72-349d8471ce1d |  | textbox | Enter: Teambinder Material Approval number
label | 864c98a8-82bb-565f-a93e-7b180f524d1c |  | note | Method - Document Review
label | 22480f11-8375-57bb-852a-5c1c1528c943 |  | note | Frequency - Each lot
label | 7b9585be-690d-5fb7-b91a-397f553be0af |  | note | Category - HP
label | 5f601394-7c21-52f9-8574-5e16fd000b39 |  | note | Responsibility - Nominated Authority
label | 16fe453e-e1eb-55ec-b9b6-45254763d6a4 |  | note | Verifying Documents - Teambinder Material Approval
text | 8eba1970-91ea-5481-8588-8c186a8afb48 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries-Documents
checkpoint-status |  |  | checkpoint | 3.1 - Subcontractor ITP (where required)
label | 0362af02-66ae-56aa-b8e3-143176e6cebc |  | note | Reference - Subcontractor ITP
label | 74fe2701-1e67-5a33-a25f-d5999fd059bf |  | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
label | f4da3484-f959-5392-9bc5-df6fa0c81d53 |  | note | Method - Document Review
label | e4b52356-3e31-5a47-80de-822155694525 |  | note | Frequency - Each Lot
label | 741383f5-65b6-5f2e-b248-01222b681a81 |  | note | Category - HP*
label | 9d7642fa-522e-5a59-95a5-399135116f82 |  | note | Responsibility - PE
label | e0f5210b-b100-5b1c-825c-947dbf860573 |  | note | Verifying Documents - Refer to ITP
text | 4587736f-0ffe-544c-8863-dc96ee2c1506 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out - Pits & Pipes
label | 70d94c64-0326-55f9-aed8-1e9443ff6694 |  | note | Reference - IFC Drawings Section 701.10
label | dd704398-4feb-5fd9-b7de-203238535d62 |  | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | 64d2893b-b9d5-5492-9634-59836d22c7a4 |  | note | • Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | 4d466f72-d787-5032-9238-749becd181fb |  | note | Method - Survey
label | 9756bab9-b149-5172-baf5-acee85f08548 |  | note | Frequency - Each Lot
label | 7d36971f-7c74-5382-98c2-bc8555c48b17 |  | note | Category - HP*
label | 8fc73ffc-44c2-519d-b384-d4c9b16b960b |  | note | Responsibility - PE
label | a721a0a8-2053-5220-8bf4-ddb3321ce645 |  | note | Verifying Documents - IFC drawings - package 13
text | 1af63d70-f385-5962-b8f5-e5fcb3ce30b0 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Pits - Excavation
label | caa95059-ace6-5199-9990-4ad82c896447 |  | note | Reference - IFC Drawings Section 705.05
label | 0df875a6-d97e-58ed-abce-9e62aba8665f |  | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
label | 005a2253-2af7-535b-b65c-d6f3aac7dcf4 |  | note | Method - Visual inspection, Measure
label | f0847ad8-fdc3-539b-9b13-d8141a2ac768 |  | note | Frequency - Each Lot
label | c320091e-83a4-50b1-960e-e9b2d0dc85ce |  | note | Category - IP
label | fba45ade-d691-57f9-b739-4c15f3139464 |  | note | Responsibility - SE
label | 0a3be269-25d8-5ce4-961b-34baa0fee62b |  | note | Verifying Documents - IFC drawings - package 13
text | 3f0fbeb9-cbf6-56bd-b405-b218c9fb5303 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Pits - Placement of Bedding Material
label | 609fab17-84d4-5385-b21c-c8c916a554e2 |  | note | Reference - IFC Drawings Section 705.05
label | f3e827c5-5f0a-5493-89aa-233561c74707 |  | note | Acceptance Criteria - Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
label | e9d78fb0-ba1d-5577-8796-a215571d5375 |  | note | • > 80mm for clay foundations
label | 8a7ca185-d9f1-571e-8179-dcfdbff540a0 |  | note | • > 150mm for rock foundations
label | e2ca7365-89fc-5740-88bb-0a1fe4cbb501 |  | note | Method - Visual inspection, Measure
label | 9b82bc28-c862-5f94-93af-31ff125b58b6 |  | note | Frequency - Each Lot
label | c3b42d33-2e82-5270-b05c-286292481427 |  | note | Category - IP
label | bda556e7-9678-564a-af54-601482fe6436 |  | note | Responsibility - SE
label | f466157f-630c-563e-b50f-0bf19e6e8284 |  | note | Verifying Documents - IFC drawings - package 13
text | 4011c2ae-7d9f-50c9-b6a9-a9c1e6354ce3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Pits - Bedding Testting
label | 30c88298-f054-5a0e-9947-59bb39746955 |  | note | Reference - IFC Drawings Section 701.20
label | efbe308c-b7fd-5388-9e83-ef80f4c80a3f |  | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | d8170177-29fc-5785-9e23-84c3c2dafca8 |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 29cc3f78-d7a9-56f9-89f3-a7e26d461c1c |  | note | Method - Compaction Test
label | 71aa1913-9300-510d-8913-56147226a8fb |  | note | Frequency - Each Lot
label | 7d473651-ab4c-56ab-86a1-2838bfdb5322 |  | note | Category - IP
label | e253adbc-c019-509f-9768-640f74766ada |  | note | Responsibility - SE
label | 00cc67cf-1598-58e7-b016-820aa2cb6e15 |  | note | Verifying Documents - Compaction test results
text | 181ec86c-9008-519a-8cfd-3f9fc4eb1ff1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Pits - Placement of Precast Drainage Pit
label | 8445a6b9-8a3d-514e-8157-37f9148cb128 |  | note | Reference - IFC Drawings Section 701.10
label | c6fb90dd-63b7-5bc1-a6bf-1c2728b8b0fb |  | note | Acceptance Criteria - Survey pick-up to verify:
label | ccfdefae-6536-5657-9d8b-dcd0e4f4e530 |  | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | 0bc0715d-666a-5418-93bd-ab4ddbc06334 |  | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | 42ae0187-5739-5608-b095-b759dd7ba63c |  | note | Method - Visual inspection, Measure
label | 3d954ba7-3fca-5eeb-bdfb-8de74a14d406 |  | note | Frequency - Each Lot
label | c6f71124-5932-5f7e-a29c-414e6a2fc497 |  | note | Category - IP
label | 4fa75a0f-ad76-5d98-bb8f-4493b007fd6f |  | note | Responsibility - SE
label | e3910c1c-1b87-513a-873b-512a664cf162 |  | note | Verifying Documents - IFC drawings - package 13
text | 173c371a-c9c3-5cdc-b815-cce2a719bfc8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Pits - Cast in Place Drainage Pit
label | 11b9adce-0de9-5265-981f-52b43044d990 |  | note | Reference - IFC Drawings Section 705.06, Section 610, Section 611
label | 66eb6791-a02b-5420-a903-48a950aef3e5 |  | note | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
label | 602e3814-ca47-5c16-9e5b-6384a1a445b4 |  | note | • Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | 1842684d-4e3f-5baa-b3a7-6face97eea13 |  | note | Method - Survey, Measure
label | 6a0db754-2204-5b87-b445-f024a2c0ebb7 |  | note | Frequency - Each Lot
label | fb5c4c5a-ebe5-5a27-be94-7fb7c2f09259 |  | note | Category - IP
label | 11db52ba-3dd5-5b3c-82db-c3e00b0c96d3 |  | note | Responsibility - SE
label | d2bd30c4-1f9f-52fe-ab8f-97a31689a72a |  | note | Verifying Documents - IFC drawings - package 13
text | 18e8b6c4-67ec-563b-816d-88c9c5d15c75 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Pits - Jointing & Drainage Connections
label | aef13145-6a72-51e8-a6c1-a49a24fa9dd2 |  | note | Reference - Section 705.11
label | 26eee097-7ab9-533a-bb3e-15befbbf2076 |  | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with Section 705.11.
label | a6d44c82-1458-5642-91dd-3f7239a9abe1 |  | note | • Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
label | a97984fa-5060-54a3-9cca-10a4c5b9f7ab |  | note | • Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | 4aa122b2-4eb3-5fbf-b6c1-3d502ab6295d |  | note | • Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | 85ebb87e-6876-54ab-a791-198b255482c0 |  | note | Method - Visual inspection, Measure
label | 2c0242e6-09e0-5907-9326-7f28423d5aa4 |  | note | Frequency - Each Lot
label | 12165db4-9657-537a-89fa-762c3e28be9e |  | note | Category - IP
label | 776ac49f-e001-513f-8e2b-e2e218704adf |  | note | Responsibility - SE
label | a68b4be4-f8fa-5ace-9228-c4a1650de199 |  | note | Verifying Documents - IFC drawings - package 13
text | 90747576-042a-5739-a315-5d5c7ba662eb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Pits - Shaping of Floor
label | 11a21eee-7f8d-5091-8e87-a3fe26b4dcb0 |  | note | Reference - Section 705.13
label | c3844a26-6931-5129-85bd-f4947853cc6f |  | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
label | 5fbcb750-2786-58ba-8e35-42be64ef7263 |  | note | Method - Visual inspection, Measure
label | 2f1c57e7-accf-5775-bcb9-21bdb4d2a645 |  | note | Frequency - Each Lot
label | 012e16f5-31dc-5eed-8a04-7e6e01bdd01c |  | note | Category - IP
label | 5279eeef-cf53-5055-a392-30e38e8e1431 |  | note | Responsibility - SE
label | 771a23d8-b310-5318-8cd3-28c3c1246ca3 |  | note | Verifying Documents - IFC drawings - package 13
text | b5efdb44-349e-5ed2-8fea-848691c36cd7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Pits - Step Irons
label | 40a287a2-a3d8-56ec-ade2-04c5881fbb4e |  | note | Reference - IFC Drawings Section 705.12
label | 20ceb859-c1dc-5169-aec8-a34318bd7296 |  | note | • Brimbank City Council Engineering Detail 275
label | 724e50b7-ddaa-5fdf-b350-a980cb98fb73 |  | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
label | 01ab8bb9-deea-5046-bafa-1bcd43095040 |  | note | • Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | 98f31534-53ac-502c-92ef-e19653b495cc |  | note | Method - Visual inspection, Measure
label | 169e9152-ac78-5188-8233-9a9bcd1bd1f3 |  | note | Frequency - Each Lot
label | 64427089-cd42-5da3-8cf0-83a58241e5d2 |  | note | Category - IP
label | 9b336f7f-c7b9-573e-bc89-19582b1842cd |  | note | Responsibility - SE
label | ad0afc5b-c6c1-5289-8523-68eb0d7aaa29 |  | note | Verifying Documents - IFC drawings - package 13
text | 3fea7099-4584-58e1-b04c-6222185ca8cc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Pits - Fitting of Covers
label | c974319c-a80a-55a8-90df-55f9cbf46fd6 |  | note | Reference - IFC Drawings Section 705.17
label | fa4568e0-8706-57b9-8ea3-66e2b131097e |  | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
label | 7e734e95-8d50-516c-b6c2-0d4f5d0d3ad0 |  | note | • Height shall be within 10mm of the design level.
label | 8cac3de9-c7b1-558e-9c08-87c7c76f56ca |  | note | Method - Visual inspection, Measure
label | 1bd06876-0670-5640-bc1e-97a7286bd1f2 |  | note | Frequency - Each Lot
label | e5b15a2b-280c-5f2f-8a8d-87edfee396e3 |  | note | Category - IP
label | fe506aea-af53-5eb5-9e98-071f3f1ebfc1 |  | note | Responsibility - SE
label | e2be20f2-4046-54c3-b10b-b0045cef53f5 |  | note | Verifying Documents - IFC drawings - package 13
text | 6a2b9740-d520-5755-bbcc-ac7a97bb5da0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Pits - Pit Lids
label | 0c45472c-5923-5b1c-86cd-21d85703da0a |  | note | Reference - IFC Drawings
label | fbc0a655-d3d6-501a-8f7c-d9bb2e23d3b7 |  | note | Acceptance Criteria - All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
label | 87cac1bf-cfc6-5b7f-b83e-af51beb10ab6 |  | note | Method - Visual inspection
label | c8be6773-b101-516a-8195-b8d4743f95f8 |  | note | Frequency - Each Lot
label | 12853f30-dfc1-521a-af48-b297d4951952 |  | note | Category - IP
label | 0003b34d-d6c8-5bd7-8814-0f49cbb1aa69 |  | note | Responsibility - SE
label | 10e02d3c-da54-5add-9402-954722e52bde |  | note | Verifying Documents - IFC drawings - package 13
text | 36a30aad-afd0-5ecc-b140-9b244fb9e3b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Pits - Backfilling Around Drainage Pits
label | 178e5b87-8106-5221-99a2-27e38afb9038 |  | note | Reference - Section 705.18
label | b131c02f-261d-57dc-b77a-974334f5c1f4 |  | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | cf2f2e73-08ae-50a3-9747-02ccf0ee94e8 |  | note | Method - Visual inspection, Measure
label | 6f61a433-63f9-55f9-867b-f61365bd85b5 |  | note | Frequency - Each Lot
label | 8ddcaab2-879c-5d47-b0d3-3f8344c33171 |  | note | Category - IP
label | 990993e6-7ca6-5e0c-b636-2ede6d5f79dd |  | note | Responsibility - SE
label | 58ed6474-63ee-503a-8879-c22329a96c36 |  | note | Verifying Documents - IFC drawings - package 13
text | c24005f5-35c8-5c2a-a895-2c956031df36 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 - Pipes - Trench Excavation
label | 70f598f8-8a81-51da-ba68-7e612d466779 |  | note | Reference - IFC Drawings Section 701.15
label | 3e383ca7-800f-530d-889d-6edad882bd3f |  | note | Acceptance Criteria - Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
label | da5cd7e0-3e89-54a4-b0a0-849a087fc333 |  | note | • > 300mm, < 600mm for RCP
label | 35dcaf5f-7278-551a-aef4-1ef908d3cfb7 |  | note | • > 150mm for Flexible Pipe
label | 939af018-0859-54ad-8d35-62179dd2f936 |  | note | • The base of the trench shall be compacted to refusal using mechanical plant.
label | afae5658-0092-52f5-9523-dd40c21b40ff |  | note | Method - Visual inspection, Measure
label | 6fe0ddd4-9fff-5ff9-a084-181a9f1bae48 |  | note | Frequency - Each Lot
label | 517bd21e-590a-57a8-a514-212e98cfb3c1 |  | note | Category - IP
label | cd68f300-3f13-5e97-a37d-f1d9e118998d |  | note | Responsibility - SE
label | 30de6eda-2a4b-53a4-bd58-e87c077dab9d |  | note | Verifying Documents - IFC drawings - package 13
text | 84b39d09-9072-509e-8217-361460d00cd1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 - Pipes - Bedding Placement
label | 39b60e51-97dd-55a5-9364-7ca2537d65df |  | note | Reference - IFC Drawings Section 701.16
label | c4a65476-e603-538b-84f6-fd22522a704f |  | note | Acceptance Criteria - Bedding material shall be provided and placed in the full width of the trench to the below minimum:
label | cd28d9ca-ab30-5164-8c8f-ebe9298a09dd |  | note | • > 100mm where D<1500mm
label | af9f4397-ef7a-59fc-8e41-e9dadf561ca0 |  | note | • > 200mmwhwere D≥1500mm
label | 73d173e5-cf31-5f96-841c-ba95e5df225f |  | note | • Bedding material shall be placed and compacted in layers <150mm loose thickness
label | 5f7b10ac-fad9-5b93-a873-db644544b6c8 |  | note | Method - Visual inspection, Measure
label | a57efc41-4bc3-5d88-b84e-04b49aceed04 |  | note | Frequency - Each Lot
label | 07897e3a-db62-5748-935c-407b60db9a71 |  | note | Category - IP
label | c706220d-d9f2-5fb6-9eeb-d061b57cc91b |  | note | Responsibility - SE
label | ea9b5601-a046-5122-9ee9-c8bd1c3e7a20 |  | note | Verifying Documents - IFC drawings - package 13
text | df3c6be1-a4d0-50c3-824a-93e0069aa5d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 - Pipes - Bedding Testting
label | fd0dd52e-857a-58e2-8649-bd8cfc704be3 |  | note | Reference - IFC Drawings Section 701.20
label | 2b30d468-d416-594a-a02a-335673a91ec8 |  | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | 0333d10c-86fe-53d3-9d6c-5a23e873a324 |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 71405129-e773-5876-bd01-f48f9913bf23 |  | note | Method - Compaction Test
label | fe6f172a-98a1-50d8-8c3b-e4a8518cab43 |  | note | Frequency - Each Lot
label | d35efc8a-9dbe-5f16-81b4-484747d42ba4 |  | note | Category - IP
label | 972fd341-9d18-5f52-9ecb-53a24adf158a |  | note | Responsibility - SE
label | 6b8ca982-9103-56b3-9bf0-48fcf9a024d5 |  | note | Verifying Documents - IFC drawings - package 13
text | b2c83092-6cc7-569c-af07-f30299d1c5d7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 - Pipes - Placement of Pipe - RCP
label | 79d8d38a-8c0b-570f-b2c0-0dcc098127d6 |  | note | Reference - IFC Drawings Section 701.17, Section 701.20
label | bae2843e-abe2-5339-a10c-aaa431adfbc1 |  | note | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
label | 8bfb2d50-bc59-504b-ac94-4444a189b866 |  | note | • Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
label | d5cfe77b-5ea8-5053-8c24-6936ab3955a4 |  | note | • Gaps between spigot and socket are in accordance with the manufacturers specifications
label | 32855b46-f922-5c71-bc08-3dc9943694e9 |  | note | • The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
label | cb9033b3-5d19-563c-af50-19ac6dad9df9 |  | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | b25b3778-9de8-5ec8-92f2-098c4b9a581c |  | note | • The spacing for multiple row culverts shall be as shown in Table 701.171
label | 4a7b9c53-4688-5330-9298-59628ac15ded |  | note | Method - Visual inspection, Measure
label | 71644f2e-28ba-5aa0-9925-174ea148acf1 |  | note | Frequency - Each Lot
label | 8b2f2ee0-b87a-52cc-baee-41b1509db581 |  | note | Category - IP
label | 10359d91-0351-586c-bd3e-9e290ab0ea9e |  | note | Responsibility - SE
label | 70a78be1-2032-529a-abc6-448e838bc2fb |  | note | Verifying Documents - IFC drawings - package 13
text | e4ddb5ec-2cde-5844-aa05-b29ba0066518 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 - Pipes-Placement of Pipe - Flexible Pipe
label | b0c2ab9d-57ef-5ded-bd87-5d462dd85064 |  | note | Reference - IFC Drawings Section 701.17, Section 701.22
label | e5938a38-d81a-5eb0-b450-73409eaabd4a |  | note | Acceptance Criteria - All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
label | f768b84b-7c54-5236-889f-b1e3b4476fab |  | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | 3a05e9d5-9e77-5e8e-b599-40d900b42864 |  | note | Method - Visual inspection
label | a8adff73-e9f9-59fe-817d-d5fe06bfd66e |  | note | Frequency - Each Lot
label | 0c4031c2-804b-5b2d-ab33-78dd4d74afd3 |  | note | Category - IP
label | 5ee5fd6a-571c-5017-bbc8-e7e41cbc80d2 |  | note | Responsibility - SE
label | 35add517-2564-5d1c-8c5b-598fd9a4982a |  | note | Verifying Documents - IFC drawings - package 13
text | 6bd024ef-bd3f-526e-ac5f-13faab451d91 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 - Pipes - Lifting Holes
label | 9f8fea2c-7e03-5cb7-b418-e0678490dce8 |  | note | Reference - Section 701.18
label | 9441d552-ba94-5e23-8e17-a4e17b05e6c0 |  | note | Acceptance Criteria - Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | 18c2728b-2318-5b6f-8a38-ed0c0966679c |  | note | Method - Visual inspection
label | 4a7e31f8-4d8f-5369-be55-ebe430fb3c3b |  | note | Frequency - Each Lot
label | 97a30247-b025-5c03-ba08-c60ab50b72eb |  | note | Category - IP
label | 62dad747-3607-5570-9953-4f90c2f600a7 |  | note | Responsibility - SE
label | 73edc9ce-b190-59b3-96d5-7a2a7f4bfe68 |  | note | Verifying Documents - IFC drawings - package 13
text | 7f98c8f4-ed28-5bd9-85c2-1d7a63cd6758 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 - Pipes - As-built survey pick-up
label | 65fdd3d3-74b9-5c3d-ac92-a9b001b83678 |  | note | Reference - IFC Drawings Section 710.10
label | 4618d72f-c6c3-5b83-a951-b278234fa0ed |  | note | Acceptance Criteria - Each run of underground drainage shall be Survey verified prior to backfilling.
label | f45f9038-e968-52e2-9528-597f2c8c9ece |  | note | – Offset pits to kerb +/- 20mm
label | 69c4d7c0-316d-51b2-85cb-7691b8f5d11a |  | note | – Plan location pits not adjacent to kerb +/- 100mm
label | a0ef3f04-dcc0-59a9-aa86-aab81cccb5d3 |  | note | – Invert level of pipes at pits +/- 50mm
label | 9fa74f1a-7edc-5d7f-a50f-4764f6e59cb7 |  | note | – Departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
label | 15298798-008a-5250-8001-f19077b40ae3 |  | note | Method - Survey
label | cc50fb2d-9898-5685-9469-49c0814208f0 |  | note | Frequency - Each Lot
label | 04be207a-fdc3-5150-8148-4758b722583a |  | note | Category - IP
label | b886bd9e-2a22-5165-8ab8-8116b0a6d842 |  | note | Responsibility - SE
label | 69b97f1a-6cd7-5db9-b3b9-ff441fb04c83 |  | note | Verifying Documents - IFC drawings - package 13
text | 86c1c59a-15f4-5a3d-93db-c181d3d47b0a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 - Pipes - Backfill Placement
label | 96c3e9ad-2cf2-5da0-bc7e-b2c75dec5bcc |  | note | Reference - IFC Drawings Section 701.16
label | f5f8ae20-1eab-5d73-9a60-08db62f9a929 |  | note | Acceptance Criteria - Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
label | 1dcca698-0276-51bf-9c7f-904510874eec |  | note | • Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
label | 52a13dd8-f804-5253-a677-74458ba968eb |  | note | Method - Visual inspection, Measure
label | a5a123bf-c02c-5a61-8fa4-d5b8329843ac |  | note | Frequency - Each Lot
label | 620523bb-cb8a-5503-921f-ba0c1b50f821 |  | note | Category - IP
label | 21a28aab-c82e-5f7f-9a55-473cf9814576 |  | note | Responsibility - SE
label | d78ec0b4-ea00-5a74-b460-10451afce3a6 |  | note | Verifying Documents - IFC drawings - package 13
text | b9786838-80ea-5cf2-9292-e42323a83b22 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 - Pipes - Backfill Testing
label | 8811f545-8abb-5afe-88ce-e518460342bb |  | note | Reference - IFC Drawings Section 701.20, Section 701.29
label | dd8b82cb-edc1-51c2-8e40-5358f688259b |  | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | 5d9fc6f0-26a4-5fe1-9f56-27a0df218c6d |  | note | • Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | e956664b-a745-58b3-ac97-e575abf8c622 |  | note | Method - Visual inspection
label | 83d8a346-7eff-5697-b8be-515e585d7c0b |  | note | Frequency - Each Lot
label | 79333351-1ce3-5a6e-bc64-51c117c2376a |  | note | Category - HP*
label | a0ac511d-0776-5f38-aba3-ddf6079c7af2 |  | note | Responsibility - PE
label | a4d07d83-1238-553e-96be-e6d1e7055b4d |  | note | Verifying Documents - Test Report
text | 9e7bc270-69ba-507c-9581-2692faef88cd |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - Flushing & CCTV
label | 17cf6dc4-ffd9-58f3-8caa-43599bf28176 |  | note | Reference - Section 701.28, Section 701.30
label | 7a2e3fc4-2ec3-5d1f-9de3-f1c2d3f09c11 |  | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | 0196d779-71f3-5cb1-96fc-6489ea45a624 |  | note | • All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | 1bb3880f-6316-5a42-86f3-06eed6286cf8 |  | note | Method - Record Review
label | 3a614928-5cf0-5b09-8fd2-5980501e453a |  | note | Frequency - Each lot
label | 2ae0775d-f109-56e2-8b17-4477a4d707e5 |  | note | Category - HP
label | 8107d998-7373-5889-a53d-f261c7e3375c |  | note | Responsibility - Nominated Authority
label | 6b5144ec-2e05-589c-884a-15b88d90b78e |  | note | Verifying Documents - This ITP, CCTV Reports
text | 018228e7-c6cc-5d84-a54c-2a9283fbd8b2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - As Built Survey
label | 5ae75aaf-1fc7-55ef-8422-197163abcd43 |  | note | Reference - Section 701.10
label | eb0c283b-efc6-50fd-b6fd-e44f5ca7a3f3 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | 0daf43af-98e3-513e-9b61-8c5691b72d87 |  | note | Method - Document Review
label | aef88904-4655-56cd-9810-656ff45a04ea |  | note | Frequency - Each lot
label | 226820df-c873-550b-8a08-e0160c39bd54 |  | note | Category - IP
label | eac9f31f-3456-5e13-b090-746d8ad12d4a |  | note | Responsibility - SE
label | 44f70784-c4e8-5fcb-b1c0-ff5d37e03d7c |  | note | Verifying Documents - This ITP, As Built Survey Report
text | fd5647ac-8aaa-53c5-b3b1-9c7146501133 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Repairs to Damaged Pipes
label | 5c826723-4332-59bb-9928-c29a9ae8d1f8 |  | note | Reference - Section 701.31
label | ac6f870a-0c4e-5988-99d9-f52cb15564c7 |  | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | bc855816-e88d-5e84-b6dd-1c24e3b48324 |  | note | • cracks wider than 0.5 mm
label | 8b6ec901-b873-59bd-a22d-c069b359394f |  | note | • spalling of concrete
label | ee7a57f0-f606-5fb8-b3a3-27a20a7fcc4d |  | note | • exposed reinforcement
label | 9ff6ace4-128e-58d6-bc9e-dad75573ee49 |  | note | • joints that are not fully engaged.
label | 3433a168-f529-522d-9b6d-665d1f2f9877 |  | note | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
label | e9759370-b10d-56d8-8795-8cc307a6b86e |  | note | • longitudinal cracks greater than 2 mm
label | 06dbd597-5fb9-5295-b0aa-779fed4bfd60 |  | note | • circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | 175fd7da-d28f-549c-9b99-d0081892e58b |  | note | • circumferential cracks around part of the circumference with width greater than 4 mm
label | 5d0f3aef-6020-5939-a10d-e17701662b55 |  | note | • penetrations with area greater than 400 mm2
label | e10ab73e-53a4-5d2e-bae1-3b6de360d7bc |  | note | • pipe joints that are separated.
label | 59be98db-ed65-556e-8cf6-dbb1a2061371 |  | note | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | d88d4f68-1c3f-56b2-8991-66bd8b000fae |  | note | • hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | 88f9cc79-2105-5f81-bbe9-95e6f077588e |  | note | • fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | e6e48f47-bb14-5765-bea0-b4226013acbd |  | note | • spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | 86306aea-5613-5599-936d-9057b2570dc9 |  | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | e5ec0a41-5042-515d-9654-20ca187032e8 |  | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | 6c1c8195-eb9a-50c0-a326-17a106e6d995 |  | note | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | 5605e607-91ad-5733-bd00-f14e7e0b3534 |  | note | Method - Document Review for Repair Procedure
label | 137d3468-82d7-5237-b61f-da1ab4ecadaa |  | note | • CCTV Report Review
label | 547350de-2c03-5f8a-84e3-101ac965cad2 |  | note | • Visual Inspection
label | 4b666407-894c-52c9-a93c-952380abc867 |  | note | Frequency - Each lot
label | d2f08c4f-eddc-55ca-a910-080b21951b32 |  | note | Category - HP
label | db8ddab2-4209-5b17-b27a-77a46540bede |  | note | Responsibility - Nominated Authority
label | cafa6c1c-4aae-5ee3-9a3f-42ae8f8509ee |  | note | Verifying Documents - This ITP
label | e2e61f29-fb84-5a37-a460-a408025f1528 |  | note | • Approved Repair Procedure
label | 509ccef0-d07c-5800-9610-be976114bee3 |  | note | • Post Repair CCTV Report
label | d443fb15-0d16-550f-83f0-bd8026e838f1 |  | note | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | c7d5bb2b-f955-580a-a40a-08c3a1b4a4fc |  | note | Reference - MRPA Quality Management Plan
label | c8117e65-da6f-5d0c-b479-bca64f7a29b4 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | b4f7b8ec-2715-5aa0-918c-c35edcb1eb64 |  | note | Method - Document Review
label | 2c361a9d-44dd-5fd9-9279-71b9efba6107 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | af3425ee-b8f6-52bd-9bdd-48c0763597f0 |  | note | Category - HP*
label | 8bd8b407-dd98-50f3-af31-9b68a7f6e7c2 |  | note | Responsibility - PE
label | c028964f-9a00-5716-86a3-cc4329510172 |  | note | Verifying Documents - This ITP
text | 6c0773a2-4df4-5eae-9cdc-b6c2bd9bc598 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 07c78d4d-dac2-5838-aa89-0901f8469d86 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 01cb9db2-ff5c-5467-8414-8baf551cf698 |  | textbox | Name:
text | 2a3c7cfe-f7cb-5b59-98e2-1fc8d6afb192 |  | textbox | Position:
text | 0948c33f-18de-5c78-830f-2a6705494b3a |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-047-CIV-CPD-Type B FIll - Road | itp |  |  |  | Yes | ITP-047-CIV-CPD-Type B FIll - Road Rev 0 | 51c5fee6-4576-467f-8804-773232db449e
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 238556f2-d3ed-5e38-8819-595bae5bb9ac |  | note | Document Title: ITP-CIV-CPD-Type B Fill - Road (Supply and Install)
label | 81e5da89-722d-5bee-b7dc-d250fba7279d |  | note | ITP Description: Type B Fill - Road (Supply and Install)
label | 5cdb59e4-d014-50a1-bf0e-1336da646ba5 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | d3f3e526-429c-566f-bbd5-34cdf01a9821 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | abd8a9d9-f56a-5b5b-a672-295fda6b7aaa |  | note | Revision Number: 0
label | 40222268-4f3d-5113-b7a4-14074b27f432 |  | note | Revision Date: 12/07/2023
label | 493eec9b-49c6-5401-87f9-d957f9f1f1df |  | note | ITP created by: Matthew Dib
label | ab42a86f-254d-55d4-a7ff-6a2f1ae0fbcd |  | note | ITP approved for use by:
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | edc683c8-f320-55b9-834f-c07f3134b756 |  | note | Reference - Reference Documents:
label | 6e638777-99c5-5d30-a075-9b8b0b9b8ad1 |  | note | • IFC Drawings
label | 40837480-245a-5b56-a9ee-e3f3ce03cc5b |  | note | • VicRoads Standard Section 176 (10/9/2008)
label | a5a69f99-ae40-5245-a663-a3712ee6d651 |  | note | • VicRoads Standard Section 204 (29/12/2015)
checkpoint-group |  |  | section | 2. Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 - Material Supply
label | 5bca1668-9f42-5837-9e42-e66adb23a36e |  | note | Reference - General Notes on IFC Section 204.4 c), 204.06 e)
label | 22c27b38-db86-5311-81f6-88d111d60441 |  | note | Acceptance Criteria - Free of topsoil, deleterious &/or perishable matter and maximum particle size ≤ 150mm. Swell < 2.5%. CBR >2%. Material classified as expansive or silt, either before or after compaction, shall not be used as Type B.
label | 0692d139-f06f-516b-ab89-b5f24a72010a |  | note | Method - Doc. Review
label | 2f3e0c7f-bf6d-5ca2-a4fd-9cdf93388967 |  | note | Frequency - Prior to Commencement
label | 008aa88b-46f1-5fd6-989b-081ab234573d |  | note | Category - HP
label | d0dbadd4-555c-57ff-a969-8a6f9667cf92 |  | note | Verifying Documents - NATA Test Certificate
text | 084d9e2e-edc3-5058-996d-51ebddc9adf1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 - Survey Set Out
label | b66f58f6-cef8-5082-acff-4b9298880e99 |  | note | Reference - Design Drawings
label | 0ebadef1-db0c-5bf3-84c0-c1ea3251b301 |  | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | c10f054b-d450-5ce8-af36-eb7d7d391067 |  | note | Method - Visual Inspection
label | 0847cf5d-2649-566f-ba96-fde0e4c6fdbd |  | note | Frequency - Each lot prior to commencement
label | 098f8d9b-9b7f-5591-96c3-390b459c6dba |  | note | Verifying Documents - Signed ITP
text | ef60b33b-f6be-577f-bf69-2d1483de5bb8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Pre-Commencement of Fill Works
label | e3039a71-713c-53f1-9af6-05562d6272d1 |  | note | Reference - Section 204.10 (b)
label | d3bfd620-fa0d-5cc6-b51f-c285af4dbfe8 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | ec640253-d01b-5781-94da-a82eecd2ea37 |  | note | • The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
label | 4e4ea450-8446-5edb-ad83-a54974b78c11 |  | note | Method - Visual Inspection
label | d0150e17-9256-547f-ab34-41c47529f16c |  | note | Frequency - Prior to commencement of fill works
label | a386c6c4-5ec2-51ed-b113-07002385d512 |  | note | Category - HP
text | e6572f72-131f-55e2-aa3e-2105bbc3f657 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Placing of Fill
label | 7d9fdeda-899d-51e9-aec9-dbfe8f115cb9 |  | note | Reference - Section 204.10 (d) (iii)
label | f92d7b5d-bc50-5dbd-9ec7-32f4d64f6346 |  | note | Acceptance Criteria - Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted by superintendent.
label | 86f976d1-155c-55a7-9c2d-57ed4afdcca2 |  | note | Method - Monitor
label | 971e86c9-19b0-524e-a66b-c41cc36d39bc |  | note | Frequency - Each layer
label | f56628d8-dd7d-5216-82b4-2836d290a22e |  | note | Verifying Documents - Signed ITP
text | 3b1c324f-a7d7-558b-8cab-cc99d716052a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Keying of Layers
label | f0afdd0c-e977-5331-9ae1-56af5e71f307 |  | note | Reference - Section 204.10(d)(i)
label | d54e699d-8a3f-5542-8ea9-a182bf0d121e |  | note | Acceptance Criteria - Each layer of fill shall be keyed into the layer above by creation of a textured surface.
label | 5a91d9fb-6c7f-506b-9770-0e88fd10b298 |  | note | Method - Monitor
label | 4b942366-bc01-5f26-a4a1-5aebff614754 |  | note | Frequency - Each layer
label | e2bb6d05-4def-5368-bca7-8edf66877833 |  | note | Verifying Documents - Signed ITP
text | c9d555b7-6f4b-589d-a84a-3e4117a1d401 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Test Rolling
label | f493f69c-e8ca-5361-900e-ccc72642aef3 |  | note | Reference - Section 204.12, 173.03
label | 53a9c0bd-81fe-54da-aa45-9dc31c1aa494 |  | note | Acceptance Criteria - All layers of fill and cut floor level to be test rolled in accordance with section 173.
label | d7a90d11-1fdb-5d79-b83f-fd0143bb4001 |  | note | Method - Measure
label | 5ddb319f-a801-50c9-b315-756e65662db4 |  | note | Frequency - Each layer
label | 302117d3-3235-53fe-b064-b2475393ff1a |  | note | Category - HP
text | ece8beec-e611-5cc0-abc0-74473f4b54dc |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Post Compaction Testing
label | 3bc8ac1d-5a0a-5de8-843d-a9722f7278c3 |  | note | Reference - Section Table 204.131, 204.13, 204.14
label | 2013c772-f4a3-5ce2-8498-ec3c87bd33ad |  | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
label | 310298ae-e1e8-5a2c-b0e2-75a06ad3d1a2 |  | note | • Ripped and re-compacted material below Cut Floor Level
label | 0258f297-895e-5171-9ab7-cb0df3d61d76 |  | note | • Scale B: Characteristic Density Ratio 98%.
label | 00a4815c-97b7-5700-85ed-74fe92c0cd72 |  | note | Attach: Compaction Test Result:
label | 3e1f624a-12e2-5188-9d1c-738367d55eb4 |  | note | Method - Doc. Review
label | ca5cab5b-f876-512b-b59d-7d55994c3b2e |  | note | Frequency - Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142:
label | f9e2c15e-51d3-582d-bb5e-c7a535e5dabb |  | note | • Placed within 400 mm of top of Type B: Test every second lot of like material and work
label | 5b666f8c-ead5-5dd8-809f-0423141ee744 |  | note | • Placed more than 400 mm below top of Type B material: Test every third lot of like material and work
label | 0004700b-db54-5d70-a993-3ea51a41cca5 |  | note | Verifying Documents - NATA Test Certificate
text | a9b5fa6b-a981-51ef-a8fc-4909c93f4afd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Preparation of final surface
label | 922f2e93-472d-5bcb-bb03-e6af5ce713c6 |  | note | Reference - Section 204.15, 204.03 (g)
label | cdb7532a-2d15-5c1c-b11f-eb4a454f43d0 |  | note | Acceptance Criteria - The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | 4ed21aac-3691-52b8-9035-782109d3f6d8 |  | note | Method - Measure
label | ff9e752b-a906-59f0-a4c2-4428f536f81e |  | note | Frequency - Top layer
label | 8280b1da-7862-51dd-99ce-9c66983d3ac7 |  | note | Verifying Documents - Signed ITP
text | 2846b091-b387-5b2b-bc3b-5a4a483e0c7b |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Survey Conformance As Built
label | 51a6e5c6-33f2-5461-85cc-a34d4d4e8ba3 |  | note | Reference - Section 204.03 (e, g & h), 206.16
label | 5bc82fd6-fe59-5fde-93a3-e737b5ffde31 |  | note | Acceptance Criteria - Surface is not to be more than 15mm or less than 30mm from what is specified in IFC drawings
label | 2d739730-aaf9-5c24-8b49-82fcbfc48fcb |  | note | • The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 14dada8c-29a9-5bd2-a31e-a5a0c16aedfc |  | note | ○ Scale B:
label | 62fbedcf-dee2-58b6-8460-f416461b8ed8 |  | note | • Min. No. of Measurements Per Lot: 40
label | b209403a-1809-561e-a38e-a01e7c751ee7 |  | note | • Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm
label | f9703d19-d000-56b8-919c-70327fe919db |  | note | Method - Review
label | be49fb87-9e4c-546c-be01-caa0ca9b724f |  | note | Frequency - Each lot (Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2)
label | 2015a153-9c07-5d1b-b4eb-ff86f7a3c33e |  | note | Verifying Documents - Survey Conformance As Built
text | 1f60b95f-b271-50c5-a21b-573eece9dfcd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 6a73f30b-f38b-5841-81cb-d23808f59b39 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 7a6529d3-4dbf-5e67-9db7-dde56f98c9d7 |  | textbox | Name:
text | 4e6cd2a3-baed-5525-8d19-28adc8275395 |  | textbox | Position:
text | b16e5600-a36b-524c-b0d3-76c612120908 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-046-CIV-CPD-Type A Fill - Road | itp |  |  |  | Yes | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | 5619ea3c-44b4-4e95-b2c1-4e01cb32eab8
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 04dff166-9dd8-5bc0-a59a-6d9dfeab4b8a |  | note | Document Title: ITP-CIV-CPD- Type A Fill - Road (Supply and Install)
label | 2e328150-ad80-516e-90ef-cfa5581b235b |  | note | ITP Description: Type A Fill - Road (Supply and Install)
label | 618d6363-7516-56a8-bc30-f93990bc1cb0 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | c6fc5f5e-87ab-5ed9-9037-9a2da1063ac2 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | 9d8abf76-5441-508f-b4ab-ff9c7bf139bd |  | note | Revision Number: 0
label | 47651862-5031-5637-9ace-f624191e10e5 |  | note | Revision Date: 12/07/2023
label | 1dc6e926-8224-5b5f-98bc-351e3c12570b |  | note | ITP created by: Matthew Dib
label | 1b7a676d-c1ab-5969-ab57-fc41ae66b9c7 |  | note | ITP approved for use by:
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 76b0e669-abb6-57da-93a9-d2f32151a410 |  | note | Reference - IFC Drawings
label | 17f45917-1af6-5194-8ce2-c7eb44b5d63e |  | note | • VicRoads Standard Section 176 (Sept 2008)
label | 45139a27-a71a-59d0-8b16-e6cb4d8e27c3 |  | note | • VicRoads Section 204 (Dec 2015)
label | 9792e7d1-e930-5283-a6bc-3abe30abbce2 |  | note | • Code of Practice RC500.20
label | 034472c1-2d1e-5515-b42a-6e878b689075 |  | note | • Code of Practice RC500.5
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance
label | 425d55c8-ac7a-5e3c-80a0-5a62732e1bb3 |  | note | Reference - Section 204.04 b) Table 204.041
label | 12bc2454-34ed-533c-903a-799dc417c27c |  | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | 8b2ead9f-fbbd-57c1-ad67-49349d13ca4b |  | note | • Assigned CBR≥6%
label | 44a7512a-e04c-59a8-8f07-c3a5f3cfa629 |  | note | • Swell ≤ 1.5%
label | e7cedf62-c5d0-5880-9958-7cd69517a655 |  | note | • Permeability ≤ 5X10-9 m/s
label | 5b61e4c9-7631-5c03-8df6-c276a4bf0594 |  | note | ○ Grading:
label | ced8d0d9-6123-5eeb-a7a9-b008fd82c536 |  | note | • 75.0mm 100%
label | 7fe02200-0009-5e62-ba49-ad35ec2a67d2 |  | note | • 4.75mm 40-80%
label | 542a4241-58d6-5ff8-b8c1-ce46563063c8 |  | note | • 0.075mm 10-40%
text | 645f5910-ebe2-5f3e-bba0-aca3bde3739d |  | textbox | Reference: Material approval in Teambinder:
label | 262ef993-9f76-5abe-bc43-69c339a4526c |  | note | Method - Document Review
label | b15c6888-c8dc-554a-a7b3-b54199b8d25d |  | note | Frequency - Once, for each material type
label | 3e70129f-1de4-5578-84f7-25616b289e6a |  | note | Category - HP
label | d83b16af-9fee-5b03-992c-bcaadfd21eb1 |  | note | Responsibility - SE/Nominated Authority
label | 36dbf726-fae6-51be-8cbb-75c96e139482 |  | note | Verifying Documents - Supplier Material Conformance Certificate
text | f10e62c9-3d93-585e-99e9-23ab1a25c3d6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Pre-Commencement of Fill Works
label | b7c34647-c4b8-5264-b632-643e8b90fe78 |  | note | Reference - Section 204.10 (b)
label | 83cec521-af0a-5bf2-8ac8-9d3d7c3774c4 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | dc9ce301-7dc7-5746-b571-f1848c0bb5ba |  | note | • The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | 34e9a4d4-1068-5b00-8e19-607ce8381364 |  | note | • No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
text | cb38de53-c079-589b-a94a-edff130e8c5b |  | textbox | Reference: Fill foundation Preparation Lot Number:
label | 6dda44b0-7bb0-5bed-abcf-ab16a75ca024 |  | note | Method - Visual Inspection
label | 34151bf9-2f53-5ba6-bf60-cec811a9f0d3 |  | note | Frequency - Prior to commencement of fill works
label | e4fce539-17cb-587d-be43-2286b784a8f9 |  | note | Category - HP
text | 48a92bbd-9539-549e-be85-560f16c08a9d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out
label | e5ebfe17-8862-5c5f-a8a4-18a59590cf51 |  | note | Reference - Design Drawings
label | 87f58417-3fbf-587c-b476-4c591f6869f7 |  | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | 8ff901ff-a5e3-565c-8f67-35d13ab31e01 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | a6a95aba-ee65-5d8f-8cfd-49e14ec1dd08 |  | note | Method - Visual Inspection
label | a7c46065-950b-5a4e-9ec0-e40ab55b67a6 |  | note | Frequency - Each lot prior to commencement
label | b1bcb0f0-33d6-5450-adb8-b842858a8243 |  | note | Category - HP*
label | 6bb44688-09a3-5e41-913c-78a76f2d5dc3 |  | note | Responsibility - PE
label | 99750622-1290-5176-bca3-ab3e16be00a3 |  | note | Verifying Documents - Signed ITP Lot Map
text | e6f517fe-6fd6-51b1-aa95-41757524b20f |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Type A Fill/Verge Activities
checkpoint-status |  |  | checkpoint | 5.1 - Placing of Fill
label | 1daa79f5-f303-59e0-b236-475956a18fcc |  | note | Reference - Section 204.10
label | f67b7119-aa2e-5ad1-91e9-e3bb89aac3db |  | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted from superintendent.
label | 24a89339-3559-5662-bb67-6c574010486c |  | note | Method - Visual
label | 5d5a3776-69f9-50fa-80a0-ab756f9973ce |  | note | Frequency - Each Lot
label | ab05be17-4baf-56cf-b638-c38289087017 |  | note | Category - WP
label | ee424c06-5c39-5370-a601-9bee8d4afdf6 |  | note | Responsibility - SE/Site Supervisor
label | d080f5fd-2fc8-5584-8b91-5aad8ad54dab |  | note | Verifying Documents - Sign ITP
text | 8aaba3a5-1d61-5166-900f-113b3023cc3c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Test Roll
label | d9ee110f-b472-56b7-b77f-125fb67633a6 |  | note | Reference - Section 173.03 Section 204.12
label | 3244da56-85d2-5017-93b6-ee8b6b7a15c6 |  | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | 4ed78b09-a3f7-519f-8c54-47b8a50c6088 |  | note | Method - Test Roll as per 173.03
label | a138b451-7031-5529-96fd-3d301e729252 |  | note | Frequency - Each Lot/Layer
label | e89a4c19-1c76-5077-af45-5e27c9c23033 |  | note | Category - HP
label | d38ec773-74f1-55d9-b9a2-9cd5db202597 |  | note | Responsibility - SE/Nominated Authority
label | 02981694-87c2-5256-a20c-8e49c5c786ee |  | note | Verifying Documents - Sign ITP
text | 5ce69613-8788-57ef-96d9-3662c9721deb |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Compaction Testing
label | 2345172b-c4dc-5fc0-b677-86c1770cc283 |  | note | Reference - Table 204.131 Section 204.14 c) Table 204.142
label | efdc2cf0-ac0f-5777-a2c0-3797e550db0c |  | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
label | dc464198-3c8d-525a-83c1-23cd01bcf2cb |  | note | ○ Standard Compactive Effort
label | 5d77e4ed-762f-5225-887d-5e901b3d85a4 |  | note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
label | 3e931e7c-7501-52db-87cd-3557f35faf15 |  | note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | f68ca55f-d106-59ab-bc60-0e4104f87a4c |  | note | ○ Compaction and Moisture content
label | 0a4fbbda-42df-5b44-a819-f1b90582b889 |  | note | • Scale A: Characteristic Density Ratio 99%.
label | 246b59c3-8506-54d3-8b45-eea82a6debc8 |  | note | • Scale B: Characteristic Density Ratio 98%.
label | 98efe837-3fdd-5f78-9647-31295b0d6c7f |  | note | • Scale C: Mean Value of Density Ratio: 100%
label | e1c3675a-45b0-5a5e-8bb9-38e2771004a4 |  | note | • Lot size - the leser of one day's production or 5,000sqm
label | f2210a02-c083-5746-b46f-95aed580c343 |  | note | • Testing of every lot shall continue until three consecutive lots of like material and work have achieved the specified requirements in the first test. After satisfying this requirement and establishing a compaction procedure to the satisfaction of the Superintendent, the Contractor may seek the Superintendent’s agreement to reduce the frequency of testing of subsequent lots to every second lot of like material and work.
label | 08382353-c5fc-5872-9c71-070d54672054 |  | note | ATTACH: COMPACTION TEST RESULTS
label | 3bbbe73a-e118-5eb1-b8d7-dd31ac7607e6 |  | note | Method - Review Document
label | 70d3700f-88ef-5b56-bd3b-957b1bdcb693 |  | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | 08a3226f-b143-5885-9c8d-2e331a76ea1e |  | note | Category - IP
label | c921312c-d068-589c-bd92-701fb5c52a6b |  | note | Responsibility - SE/Site Supervisor
label | a6e81cf5-5b8a-58bc-8b44-14e84b9f13ab |  | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
text | ab47b4c7-fac8-5ba2-9bc4-23109f0e52ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Preparation of final surface
label | 9b24c781-0301-52f6-ab67-e82459f83e53 |  | note | Reference - Section 204.15, 204.03 (g)
label | d9b583c2-9cc2-5001-b028-5c0e42ac694a |  | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | e3862c83-ee01-5b3f-b68b-7542e6c9df6f |  | note | Method - Measure
label | ed4f6255-30b0-5f65-a6a2-8962ba80f072 |  | note | Frequency - Top layer
label | 8e9aadf0-3e0f-5adf-ac0c-832a23cadccb |  | note | Category - IP
label | 30467f77-3fb7-5cb7-962c-19975dfb9ced |  | note | Verifying Documents - Signed ITP
text | 04698542-b2f2-5ed2-bd23-77bde2230d16 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Post Compaction Material Property Testing
label | 360219e7-8bcc-589b-bf63-614e39f7cd68 |  | note | Reference - Table 204,041 Table 204.141 Section 204.14 a) or b)
label | c5851ff8-f55e-5ff4-8560-417a2be0e0e7 |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | d92164c7-d89d-587f-86da-e5e329550b1d |  | note | • CBR ≥ 6% and Swell ≤ 1.5%
label | 97818fc0-114a-535d-9fb6-993420c0fc26 |  | note | • Max Permeability = 5X10-9 m/s
label | 2b096aa2-ef1a-56dd-aa12-65a76eab51e1 |  | note | ○ Grading:
label | 96800a91-c8a3-58c7-884b-de2bd9442ebb |  | note | • 75.0mm 100%
label | afb008c9-0036-516e-b8cf-9c4861a3c406 |  | note | • 4.75mm 40-80%
label | 9c590be7-6107-5620-8381-a9436bbbede2 |  | note | • 0.075mm 10-40%
label | 7f6e35a9-9a2b-5143-ac14-0a4dac96d6bd |  | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | ffadd300-21a0-5226-a4c1-7e0bbabc0ff4 |  | note | ○ Scale B:
label | 40489fb7-1139-5dd5-a504-6fb97d8a396c |  | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | a7c3fa0a-ac3b-5b31-ae34-a32cb9fc650a |  | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 576fd385-bcd2-5b04-9904-40894963473f |  | note | Attach: Post compaction test results:
label | 1045710d-9dd8-56e0-990d-aeec79925c14 |  | note | Method - Review Document
label | b7948c2e-3816-5d25-b402-62acc2fb9b9b |  | note | Frequency - Refer to Section 204
label | ff151421-d598-5dec-9c60-a8d5fe8bdfca |  | note | Category - IP
label | f9cc41c8-e8e0-546a-90db-cb38e4a7fcf2 |  | note | Responsibility - SE/Site Supervisor
label | 9faa9b84-20a6-50fe-a579-9c01ba4ddff1 |  | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
text | 10a98b07-9aa8-55e9-bd5e-e3d392607aaa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Survey Conformance
label | be92c2fb-eb93-510d-ad19-d3aed14f3092 |  | note | Reference - VicRoads 204.03f,g and h
label | 5f6f6e39-fec8-5bac-8c43-0d16dc135843 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 127f48d8-796d-5558-8212-47324ccbf5a0 |  | note | ○ Level tolerances Scale A:
label | 4f6d068e-bd29-5623-9272-2ac784007c7a |  | note | • Range x = +5, -15mm
label | a90325d6-4ea5-5351-8008-7ab3ae0b1e48 |  | note | • Max S = 12 mm
label | 50e2cc4d-ccb9-5215-988d-37906fe414ad |  | note | • 80 measurements per lot
label | b5784200-319f-5d39-9358-fdbc4472de9f |  | note | ○ Level tolerances Scale B:
label | 1e48be07-2ece-59d0-a181-865f69f8893e |  | note | • Range x = +5, -25mm
label | 6bf99577-f270-5b07-be2b-6e781f5d3a49 |  | note | • Max S = 15 mm
label | 78e5e603-bcd8-5b88-9c2c-c59ba999fc93 |  | note | • 40 measurements per lot
label | 6be9b64d-98f4-5ca9-8e9f-8b6dae2b0327 |  | note | ○ Level tolerances Scale C:
label | 831a17ba-ddee-558a-82c1-ad599c8374ec |  | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | 7ee7365c-1cea-5223-b01a-771287295a7d |  | note | Method - Document Review
label | 764939f0-487d-5636-b284-ba7d78a18c19 |  | note | Frequency - Top of Type A/Verge
label | 3ec689ef-8188-5e9b-bbd1-584980ac0572 |  | note | Category - IP
label | 306d8828-0fd1-5736-a4b1-146ccef0a809 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 0f69f592-453b-5ba1-b218-17af3155d40d |  | note | Verifying Documents - This ITP, Survey Conformance Report
text | 144a076e-6143-5229-9c59-99f9713efa54 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 2a4e9695-02e3-5f4e-955c-f1cedfae2ddb |  | note | Reference - MRPA Quality Management Plan
label | 0ac6cd56-1ef4-51e4-88c4-29eb5eed1866 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | f1071e79-8b53-52ee-8683-6eec9fb98b76 |  | note | Method - Document Review
label | c2bc63fb-e42b-5ff0-a010-8fcf91dafb47 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 1ae8b622-83df-5c63-9ec3-331070490178 |  | note | Category - HP*
label | 7679b883-4ef0-5bf0-b1f7-f2a5f757dcf3 |  | note | Responsibility - SE/PE/SPE
label | 12643d86-9f7a-5016-b432-f3636c1a94af |  | note | Verifying Documents - This ITP
text | 97088407-c4b8-555b-b8e1-74b7a73d71ab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0ae9d3e5-fa94-57b3-9ab4-9dd60cdd2481 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c34cd726-4ca4-55d1-86af-c46580d04874 |  | textbox | Name:
text | ebc653a5-e87e-5d4d-8970-33127db15e24 |  | textbox | Position:
text | 360777e6-6e81-5d3a-96a4-efae52176481 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-049-CPD-RAIL-Calder Park-OHLE Wire Regrading | itp |  |  |  | Yes | ITP-049-CPD-RAIL-Calder Park-OHLE Wire Regrading - Rev 1 | 7efa8c2e-b70e-48d9-bb2d-4b498511bc9a
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | a32b4918-940b-59df-b037-fa678be9004c |  | note | Document Title: OHLE-ITP-MRPA-Calder Park-OHLE Wire Regrading
label | b24f3662-d736-5c6d-8c24-1d295100b84e |  | note | ITP Description: OHLE
label | 25492ccc-2582-53b0-8943-12fa0f2c38ee |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | ad3f5baa-9994-5773-8391-035c461cc5bb |  | note | Discipline (e.g. CIV/STR/RAIL): OHLE
label | 2ff6095e-5e05-59bc-8c1a-3f3a106d120f |  | note | Revision Number: 1
label | 7b1e0a27-d0fd-585b-ab34-32628600583d |  | note | Revision Date: 24/07/2023
label | 76f350fc-106a-58a1-9353-3bfa21a11786 |  | note | ITP created by: Kevin Liang
checkpoint-status |  |  | checkpoint | 1.1 - Overhead Line Electrification
label | b0e71249-5732-5839-8aa7-204459f9897d |  | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
checkpoint-status |  |  | checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | 7779b8a7-1e6b-53c9-8f90-7b8dbcb2306a |  | note | Reference - VRIOGS 001 AS 4100
checkpoint-status |  |  | checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
label | 030b68d1-71cd-5c0e-9f23-0387c5c47313 |  | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1)
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Procurement Materials delivered/collected to stores/Site.
label | 54441720-fbb6-54e2-8cc1-9ca4f15bccfe |  | note | Reference - Contractor - Site Material Control procedure.
label | c0bce270-39db-5290-9909-bc2c47a7b758 |  | note | • Cat5 Material received -Calder Park Tracking sheet
label | 3b6ef55b-9201-5c65-a128-3585c4986c4e |  | note | Acceptance Criteria - Ensure materials are delivered/collected as required.
label | f4ee23b4-670b-593e-a89a-961727b3bc66 |  | note | • Certificates of Conformity provided by MRPA
label | bd78a38b-586f-5ad2-9406-72a4423dad64 |  | note | Method - Document Review
label | caab6fb3-90b0-5893-a66d-d122f9b1eee7 |  | note | Frequency - Once for each supplier, prior to works start
label | f955e49b-709c-51b7-bd0c-72cb3503037e |  | note | Category - IP
label | 30a7aad7-fe4b-5159-b948-7cb08e009544 |  | note | Responsibility - MRPA Issue, CAT5 Receive
label | bb90ef3a-5489-539e-a3ec-461a9040c153 |  | note | Responsible person - MRPA
label | 3ad1ec87-e13a-5674-9029-aa29982fd44b |  | note | Verifying Documents - This ITP Signed Off
text | df87d913-b5da-5e87-8523-c5a62b89408c |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Produce Work Package Plan
label | 647875d4-ab8c-5fa6-8e49-391202f8d49d |  | note | Reference - Work Package Plan
label | b7610fde-5ea1-56cc-a47e-805de3163062 |  | note | Acceptance Criteria - Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
label | def1689c-a197-56e6-aa61-18cc255c16bc |  | note | Method - Document Review
label | e2870b42-77a5-5e1b-84d1-5d9ad90f550d |  | note | Frequency - Prior to Works Start
label | 47a18377-211b-5f96-9465-1915acc64675 |  | note | • TBC in accordance with MTM Standards
label | c9c74a07-8335-5d37-b59c-c4950b67d386 |  | note | Category - HP
label | c95f874b-9c52-57d4-a123-382c705256e6 |  | note | Responsibility - MRPA/CAT5
label | 6358471a-4c1a-5c3b-b892-558e74d1ce70 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 2860e522-3ee5-5c5e-a9f2-a0971b13b4ad |  | note | Verifying Documents - This ITP Signed Off
text | a0b619fa-dc12-5c02-b0dc-232aa45ee6a2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Approval of IFC drawings
label | 25dbfc00-e399-5ca6-abde-bdd51077fc7f |  | note | Reference - Contractor Design Management procedure. MRP-DPK-060-00-ETN
label | c269feec-0bfd-5bcd-a7ae-31831e3339eb |  | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
label | 404e5e9a-64ee-5f13-af6d-60a00acf2835 |  | note | Method - Document/Drawings Review
label | d9b6a5e5-4e8f-5d34-8329-36b075237912 |  | note | Frequency - Prior to Works and at regular intervals.
label | 158fd854-05e8-5929-b1ff-e8ff8acf739c |  | note | • TBC in accordance with MTM Standards
label | f782056f-48db-56be-b252-bb05cab118de |  | note | Category - HP
label | c870d3db-8fde-5b4b-951d-4fdb1182d6c6 |  | note | Responsibility - MRPA/CAT5
label | bef60c99-85cf-5472-8b1c-1100aa422779 |  | note | Responsible person - MRPA/CAT5 Engineer
label | a50307b9-ad1f-5342-8248-d328ef67cd0f |  | note | Verifying Documents - This ITP Signed Off
text | 4699bce0-8eec-568f-8233-df558510a9b4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Task Specific Permits
label | f5693ae4-51d0-5bdc-b68c-01197ecbde09 |  | note | Reference - Working at height permit. OHLE SWMS
label | be6a0bfa-dd26-5850-a84b-e6a0ccba74dc |  | note | Acceptance Criteria - Ensure all task and activities have relevant permits issued and received.
label | 3eac8767-508d-59f4-9ee7-be71a87a6bbd |  | note | • Task Permits to be generated and signed off by appointed person.
label | 2547ba90-72b5-58a6-8515-04a29f67b073 |  | note | • Task specific documents - MTM to issue permit to enter/Isolation permits etc.
label | ec1b4d5c-2480-5ec2-9cd1-e3f9b8b800c8 |  | note | Method - Visual, Document Review
label | bd3bdf82-9a9d-5848-a0c7-3c9a5b8d5558 |  | note | Frequency - Each Task prior to works start.
label | 6620f226-5971-5a24-af39-b497cb6a2c99 |  | note | • TBC in accordance with MTM Standards
label | 40a14e7f-b66b-5731-91c6-ab61c1901611 |  | note | Category - IP
label | 6e65d00b-e6e7-5885-93fc-6577fc136f31 |  | note | Responsibility - CAT5/MRPA
label | 69bdd03a-23f7-564d-bf66-f14fd2b487f5 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 4bdad0fd-9bed-5fd3-b8ba-3d3c30b28a64 |  | note | Verifying Documents - This ITP Signed Off
text | 561ca558-88d3-5449-8222-081dd03ace9c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Cantilever assembled.
label | c6f514ff-5b85-5b76-ae5f-db71e1a92cc2 |  | note | Reference - Cantilever assembled as per IFC design.
label | 54410576-e071-54ff-b894-47642dcfb53c |  | note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | 7f70a447-3296-5b97-8bd5-2048bdd1bbe2 |  | note | Method - Visual, Document Review
label | a7662440-4f59-5384-9cc0-c18322251eed |  | note | Frequency - Each Task prior to works start.
label | 1717de01-4438-5896-9e4a-6cc21c133f83 |  | note | • TBC in accordance with MTM Standards
label | 66fb8fcd-5d20-5803-947d-2c01af582821 |  | note | Category - IP
label | 49523014-be97-58e2-8c29-29682e00ef57 |  | note | Responsibility - CAT5/MRPA
label | ec8d59bc-7c66-5544-9eef-38c773955d85 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 81932f57-0373-533d-bf5d-69ce22f26c5c |  | note | Verifying Documents - This ITP Signed Off
text | 63e8aec9-4f7f-5b12-b365-f2664527ba8e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Pre-Installation check
label | a91c08d8-6384-5fa7-8087-08a9303875c0 |  | note | Reference - IFC wiring layouts, IFC cross sections and BOQ.
label | e3b8e6f6-0331-5c47-9aa5-1c9618f488c3 |  | note | • Engineering Drawings Management Policy (IFC/As-built) L1-CHE-MAN-001
label | 4d69206f-9f12-5690-97ef-16cb37c70214 |  | note | Acceptance Criteria - Ensure that locations matches most relevant IFC drawings
label | 2679c460-2750-5b67-aaf7-ceb62daf332b |  | note | Method - Visual, Document Review
label | 0e3016a0-62c0-5177-949f-8ce5a19f84d5 |  | note | Frequency - Each Task prior to works start.
label | 5e5f481c-b1ff-5c60-af3d-4f1b54ea2fee |  | note | • TBC in accordance with MTM Standards
label | 27998cf5-0dc6-5138-847c-2ae77523d8fe |  | note | Category - IP
label | 7ba89816-325d-5da0-b30c-b8a1dd8c3559 |  | note | Responsibility - CAT5/MRPA
label | 04ebf7e0-da85-5683-8f77-13716a65ffc9 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 61814104-be95-57a7-b96d-314684428da6 |  | note | Verifying Documents - This ITP Signed Off
text | 88c96d68-69d4-520d-8f87-9c05a72db722 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Cantilever installed.
label | 46babaf0-d542-598d-b243-d16c8d31c5af |  | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | a0e36c4d-6bf9-510d-b641-fbdd9f666b6a |  | note | Acceptance Criteria - Work instructions in accordance to IFC design
label | f1dda229-c289-5dc6-b5bc-bc493e5eb90b |  | note | Method - Measure, Visual
label | 4b902408-c214-568f-833f-f2ffe38b040e |  | note | Frequency - Each OHLE Structure
label | f0dce753-f7e9-5016-ac82-1dcf63e778ea |  | note | Category - IP
label | 87b88d2d-ef3f-55d8-a17d-484bec024cf9 |  | note | Responsibility - CAT5/MRPA
label | dc03a787-ba63-5fe8-a9cc-39c40e54c438 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 8c039af6-eaec-53fe-8fae-14f26be2a424 |  | note | Verifying Documents - This ITP Signed Off
text | cbdf85a3-28cc-5a29-a0f1-c6d557a5142f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Install SPS to correct height / position relative to track
label | 3f49ec51-9932-514f-9d17-d8b2047e4e26 |  | note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | dcbc225e-93bf-5ae4-91a4-f1431fdef5ff |  | note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
label | e995ab48-9f4a-5fdc-a87c-8c29d0047dbc |  | note | Method - Measure, Visual
label | c5ee7828-1c17-5ea1-ae0a-201fc80dd52f |  | note | Frequency - Each OHLE Structure
label | bab6a7d8-c23b-504b-9816-35f7129d979e |  | note | Category - IP
label | 53bc6145-954b-5c67-91c5-7df31f70320e |  | note | Responsibility - CAT5/MRPA
label | 82b42f6e-d39a-53e6-ad04-6eaf22c66661 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 908bbc34-b7b1-568a-8f29-656ca5be4740 |  | note | Verifying Documents - This ITP Signed Off
text | 05777c99-1d8c-5e24-a52d-0175c6596b40 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Cantilever checked once installed.
label | acf75bd7-67eb-5787-a3e7-c23d8f3be8ab |  | note | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet.CAT5/OHLE/CHK002
label | 10373dc7-d52e-5cb4-8e0c-a2eeba8b1597 |  | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
label | 3e19309a-fb3a-5912-9c71-1862aa63d414 |  | note | Method - Measure, Visual
label | 9a8f3773-f711-5484-935f-a0025e4efe38 |  | note | Frequency - Each OHLE Structure
label | 3eef33ed-d060-5161-818a-67b77e065384 |  | note | Category - IP
label | 80e4972f-c054-579d-a4ec-64409289227d |  | note | Responsibility - CAT5/MRPA
label | 59773a61-49cc-5c46-8218-8c175358af61 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 262efde4-d01c-5504-a1b4-d422bb6fc0a4 |  | note | Verifying Documents - This ITP Signed Off
text | fd70e711-a0cf-5756-b39e-9479e50515b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Installation of wire supports at the correct height and stagger.
label | 0cfcd28f-03ee-56d3-9c6e-12b45a52ecf5 |  | note | Reference - Install as per design drawings.
label | e4efe236-000d-534c-8644-905b6ae8c1e6 |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | 5bcca83a-6398-53fc-9a89-0f11b0d4e902 |  | note | Method - Visual
label | 03b9fe89-920c-5c59-bd3d-3194104e6528 |  | note | Frequency - Each OHLE BWA structure
label | bb3c2c82-e2a7-5e35-9c20-b9cad02f8ec2 |  | note | Category - IP
label | 1c77a65b-a7b8-5fa5-b9e5-f764a2da5b8e |  | note | Responsibility - CAT5/MRPA
label | 9fab31a5-26b9-5f93-ba2c-af1437e999c1 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 3a6c2ea2-2def-5657-81c8-767ff34c380a |  | note | Verifying Documents - This ITP Signed Off
text | a15d33f4-22a2-5f9b-b57d-1f8b9ba971b2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Installation of small parts
label | 01a6bf55-fe0e-5dae-8cea-a806ac0f6a33 |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | ff75c1b3-9a05-5327-a803-83a409b6f2a3 |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | 5fe3c8d8-b4c5-538e-b3c6-70bd9f1b32e4 |  | note | Method - Measure, Visual
label | bae12386-ad01-5f14-ae96-021dd9689cda |  | note | Frequency - Prior termination
label | 049e82bc-b4c4-5efc-9ffc-ea355c0bd9a1 |  | note | Category - IP
label | 300b6b3a-112f-5c8b-a643-8f261499ad9b |  | note | Responsibility - CAT5/MRPA
label | 3d3a7935-ef13-5990-8128-3867d448141c |  | note | Responsible person - MRPA/CAT5 Engineer
label | bac1c9f5-f9e6-5bc6-b914-80fc885e216c |  | note | Verifying Documents - This ITP Signed Off
text | 8adb4494-5bf8-5d89-8fc3-a087a0ae59cd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Complete Clearance Checks
label | 96e12612-ca9c-5885-b9ac-ea845f610e0b |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | 8d8dd6ad-0c7c-5279-bfd3-9e5298846e68 |  | note | Acceptance Criteria - Visual inspection for clearance and wire staging from Hirail EWP
label | d4940203-2538-59aa-acc6-f58d35656e06 |  | note | Method - Measure, Visual
label | e87512dc-8f7d-55cd-9cb9-9f8a70d2416c |  | note | Frequency - Prior termination
label | e0f6ce63-5600-59a5-a195-1c99018bf51a |  | note | Category - IP
label | 15a4daf7-81fd-56af-91a2-8b51fd545ce5 |  | note | Responsibility - CAT5/MRPA
label | 0ecd002e-102c-5c4e-b7f6-d82cd9dcabf7 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 28ff49eb-cb96-5369-a071-2264c7ce497a |  | note | Verifying Documents - This ITP Signed Off
text | 2a42cc65-30bf-5c9d-a604-923a29fc6dc1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Complete Pan Run Test
label | 81a48cdb-b208-58b7-8f97-d9992f0d3c0c |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | 65116da3-f7c2-5698-bea3-4cd747d22d13 |  | note | Acceptance Criteria - Check for wire take up, clearance, stagger limits and pantograph interaction to the contact wire
label | 04e8a10e-15e7-50a2-8ec0-2506a6f4ba73 |  | note | Method - Measure, Visual
label | 27fc42ac-2c22-5399-b825-773b5a6d4b00 |  | note | Frequency - Prior termination
label | 3b7fe085-bbd2-50df-b813-7e8473721916 |  | note | Category - IP
label | 596278d9-8f1c-58bc-8afc-d3eff7febff7 |  | note | Responsibility - CAT5/MRPA
label | cc9798b7-c56e-5b0b-9612-51270f42fbbd |  | note | Responsible person - MRPA/CAT5 Engineer
label | 9b901689-cef1-59e9-9587-5de88a4d0297 |  | note | Verifying Documents - This ITP Signed Off
text | bd832821-46fb-53de-bc27-03938d98398e |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Defects/Temporary Works
label | eec8f481-2a40-502f-bc3b-44b3db3ac3b3 |  | note | Reference - IFC wiring layouts, cross sections and design drawings.
label | 98ef030a-e015-59fc-861a-d66f37749259 |  | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
label | e6cb15dd-ea29-5e22-94d3-6602589e7e20 |  | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
label | 640fe297-343f-55d0-9da0-a273f1af8169 |  | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | 4de6b930-d150-57d4-adf4-34d54d0e6d5d |  | note | Method - Document Review, Visual
label | d9f9dedd-c24d-53bf-b0dc-cb2364dce366 |  | note | Frequency - Each OHLE Structure
label | 3c96d655-8276-5b16-8eb8-982d5b411e5a |  | note | Category - IP
label | 90f688aa-dd5a-5007-86f8-604832b8845a |  | note | Responsibility - CAT5/MRPA
label | f2cf3eaa-589b-5e8c-8be7-7d4c955441bb |  | note | Responsible person - MRPA/CAT5 Engineer
label | e76874d9-3dcf-5f2e-9e56-653fda0eab08 |  | note | Verifying Documents - This ITP Signed Off
text | 52c032e1-d094-5125-9a04-2b491f96d651 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
label | 73fd6133-97c5-5748-b0e1-5c77ae4044cc |  | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
label | 90fca279-7bd9-5a24-ae89-1645d315c920 |  | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
label | 8f162cbd-862c-53e5-ba1f-e5836b38d5d9 |  | note | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
label | 26fe2918-5922-5ca0-966c-04d0b2be1918 |  | note | Method - Document Review, Visual
label | 9adac229-0d5e-5586-bb68-e2e8fc5630f2 |  | note | Frequency - Each OHLE Structure
label | 298e6225-2bdf-51e5-9c2a-5fe7706f7151 |  | note | Category - IP
label | 5f7262c5-45a7-5c09-9b34-c6efe70a3d5f |  | note | Responsibility - CAT5/MRPA
label | 2a95a4ec-feb4-53a3-8be8-9d26485dda4f |  | note | Responsible person - MRPA/CAT5 Engineer
label | de63686d-8807-57c4-a5ce-245df97f28d9 |  | note | Verifying Documents - This ITP Signed Off
text | 8ac3918d-1b09-5b6e-9c72-ddc29fd4ca8d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 34ef5da5-0fd8-5c77-a52f-1f90a7f17d3d |  | note | Reference - MTM Quality Management Plan
label | e30c34da-27c4-5d0d-8323-6e6871e15db0 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 20fdd725-2040-5c87-814d-52fc7256a97a |  | note | Method - Document Review
label | 50b5cab6-21ae-5c0a-8081-ab21758dac42 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 3e43dfd8-96ac-552e-b248-e9fb750b7f5a |  | note | Category - HP
label | d6071b4b-2cfb-5ef2-abe4-cadbdf8a2a75 |  | note | Responsibility - CAT5/MRPA
label | 57deea1c-4c99-5837-83d7-970e1b715070 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 121d5590-2517-53cb-bbc6-6938e940adc5 |  | note | Verifying Documents - This ITP Signed Off
text | 687d1eb8-2574-5c17-a9df-7c2123e8bf5d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 9b47ebcf-8d0c-5760-aaac-2b4d451d3fac |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 6819ad12-5e86-5f4f-a24e-08239dab2609 |  | textbox | Name:
text | 7b5045be-d17f-5b25-b8da-95c5214d527c |  | textbox | Position:
text | 49fce55a-18dc-5059-9808-a61c0ae69067 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-045-CIV-CPD-Subgrade Preparation - Road | itp |  |  |  | Yes | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | 9430c0e8-7582-45cd-bdc8-07b023f65665
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 7528f190-4343-5025-8b1e-528d2d9de0f6 |  | note | Document Title: ITP-CIV-CPD-Subgrade Preparation - Road
label | aaa761ab-3732-580d-9648-a5cd54f95c3b |  | note | ITP Description: Subgrade Preparation - Road
label | aab28051-4d93-54b3-b9ab-33ceaa561a9d |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 5c1d458b-4804-521b-9d62-ba7b625d9a5d |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | 437a1dda-629e-52a0-a8b0-041f8633de3c |  | note | Revision Number: 0
label | 60823dcb-b438-5709-8bc9-c8433430c392 |  | note | Revision Date: 12/07/2023
label | a034d993-29b4-56be-ad05-f59c38b94c9c |  | note | ITP created by: Matthew Dib
label | 1ec0b0cc-c1f5-56ae-8819-961862550527 |  | note | ITP approved for use by:
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 8001842c-e8f6-57fb-b222-6919b0f65418 |  | note | Reference - VicRoads Section 204
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 0b420d85-5188-58ba-ac75-13e88ef529d3 |  | note | Reference - VicRoads Section 173
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Non Dependent
checkpoint-group |  |  | section | 3. Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Non Dependent
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-Out
label | 92b8bc7c-0f24-5f3f-8d04-19e7fafeb1cd |  | note | Reference - IFC Drawings
label | 69784157-e96d-5af0-a8c3-23c13af41a7d |  | note | Acceptance Criteria - Area has been set out in accordance with the drawings
label | ff167d6c-9f9e-5592-83a3-fdff8f3589db |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | 3d41f110-1874-5e5b-9fc0-17cb21b10254 |  | note | Method - Verify
label | f5973371-b5eb-5762-bbc6-fb5d33154ed3 |  | note | Frequency - Prior to commencement of excavation
label | c8bfbfd9-1af2-56f2-bb39-627c5e221c96 |  | note | Category - IP
label | a9f9025a-de76-5f2b-b26a-50fd2d30869a |  | note | Responsibility - SE/Surveyor
label | 013ee332-2057-5223-a622-210662cf1ab3 |  | note | Verifying Documents - This ITP
text | 4e8b7852-b687-5215-a0c4-da98a49cf4f6 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
label | 2bdd789a-590b-550e-9877-560dadc46cd6 |  | note | Reference - Section 204.06 (c) Section 204.06 (e) IFC Drawings
label | ae0922c9-49c6-59c7-836d-69f6aacee5d7 |  | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | 592e1378-f6da-5917-b7c5-f14a0fc5ea75 |  | note | • Assigned CBR ≥ 2.0%
label | 753d4573-6990-5138-9b66-4f45131492e4 |  | note | • Assigned Swell less than 2.5%
label | 8bddbe8c-736c-579f-9c5a-00ffd80d1a99 |  | note | • If parameters are met, rip and re compact to a depth of 150mm.
label | 78fc6b54-23d9-51c4-b940-c7fc22f262c2 |  | note | • If assumed design parameters not met, remove 400mm of material and replace with conforming Type B fill.
label | 3badb9dd-e517-528a-9b45-d84c6c65f2c0 |  | note | • If existing material needs to be removed and replaced with Type B Fill, ITP-CIV Type A/B Fill - Road is to be utilised.
label | ecf92566-2511-5e3c-bb1c-2333101b8f72 |  | note | Attach: Laboratory testing Verification:
text | 9e84f50b-1a6b-52a6-936f-53c051b760cf |  | textbox | Enter: Type A/B fill Lot Number:
label | 55d72201-f997-533f-9d5e-23be8434b22c |  | note | Method - Verify-Document Review
label | b38f8eba-0704-5b66-8017-2847545f72b7 |  | note | Frequency - Each lot
label | 5f14b3dc-576a-55fe-9a2c-ecdcc7fee1d9 |  | note | Category - HP
label | 52ee2822-4898-58a8-a671-054db7a9d298 |  | note | Responsibility - PE/Nominated Authority
label | 8792767d-86cb-5c6c-9322-56454fb74e15 |  | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
text | ef8771b3-be1f-532d-b8ec-1311e5e3b26b |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Material classified as silt
label | 47c295e5-d53c-5a3d-a69c-d45140037f47 |  | note | Reference - Section 204.04 b)
label | 9f071f05-e20a-54e7-a056-6f89f7791b07 |  | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
label | 70e04e18-557a-558c-8d71-cfbd719636e1 |  | note | Method - Document Review
label | 61dec7c8-c92d-5362-a773-10b7b0a7999a |  | note | Frequency - Prior to commencing
label | ba41a107-e41f-5fcb-96a7-c3cdb6951451 |  | note | Category - HP
label | 42a3433c-dfa3-542f-aacb-e1822486378c |  | note | Responsibility - SE/Nominated Authority
label | e0ad02b7-e98e-56bd-a674-652e4b9c2789 |  | note | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/ records
text | 642aac42-4690-574d-8057-d68303bb2756 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
label | 76b47cd4-cc3b-5c7e-8d87-f08bcf9d4089 |  | note | Reference - Section 204.06 f)
label | 64fc65df-f123-5d91-88dc-0572cd2ea923 |  | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | a6015c38-efbf-59e0-a517-764dff1cac5d |  | note | • Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | c38d6e61-adb1-5559-9d5e-62bce7fb5db4 |  | note | Method - Site Inspection/ Document Review
label | b31b64af-b876-5e40-9dd1-9751636574e6 |  | note | Frequency - Prior construction of the regulating layer
label | 77763d8a-60ce-5aaa-8330-e248b24ae92b |  | note | Category - HP
label | 6c53df8b-354d-5e58-8d6f-531e41aede24 |  | note | Responsibility - SE/Nominated Authority
label | b7aeb5ac-2283-560d-95d3-52cdc0f6a486 |  | note | Verifying Documents - This ITP
text | 0f1c4a40-bf8d-5e15-92eb-cfb1e25f2ce7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Unsuitable Material
label | 28637f27-eaf7-5be4-88da-777592a2daf8 |  | note | Reference - Section 204.07 d)
label | 4ee12dad-2e21-58a0-b273-0c7dbb8c729a |  | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | 6a657f8e-ae64-5f69-99a7-7e1e1b9866dd |  | note | Method - Visual inspection
label | ab393f88-697d-547c-891a-6d7e78973f03 |  | note | Frequency - Each lot
label | 77bad8b5-45a8-5f90-9c35-d663e4f73afc |  | note | Category - HP
label | 79f88cef-cac3-5aec-985f-506b9bbcf11a |  | note | Responsibility - SE/Nominated Authority
label | 341c15c8-e2e0-5dd3-b553-1cd4cc68d14e |  | note | Verifying Documents - This ITP
text | 25d2ce05-845f-5da8-89be-97ff1260146e |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Groundwater
label | ef343f13-e50b-5da7-8a84-e093c4d5a21c |  | note | Reference - Section 204.06 h)
label | 553a028e-a3f3-5266-bba5-6377136eed5f |  | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | 4224f83f-f9cb-5cff-89fe-b1c8fae0c323 |  | note | • The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | c5fcd095-4929-5abc-97ab-e5fe82d60455 |  | note | Method - Visual inspection
label | cb35badf-1863-5735-b1c1-ae4e765516b4 |  | note | Frequency - Each lot
label | a6f3a1bb-a48f-56d2-b31a-07b7f663ae6c |  | note | Category - HP
label | e8ec8778-934e-5ac4-b845-7d428923cdc7 |  | note | Responsibility - SE/Nominated Authority
label | 321c9b77-559f-5c77-8850-2e0d0029e0b2 |  | note | Verifying Documents - This ITP
text | 5cc29c93-d7de-5004-bc70-edbf8bd26523 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Cut to Fill Zones
label | ef28fff6-7581-5a5c-ab8f-4b05185198c4 |  | note | Reference - Section 204.06 g)
label | 3740c484-3c6b-54eb-8dab-33ba06d58700 |  | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A/B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A/B material.
label | d2067d64-9d70-5c10-a702-ce2fda4178e0 |  | note | Method - Site Inspection
label | 271825e0-9032-5c98-9acf-c4eaae8913d0 |  | note | Frequency - Each lot
label | d7fa463f-ff5d-555e-9341-fcaa58cf3328 |  | note | Category - IP
label | 62bf0744-cfab-555e-8ea4-d9958fe4b7e2 |  | note | Responsibility - SE/Site Supervisor
label | d21ae106-4872-528c-9664-04246baf6f04 |  | note | Verifying Documents - Sign ITP
text | b7853a3f-89bc-5801-a22c-68fc8e9429d2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Proof Roll
label | 5f3b3b00-da79-5f70-bc4b-e313b36e579d |  | note | Reference - Section 173
label | c4e504ad-695b-522c-b17a-cdcad9f2b836 |  | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | 508d3ee8-213d-5ad1-92a6-28c55123ebb8 |  | note | Method - Visual inspection
label | d5ffe7ed-e254-53b0-8069-3c6fcdcc8987 |  | note | Frequency - Each lot
label | 145e8b0f-9872-570e-b580-d47b7bda2c4e |  | note | Category - HP
label | c1ee7c7f-c73e-5f50-9a3b-a4dbb871bdf7 |  | note | Responsibility - Site Engineer/Superintendent
label | f8adeb94-f708-594a-9294-8b10a7ce524d |  | note | Verifying Documents - This ITP
text | e8841163-2d3a-5df2-8ae8-8b18e8c3f3dc |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 - Compaction Testing
label | d57adf16-9421-572e-b4b8-dbd82f284b34 |  | note | Reference - Table 204.131
label | e3dbf970-9030-5587-b14e-b74169b5bc7a |  | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
label | b4804177-9c95-573b-a756-31886a0486b0 |  | note | • Ripped and re-compacted material below Cut Floor Level
label | db61d721-c6bc-5d4f-a6a5-55b15a87f3cd |  | note | • Scale B: Characteristic Density Ratio 98%.
label | b1e2ed62-9bb6-5bb2-b4b5-7ed16ddf8a4b |  | note | Attach: Compaction Test Result:
label | ddc47195-8f0c-5643-bbef-4e37faa0410c |  | note | Method - Document Review
label | 69930ca9-0e1d-55ff-a6f9-30d727e58333 |  | note | Frequency - Each lot
label | d3d77cbc-48e6-56f9-a13e-105eff55b590 |  | note | Category - IP
label | b9a7605a-22a6-58d9-a440-590963cc44a0 |  | note | Responsibility - PE/SE
label | 89aa4ba2-bf69-581e-881f-28a966fd5d40 |  | note | Verifying Documents - Test Records, Lot Register
text | 6f29cbb8-4dd8-5399-beff-85aa39d1a2c5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Post Compaction Material Property Testing
label | 4ae9b3e7-8a12-54d1-99bd-faa1cdf30a9b |  | note | Reference - Table 204,041 Table 204.141 Section 204.14 a) or b)
label | f5710c54-1e84-5b92-a5f7-830085788686 |  | note | Acceptance Criteria - Material Properties:
label | ad89f386-e9d4-5372-a868-7501995be6f4 |  | note | • CBR ≥ 2% and Swell ≤ 1.5%
label | c2117359-31fd-5765-889a-e7bee849a3f2 |  | note | • Max Permeability = 5X10-9 m/s
label | f24e6698-1386-5684-8536-ba05524ad8e4 |  | note | ○ Grading:
label | c58faac6-e896-525c-a11d-55fd4d1a335d |  | note | • 75.0mm 100%
label | db326a2f-d598-5bfe-b546-f5ef655ae1e6 |  | note | • 4.75mm 40-80%
label | b0499f27-fb8b-5ad8-85de-454ec66c0d61 |  | note | • 0.075mm 10-40%
label | 7c059b4b-9219-5f86-96dd-eff2cc5ae94f |  | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | 38d1faac-8ac9-5314-adde-4296e4e314e8 |  | note | ○ Scale B:
label | 8afa9151-0146-5863-8d72-841d801468c2 |  | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 7c34bbba-08e2-5054-a1b8-c61bbc2bb70d |  | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | b7a7f372-b7b6-5ae6-a786-987a3bd8efa5 |  | note | Attach: Post compaction test results:
label | 062f77fc-d78d-5c47-accd-8dace84592d7 |  | note | Method - Review Document
label | 51f8bee4-78a0-5201-ac8e-2233a55008ff |  | note | Frequency - Refer to Section 204
label | 2cd4ef93-85d9-5248-a4a6-539e9e5531c9 |  | note | Category - IP
label | c9482379-d5c9-5c2d-8d50-965324b74aca |  | note | Responsibility - PE/SE
label | fc808f2e-1cdb-557e-b086-3b82c92e0284 |  | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
text | eff53af4-12f9-5149-be92-f8bd6bcd573e |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6. Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Survey Conformance
label | 20060779-5a77-5092-a6e5-776a091596b1 |  | note | Reference - VicRoads 204.03f,g and h
label | 7eed938e-9995-501a-8e5e-5519c55c9e4d |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 1387e5f0-f68f-5c45-b871-376cc627e08e |  | note | ○ Level tolerances (Scale B):
label | 35e26a69-1726-587b-809c-4f2b298e5382 |  | note | • Range x = +5, -25mm
label | 6bcc3e01-eab6-54a4-bf72-89385e157d83 |  | note | • Max S = 15 mm
label | 38ee0337-3c92-5ac5-aae1-6f4b2e1c27e9 |  | note | • 40 measurements per lot
label | bb92d6a5-2093-59f1-9499-c35b6b5307ca |  | note | Method - Review Document
label | a828d010-5c8f-5e91-8047-93f965d5abf3 |  | note | Frequency - Each lot
label | f3c686bf-6e0b-5acc-b9a5-848b18ffb438 |  | note | Category - SCP
label | 3d276712-2c98-546e-8762-4841d5a5806f |  | note | Responsibility - SE/Surveyor
label | 574bf915-86aa-51a6-8b38-61942295620c |  | note | Verifying Documents - Sign ITP, Attach Survey Report
text | a448b87e-fc1e-5e41-bf7d-a0b4996be48f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 25c9af64-aa07-5448-8829-5645b0a39ac1 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 490ce730-3f19-599e-8aee-2917414efb0e |  | textbox | Name:
text | 496d3e96-9853-5840-8843-b9f1cabca955 |  | textbox | Position:
text | f9b058e4-08e6-54d4-b8bb-1fc719ff9336 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP