## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-054-CPD-Subsurface Drainage (Supply and Install) | itp |  |  |  | Yes | ITP-054-CPD-Subsurface Drainage (Supply and Install) - Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-CIV-CPD - Subsurface Drainage (Supply and Install)
label | ITP Description: CPD - Subsurface Drainage (Supply and Install)
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 27/07/2023
label | ITP created by: William McCuskey
label | ITP approved for use by: Pradeep Talasila
checkpoint | 1.1 - Non Dependent
label | Reference - VicRoads Section 702 (May 2019)
checkpoint | 1.2 - Non Dependent
label | Reference - VicRoads Section 204 (Dec 2015)
checkpoint | 1.3 - Non Dependent
label | Reference - VicRoads SD1611
checkpoint | 1.4 - Non Dependent
label | Reference - VicRoads SD1051
checkpoint | 1.5 - Non Dependent
label | Reference - VicRoads SD1631
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Drainage Pipes
label | Reference - IFC Drawings Section 702.04
label | Acceptance Criteria - Subsurface drainage pipes:
label | • Category 1, 100mm DIA Class 1000 corrugated perforated plastic pipe - with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
label | • Attach: Material Approval Ref Nos
label | Method - Verify, Document Review
label | Frequency - Each Lot prior to work start
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Granular Filter Material
label | Reference - IFC Drawings Section 702.05 Table 702.051
label | Acceptance Criteria - Granular filter material:
label | • Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
label | • Attach: Material Approval Ref Nos
label | Method - Verify, Document Review
label | Frequency - Each Lot prior to work start
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - No Fines Concrete
label | Reference - IFC Drawings Section 702.05
label | Acceptance Criteria - No Fines Concrete:
label | • Shall comply with 702.05 (e)
label | • Attach: Material Approval Ref Nos
label | Method - Verify, Document Review
label | Frequency - Each Lot prior to work start
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Geotextile Filter
label | Reference - IFC Drawings Section 702.06 Table 702.061
label | Acceptance Criteria - Geotextiles:
label | • Shall comply with 702.06
label | • Attach: Material Approval Ref Nos
label | Method - Verify, Document Review
label | Frequency - Each Lot prior to work start
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - SSD Pits, Pit Lids, Flushout Risers
label | Reference - IFC Drawings SD-1051 SD-1611 SD-1631
label | Acceptance Criteria - Subsurface drain pits: shall be Type S1 (as per SD 1611).
label | • Pit Lids shall be: Type M3 circular lid (as per SD 1051) for Type S1 pit.
label | • Flushout risers: As per SD 1631
label | • Attach: Material Approval Ref Nos
label | Method - Verify, Document Review
label | Frequency - Each Lot prior to work start
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Documentations
checkpoint | 3.1 - Check for correct documentation
label | Reference - IFC Drawings
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Method - Visual inspection
label | Frequency - Prior to commencing any activity
label | Category - WP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed-off
textbox | Date Completed:
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set Out
label | Reference - IFC Drawings Section 702.03
label | Acceptance Criteria - Survey to set out Subsurface Drainage line.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/Site Supervisor Surveyor
label | Verifying Documents - This ITP Signed-off
textbox | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Trench Excavation
label | Reference - Section 702.08
label | Acceptance Criteria - The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
label | • There shall be no departures from the grade of the base of the trench that would allow ponding of water.
label | • Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
label | • The base of the trench shall be inspected by a superintendent to verify compliance with 702.08 prior to placing beding in completed excavations.
label | Method - Visual Inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE, NA (Nominated Authority)
label | Verifying Documents - Conqa HP Release
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Placement of bedding
label | Reference - Section 702.09 (c)
label | Acceptance Criteria - Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level.
label | • Attach bedding material delivery dockets
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed-off
textbox | Date Completed:
checkpoint | 5.3 - Pipe and Geotextile Installation (if required)
label | Reference - Section 702.03, Section 702.09
label | Acceptance Criteria - Pipe shall be placed centrally in the trench on the prepared bedding and held firmly in place. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements.
label | Attach Suburface pipe and geotextile delievery dockets (if applicable)
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed-off
textbox | Date Completed:
checkpoint | 5.4 - Backfill Installation (Granular Filter Material)
label | Reference - Section 702.09 (g)
label | Acceptance Criteria - Material shall be placed moist and compacted in layers not exceeding 300mm.
label | • The method of compaction shall be in accordance with the procedures and reviewed by the NA.
label | • Attach Backfill Delivery Dockets
label | Method - Visual
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - SE, NA
label | Verifying Documents - This ITP Signed-off
textbox | Date Completed:
checkpoint | 5.5 - Backfill Installation (No Fines)
label | Reference - Section 702.09 (g)
label | Acceptance Criteria - All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing.
label | • Attach Backfill Delivery Dockets
label | Method - Visual
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - SE, NA
label | Verifying Documents - This ITP Signed-off
textbox | Date Completed:
checkpoint | 5.6 - Install Pits and Flushouts
label | Reference - Section 702.10
label | Acceptance Criteria - Subsurface drains shall have access points at the start and finish of each run.
label | • Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings.
label | • Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
label | • Attach Pit and Flushout Delivery Dockets
label | Method - Visual
label | Frequency - Each lot
label | Category - WP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed-off
textbox | Date Completed:
checkpoint | 5.7 - Marker Points
label | Reference - Section 702.11
label | Acceptance Criteria - At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
label | • Attach Marker Post Delivery Dockets
label | Method - Visual
label | Frequency - Each outlet
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed-off
textbox | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - As Built Information
label | Reference - Section 702.03
label | Acceptance Criteria - The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
label | • Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length.
label | • Attach Survey Conformance Report
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed-off
textbox | Date Completed:
checkpoint | 6.2 - Flushing
label | Reference - Section 702.09 (h)
label | Acceptance Criteria - Flushing test shall be witnessed by the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
label | • Attach Flushing Tests Records
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE, NA
label | Verifying Documents - Conqa HP Release
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Inspection of Subsurface Drainage - CCTV
label | Reference - Section 702.09 (i)
label | Acceptance Criteria - All subsurface drainage lines shall be inspected, after the flushing test as per clause 702.09(h), and prior to placement of asphalt by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is free from obstruction and to check for visible signs of defects.
label | • Attach CCTV Inspection Record
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE, NA
label | Verifying Documents - Conqa HP Release
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed-off
textbox | Date Completed:
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP