## Breakdown
Thermal Solutions
B05
Ground Floor
|  |  | Car Park | pre-populate | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
|  |  | MSB/COMMS | pre-populate | S - S - Kitch Extraction
|  |  | Corridor | pre-populate | S - S - Ventilation - Corridors Ventilation
|  |  | A54 | pre-populate | S - S - Ventilation - Apartment Ventilation
|  |  |  | pre-populate | S - S - Air conditioning
|  |  |  | pre-populate | S - S - Kitch Extraction
|  |  | A55 | pre-populate | S - S - Ventilation - Apartment Ventilation
|  |  |  | pre-populate | S - S - Air conditioning
|  |  |  | pre-populate | S - S - Kitch Extraction
Level 1
|  |  | Corridor | pre-populate | S - S - Ventilation - Corridors Ventilation
|  |  | Cable riser | pre-populate | S - S - Kitch Extraction
|  |  | B54 | pre-populate | S - S - Ventilation - Apartment Ventilation
|  |  |  | pre-populate | S - S - Air conditioning
|  |  |  | pre-populate | S - S - Kitch Extraction
|  |  | B55 | pre-populate | S - S - Ventilation - Apartment Ventilation
|  |  |  | pre-populate | S - S - Air conditioning
|  |  |  | pre-populate | S - S - Kitch Extraction
|  |  | B56 | pre-populate | S - S - Ventilation - Apartment Ventilation
|  |  |  | pre-populate | S - S - Air conditioning
|  |  |  | pre-populate | S - S - Kitch Extraction
|  |  | B57 | pre-populate | S - S - Ventilation - Apartment Ventilation
|  |  |  | pre-populate | S - S - Air conditioning
|  |  |  | pre-populate | S - S - Kitch Extraction
|  | Completion documents-BCO10332878 |  | pre-populate | CST - S - Completion Documents

## Checklist
checklist | S - S - Ventilation - Apartment Ventilation
section | Pre-start checks
checkpoint | Penetrations done in floors and walls (if needed)
checkpoint | Space for ducting (no trades in the way)
checkpoint | Pipe through exterior wall installed by RHC to connect to
checkpoint | Drawings and work scope confirmed
section | First Fix
checkpoint | Ductwork run straight level and well supported
checkpoint | All ductwork joints sealed
checkpoint | All SAB joints sealed and taped
checkpoint | All flexible ducts cable tied and taped to duct
checkpoint | Identify locations and correct model of Fire damper to be installed
checkpoint | Inform RHC PM Fire Dampers are ready for sealing
checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required postition
checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
checkpoint | Install using Materials specified in the PS1
checkpoint | Upload Photos of Install
checkpoint | All seismic restraints in place (if needed)
checkpoint | Flexible ducts fixed in place to grille location
checkpoint | Identify Fan Upgrade Requirement
checkpoint | Area Clear for Install of Ducting, Fan, and Control Box
checkpoint | Install Fan, ducting and control box as per spec.
checkpoint | Grille locations/access panels marked on plans
checkpoint | Mechanical First Fix complete
section | Second Fix
checkpoint | Ceiling fans installed square and level
checkpoint | Kitchen range hood installed by RHC to connect to
checkpoint | Fingerprints removed from grilles/walls/ceilings
checkpoint | Fan plugged in before install to ceiling
checkpoint | External louver supplied by TSL, installed by RHC completed
checkpoint | Commissioning form completed & given to TSL
checkpoint | Mechanical Second Fix complete
section | Commissioning
checkpoint | Correct product used as per requirements
checkpoint | Correct design followed as per drawings
checkpoint | Mechanical Plant commissioned
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
section | Pre-start checks
checkpoint | Area clear, access good, enough space for install
checkpoint | Duct Route clear, Penetrations completed
checkpoint | Nogs/Supports in place
section | First Fix
checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations&)
checkpoint | Mechanical First Fix complete
section | Second Fix
checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
checkpoint | Mechanical Second Fix complete
section | Commissioning
checkpoint | Good access to all areas of building
checkpoint | Power live to Mechanical Plant
checkpoint | Mechanical Plant commissioned
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | S - S - Ventilation - Corridors Ventilation
section | Pre-start checks
checkpoint | Area clear, access good, enough space for install
checkpoint | Duct route clear, Penetrations complete
checkpoint | Nogs/Supports in place
section | First Fix
checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations&)
checkpoint | All flexible ducts cable tied and taped to duct
checkpoint | Identify locations and correct model of Fire damper to be installed
checkpoint | Install to Manufacturers Specifications
checkpoint | Inform RHC PM Fire Dampers are ready for sealing
checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required postition
checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
checkpoint | Install using Materials specified in the PS1
checkpoint | Upload Photos of Install
checkpoint | Refer back to Seismic Engineer for PS4 Production.
checkpoint | Mechanical First Fix complete
section | Second Fix
checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
checkpoint | Mechanical Second Fix complete
section | Commissioning
checkpoint | Mechanical Plant commissioned
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | S - S - Kitch Extraction
section | Pre-start checks
checkpoint | Area clear, access good, enough space for install
checkpoint | Duct Route clear, Penetrations completed
checkpoint | Nogs/Supports in place
section | First Fix
checkpoint | Fan installed straight and level and correct orientation
checkpoint | Correct Fan installed
checkpoint | Fan seismically braced and vibration isolated
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | S - S - Air conditioning
section | Pre-start checks
checkpoint | Area/base/wall ready for outdoor unit
checkpoint | Pipework route all clear, penetrations complete
checkpoint | Nogs/ply in place for indoor unit
checkpoint | Drain 1m from indoor unit location by plumber
section | First Fix
checkpoint | Complete length of pipework is insulated and acceptable
checkpoint | Drain installed and insulated
checkpoint | Supply cable installed correctly, protected and secured
checkpoint | Outdoor wall brackets in place
checkpoint | Interconnecting cables correctly installed and protected
checkpoint | Mechanical First Fix complete and acceptable
section | Second Fix
checkpoint | System pressure checked and still holding pressure and acceptable
checkpoint | Correct Indoor unit installed, level and tight to wall and acceptable
checkpoint | Correct Outdoor unit installed and secure
checkpoint | Indoor unit serial no. recorded
checkpoint | Outdoor Unit serial no. recorded
checkpoint | Indoor unit run, fan speeds, modes etc. are acceptable
checkpoint | Air conditioning Second Fix complete and acceptable
section | Commissioning
checkpoint | Installer confirmed commissioned and paperwork submitted
checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint | Electrical testing complete
checkpoint | Commissioning complete and acceptable
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
bool | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS