## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | f67b7922-5df5-43e5-ae1b-ac8a671e7706 |  | checklist | PRE - S - First Fix - Ventilation |  |  |  |  | Yes | PRE - S - First Fix - Ventilation | 04d37161-d0e2-4489-aee4-e36d8e89ea76
checkpoint-status | ee2079ed-1584-4e26-9401-d653001d0145 |  | checkpoint | Ductwork run straight level and well supported
checkpoint-status | 4b3e7dfe-558f-4a54-b285-5cc5c9947e66 |  | checkpoint | All ductwork joints sealed and acceptable
checkpoint-status | 881173d2-3285-4b4c-b0b1-ab0aa12811d1 |  | checkpoint | All SAB joints sealed and taped and acceptable
checkpoint-status | 0d645ded-6cdf-49af-855a-e78f5856ae8d |  | checkpoint | All flexible ducts cable tied and taped to duct and acceptable
checkpoint-status | e7915e73-0570-4620-9275-35773a373bf1 |  | checkpoint | All seismic restraints in place (if needed) and acceptable
checkpoint-status | 0d44829b-b042-4ad7-a1a1-069f0ab5fb16 |  | checkpoint | Flexible ducts fixed in place to grille location and acceptable
checkpoint-status | 8c16030f-4797-4b1e-819a-76acc3495b9e |  | checkpoint | Grille locations/access panels marked on plans and acceptable
checkpoint-status | e710736e-d3b1-4cab-80d5-28a88ea1c5d2 |  | checkpoint | Mechanical First Fix complete and acceptable and area clean and tidy for next trade
checklist-sectioned | 8faf74b7-5208-4496-bf4c-3c93ec79b4ba |  | checklist | Coolroom |  |  |  |  | Yes | Coolroom | 1db475f6-acbe-43dd-8a52-01be30bf2950
checkpoint-group | 02a9b6dc-6480-4cfe-b43b-426b17f41692 |  | section | Pre-start:
checkpoint-status | 26fd7fb5-565c-437f-b9ad-9e751010acb7 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 8c7319ef-125a-4e17-8575-2b91741887d0 |  | checkpoint | Area/base/wall ready for outdoor unit
checkpoint-status | 7718d102-b28d-4daf-bfb0-226ed2a1de6e |  | checkpoint | Any required drains for outdoor unit in place
checkpoint-status | 24b7b3a2-9b0b-4147-9207-f599aecd2a94 |  | checkpoint | Area/Base/Walls ready for Coolroom Panels. Floor requirements met.
checkpoint-status | aadb8c59-57b4-4f6f-8c23-9c36fb69ed9a |  | checkpoint | Check set down for any rough surfaces (Smooth set down required).
checkpoint-status | ba9b82d5-6d77-4229-8fb1-ba56311684cd |  | checkpoint | Pipework route all clear, penetrations complete
checkpoint-status | 6db43ac2-b9c1-41e6-bfae-454d2c47cf13 |  | checkpoint | Nogs in place
checkpoint-status | b706975c-ba59-4b78-91d7-fdeeeb826b43 |  | checkpoint | Drain in place by plumber
checkpoint-status | b70f428b-b5ea-4a9c-b711-1538d0579eb8 |  | checkpoint | Measure set down and mark out door cut out
checkpoint-status | c4ac3401-872d-4564-9b13-c306a5fbdf27 |  | checkpoint | Check if set down is dry and area is water tight
checkpoint-group | 6bd52628-3da2-4190-8d86-fa47a2d73d3c |  | section | First Fix:
checkpoint-status | 5d942f9b-7293-456c-bbf6-f36f78717d86 |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | 3b61df33-ee92-42a9-a224-d1c9a1a5c663 |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
checkpoint-status | 3efeb514-de0f-4e4f-a78a-4b39fa97b695 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | ae9d58b9-973d-4182-a52b-72b97487b6e5 |  | section | Second Fix:
checkpoint-status | 3133b3c4-0fc9-48c8-a11c-4637aa81c00c |  | checkpoint | Area clear and access good for Second Fix
checkpoint-status | 353a1dd8-7b43-4edb-9bf9-ac644accb7a2 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
checkpoint-status | 3abfbed8-5eea-47fb-aaf7-2d29fbcf62c7 |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | 096886d7-6dc9-46f2-a1a9-e3049d4f56da |  | section | Commission:
checkpoint-status | 42c88671-7aa4-42d8-af8f-a60b7cd367cd |  | checkpoint | Good access to all areas of building
checkpoint-status | b3ec6c7e-ef68-41c3-bb7f-22b94f75a5a2 |  | checkpoint | Power live to Mechanical Plant
checkpoint-status | 484fface-5ca2-46b6-b6a7-3202642048b2 |  | checkpoint | Mechanical Plant commissioned
checklist-sectioned | 5428607a-d96a-4748-88d9-e2b0306d4279 |  | checklist | Car Park SF/EF |  |  |  |  | Yes | Car Park SF/EF | 311034f1-6e59-4c69-beca-709bf1831724
checkpoint-group | a0e20fca-5ec5-4fc5-b0d3-aabefd84a8c5 |  | section | Pre-Start SA Fan
checkpoint-status | ffb211ba-abde-4e81-95c7-1233337e46a1 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | a3a85950-2d3c-4078-9154-f8c9cff65f50 |  | checkpoint | Penetrations complete
checkpoint-group | c75a4771-c4fa-4bde-889d-cf1c17bebbce |  | section | First Fix SA Fan
checkpoint-status | 9d73ce30-0a2d-4813-a9a4-cc5ee958fd5b |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | ac47ca67-8bdc-49bc-b65f-c4476abcc455 |  | checkpoint | Correct Fan installed
checklist-flat | cd087dcc-13f7-412d-82bc-02c8e62ce6b9 |  | checklist | Pre-commencement checks |  |  |  |  | Yes | Pre-commencement checks | 33b8dcda-128a-4a85-b4d4-f75c3403b125
checkpoint-status | b9ba1e75-0615-4cc4-ae62-fb0c92edf6fc |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status | 58fa83dd-00ec-4019-b4be-037373fb5406 |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status | 3646550b-9e48-49d5-82a7-59409f6c8622 |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
checkpoint-status | bd2b938e-d5ec-41d5-a4a0-4eff75d9b558 |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status | 8942f9e2-3af3-4499-885d-0c9a01375fa9 |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status | e7af5502-cca0-471b-ad47-91343c12f785 |  | checkpoint | Matrix/insights Setup (if required)
checklist-sectioned | 79f96284-8818-45a7-b1be-e49d014bfae6 |  | checklist | Split HW |  |  |  |  | Yes | Split HW | 34702873-fbcb-4074-9591-b2e114a9e817
checkpoint-group | 17926349-01cc-4540-9ff0-69e6a748644d |  | section | Pre-start:
checkpoint-status | 62f66d30-c4cc-4e32-b5e5-3ce56bd46548 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 13d89616-1ec0-4b1e-9266-75ea470ae131 |  | checkpoint | Area/base/wall ready for outdoor unit
checkpoint-status | 5d12cfd1-5a94-4077-bafd-f6a0cba02e38 |  | checkpoint | Pipework route all clear, penetrations complete
checkpoint-status | 79a2a823-7872-4526-bfa8-ab5acc244d20 |  | checkpoint | Nogs in place
checkpoint-status | 585c101a-892b-4fd9-91c1-775ff95d4d66 |  | checkpoint | Drain 1m from Indoor unit location by plumber
checkpoint-group | 539902a4-e89b-45a9-898a-4fae957229c0 |  | section | First Fix:
checkpoint-status | 0b8b12f1-d21f-457f-a720-eaff8e6b73d3 |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
checkpoint-status | 883d85d4-c7ac-4c81-af4a-9ab30306874b |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 4aed454c-4ccd-48c3-9845-71c03e75ba02 |  | section | Second Fix:
checkpoint-status | fb6ad031-a7d8-42ea-b488-c8227fffa24f |  | checkpoint | Area clear and access good for Second Fix
checkpoint-status | 9f320225-6d82-4bd9-a2e5-0ee3113fe259 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
checkpoint-status | 0cb6fc73-3188-4100-bbed-72c1243cdcd7 |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | 30b63218-be0e-4be2-8f27-8fcd7b201864 |  | section | Commission:
checkpoint-status | 4acd4b26-5987-46c9-b8d9-bed9848c4127 |  | checkpoint | Mechanical Plant commissioned
checklist-sectioned | ea711d37-9424-4214-bad5-76313303b5be |  | checklist | Jet Pulse Fan |  |  |  |  | Yes | Jet Pulse Fan | 351c9fe9-420f-4516-8266-7de82966129d
checkpoint-group | 13ef82dd-798e-4b69-a534-557469c62633 |  | section | Pre-Start SA Fan
checkpoint-status | 654ca13a-88ae-4e1a-afd8-5b55b9006d54 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | a27fdf3e-9fd9-4b70-8d9a-61ebec2ce5c6 |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status | 962e909c-a85b-4b23-89dd-08ad136d2be9 |  | checkpoint | Nogs/Supports in place
checkpoint-group | ce67b652-a5df-40d0-aa6b-44265051db54 |  | section | First Fix SA Fan
checkpoint-status | 70a69cb6-eaa2-4884-bca0-a447aad5d45f |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | c8a1eeb1-2ee0-4ccc-98ba-be0bb3b61eea |  | checkpoint | Correct Fan installed
checkpoint-status | c14a7536-ecf0-4058-8aac-b514fab5a1b1 |  | checkpoint | Fan seismically braced and vibration isolated
checklist-sectioned | d504bf80-58a7-4cf1-b4cf-f77f47998158 |  | checklist | S - S - Ventilation - Apartment Ventilation |  |  |  |  | Yes | S - S - Ventilation - Apartment Ventilation | 3927f38a-c444-4b05-9c99-ddd2f1adef6f
checkpoint-group | 9791abeb-7b3e-486b-9434-fba7f7a83dce |  | section | Pre-start checks
checkpoint-status | 39e4c9ba-a20f-4edf-b2a0-a839cd90444c |  | checkpoint | Penetrations done in floors and walls (if needed)
checkpoint-status | ee1b16d9-44a2-4de9-bdd6-18d8d620c316 |  | checkpoint | Space for ducting (no trades in the way)
checkpoint-status | 1bbd186f-cf51-4d44-9382-d2060ea9a333 |  | checkpoint | Pipe through exterior wall installed by RHC to connect to
checkpoint-status | 79876caf-5172-48b6-85db-da8d6e218867 |  | checkpoint | Drawings and work scope confirmed
checkpoint-group | 24156794-a6ce-4f7f-bc6e-883a21339bb4 |  | section | First Fix
checkpoint-status | 39df880d-9eee-41b3-bc48-6d3ed16da32e |  | checkpoint | Ductwork run straight level and well supported
checkpoint-status | 492868c5-d82e-473d-93aa-a21bb8abdf60 |  | checkpoint | All ductwork joints sealed
checkpoint-status | 19eb9e6c-b58f-4c8b-b585-1beb26efcc3c |  | checkpoint | All SAB joints sealed and taped
checkpoint-status | 23a3fbc5-0883-4054-912d-1fec657a3cfb |  | checkpoint | All flexible ducts cable tied and taped to duct
checkpoint-status | 3cf110ec-bea9-4ebf-8df0-2cc72176b99e |  | checkpoint | Identify locations and correct model of Fire damper to be installed
checkpoint-status | 2e865a79-52b2-42b2-a497-0b74c36ee4f9 |  | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
checkpoint-status | 93cd6dda-a2ca-44ac-a12d-50a4d3a89fec |  | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
checkpoint-status | 41068e40-1a57-42a6-a85b-e02eccd1570b |  | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
checkpoint-status | ba2de229-af99-4356-b384-c12c68580f8b |  | checkpoint | Install using Materials specified in the PS1
checkpoint-status | a75ab1a7-ceb0-4942-a98e-b0766a7ec61b |  | checkpoint | Upload Photos of Install
checkpoint-status | 66a42859-37ae-4db8-a08d-bb39a23df827 |  | checkpoint | Refer back to Seismic Engineer for PS4 Production.
checkpoint-status | 9a1c0500-cfee-4c24-9794-59df594b27de |  | checkpoint | Flexible ducts fixed in place to grille location
checkpoint-status | 106fd41b-98c5-4c65-b7c3-008e00c95c03 |  | checkpoint | Identify Fan Upgrade Requirement
checkpoint-status | 480dca99-842b-49f8-bb36-720f407cffac |  | checkpoint | Area Clear for Install of Ducting, Fan, and Control Box
checkpoint-status | 58eecc94-6768-4777-bfaa-b68fd00bc854 |  | checkpoint | Install Fan, ducting and control box as per spec.
checkpoint-status | ea78aab6-a0f9-4528-bd6e-36f0f30a3683 |  | checkpoint | Grille locations/access panels marked on plans
checkpoint-status | 9c4b2b4b-d4f9-47c5-a638-0de4d2b8d208 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 7505c5ee-190f-45c9-a537-fa41eec36f5d |  | section | Second Fix
checkpoint-status | af4ae69a-21a0-4a4f-95cf-773baf94dc5f |  | checkpoint | Ceiling fans installed square and level
checkpoint-status | 1c8a0306-8b7b-45f2-9af6-615adb5b7626 |  | checkpoint | Kitchen range hood installed by RHC to connect to
checkpoint-status | a56c67f8-2a9f-46fd-b088-0402ac8bdd22 |  | checkpoint | Fingerprints removed from grilles/walls/ceilings
checkpoint-status | 993b144a-77de-4fda-9020-691601797eb9 |  | checkpoint | Fan plugged in before install to ceiling
checkpoint-status | f83b8baf-e9a2-4a2a-9e46-593d9d9092cb |  | checkpoint | External louver supplied by TSL, installed by RHC completed
checkpoint-status | e109c387-1a0e-4c44-ab9a-76dae3c9d398 |  | checkpoint | Commissioning form completed & given to TSL
checkpoint-status | 65658b0a-858a-4afb-96a2-ecec5fe1c61e |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | 6f93f530-81ab-4909-932e-b1f15d50fb77 |  | section | Commissioning
checkpoint-status | f010f465-b290-4a76-a69d-5fb612463308 |  | checkpoint | Correct product used as per requirements
checkpoint-status | 8287d2e7-fdc4-4c7f-ba07-3716e08379c3 |  | checkpoint | Correct design followed as per drawings
checkpoint-status | 1d79833b-972d-48e0-b3c9-39644ec95b25 |  | checkpoint | Mechanical Plant commissioned
checkpoint-status | 1b477b5b-7cee-4246-91de-2fd82a5cdde0 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | c8f6ad1a-95e1-4f3c-8d27-49d665d62175 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | e533d10a-e37b-4979-87d8-3bf8870f8478 |  | checklist | VRV Cass |  |  |  |  | Yes | VRV Cass | 4a572a07-2c56-4969-85f3-8112ad6a45e0
checkpoint-group | c247870d-2eb9-490f-bf16-1143d6e6202d |  | section | Pre-start:
checkpoint-status | 24f2fb4c-9e96-4c7f-aa5a-372e626fe3b5 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 52e44925-603a-46e2-abbd-ef8b2f79d848 |  | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
checkpoint-group | cf443687-19dd-49ba-81b0-2687e6854a8b |  | section | First Fix:
checkpoint-status | 686e094f-a7ef-4669-a068-07c6a84793f9 |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | c1c57378-9500-4712-91bc-97b1e39f6c4c |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
checkpoint-status | b9bdcc83-3a65-4a7c-ba4b-d82c5078eb77 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 0e196969-5c0e-42be-9516-2e70b0182580 |  | section | Second Fix:
checkpoint-status | 0643f844-5ecf-4d5b-ad69-62e499bce52c |  | checkpoint | Area clear and access good for Second Fix
checkpoint-status | c2a65c14-e259-4721-b31a-a39930c554e2 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
checkpoint-status | 9620d72c-45dd-4beb-a9e7-310974821911 |  | checkpoint | Mechanical Second Fix complete
checklist-sectioned | bcafe476-0724-438f-a64f-283296bb9f77 |  | checklist | HRV QA |  |  |  |  | Yes | HRV QA | 59453ec0-a3f7-4857-84a6-7eb90dca3342
checkpoint-group | 34b5f5f5-da44-48dd-8618-1d39d29e5874 |  | section | Pre-start:
checkpoint-status | ab86fcb3-ec84-440c-ab35-063d0d50c469 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 893b15a8-b5a4-45fe-b290-370a766b57ff |  | checkpoint | Duct route clear, Penetrations complete
checkpoint-status | 2659339c-f852-4c4a-bf79-e5cff8b94376 |  | checkpoint | Nogs/Supports in place
checkpoint-group | 102b2555-9219-46a3-8f1f-41c9f08c5d28 |  | section | First Fix:
checkpoint-status | df715d3e-a909-4f97-bc87-aa1deb6c874d |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | 7b3b0de6-dfdb-44e7-9b28-7474909e496a |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
checkpoint-status | f98073a1-1dd7-4762-b6b8-e537691c5613 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 8489451c-4bda-4975-b84c-5dfaee4fe47c |  | section | Second Fix:
checkpoint-status | 50c8e6fa-7602-4eaf-a52d-bd72aad52e87 |  | checkpoint | Area clear and access good for Second Fix
checkpoint-status | 9ca8b067-2d2a-4539-9017-bbf04f52e6f0 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
checkpoint-status | 03248a8a-b71a-46ef-9a37-0ea69165486b |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | 18496132-013c-46e6-9467-72c98ac71e5d |  | section | Commission:
checkpoint-status | 672ead26-fe6e-4822-a420-72583c156f04 |  | checkpoint | Good access to all areas of building
checkpoint-status | ea5566d3-e3ae-4beb-936f-153c1ae51660 |  | checkpoint | Power live to Mechanical Plant
checkpoint-status | 3579c4a0-e962-4e31-965b-320c787db890 |  | checkpoint | Mechanical Plant commissioned
checklist-flat | a9673207-c98b-45af-b455-d73d0c793cb2 |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 689dc699-8da8-47ff-ad58-69104fe51f8b
checkpoint-status | e1df456c-6a98-451e-8ff6-9b13a4338fa2 |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | 63826e29-d281-579e-ba7a-b348ad99a991 |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | 975c6935-98cb-590a-872a-22ed164e902c |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | e6b2c015-e866-4b00-99bc-9f33b8019c9e |  | signoff | Request Signoff
checkpoint-status | be18782d-136f-440a-aef2-19018d730d75 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 00af2a18-14fd-41e2-bcbe-e6331ad154d8 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | 125c2c8c-cb1b-4fae-861d-71ed3ce6cddd |  | checklist | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  |  |  |  | Yes | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan | 7a3c63d8-7824-44ea-9e80-3c6c1672ecc9
checkpoint-group | 3286817e-b66e-494a-9411-805652416d2e |  | section | Pre-start check
checkpoint-status | c6a765bd-7aa3-4bd3-8987-89e764a54942 |  | checkpoint | Area clear, access god, enough space for install
checkpoint-status | bce85748-c6cc-424b-ba1b-541982a94383 |  | checkpoint | Duct Route clear, Penetrations completed
checkpoint-status | 04634d0d-68c8-4126-8e5a-a8d8e61a983c |  | checkpoint | Nogs/Supports in place
checkpoint-group | 216dfc8b-0090-4cae-a743-69905d5c0487 |  | section | First Fix
checkpoint-status | fdd38ffb-6bc0-4643-b91d-9238f4084149 |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | 8f13699b-fffc-4d1e-b03f-2325b3abd8f5 |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
checkpoint-status | 1af4b372-6d4f-47dc-86dd-52010d9819e9 |  | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
checkpoint-status | 76ca3fed-c3ca-4298-a385-f858149b03b4 |  | checkpoint | Install using Materials specified in the PS1
checkpoint-status | f5fb0574-b92b-4470-9aa0-aa7e43173346 |  | checkpoint | Upload Photos of Install
checkpoint-status | e7cc22b9-c4e7-4c55-9def-2c9e36f546ec |  | checkpoint | Refer back to Seismic Engineer for PS4 Production.
checkpoint-status | 2fc034dc-2963-45c5-a645-3db3f20fbaa0 |  | checkpoint | All seismic restraints in place (if needed)
checkpoint-status | a240a9a1-3060-4b85-b3ab-9aa9a2107392 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 6d88c13f-6977-4aef-9274-c9a840d14894 |  | section | Second Fix
checkpoint-status | cddb5d8f-1f0c-4d46-a837-078171a6a208 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
checkpoint-status | 708635ba-37fe-4cc3-a06c-7a3fe3351369 |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | bd5ed38e-bfbf-4689-a0df-d558bf3674b9 |  | section | Commissioning
checkpoint-status | f84c39e0-3d37-4641-872c-aba3fa5b0298 |  | checkpoint | Good access to all areas of building
checkpoint-status | 74333665-8e5e-4997-aed3-88bbd46ed2a9 |  | checkpoint | Power live to Mechanical Plant
checkpoint-status | f74e7e53-44b1-400d-956e-43d89007eac4 |  | checkpoint | Mechanical Plant commissioned
checkpoint-status | 189796be-37ea-4f29-ad36-60f9ce334f15 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 84a20122-3e11-4659-8b99-1604b0c65a51 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | 39db1fd7-06da-45d9-93d6-be7a1b7cd827 |  | checklist | S - S - Ventilation - Corridors Ventilation |  |  |  |  | Yes | S - S - Ventilation - Corridors Ventilation | 7e16931e-414d-4c1d-8207-be93b4529e77
checkpoint-group | 0fc0d336-2355-4b6e-a40d-26ff632772eb |  | section | Pre-start checks
checkpoint-status | 0fe2d1cb-2dc7-4267-85df-52253fb4d395 |  | checkpoint | Area clear, access god, enough space for install
checkpoint-status | f93067d4-12ce-405d-85c7-3e09e4e8437a |  | checkpoint | Duct Route clear, Penetrations completed
checkpoint-status | 19b5160e-2be5-45d5-98ab-d0990efb0d25 |  | checkpoint | Nogs/Supports in place
checkpoint-group | 27b4b2d5-ed6b-4a22-b97e-ab4633efa1aa |  | section | First Fix
checkpoint-status | 32fd0144-a189-4c06-885d-56ab9aae837e |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | acf7cdb4-fe74-4946-a16c-40ddda1aec0a |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
checkpoint-status | ecee6e5f-8d34-4d93-b4dc-dee4494872fa |  | checkpoint | All flexible ducts cable tied and taped to duct
checkpoint-status | e61f2145-cb3a-430c-92d9-f658f1bc738d |  | checkpoint | Identify locations and correct model of Fire damper to be installed
checkpoint-status | 1fca6b58-a937-416f-b68f-a08186bc3753 |  | checkpoint | Install to Manufacturers Specifications
checkpoint-status | 8f657218-4b92-4e2f-abc4-5ee72d977f25 |  | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
checkpoint-status | d262feb8-2484-4819-81b4-f068b7a5c848 |  | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
checkpoint-status | 1e1e5471-ee10-4f79-841a-a488aedf73fb |  | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
checkpoint-status | bd6d8eb6-5ed3-42c1-a7c6-0f1ec26fda5f |  | checkpoint | Install using Materials specified in the PS1
checkpoint-status | 3cc3f6bd-398d-4bbf-8721-6b4c698ec14a |  | checkpoint | Upload Photos of Install
checkpoint-status | 9db358c8-f3e2-48b8-9edc-0ac40b52e9d5 |  | checkpoint | Refer back to Seismic Engineer for PS4 Production.
checkpoint-status | 8b8e9242-bbfc-4f30-bba2-49fc9d13fdbc |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 85378251-173f-451a-abd3-57073e0de7bb |  | section | Second Fix
checkpoint-status | c0527c0d-0007-44fa-a55f-3c234651f784 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
checkpoint-status | 5df1d904-fb62-41d9-8a63-c6cd8ab02afd |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | 0a446913-9482-4366-a8a4-e8556d4eb2fd |  | section | Commissioning
checkpoint-status | 90264f31-bc6e-46a9-b185-11d1f1eb8a7c |  | checkpoint | Mechanical Plant commissioned
checkpoint-status | dae73bdc-03d0-4e65-be1d-4f204ad10814 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | cebbb8d7-a7de-4c42-b125-fbec9618823b |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 0bf1e89c-0c2c-4805-9feb-5ce333e2fe2c |  | checklist | PRE - S - First Fix - Air Conditioning |  |  |  |  | Yes | PRE - S - First Fix - Air Conditioning | 828d1cf5-885b-4cbb-9bf4-be1d050a9e4b
checkpoint-status | b80b8b8c-00e3-4567-9581-4bdc4cfced98 |  | checkpoint | Complete length of pipework is insulated and acceptable
checkpoint-status | ecc4b35c-3754-4f55-b51a-35f11e025a4f |  | checkpoint | Drain installed and insulated
checkpoint-status | 703f3add-a2c0-492e-ba82-eb2bdce2a228 |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | 6edc5a89-f470-4707-a83b-fc491d60778d |  | checkpoint | Outdoor wall brackets in place
checkpoint-status | aea5a391-6a64-4e3d-8b11-201f599c8909 |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | dd58e550-dc53-4581-af8e-6f156adbe628 |  | checkpoint | Mechanical First Fix complete and acceptable and area clean and tidy for next trade
checklist-sectioned | f2532f17-de54-44d6-bc3e-f110bd5b51c3 |  | checklist | VRV HW |  |  |  |  | Yes | VRV HW | 8edb5d38-c57e-4f98-9100-429e0c3063e5
checkpoint-group | 968cc2fb-82e7-4b19-a811-1722814f5459 |  | section | Pre-start:
checkpoint-status | c388687f-9ff8-492c-ac66-eadb18b09f28 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | db124dc7-fc9c-428c-bcad-9ff8fa3894b3 |  | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
checkpoint-group | 62d19ca9-9ecd-4e7a-96bc-0086fb3d7d6a |  | section | First Fix:
checkpoint-status | 3473b7c2-d4ed-45bd-b1ab-729e84e1032e |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | 5a2369c4-f354-46ed-9f74-d7765eafc2c2 |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
checkpoint-status | 87ccb11a-62bf-4a38-a9ed-7d9240702873 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 013806b9-ffa9-4176-ab23-d9f9f61a13ba |  | section | Second Fix:
checkpoint-status | 5e106cee-3c51-41d7-b766-0fe45dcd655a |  | checkpoint | Area clear and access good for Second Fix
checkpoint-status | 49a945f5-8ca3-48f7-9e00-a6154316f671 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
checkpoint-status | cdf8c3c8-dd90-4e00-b23d-d1b2a6052fae |  | checkpoint | Mechanical Second Fix complete
checklist-sectioned | ef697c85-d7ca-4adb-b376-67d34cb34d55 |  | checklist | SA Fan |  |  |  |  | Yes | SA Fan | 90741ac5-a876-49f0-a360-9d5f3dbd0d7e
checkpoint-group | 3016b3f1-fd26-452b-b156-2b08a63401a4 |  | section | Pre-start:
checkpoint-status | 87f0fcc0-e467-4227-8b29-b8f29fa3157a |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 96aa72fa-8d4e-45a5-b7f6-6ca44e12be38 |  | checkpoint | Duct route clear, Penetrations complete
checkpoint-status | 76da37c2-bd55-48b9-a2ec-909caf84367c |  | checkpoint | Nogs/Supports in place
checkpoint-group | 13ad43db-f07c-4450-b5f1-18695c6ee574 |  | section | First Fix:
checkpoint-status | 9c562a75-8b65-42af-aa20-f9d1caf1b6d0 |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | 12141cde-e4fe-4414-8392-9ce1baed7b62 |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
checkpoint-status | 450b7cd8-06ce-4119-b677-250a3a0fb55a |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 20549bce-f110-4af7-b9fe-b928bd5a611f |  | section | Second Fix:
checkpoint-status | 99528c7b-5644-411a-afdc-a57eae733654 |  | checkpoint | Area clear and access good for Second Fix
checkpoint-status | 317cce1a-476b-4e63-96f9-5e558bd0127b |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
checkpoint-status | ed1af5cf-5375-470f-b4f4-541e799eea1f |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | d06f1af5-da6a-45c9-b3f2-39adb8d21335 |  | section | Commission:
checkpoint-status | 88d5bc0e-c59b-4258-983a-e949d2d61309 |  | checkpoint | Mechanical Plant commissioned
checklist-sectioned | aab361e0-b9d0-49d8-93cc-fc6fb7337b89 |  | checklist | Ventilation |  |  |  |  | Yes | Ventilation | ce7a1dfe-0c73-4a40-8036-ea3190f62669
checkpoint-group | 4e5d2d19-4ad7-4634-98a8-3d21becbd234 |  | section | Preinstall checks
checkpoint-status | b09bc95d-c2f6-425d-8759-1d2acabbc05b |  | checkpoint | Area accessible, clean and tidy
checkpoint-status | 2cb9e568-156e-4f59-a5e4-d2bb628a7a02 |  | checkpoint | Penetrations done in floors and walls (if needed)
checkpoint-status | 624266ac-bdee-4733-bf4f-dcc10bec3b3a |  | checkpoint | Space for ducting (no trades in the way)
checkpoint-status | b9b9fb0d-4534-47c7-a2df-64783939a450 |  | checkpoint | Pipe through exterior wall installed by RHC to connect to
checkpoint-status | 96130a53-dc6c-4e01-877a-596673005b42 |  | checkpoint | Drawings and work scope confirmed
checkpoint-group | bf1b9f86-983c-4e35-927d-1bb823a65c4d |  | section | First Fix - Apartment Ventilation
checkpoint-status | 0815da4a-934a-42d6-97c0-706164aaf2af |  | checkpoint | Ductwork run straight level and well supported
checkpoint-status | 3353c35e-e0b4-49d7-afac-95fb9b8ba77a |  | checkpoint | All ductwork joints sealed
checkpoint-status | 9cedb65b-1679-484c-b66d-895b826a5ae7 |  | checkpoint | All SAB joints sealed and taped
checkpoint-status | 789070a9-8a97-428e-8c26-906b09af4a12 |  | checkpoint | All flexible ducts cable tied and taped to duct
checkpoint-status | d85e7179-bd26-494e-94a5-3a99bbd43169 |  | checkpoint | All seismic restraints in place (if needed)
checkpoint-status | bd42f1a3-1600-428a-9af3-61b7d0c66b9e |  | checkpoint | Flexible ducts fixed in place to grille location
checkpoint-status | 1670c60d-28ed-451d-9560-46b5e96c86b8 |  | checkpoint | Grille locations/access panels marked on plans
checkpoint-status | d2dfa05a-a76e-42f2-9d16-9ed1df087605 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | ad2cf5c5-e185-473b-8879-3de9a6e10b81 |  | section | Second Fix - Apartment Ventilation
checkpoint-status | 9caf8999-b716-4664-a5aa-0446e96ffb70 |  | checkpoint | Ceiling fans installed square and level
checkpoint-status | 73e5db31-984c-4518-8fda-c0bf4c4bbe18 |  | checkpoint | Kitchen range hood installed by RHC to connect to
checkpoint-status | 232a9104-cb8c-49a4-ac19-4791c8f00394 |  | checkpoint | Fingerprints removed from grilles/walls/ceilings
checkpoint-status | 339d0597-f1ad-40e8-97f0-cfdf5748ec19 |  | checkpoint | Fan plugged in before install to ceiling
checkpoint-status | eca03057-95a3-4f85-93bf-018567d35acf |  | checkpoint | External louver supplied by TSL, installed by RHC completed
checkpoint-status | 1f0f1fc3-7726-4901-b1b3-7773028b0b51 |  | checkpoint | Commissioning form completed & given to TSL
checkpoint-status | 16bd6e14-ba2c-4f6b-b6ae-3ffdab92338c |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | 90d8b28d-691b-405f-84fa-db03d0cca5fe |  | section | Post check & Commission
checkpoint-status | 04329606-e02c-4ba0-84bc-f31f67a831c8 |  | checkpoint | Correct product used as per requirements
checkpoint-status | 5fd13cd0-1295-4a78-8cff-ef5763a0c097 |  | checkpoint | Correct design followed as per drawings
checkpoint-status | e32b243d-972c-4110-9876-965a54679068 |  | checkpoint | Mechanical Plant commissioned
holdpoint | 1e950f36-74bb-4676-9129-66c3e19a8a38 |  | signoff | Request sign off/remedial from RHC
checklist-sectioned | a9c67181-aa8d-4c67-a400-1592db4d4b65 |  | checklist | VRV OU |  |  |  |  | Yes | VRV OU | d7bae36e-dc95-4b32-b43c-7278435547a1
checkpoint-group | ba0a00eb-08bd-475f-a7cf-28a0edd70f0a |  | section | Pre-start:
checkpoint-status | 59d4d28b-1b71-48dd-b06e-9100768705bf |  | checkpoint | Area/base ready for outdoor unit
checkpoint-status | c340ab0e-45c5-4db7-8768-1eb5ef5c5c57 |  | checkpoint | Any required drains in place
checkpoint-status | bae92d50-ed3a-4259-86cb-d35634466898 |  | checkpoint | Outdoor unit area accessible
checkpoint-status | 72d61da7-a03a-4ef3-8f4c-75b2633e99c4 |  | checkpoint | Pipework route from OU to BS box all clear, penetrations complete
checkpoint-status | 6a34ac5d-4591-423a-9273-cc41ad35afd5 |  | checkpoint | Area clear for BS Box installation
checkpoint-group | b8550531-5fed-4d73-a47c-7289cf269bed |  | section | First Fix:
checkpoint-status | 554bcfb8-6bf9-4814-b413-a0e6f7b50186 |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | d63c5ab1-8b71-4388-a609-e8ad9294f022 |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
checkpoint-status | 0b35fff6-1802-4687-9bf1-598b38f2bc97 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 90795f30-5b7d-4ef5-9ba9-2c8af34ef6fa |  | section | Commission:
checkpoint-status | da34ce7c-b15c-4715-8ba0-7a5b4e39950a |  | checkpoint | Good access to all areas of building
checkpoint-status | 2a03e22d-b3e6-4000-91ae-33f8f9070d8b |  | checkpoint | Power live to Mechanical Plant
checkpoint-status | 0566efc3-5f45-4804-8ae7-46b0557f2f8d |  | checkpoint | Mechanical Plant commissioned
checklist-sectioned | af521e47-0347-472f-8e4d-147beea25396 |  | checklist | Extract Fan |  |  |  |  | Yes | Extract Fan | dd8e2b2c-43f5-409c-a419-82c0e5b22ef8
checkpoint-group | 75eb8133-4f11-47e7-97d9-d5b2ed5a5fb7 |  | section | Pre-start:
checkpoint-status | 96c37fba-1c50-4ddd-a7b3-d8750e4498b1 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | f482ed07-0552-4999-92be-916d45261c38 |  | checkpoint | Duct route clear, Penetrations complete
checkpoint-status | 43f6e564-7984-47a9-8d3c-ff237062445e |  | checkpoint | Nogs/Supports in place
checkpoint-group | fedb4cf3-03d9-4bb4-859d-fd0d39b00b3d |  | section | First Fix:
checkpoint-status | 5d4460f3-a6d1-4a83-8558-6896644c9a6b |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | 67b8e271-93e9-440d-aefa-7242b40bbcb3 |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
checkpoint-status | 54385dbc-ae26-47af-a49b-a0295a9c15ab |  | checkpoint | Mechanical First Fix complete
checkpoint-group | ff1dacc6-8032-40ea-803b-c7b5e1882eca |  | section | Second Fix:
checkpoint-status | 8d30e011-16f9-4d22-a3c7-eff0854ff4c0 |  | checkpoint | Area clear and access good for Second Fix
checkpoint-status | 8acc6c88-a62f-473d-aa10-01742e937926 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
checkpoint-status | 8ff77f37-7df5-4255-ab07-62484ee1c80f |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | 688efd7c-f3b8-4e2d-a326-91f32eb97db1 |  | section | Commission:
checkpoint-status | 2780f31a-09d1-4cdc-a5bd-b389a53674db |  | checkpoint | Mechanical Plant commissioned
checklist-sectioned | 22200eb9-a2c3-433a-93d6-fafb0260a5d5 |  | checklist | Kitch Ext |  |  |  |  | Yes | Kitch Ext | ea7adf80-b073-4bf2-ba4a-3deb99f9f86f
checkpoint-group | 2db9b20a-fdf6-46df-868b-d92128707da1 |  | section | Pre-start:
checkpoint-status | 1cbc54ce-62fc-4a14-98d9-ebcf2da571d7 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | fa43d522-ad5c-4d2b-88d8-bdf5338b49d0 |  | checkpoint | Duct route clear, Penetrations complete
checkpoint-status | 62def74d-3d08-4b51-a906-2ac18d72a876 |  | checkpoint | Nogs/Supports in place
checkpoint-group | 6d2fe0cf-29bd-4f85-bf70-777530ca238c |  | section | First Fix:
checkpoint-status | 5ae0c8a9-b12b-4ff5-81b8-c79cf088db18 |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | c945f168-94fa-48c6-836e-9ffe2344cee6 |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
checkpoint-status | e80126af-5f9f-45ef-98e6-4c7efa6f0aa6 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 3263804d-1fad-4138-b8ac-d13544220b04 |  | section | Second Fix:
checkpoint-status | 5c2b206d-8408-48e9-81f0-eb7dd1a176f1 |  | checkpoint | Area clear and access good for Second Fix
checkpoint-status | d08c95ff-3466-4278-8daa-87802a5157e5 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
checkpoint-status | e4b24919-b9ea-45df-831b-23308c3cee8f |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | b6b03671-5ffa-4dae-84d6-7080079d6bbb |  | section | Commission:
checkpoint-status | 1f4acbc7-d515-4953-af9f-623ac6a80616 |  | checkpoint | Good access to all areas of building
checkpoint-status | 00fef09d-c30f-4d5e-b6a7-5891e4441579 |  | checkpoint | Power live to Mechanical Plant
checkpoint-status | 5cd51d34-c9ca-42c8-93a8-9edb9d638f5a |  | checkpoint | Mechanical Plant commissioned
checklist-sectioned | 75169c75-d9cc-4775-924e-36cc756aed85 |  | checklist | AHU |  |  |  |  | Yes | AHU | ef2533a8-fb46-4a97-9630-c5d6fd1d1fd9
checkpoint-group | 1b3e9c9b-4432-4e81-9c13-234d2550d15a |  | section | Pre-start:
checkpoint-status | 41aafcc1-5615-4488-879a-94e2a89b598e |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 3e2e3fa7-04a5-4419-a256-8acb8e681430 |  | checkpoint | Duct route clear, Penetrations complete
checkpoint-status | 7e3f0196-6789-4a44-bc54-9ca916076621 |  | checkpoint | Nogs/Supports in place
checkpoint-group | 0623beb5-2b5c-4d6e-9d9b-9577ef17209b |  | section | First Fix:
checkpoint-status | 23c3091a-174c-403b-9fb2-8546aee135fd |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | 6d0d9d34-a900-42ba-ae6b-8c5297f2c07d |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
checkpoint-status | 87249542-5c3d-423a-8a91-c0bbf7d09a00 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | b9d4d20d-93c7-4fcf-86c4-cf8b4f290eee |  | section | Second Fix:
checkpoint-status | e212c6e1-b22b-496f-922e-c799c06da8a1 |  | checkpoint | Area clear and access good for Second Fix
checkpoint-status | c9d91a22-a716-4348-8a51-cb5561e3d0af |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
checkpoint-status | ad1fca3d-d654-42b8-97f1-4fb825e35ab7 |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | 2ee238f1-c49f-45a6-b61f-272f7ba6d20a |  | section | Commission:
checkpoint-status | c1f7b03b-6c7f-4a5c-a1f6-45151165dfa8 |  | checkpoint | Good access to all areas of building
checkpoint-status | c2ba895a-158e-4104-b44e-68d604650f01 |  | checkpoint | Power live to Mechanical Plant
checkpoint-status | c71f6c21-8567-4a80-bb92-48eb9fa083a8 |  | checkpoint | Mechanical Plant commissioned
checklist-sectioned | 13af1f3a-997d-435a-b924-ed896339d203 |  | checklist | VRV Bulkhead |  |  |  |  | Yes | VRV Bulkhead | f0c7e410-e022-4468-9c0f-34b4102b78fd
checkpoint-group | 538502c2-d518-4264-bd4e-0ade30c85fd4 |  | section | Pre-start:
checkpoint-status | 2f3ab74f-db11-4d44-952d-64b09d5fa43d |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | bb2fe9d4-cc01-48c4-bd45-b0f11cf2746d |  | checkpoint | Pipework route from BS to Indoor unit all clear, penetrations complete
checkpoint-status | c22b6be0-e90a-4756-9fc0-cf81aeaaaf33 |  | checkpoint | Ply fixed to ceiling
checkpoint-status | e71fe86d-50c6-46e8-9442-3ecd593e9e08 |  | checkpoint | Bulkhead frame built
checkpoint-status | 5c858e2d-e707-49c4-9f85-485f948000a0 |  | checkpoint | Grille openings framed out
checkpoint-status | 140ecf0a-9aa3-4c5a-848a-413713498351 |  | checkpoint | Drain 1m from Indoor unit location by plumber
checkpoint-group | 47f1db2e-677b-4fa6-870d-92811e307b76 |  | section | First Fix:
checkpoint-status | 2a7a7657-7a7e-4e25-84bf-5c6db01b6931 |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | e16a879f-62d1-42ff-9c6d-229108743790 |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g. drains, framing, penetrations…)
checkpoint-status | 9820a0aa-6d80-4469-a0b3-bdacebe83c5e |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 35359960-1089-4de8-a8b8-39e268faa168 |  | section | Second Fix:
checkpoint-status | ab703919-a0af-41bf-9a6a-fff5a87a6b1f |  | checkpoint | Area clear and access good for Second Fix
checkpoint-status | cfff1eac-5406-4023-93b9-23474541a54d |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g. painting, waterproofing...)
checkpoint-status | 6105dbed-3332-4b06-aeed-35994750ab27 |  | checkpoint | Mechanical Second Fix complete