## ITP Cover Page
Earthworks Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - 036-01 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 |  |  |  |  | ITP Number: |  |  | 036-01
Project Number: |  |  | DN1210 - SP2 |  |  |  |  | ITP Status: |  |  | Approved
ITP Description: |  |  | Earthworks Inspection and Test Plan |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-GEO
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Project specification
Quality Specified: |  |  | ISO9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2025-09-19 |  | Nick Adams | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Approved | 2025-09-25 |  | Nick Adams |  | WSP made comments regarding 4.1.6 testing frequency which was changed to be in line wth the project spec |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams |  |  | #VALUE! |  | 26/09/2025 | Downer PM
Downer QM |  | Cordelia Girdler Brown |  |  |  |  | 26/09/2025 | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Earthworks Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - 036-01 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS
3.1 | General
3.1.1 | Earthworks Construction Pack | The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points on Ineight for review and approval prior to works. | Engineers Approval | Appendix V | Approved Methodology | Prior to Earthworks | HP | ENG | d
3.1.2 | Ecology Sign Off | Confirmation from Ecology that earthworks can proceed | Email | Internal Hold Point | Email from Ecology NZ | Prior to Earthworks | H | SE | d
3.1.3 | Erosion & Sedimentation Controls | Confirm that Erosion and Sedimentation Controls are in place prior to earthworks proceeding | As-built Completed | Internal Hold Point | ESC As-built | Prior to Earthworks | H | SE | d
SECTION 4 – MATERIAL, PERSONNEL, TESTING & THIRD PARTY APPROVAL
4.1 | Imported Material Testing - Source Property Tests for Type A1 Imported Structural Fill - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
4.1.1 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB, or CA | Appendix XVIII PS 16.5.5 Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG | d
4.1.2 | Los Angeles Abrasion Test | NZS4407:2015, Test 3.12 - The Abrasion Resistance of Aggregate by use of the Los Angeles Machine | <50% | PS 16.5.5 Appendix V | IANZ Accredited Report | 1 Test Required Results to Engineer 2 wks before importing | HP | ENG | d
4.1.3 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | No Particles >200mm Maximum fines 10% passing 75micron sieve | Appendix XVIII PS 16.5.5 Appendix V | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG | d
4.1.4 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | Appendix XVIII Appendix V | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG | d
4.1.5 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | >25% | PS 16.5.5 Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG | d
4.1.6 | Solid Density | NZS4407:2015, Test 3.7.1 - The Solid Density of Aggregate Particles | Report Value Only | Appendix XVIII Appendix V | IANZ Accredited Report | 1 SET (5 TESTS) PER MATERIAL TYPE AND SOURCE THEN 1 TEST PER 200M3 FOR THAT MATERIAL TYPE AND SOURCE Results to Engineer 2 wks before importing | HP | ENG | d
4.1.7 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | Appendix XVIII Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG | d
4.2 | Pumice Sand Fill
4.2.1 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Report Value Only | PS 16.5.12 | IANZ Accredited Report | Number of Tests Required? Stockpile size: 0 to 400m3 – 2 tests 400 to 1500m3 – 3 tests 1500 to 4000m3 – 4 tests >4000m3 – 1 test for each additional 1,000m3 Results to Engineer 2wks before importing | HP | ENG | NA
4.2.2 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | PS 16.5.12 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG | NA
4.3 | Drainage Aggregate - Used in Subsoil Trench Drains & Drainage Blankets
4.3.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | Appendix XVIII | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG | NA
4.3.2 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Max Particle Size 53mm Max 10% passing 13.2mm sieve | Appendix XVIII | IANZ Accredited Report | 1 Test per 100m3 Results to Engineer 2wks before importing | HP | ENG | NA
4.3.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | CA or better | Appendix XVIII PS 16.5.5 Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG | NA
4.4 | Geotextile and Geogrid
4.4.1 | Geotextile | The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation. | Engineers Approval | PS 16.5.7 Appendix V | Delivery Docket/Material certificate | Results to Engineer for Approval | HP | ENG | D
4.4.2 | Geogrid | All uniaxial, biaxial and triaxial geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001 and shall submit to the Engineer for approval. | Engineers Approval | PS 16.6.5 BS EN ISO 9001:2000 Appendix V | Delivery Docket/Material certificate | Results to Engineer for Approval | HP | ENG | D
4.5 | Topsoil Source Testing
4.5.1 | Laboratory Testing for Soil Suitability | Soil Test Results from Hill Laboratories to confirm that topsoil suitable to for reuse Soil Reaction Electrical Conductivity Mechanical Analysis (texture) Stone Content Nutrient Levels of nitrogen, available phosphorus, available potassium and available magnesium Organic Matter Content Check for Toxic or Hazardous substances | Engineers Approval | NZTA P39:2013 3.1 | Hill Laboratories Test Report | 10 equal samples taken from site, mixed together, then 1kg of soil sealed into a plastic bag and sent to lab for sampling | I | SE | D
4.6 | Rock Ballast Aggregate
4.6.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | PS 16.5.15 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG | NA
4.6.2 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Max Particle Size 130mm Max 5% passing 19mm sieve Grading Sieve Size % Passing 130mm 100 100mm 70-80 63mm 40-50 37.5mm 20-25 19mm 0-5 | PS16.5.15 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG | NA
SECTION 5 – CUT SUBGRADE TESTING
5.1 | Cut Subgrade Testing - All Soils
5.1.1 | Subgrade Level Confirmation | Confirm subgrade is 705mm from finished height | String lines - or equivalent are 705mm +0mm/-30mm | PS 20.14.5 | Survey as-builts | Every 20m chainage | I | SE | D
5.1.2 | Proof Roll | Visual Inspection of Proof Roll | Displacement <15mm | Appendix XVIII | Visual Observation | Across stripped area | HP | ENG | D
5.1.3 | Cut Subgrade Inspection | Engineer to inspect all foundation surface inspections | Engineers Approval | Appendix V | Visual Observation | Across stripped area | HP | ENG | D
5.2 | Cut Subgrade Testing - Cohesive Soils
5.2.1 | Cut Subgrade Testing - Cohesive Soil Shear Vane | NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level | Average Minimum SU: > 60kPa Single Test Min SU: >50kPa 2-3m deep | Appendix XVIII | Shear Vane Report | 0.5m interval 4 test per 400M2 | I | SE | D
5.2.2 | Cut Subgrade Testing - Cohesive Soil Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material | Minimum 3 blows per 100mm penetration | Appendix XVIII | Scala Report | 4 test per 400M2 | I | SE | NA
5.3 | Cut Subgrade Testing - Granular Soils
5.3.1 | Cut Subgrade Testing - Granular Soil Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level | Minimum 3 blows per 100mm penetration 2m deep | Appendix XVIII PS - 16.6.5 | Scala Report | 4 test per 400M2 | I | SE | D
5.4 | Cut Subgrade - Hold Point Release - Import Structural Fill
5.4.1 | Release of Hold Point | To release the subgrade hold point and be able to start placing fill, the Contractor shall provide written certification that all insepcted and tested subgrade comlies with the requirements in PS 16.6 | Engineers Approval | PS 16.9.3 | CONQA Approval | Engineers Approval | HP | ENG | D
5.5 | Foundation Subgrade - Hold Point Release - Import Pavement Subgrade Improvement Layer
5.5.1 | Subgrade CBR Testing | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m | Pavement Type 1 CBR >6 Min 3 blows / 100mm Pavement Type 2, 6, 7 CBR >2.5 Min 2 blows / 100mm Pavement Type 3, 4, 5, 8 CBR >3 Min 2 blows / 100mm | PS 20.4.1 | Scala Report | 1 test per 100M2 | I | SE | D
5.5.2 | Release of Hold Point | To release the subgrade hold point and be able to start placing pavement layers, the Contractor shall provide written certification that all inspected and tested subgrade complies with the requirements in PS 16.6 | Engineers Approval | PS 16.9.3 | CONQA Approval | Engineers Approval | HP | ENG | D
SECTION 6 – CUT SLOPE INSPECTIONS
6.1 | Cut Slope Inspection
6.1.1 | Cut Side Slope Inspection | Inspection records to include photographs, logged soils (to NZ Geotechnical Guidelines) and shear vane testing | Engineers Approval | PS 16.6.4 | Site Records | As per Engineer | W | ENG
6.1.2 | Cut Slope - Soil Log | Soils to be logged to NZ Geotechnical Guidelines |  | PS 16.6.4 | Soil Log |  | I | SE
6.1.3 | Cut Slope - Shear Vane Test | NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level | Average Minimum SU: > 60kPa Single Test Min SU: >50kPa | PS 16.6.4 | Shear Vane Report |  | I | SE
6.1.4 | Drainage Measures if Seepage Encountered | Borehole Drains or ballasting may be required, to be directed by Engineer | Engineers Approval | PS 16.6.4 | Engineer approval | As per Engineer | I | ENG
6.1.5 | Design and Grade Check | Confirm cut slopes have been correctly excavated to design and grade |  | PS 16.7.1 | Survey Records |  | D | SV
6.1.6 | Stabilisation of Cut Slope Surface | Cut slope surfaces to be topsoiled and grass seeded or planted as soon as possible |  | PS 16.6.4 | Site Records |  | C | SE
6.2 | Foundation Subgrade Hold Point Release
6.2.1 | Release of Hold Point | To release the subgrade hold point and be able to start placing fill, the Contractor shall provide written certification that all insepcted and tested subgrade comlies with the requirements in PS 16.6 | Engineers Approval | PS 16.9.3 | CONQA Approval | Engineers Approval | HP | ENG
SECTION 7 – UNDERCUT TO WASTE & BACKFILL
7.1 | Undercut to Waste & Backfill
7.1.1 | Undercut Surface Inspection | Engineer to inspect undercut surface | Engineers Approval | Appendix V | Engineers Approval | Across stripped area | W | ENG | d
7.1.2 | Placement of Geotextile on Undercut | Geotextile to be placed across the undercut base and up the sides, with joints overlapped by 500mm minimum | Engineers Approval | PS 16.6.4 TNZ F/7: 2003 8.3 |  |  | W | ENG | d
7.1.3 | Subsoil Drain inspection | Subsoils to be placed at base of cuts where directed by the Engineer | Engineers Approval | PS 16.6.4 |  | No less than 24 hours prior to placement of backfill | W | ENG | d
7.2 | Foundation Subgrade Hold Point Release
7.2.1 | Release of Hold Point | To release the subgrade hold point and be able to start placing fill, the Contractor shall provide written certification that all insepcted and tested subgrade comlies with the requirements in PS 16.6 | Engineers Approval | PS 16.9.3 | CONQA Approval | Engineers Approval | HP | ENG | d
SECTION 8 – COMPACTION OF FILL Material
8.1 | Placement of Geotextile/Geogrid Under Structural Fill
8.1.1 | Placement of Geotextile | A layer of Class B Geotextile Fabric to be placed between cut surface and imported A1 Structural Fill with 500mm overlaps | Visual Inspection | NTC084 | Visual Observation | As Required | I | SE
8.1.2 | Placement of Geogrid | A layer of Geogrid to be placed between cut surface and imported A1 Structural Fill with 500mm overlaps. | Visual Inspection Test results of underlying subgrade | PS 16.9.4 | Visual Observation | As Required | I | SE
8.2 | Compaction Requirements for Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
8.2.1 | Compaction - Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Structural Fill Min CIV 18 Ave CIV 20 Non-Structural Fill Min CIV 10 Max CIV 12 | Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | I | SE | d
8.2.2 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD Non Granular Material Max Air Voids 8% | Appendix XVIII | IANZ Accredited Report | 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed | I | SE | d
8.2.3 | Compaction Trials | The Contractor shall carry out compaction trials of the various soil types and combinations on site, and any imported fill materials, using different layer thicknesses, types of rollers and conditioning plant (ie construction discs and scarifiers). The trials shall be conducted over the duration of the earthworks operation with the objective of determining the most suitable and efficient techniques to meet the compaction requirements. The trial details, test data and conclusions shall be reported and copied to the Engineer within five days of completion of each trial. | Engineers Approval | PS 16.6.5 | Trial Results |  | R | ENG | d
8.3 | Compaction Requirements for Pumice Sand Fill
8.3.1 | Compaction - Structural Fill Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material | Minimum 5 blows per 100mm penetration | PS 16.5.12 | Scala Report | Minimum 1 test per 500m3 of filling evenly distributed over the extent and depth of the filling. A minimum of 1 test per 500mm lift or part thereof to be completed through the full lift thickness. | I | SE | na
8.3.2 | Compaction - Structural Fill NDM | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | PS 16.5.12 | IANZ Accredited Report | 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed | I | SE | na
8.3.3 | Pumice Sand Fill | Pumice Sand Material shall be contained with an outer layer of fill with a minimum thickness of 600mm. Must be Hardfill and/or imported Type A1 material and/or Type A2 material and/or Type A3 material |  | PS 16.5.12 | Site Records |  | H | SE | na
8.4 | Compaction Requirements for Cut to fill material
8.4.1 | Cut ot fill | Cut from classic building and use as a fill material | Engineers Approval | PS 16.5.5 (b) | Visual Observation | If there is change in colour or after every 1000m2 of placed | HP | ENG | d
8.4.2 | Compaction - Structural Fill Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Scala penetrometer testing to be undertaken | Minimum 4 blows per 100mm penetration | PS: XVIII | Scala Report | Minimum 1 set(5test) per 100m3 of filling evenly distributed over the extent and depth of the filling. A minimum of 400mm lift required | I | SE
SECTION 9 – TOPSOIL PLACEMENT
9.1 | Cut and fill embankments
9.1.1 | Topsoil Placement on cut and fill embankments | Confirmation of thickness and material suitability | Meets spec and thickness requirements as per drawings | PS 16.6.3 b) | Visual Observation | Once per lot after topsoil re-spread | H | SE
SECTION 10 – SETTLEMENT INSTALLATION & MONITORING
10.1 | Settlement Monitoring
10.1.1 | Instrument Reading Notice | The Contractor shall inform the Engineer two days in advance of planned instrument readings so that the Engineer may observe the work. | 2 days notice to Eng | PS 16.8.2 | Site Records | Every Time | H | SE
10.1.2 | Results Submitted to Engineer | Results will be submitted to the Engineer within 1 day of reading the instruments | To Engineer within 1 day of Reading | PS 16.8.2 | Site Records | Every Time | H | SE
10.1.3 | Baseline Readings | The Contractor shall take 3 sets of baselines readings from all instruments at 2 day intervals | Engineers Approval | PS 16.8.2 | Site Records | Every 2 days | H | SE
10.1.4 | Readings During Active Fill Placement | During active fill placement, the Contractor shall read all monitoring plates twice a week or every 1 metre of fill whichever is more frequent | To Engineer within 1 day of Reading | PS 16.8.2 | Site Records | Twice a week | R | SV
10.1.5 | Readings During No Active Earthworks in Area | The Contractor shall read all monitoring plates weekly if there is no active earthworks taking place in the area | To Engineer within 1 day of Reading | PS 16.8.2 | Site Records | Weekly | R | SV
10.1.6 | Settlement Monitoring Termination | The criteria for terminating the embankment preload are either: Three consecutive measurements indicating the t90 settlement value has been achieved, A rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed. The settlement readings shall be evaluated by the Engineer to assess the need to extend the monitoring. | Either: 3 Consecutive Measurements showing T90 settlement value achieved Or Rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed | PS 16.8.5 | Site Records | Engineers Approval | HP | ENG
SECTION 11 – AS-BUILTS
11.1 | As-Builts | As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets. | As-build record | PS 16.7.6 | Survey Records/redpen markups | During Earthworks | D | SV