## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP2-036-01 ITP Stg 2 Earthworks SH29 CH340-840 Nth | itp |  |  |  |  | DN1210-SP2-036-01 ITP Stg 2 Earthworks SH29 CH340-840 Nth Rev 1
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS
checkpoint | 3.1.1 - Earthworks Construction Pack
label | Detail - The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points on Ineight for review and approval prior to works.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Approved Methodology
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.1.2 - Ecology Sign Off
label | Detail - Confirmation from Ecology that earthworks can proceed
label | Acceptance / Conformance Criteria - Email
label | Standard / Specification - Internal Hold Point
label | Verifying Document - Email from Ecology NZ
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.1.3 - Erosion & Sedimentation Controls
label | Detail - Confirm that Erosion and Sedimentation Controls are in place prior to earthworks proceeding
label | Acceptance / Conformance Criteria - As-built Completed
label | Standard / Specification - Internal Hold Point
label | Verifying Document - ESC As-built
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 4 – MATERIAL, PERSONNEL, TESTING & THIRD PARTY APPROVAL
checkpoint | 4.1.1 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, or CA
label | Standard / Specification - Appendix XVIII, PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.1.2 - Los Angeles Abrasion Test
label | Detail - NZS4407:2015, Test 3.12 - The Abrasion Resistance of Aggregate by use of the Los Angeles Machine
label | Acceptance / Conformance Criteria - <50%
label | Standard / Specification - PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Required
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.1.3 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - No Particles >200mm
label | ○ Maximum fines 10% passing 75micron sieve
label | Standard / Specification - Appendix XVIII, PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.1.4 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - Appendix XVIII, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.1.5 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - >25%
label | Standard / Specification - PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.1.6 - Solid Density
label | Detail - NZS4407:2015, Test 3.7.1 - The Solid Density of Aggregate Particles
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - Appendix XVIII, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 SET (5 TESTS) PER MATERIAL TYPE AND SOURCE THEN 1 TEST PER 200M3 FOR THAT MATERIAL TYPE AND SOURCE
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.1.7 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Appendix XVIII, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.2.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - PS 16.5.12
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required?
label | ○ Stockpile size:
label | — 0 to 400m3 – 2 tests
label | — 400 to 1500m3 – 3 tests
label | — 1500 to 4000m3 – 4 tests
label | — >4000m3 – 1 test for each additional 1,000m3
label | ○ Results to Engineer 2wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.2.2 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - PS 16.5.12
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.3.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.3.2 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Max Particle Size 53mm
label | ○ Max 10% passing 13.2mm sieve
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per 100m3
label | ○ Results to Engineer 2wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.3.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - Appendix XVIII, PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.4.1 - Geotextile
label | Detail - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.5.7, Appendix V
label | Verifying Document - Delivery Docket/Material certificate
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.4.2 - Geogrid
label | Detail - All uniaxial, biaxial and triaxial geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001 and shall submit to the Engineer for approval.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.5, BS EN ISO 9001:2000, Appendix V
label | Verifying Document - Delivery Docket/Material certificate
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.5.1 - Laboratory Testing for Soil Suitability
label | Detail - Soil Test Results from Hill Laboratories to confirm that topsoil suitable to for reuse Soil Reaction
label | ○ Electrical Conductivity
label | ○ Mechanical Analysis (texture)
label | ○ Stone Content
label | ○ Nutrient Levels of nitrogen, available phosphorus, available potassium and available magnesium
label | ○ Organic Matter Content
label | ○ Check for Toxic or Hazardous substances
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - NZTA P39:2013 3.1
label | Verifying Document - Hill Laboratories Test Report
label | Testing Quantity Required (based from schedule qtys) - 10 equal samples taken from site, mixed together, then 1kg of soil sealed into a plastic bag and sent to lab for sampling
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.6.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - PS 16.5.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 4.6.2 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Max Particle Size 130mm
label | ○ Max 5% passing 19mm sieve
label | — — — — — — —
label | Grading
label | Sieve Size ¦¦ % Passing
label | — — — — — — —
label | 130mm ¦¦ 100
label | 100mm ¦¦ 70-80
label | 63mm ¦¦ 40-50
label | 37.5mm ¦¦ 20-25
label | 19mm ¦¦ 0-5
label | — — — — — — —
label | Standard / Specification - PS16.5.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
section | SECTION 5 – CUT SUBGRADE TESTING
checkpoint | 5.1.1 - Subgrade Level Confirmation
label | Detail - Confirm subgrade is 705mm from finished height
label | Acceptance / Conformance Criteria - String lines - or equivalent are 705mm +0mm/-30mm
label | Standard / Specification - PS 20.14.5
label | Verifying Document - Survey as-builts
label | Testing Quantity Required (based from schedule qtys) - Every 20m chainage
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.1.2 - Proof Roll
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Displacement <15mm
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 5.1.3 - Cut Subgrade Inspection
label | Detail - Engineer to inspect all foundation surface inspections
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 5.2.1 - Cut Subgrade Testing - Cohesive Soil Shear Vane
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU:
label | — > 60kPa
label | ○ Single Test Min SU:
label | — >50kPa
label | — 2-3m deep
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 0.5m interval, 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2.2 - Cut Subgrade Testing - Cohesive Soil Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3.1 - Cut Subgrade Testing - Granular Soil Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | ○ 2m deep
label | Standard / Specification - Appendix XVIII, PS - 16.6.5
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4.1 - Release of Hold Point
label | Detail - To release the subgrade hold point and be able to start placing fill, the Contractor shall provide written certification that all insepcted and tested subgrade comlies with the requirements in PS 16.6
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.9.3
label | Verifying Document - CONQA Approval
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 5.5.1 - Subgrade CBR Testing
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m
label | Acceptance / Conformance Criteria - Pavement Type 1
label | — CBR >6
label | — Min 3 blows / 100mm
label | ○ Pavement Type 2, 6, 7
label | — CBR >2.5
label | — Min 2 blows / 100mm
label | ○ Pavement Type 3, 4, 5, 8
label | — CBR >3
label | — Min 2 blows / 100mm
label | Standard / Specification - PS 20.4.1
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 1 test per 100M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.5.2 - Release of Hold Point
label | Detail - To release the subgrade hold point and be able to start placing pavement layers, the Contractor shall provide written certification that all inspected and tested subgrade complies with the requirements in PS 16.6
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.9.3
label | Verifying Document - CONQA Approval
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
section | SECTION 6 – CUT SLOPE INSPECTIONS
checkpoint | 6.1.1 - Cut Side Slope Inspection
label | Detail - Inspection records to include photographs, logged soils (to NZ Geotechnical Guidelines) and shear vane testing
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.4
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - As per Engineer
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 6.1.2 - Cut Slope - Soil Log
label | Detail - Soils to be logged to NZ Geotechnical Guidelines
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 16.6.4
label | Verifying Document - Soil Log
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.1.3 - Cut Slope - Shear Vane Test
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
label | ○ Single Test Min SU: >50kPa
label | Standard / Specification - PS 16.6.4
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.1.4 - Drainage Measures if Seepage Encountered
label | Detail - Borehole Drains or ballasting may be required, to be directed by Engineer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.4
label | Verifying Document - Engineer approval
label | Testing Quantity Required (based from schedule qtys) - As per Engineer
label | Verification Activity: Activity - I
label | Verification Activity: By - ENG
checkpoint | 6.1.5 - Design and Grade Check
label | Detail - Confirm cut slopes have been correctly excavated to design and grade
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 16.7.1
label | Verifying Document - Survey Records
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | 6.1.6 - Stabilisation of Cut Slope Surface
label | Detail - Cut slope surfaces to be topsoiled and grass seeded or planted as soon as possible
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 16.6.4
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 6.2.1 - Release of Hold Point
label | Detail - To release the subgrade hold point and be able to start placing fill, the Contractor shall provide written certification that all insepcted and tested subgrade comlies with the requirements in PS 16.6
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.9.3
label | Verifying Document - CONQA Approval
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
section | SECTION 7 – UNDERCUT TO WASTE & BACKFILL
checkpoint | 7.1.1 - Undercut Surface Inspection
label | Detail - Engineer to inspect undercut surface
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 7.1.2 - Placement of Geotextile on Undercut
label | Detail - Geotextile to be placed across the undercut base and up the sides, with joints overlapped by 500mm minimum
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.4, TNZ F/7: 2003 8.3
label | Verifying Document -
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 7.1.3 - Subsoil Drain inspection
label | Detail - Subsoils to be placed at base of cuts where directed by the Engineer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.4
label | Verifying Document -
label | Testing Quantity Required (based from schedule qtys) - No less than 24 hours prior to placement of backfill
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 7.2.1 - Release of Hold Point
label | Detail - To release the subgrade hold point and be able to start placing fill, the Contractor shall provide written certification that all insepcted and tested subgrade comlies with the requirements in PS 16.6
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.9.3
label | Verifying Document - CONQA Approval
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
section | SECTION 8 – COMPACTION OF FILL Material
checkpoint | 8.1.1 - Placement of Geotextile
label | Detail - A layer of Class B Geotextile Fabric to be placed between cut surface and imported A1 Structural Fill with 500mm overlaps
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - NTC084
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - As Required
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 8.1.2 - Placement of Geogrid
label | Detail - A layer of Geogrid to be placed between cut surface and imported A1 Structural Fill with 500mm overlaps.
label | Acceptance / Conformance Criteria - Visual Inspection
label | ○ Test results of underlying subgrade
label | Standard / Specification - PS 16.9.4
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - As Required
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 8.2.1 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Structural Fill
label | — Min CIV 18
label | — Ave CIV 20
label | ○ Non-Structural Fill
label | — Min CIV 10
label | — Max CIV 12
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 8.2.2 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | ○ Non Granular Material
label | ○ Max Air Voids 8%
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 8.2.3 - Compaction Trials
label | Detail - The Contractor shall carry out compaction trials of the various soil types and combinations on site, and any imported fill materials, using different layer thicknesses, types of rollers and conditioning plant (ie construction discs and scarifiers). The trials shall be conducted over the duration of the earthworks operation with the objective of determining the most suitable and efficient techniques to meet the compaction requirements. The trial details, test data and conclusions shall be reported and copied to the Engineer within five days of completion of each trial.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.5
label | Verifying Document - Trial Results
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - R
label | Verification Activity: By - ENG
checkpoint | 8.3.1 - Compaction - Structural Fill Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 5 blows per 100mm penetration
label | Standard / Specification - PS 16.5.12
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - Minimum 1 test per 500m3 of filling evenly distributed over the extent and depth of the filling. A minimum of 1 test per 500mm lift or part thereof to be completed through the full lift thickness.
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 8.3.2 - Compaction - Structural Fill NDM
label | Detail - Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - PS 16.5.12
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 8.3.3 - Pumice Sand Fill
label | Detail - Pumice Sand Material shall be contained with an outer layer of fill with a minimum thickness of 600mm. Must be Hardfill and/or imported Type A1 material and/or Type A2 material and/or Type A3 material
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 16.5.12
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 8.4.1 - Cut ot fill
label | Detail - Cut from classic building and use as a fill material
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.5.5 (b)
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - If there is change in colour or after every 1000m2 of placed
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 8.4.2 - Compaction - Structural Fill Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken
label | Acceptance / Conformance Criteria - Minimum 4 blows per 100mm penetration
label | Standard / Specification - PS: XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - Minimum 1 set(5test) per 100m3 of filling evenly distributed over the extent and depth of the filling. A minimum of 400mm lift required
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 9 – TOPSOIL PLACEMENT
checkpoint | 9.1.1 - Topsoil Placement on cut and fill embankments
label | Detail - Confirmation of thickness and material suitability
label | Acceptance / Conformance Criteria - Meets spec and thickness requirements as per drawings
label | Standard / Specification - PS 16.6.3 b)
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Once per lot after topsoil re-spread
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 10 – SETTLEMENT INSTALLATION & MONITORING
checkpoint | 10.1.1 - Instrument Reading Notice
label | Detail - The Contractor shall inform the Engineer two days in advance of planned instrument readings so that the Engineer may observe the work.
label | Acceptance / Conformance Criteria - 2 days notice to Eng
label | Standard / Specification - PS 16.8.2
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - Every Time
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 10.1.2 - Results Submitted to Engineer
label | Detail - Results will be submitted to the Engineer within 1 day of reading the instruments
label | Acceptance / Conformance Criteria - To Engineer within 1 day of Reading
label | Standard / Specification - PS 16.8.2
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - Every Time
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 10.1.3 - Baseline Readings
label | Detail - The Contractor shall take 3 sets of baselines readings from all instruments at 2 day intervals
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.8.2
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - Every 2 days
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 10.1.4 - Readings During Active Fill Placement
label | Detail - During active fill placement, the Contractor shall read all monitoring plates twice a week or every 1 metre of fill whichever is more frequent
label | Acceptance / Conformance Criteria - To Engineer within 1 day of Reading
label | Standard / Specification - PS 16.8.2
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - Twice a week
label | Verification Activity: Activity - R
label | Verification Activity: By - SV
checkpoint | 10.1.5 - Readings During No Active Earthworks in Area
label | Detail - The Contractor shall read all monitoring plates weekly if there is no active earthworks taking place in the area
label | Acceptance / Conformance Criteria - To Engineer within 1 day of Reading
label | Standard / Specification - PS 16.8.2
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - Weekly
label | Verification Activity: Activity - R
label | Verification Activity: By - SV
checkpoint | 10.1.6 - Settlement Monitoring Termination
label | Detail - The criteria for terminating the embankment preload are either: Three consecutive measurements indicating the t90 settlement value has been achieved, A rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed. The settlement readings shall be evaluated by the Engineer to assess the need to extend the monitoring.
label | Acceptance / Conformance Criteria - Either:
label | ○ 3 Consecutive Measurements showing T90 settlement value achieved
label | Or
label | ○ Rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed
label | Standard / Specification - PS 16.8.5
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
section | SECTION 11 – AS-BUILTS
checkpoint | 11.1 - As-Builts
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Acceptance / Conformance Criteria - As-build record
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Survey Records/redpen markups
label | Testing Quantity Required (based from schedule qtys) - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-SP2-036-02 ITP Stage 2 Pavement 4 CH340-840 SH29 Nth | itp |  |  |  |  | DN1210-SP2-036-02 ITP Stage 2 Pavement 4 CH340-840 SH29 Nth Rev 1
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONEL & THIRD PARTY APPROVALS
checkpoint | 3.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 100kN
label | Standard / Specification - NZS4407:2015, Test 3.10, TCC-IDC-IT-4.3.1-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.1.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥60%
label | Standard / Specification - NZS4402, Test 6.1.1, TCC-IDC-IT-4.3.1-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.1.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, CA or CB
label | Standard / Specification - NZS4407, Test 3.11, TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.2.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 68-90% passing
label | 19.0mm ¦¦ 42-76% passing
label | 9.5mm ¦¦ 26-58% passing
label | 4.75mm ¦¦ 16-44% passing
label | 2.36mm ¦¦ 10-33% passing
label | 1.18mm ¦¦ 6-24% passing
label | 0.425mm ¦¦ 3-14% passing
label | 0.075mm ¦¦ 1-6% passing
label | Standard / Specification - NZS4407, Test 3.8.1, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.2.2 - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 34-50%
label | 19.0 – 4.75 ¦¦ 18-40%
label | 9.5 – 2.36 ¦¦ 12-32%
label | 4.75 – 1.18 ¦¦ 6-24%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 0-15%
label | 0.6 – 0.15 ¦¦ 0-12%
label | Standard / Specification - TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.2.3 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407, Clause 4.3, TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.2.4 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - ≤ 8
label | Standard / Specification - NZS4407:2015, Test 3.4, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.2.4 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent Washing method
label | Acceptance / Conformance Criteria - ≥25
label | Standard / Specification - NZS4407, Test 3.6, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.2.5 - Accelerated Weathering
label | Detail - NZTA T/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.3.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 130kN
label | Standard / Specification - TCC-IDC IT-4.7.1 table 4.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.3.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥ 60%
label | Standard / Specification - TCC-IDC IT-4.7.1 table 4.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.3.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - TCC-IDC IT-4.7.1 table 4.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.4.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 55-85% passing
label | 19.0mm ¦¦ 33-65% passing
label | 9.5mm ¦¦ 20-50% passing
label | 4.75mm ¦¦ 10-36% passing
label | 2.36mm ¦¦ 5-27% passing
label | 1.18mm ¦¦ 2-20% passing
label | 0.425mm ¦¦ 1-13% passing
label | 0.075mm ¦¦ 6% max passing
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.4.2 - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 34-50%
label | 19.0 – 4.75 ¦¦ 18-40%
label | 9.5 – 2.36 ¦¦ 12-32%
label | 4.75 – 1.18 ¦¦ 6-24%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 0-15%
label | 0.6 – 0.15 ¦¦ 0-12%
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.4.3 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - ≥ 30
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.4.4 - Cone Penetrometer Limit
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | Acceptance / Conformance Criteria - Cone Penetrometer ≤ 25
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.4.5 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - Plasticity Index ≤ 8
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.4.6 - Accelerated Weathering
label | Detail - NZTA T/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - TCC-IDC IT-4.7.2 table 4.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.4.7 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - TCC-IDC IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 1.5.1 - Geogrid
label | Detail - The Contractor shall submit the full details of the geogrid they propose to use to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 20.5.2, PS 16.5.13
label | Verifying Document - Data Sheets and Approval
label | Testing Quantity Required (based from schedule qtys) - Once prior to works commencting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 1.5.2 - Geotextile Fabric
label | Detail - The Contractor shall submit the full details of the geotextile fabric they propose to use to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 20.5.2, PS 16.5.14
label | Verifying Document - Data Sheets and Approval
label | Testing Quantity Required (based from schedule qtys) - Once prior to works commencting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
section | SECTION 4 – SUBGRADE HANDOVER FROM EARTHWORKS
checkpoint | 4.1 - QA Submission
label | Detail - Submit all Subgrade QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Conqa Siggnoff
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 5.1.1 - Placement of Geotextile Fabric
label | Detail - Place Geotextile Fabric Strength Class B across pavement area, with 500mm overlaps
label | Acceptance / Conformance Criteria - Place Geotextile Fabric Strength Class B across pavement area, with 500mm overlaps
label | Standard / Specification - NTC0097, 232735.02-WSP-DR-PVS-0401-REV4
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 5.1.2 - Onsite Check by Engineer on Geogrid
label | Detail - Installation of Geogrid shall not commence until the Engineer has inspected the proposed geogrid on site and confirmed that the correct types of geogrid have been supplied.
label | Acceptance / Conformance Criteria - Installation of Geogrid shall not commence until the Engineer has inspected the proposed geogrid on site and confirmed that the correct types of geogrid have been supplied.
label | Standard / Specification - NTC0100, 232735.02-WSP-DR-PVS-0401-REV4
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 5.1.3 - Placement of Geogrid
label | Detail - The Duragrid X 30/30 Geogrid shall be placed on top of the Geotextile Fabric, and overlap areas of structural fill by a minimum of 2m, or as directed by the Engineer on site where the layer depth of structural fill is insufficient to limit deflections from the subgrade.
label | Acceptance / Conformance Criteria - The Duragrid X 30/30 Geogrid shall be placed on top of the Geotextile Fabric, and overlap areas of structural fill by a minimum of 2m, or as directed by the Engineer on site where the layer depth of structural fill is insufficient to limit deflections from the subgrade.
label | Standard / Specification - NTC0100, 232735.02-WSP-DR-PVS-0401-REV4
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
section | SECTION 6 - PAVEMENT TYPE 4
checkpoint | 6.1.1 - Plateau Density Test
label | Detail - Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes
label | Acceptance / Conformance Criteria - Plateau Density Report
label | Standard / Specification - TNZM/03, TCC IDC IT-4.7, AS per NTC 349
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.1.2 - 3m Straight Edge
label | Detail - Formation check to ensure surface is smooth
label | Acceptance / Conformance Criteria - +/- 10mm
label | Standard / Specification - TNZM/03, TCC IDC IT-4.7, AS per NTC 350
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - Every 20m Centres
label | ○ 1 each lane
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.1.3 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -15mm + 0mm
label | Standard / Specification - TNZM/03, TCC IDC IT-4.7, AS per NTC 351
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.1.4 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - TNZM/03, TCC IDC IT-4.7, AS per NTC 352
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.1.5 - Benkelmen Beam
label | Detail - As directed by Engineer 15m staggered by wheel path for each lane.
label | Acceptance / Conformance Criteria - 90th Percentile: 2.1mm
label | ○ Maximum: 2.62mm
label | Standard / Specification - PS 20.14.5, NTC0160
label | Verifying Document - Test Report
label | Testing Quantity Required (based from schedule qtys) - As directed by Engineer
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 6.2.1 - QA Submission
label | Detail - Submit all Subbase QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - All test reports
label | ○ Material Test Results
label | ○ Laboratory MDD
label | ○ NDM results
label | ○ Proof Roll
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 6.3.1 - Plateau Density Test
label | Detail - Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes
label | Acceptance / Conformance Criteria - Plateau Density Report
label | Standard / Specification - NZTA B/02 7.5 (a)
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.3.2 - 3m Straight Edge
label | Detail - Formation check to ensure surface is smooth
label | Acceptance / Conformance Criteria - +/- 10mm
label | Standard / Specification - TNZ B/2 7.7
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - Every 20m Centres
label | ○ 1 each lane
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.3.3 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -15mm + 0mm
label | Standard / Specification - NZTA B/02 5.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.3.4 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >98% of MDD
label | ○ Min >95% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.3.5 - Benkelmen Beam
label | Detail - As directed by Engineer 15m staggered by wheel path for each lane.
label | Acceptance / Conformance Criteria - 90th Percentile: 1.44mm
label | ○ Maximum: 1.78mm
label | Standard / Specification - PS 20.14.5, NTC0160
label | Verifying Document - Test Report
label | Testing Quantity Required (based from schedule qtys) - As directed by Engineer
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
section | SECTION 7 – AS-BUILTS / REDPEN MARKUPS
checkpoint | 7.1 - As-Builts/ Red pen markup
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red pen markups
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - D
label | Verification Activity: By - SV/SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-SP2-036-03 ITP Stg2 2 Krb Chnl SH29 CH340-840 Nth | itp |  |  |  |  | DN1210-SP2-036-03 ITP Stg2 2 Krb Chnl SH29 CH340-840 Nth Rev 1
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 3.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Project Specifications Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.1.2 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - Project Specifications Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 3.1.3 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 37.5mm ¦¦ 100% passing
label | 19.0mm ¦¦ 60-75% passing
label | 9.5mm ¦¦ 37-50% passing
label | 4.75mm ¦¦ 20-35% passing
label | 2.36mm ¦¦ 12-28% passing
label | 1.18mm ¦¦ 9-20% passing
label | 0.600mm ¦¦ 7-12% Passing
label | 0.300mm ¦¦ 3-10% Passing
label | 0.150mm ¦¦ 0-5% passing
label | 0.075mm ¦¦ 0-5% passing
label | Standard / Specification - Project Specifications Appendix XVIII, Tauranga Council IDC - Table IT-4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
section | SECTION 4 – CONSTRUCTION - KERB & CHANNEL PREPARATION
checkpoint | 4.1.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -0mm + 20mm
label | Standard / Specification - NZTA B/06 8.2.2 - Table 3
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.2 - Compaction - Clegg
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min CIV 18
label | ○ Ave CIV 20
label | Standard / Specification - PS Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 – CONSTRUCTION - KERB & CHANNEL PREPARATION
checkpoint | 5.1.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - Project Specifications 21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.1.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Concrete Delivery dockets, Concrete Test Results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.1.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - Project Specifications 27.4.5 (c)
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.1.4 - Final Finish
label | Detail - Slip form kerb and channel
label | Acceptance / Conformance Criteria - Slip form kerb and channel
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - Project Specifications 21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Concrete Delivery dockets, Concrete Test Results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - Project Specifications 27.4.5 (c)
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2.4 - Final Finish
label | Detail - Slip form kerb and channel
label | Acceptance / Conformance Criteria - Slip form kerb and channel
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - Project Specifications21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Concrete Delivery dockets, Concrete Test Results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - Project Specifications 27.4.5 (c)
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3.4 - Final Finish
label | Detail - Slip form kerb and channel
label | Acceptance / Conformance Criteria - Slip form kerb and channel
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - Project Specifications21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Concrete Delivery dockets, Concrete Test Results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - Project Specifications 27.4.5 (c)
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4.4 - Final Finish
label | Detail - Slip form kerb and channel
label | Acceptance / Conformance Criteria - Slip form kerb and channel
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.5.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - Project Specifications21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.5.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Concrete Delivery dockets, Concrete Test Results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.5.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - Project Specifications 27.4.5 (c)
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.5.4 - Final Finish
label | Detail - Slip form kerb and channel
label | Acceptance / Conformance Criteria - Slip form kerb and channel
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.6.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - Project Specifications 21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.6.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - Project Specifications 26.7.3
label | Verifying Document - Concrete Delivery dockets, Concrete Test Results
label | Testing Quantity Required (based from schedule qtys) - During construction - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.6.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - Project Specifications 27.4.5 (c)
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.6.4 - Final Finish
label | Detail - Hand poured and formed concrete kerbs
label | Acceptance / Conformance Criteria - F3 Surface Finish / Slip form kerb and channel
label | Standard / Specification - Project Specifications 22.10.2
label | Verifying Document - Post-Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 6 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.1 - Final Inspection
label | Detail - Final inspection of all concrete work.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - NZTA P39: 2013
label | Verifying Document - Final inspection report
label | Testing Quantity Required (based from schedule qtys) - 100% Completion of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORTY HOLDPOINT
checkpoint | 6.2 - As-Builts
label | Detail - Final inspection of all concrete work.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | — Any changes to be added to redpen markup Project Specifications
label | Standard / Specification - Project Specifications 16.7.6
label | Verifying Document - Redpen markuProject Specifications
label | Testing Quantity Required (based from schedule qtys) - 100% Completion of works
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature